TABLE OF CONTENTS

Preface	3

Acronyms and Definitions	4

1.0	Oversight/Verification	5

1.1	Deliverables and Commitments	10

1.2	Audits and Reviews	13

1.2.1	Process Reviews	13

1.2.2	Labor Compliance	19

1.2.3	EEO/DBE Compliance	23

1.3	Contract Revisions (Change Orders)	25

1.4	Documentation	33

1.4.1	Contract Records (Security/Confidential Documents)	33

1.4.2	Document Control	35

1.4.3	Progress Meeting Notes	52

1.5	Schedule Review	54

1.6	Invoice Review	59

1.6.1	Design Invoice Review	59

1.6.2	Construction and Non-Design Invoice Review	67

1.7	Design	70

1.7.1	Design Oversight Roles	70

1.7.2	Quality Manual	76

1.7.3	Design Oversight Meetings	79

1.7.4	Design Oversight Reviews	82

1.7.4.1	Over-the-Shoulder Reviews (OTS)	82

1.7.4.2	Released for Construction – For Review	84

1.7.4.3	Released for Construction-Final	90

1.7.5	Design Process Reviews	93

1.7.6	Right of Way (R/W)	94

1.8	Construction	97

1.8.1	Construction Inspection and Testing Roles	97

1.8.2	Quality Manual	104

1.8.3	Critical Activity Points	107

1.8.4	Construction Process Reviews	111

1.8.5	Requests for Information (RFI)	112

1.8.6	Field Design Changes	114

1.8.7	Notices of Design Change	121

1.9	Environmental	125

1.10	Contacts with the Public, Media or Attorneys	129

1.11	Third Parties	132

1.11.1	Utilities	132

1.11.2	Railroad	136

1.12	Final Acceptance/Project Close-Out	137

1.13	Warranty Enforcement	141

# Preface

Manual Purpose

The purpose of this manual is to standardize MnDOT design-build Construction Administration practices statewide.  For each new design-build project, MNDOT traditionally forms a Contract Administration Team that consists of individuals assigned to perform administrative functions including the project manager, design oversight staff, construction verification staff and other support staff such as document control, change control and the like.

This manual is intended to serve as a reference to allow a standardized approach, while recognizing that each design-build project is different, and that each MnDOT Contract Administration Team is unique in experience and physical structure. The MnDOT Project Manager and the Design-Build Program Manager are responsible for training, management and enforcement of the procedures set forth in this document.

This manual provides guidelines for implementing a design-build project after the contract is awarded.  It is not intended to replace either of the following:

The Conformed Contract: which governs over all other documents

Construction Administration Manual: this Manual is intended to supplement the MnDOT Construction Administration Manual, as much of this manual applies to design-build projects.

The material in this manual enhances both of the above documents with easy-to-follow steps and lessons learned from previous design-build projects.

Note that in this Manual, the MnDOT Contract Administration Team is also referred to as an oversight or verification team when discussing design or construction contract administration activities.

Process for Developing this Manual

This manual was written by MnDOT Office of Project Management and Technical Support (OPMTS) with support from MnDOT Districts and the Federal Highway Administration (FHWA), and incorporates lessons learned from previous design-build projects.

Process for Updating this Manual

Because design-build is an evolving process, this manual will be updated frequently, at the direction of the Design-Build Program Manager, to address lessons learned, evolving approaches, and changes to state and local laws, regulations, and policies.

# Acronyms and Definitions

For acronyms and definitions refer to the following documents:

Acronyms in Section 1101 “Abbreviations” of the MnDOT Standard Specifications for Construction

Definitions in Section 1103 of the MnDOT Standard Specifications for Construction

Construction Administration Manual (for design-bid-build)

Design-Build Manual

Book 1 Exhibit A of the Conformed Contract for the Project

In this Manual, words that are capitalized are defined terms in one of the above references. Additional acronyms that are common to design-build contract administration are provided below:

Acronyms

FDC		Field Design Change

NDC		Notice of Design Change

OPMTS	Office of Project Management and Technical Services

OTS		Over-the-Shoulder reviews

PODI		Projects of Division Interest (Federal Highway Oversight)

RFC		Released for Construction

RFI		Request for Information

## Oversight/Verification

This Contract Administration Manual provides MnDOT Design-Build Contract Administration Teams with additional guidance the team will need for design-build projects.  Contract administration for design-build projects is significantly different from design-bid-build and construction manager general contractor (CMGC) projects because many of the roles typically performed by MnDOT or MnDOT consultants (e.g., design and quantity determination) are assigned to the Contractor.  MnDOT’s responsibilities under a design-build contract are more of an oversight and verification role confirming contract conformance. .

Similarly, other aspects of contract administration differ from design-bid-build due to the payment and acceptance approach to the projects. The payment process involves the design-builder developing a Payment Breakdown by activity, not by quantities.  Design drawings and many other deliverables undergo an acceptance process during the project and are therefore not “approved” by MnDOT.  Final acceptance of design and construction occur at final completion. These processes are detailed later in this manual.

This section introduces the roles and responsibilities of the MnDOT Contract Administration Team for design-build projects.  The following sections provide detailed Purposes, Procedures, Useful Tips/Lessons Learned and helpful references and examples of the following topics to assist MnDOT staff in the execution of their responsibilities:

1.1	Deliverables and Commitments

1.2	Audits and Reviews

1.3	Contract Revisions (Change Orders)

1.4	Documentation

1.5	Schedule Review

1.6	Invoice Review

1.7	Design

1.8	Construction

1.9	Environmental

1.10	Contacts with the Public, Media, or Attorneys

1.11	Third Parties

1.12	Final Acceptance/Project Close-Out

1.13	Warranty Enforcement

Sample Metro and outstate District organization charts from design-build projects are provided at the end of this section, showing how MnDOT staffing needs differ from design-bid-build.  These charts also illustrate how design-build Contract Administration Teams can vary from project to project, in response to each one’s unique features.

MnDOT, generally through its design-build GEC, prepares an RFQ and RFP that define the contractual roles and responsibilities of MnDOT and the Contractor, which can vary by project.  Pre-defined Key Personnel required to fill these roles are also defined in the RFQ and RFP, and may similarly vary by project.  The MnDOT Contract Administration Team should refer to these documents to understand how the roles and responsibilities are defined for an individual project.

Examples of typical MnDOT design-build Contract Administration Team roles, including items that illustrate the differences between design-build and design-bid-build contracts, are listed below:

Quality Management:  As noted above, the MnDOT Contract Administration Team’s role in design-build is oversight and verification. Although the Contractor holds ultimate responsibility for the quality of both design and construction, the MnDOT Contract Administration Team will perform design reviews and construction testing. The general characteristics of design-build quality management are as follows:

Project quality is governed by a quality manual prepared by the Contractor and approved by MnDOT (see Sections 1.7.2 and 1.8.2 Quality Manual)

The Contractor is required to provide personnel to manage project quality, which may include a Design Quality Manager, Construction Quality Manager, and an overall Project Quality Manager

Relationship between Design Consultant and Construction Contractor:  The designer is contracted to the Contractor, making the relationship between reviewer and designer different than under design-bid-build projects, where MnDOT staff are responsible for communications between designer and contractor, and for providing design approval for proposed field changes. In design-build this is the designer’s responsibility.

Plan Review:  MnDOT is typically allowed only one formal opportunity to review plans, but also has informal review opportunities during Over-the-Shoulder reviews and project meetings (defined later in this Manual).

Public Relations:  The Contractor generally provides a Public Information Liaison for the project.

Environmental Commitments:  The Contractor generally provides an Environmental Compliance professional to obtain needed permits, to track that environmental commitments are being kept, and to ensure that proper procedures (e.g., BMPs) are being adhered to during construction.

Design and Construction Quality:  quality management is covered in Sections 1.7 and 1.8; examples of differences in quality management roles for design-build contracts include:

Design:

The Contractor’s designer performs both a QC and QA role; they must provide detailed QC checks of design documents and provide a QA role confirming their QC was performed.

MnDOT typically officially reviews each design package one time (or more, if specified in the contract).

Construction:

The Contractor must define Critical Activity Points for the project, and is required to prove at each of these points that contract quality obligations have been met before moving to the next construction task/stage.

The Contractor’s Quality Team must have stop work authority and is required to stop work upon discovery of non-conforming Work.

#### Exhibits

1.0.E-1		MnDOT Metro Typical Organizational Chart

1.0.E-2		MnDOT Outstate Typical Organizational Chart

Exhibit 1.0.E-1:  Typical Organization Chart of a MnDOT Metro Design-Build Contract Administration Team

Exhibit 1.0.E- 2  Typical Organization Chart of a MnDOT Out-State Design-Build Contract Administration Team

## Deliverables and Commitments

#### Purpose

In design-build, the RFP and the Contractor’s Proposal become the Contract Documents.  These define the requirements for deliverables and other contract commitments (e.g. enhanced BMP commitment in the Proposal, a commitment to a design element in the proposal, an acceptable luminaire in the RFP). This section provides guidance to the MnDOT Contract Administration Team for identifying required deliverables and commitments, and a means for tracking progress during execution of the contract.

#### Procedure

##### MnDOT oversight and verification staff develop a list of deliverables and commitments required by the contract. MnDOT defines many of the project’s deliverables and their timing in the RFP. Note that typically there are two notice to proceeds in a design-build contract.  There are typically several deliverables required prior to the first notice to proceed (NTP1).  Acceptance or approval of additional items are required for NTP2. These requirements can be found in the following RFP locations:

###### Book 1

###### In individual Sections of Book 2 (e.g., Section 5 Quality)

##### MnDOT oversight and verification staff add the additional deliverables and commitments made by the Contractor in their technical proposal.

##### The list of deliverables and commitments from the Contractor’s proposal should be started before NTP 1.  The Contractor and the design oversight staff should both agree to the deliverables and commitments made by the Contractor in the Proposal.

##### The MnDOT verification staff assigns a point person who tracks that all deliverables and commitments are provided and honored by the Contractor in accordance with the deliverable and commitment tracking checklists (see Exhibits at the end of this section, including an electronic version of the forms).

#### Useful Tips/Lessons Learned

##### The list of deliverables and commitments required by the RFP should be prepared before the Technical Proposals are due.  Ideally, the list, including construction deliverables, should be prepared early enough to be incorporated in the RFP.  It is important that the Contract Administration Team members who will be using this list be involved in its preparation, so that they will understand what is being required.

##### The list generated from the Contractor’s proposal should be merged with the list prepared from the RFP.  Compiling these lists early and merging them will help when reviewing the baseline schedule prior to NTP2.

##### Many of the deliverables are required as a condition of NTP1 or NTP2, such as insurance policies and bonds (NTP1) and acceptance of the Baseline project schedule, and approval of the Quality Manual (NTP2).  Review Book 1 for specific deliverables that are required prior to NTP1 and NTP2.

##### The Quality Manual is an early deliverable for every design-build contract.  Note that, in accordance with the Quality Manual Template Section 2.4.3.1, the design-build team may request approval of the Design Quality Management Plan (DQMP), in lieu of full approval of the entire manual as described in Book 1 Section 4.2.2, “Issuance of NTP 2”.

C.5	Some reports and other deliverables are required to be submitted monthly or at intervals.  Exhibit 1.1.E-2 may be used to track these as well, perhaps with multiple listings such as “Monthly Report – August”, “Monthly Report – September”, etc.  If this would add to much clutter or be difficult to manage, it may be more manageable to set up Reminders or Tasks within an Outlook calendar.

#### References

##### Project RFP Book 1

##### Project RFP Book 2 Section 5 (including Exhibits)

#### Attachments/Exhibits

Sample List of Deliverables (spreadsheet)

Sample List of Commitments (spreadsheet)

Exhibit 1.1.E-2  List of Deliverables

| Deliverable Description | RFP / Proposal Reference Section | Tied to NTP 1 or NTP 2 | Deliverable Submittal Date | Deliverable Acceptance Date | Doc Control # | Notes |
| --- | --- | --- | --- | --- | --- | --- |

Exhibit 1.1.E-2  List of Commitments

| Commitment Description | RFP / Proposal Reference Section | Time Component (if applicable) | Inspection Date | Doc Control # | Notes |
| --- | --- | --- | --- | --- | --- |

Both tables are available in the attachment below:

## Audits and Reviews

### Process Reviews

#### Purpose

##### The purpose of this section is to establish an approach for reviewing processes set up by the Contractor, including, but not limited to, process reviews of the Quality Manual, Safety Manual, and management practices.

#### Procedure

##### Determine the specific process(es) to be reviewed (e.g., Design Quality Procedures, payroll conformance)

##### Develop a list of sections within each process that you wish to review.  For example:

DQP 404:  Review Comment Procedure

DQP 411:  Detail Checking of Plans

DQP 410:  Detail checking of calculations

##### Determine what packages or Work on which to perform the process review (e.g., Abutment #1 RFC, Lighting RFC, Week ending March 4, 2014 payroll)

##### Notify the appropriate Contractor contact (either in person, by email or via telephone) that you will be performing an audit.  Identify the items of Work (listed in B.2 and B.3 above) to be included in the audit.  Note that while advance warning of the audit is not required, it is generally encouraged.

##### Request that the Contractor provide the necessary documents by a specific time.  A spontaneous audit may require immediate delivery, however, typically a few days is considered appropriate notice.

##### Review the information provided, and compare it to the appropriate procedures and processes established for the project.

##### Contact the Contractor during the course of the review to request additional information or request clarification if needed.  Document the results of these conversations or inquiries.

##### Document findings on the Process Review forms. See Exhibit 1.2.1.E-1 (blank form) and Exhibit 1.2.1.E-2 which provides a completed sample of this form.

##### Label each audit sequentially using the following file naming convention:

Audit report# (date).doc. (date is six characters MoDyYr)

##### Log each audit into Document Control and transmit to the Contractor.

##### If necessary, contact the Contractor to discuss a draft of the process review.  The purpose of discussing a draft is to ensure that your findings have been accurately stated.  Do not provide the Contractor copies of any draft documents.

##### The MnDOT Project Manager, or designated representative, reviews the findings of the process review with the Contractor.  For major non-conformances or systemic problems, Corrective and Preventative action plans should be prepared by the Contractor and implemented as detailed in the approved project quality manual (Section 2.4 of Quality Manual Template).

###### Corrective Actions should include revising any process, procedure or step which has been identified as the root cause (or a contributing factor to the root cause) of the non-conformance or systemic problem.

###### The Quality Manual should be revised as necessary to accommodate the corrective or preventative action.

###### In some instances the root cause is a step or process that is not fully developed in the Quality Manual.  For example, if quality problems are arising in part because proper individuals are not being provided the opportunity to review an item, the root cause may be that the Quality Manual does not fully define the distribution list of a deliverable.  The corrective action would then be to define the deliverable distribution list in the Quality Manual.

###### In some instances the root cause is a step or process that is fully developed in the Quality Manual but is not being carried out properly.  For example, the Quality Manual may define a Critical Activity Point at the leveling pad stage of an MSE wall, however the review at this point has been missed several times.  Here the corrective action may be requiring training of appropriate personnel, or possibly disciplinary measures for the individual responsible.

#### Useful Tips/Lessons Learned

##### The intent of any audit is to verify that processes are being followed properly, and to allow for correction and continued improvement if they are not.  Audits are not intended to be a venue for “gotcha,” but rather to identify areas in the process being audited that require additional attention, and to work with the Contractor to improve quality.  When a process is known to be functioning poorly, discussions should be held immediately, instead of waiting for an Audit to “reveal” the situation.  An Audit can be performed to confirm a process is not functioning.  Audit reports are useful in identifying any patterns of poor performance, and are needed to track ongoing compliance with corrective action recommendations.

##### Advise the Contractor at early Project meetings that there will be audits of processes during the Project.  This proactive approach helps avoid Contractor anxiety when the audits are performed, and can benefit the quality process by reducing adversarial attitudes.

##### Generally provide adequate time for the Contractor to be prepared for an audit, several days’ notice is usually sufficient to ensure that the audit does not cause undue hardship.

##### Audits are part of MnDOT’s quality responsibilities, and are ongoing.  Do not wait until it appears that something is not functioning to begin your first audit.

##### Early audits and spot audits are a useful way to impress on everyone the importance of following the processes at all times.

##### Proper timing of audits can help ensure that all parties are aware of processes and helps promote proper behavior early in a project.  Suggested timing of selected audits is as follows:

###### Payroll certification after the first invoice with significant labor, and another after the first invoice with significant construction labor

###### Staff qualifications prior to first submittals

###### DQP’s after the first major design package is submitted

###### Critical Activity Points early in construction

###### Document control processes shortly after initial submittals and correspondence

#### References

##### Document Control Procedure

#### Attachments/Exhibits

Process Review Form (sample)

Sample Audit

Exhibit 1.2.1.E-1  Process Review Form (sample)

Blank form embedded below:

Exhibit 1.2.1.E-2  Sample Audit

Blank form embedded below:

### Labor Compliance

#### Purpose

This section describes the process and procedures that the MnDOT Contract Administration Team will use to verify and document labor compliance on the project.

Contractors are required to pay prevailing wages in accordance with Book 1, Section 7 of the contract.  This includes Exhibit F of Book 1, which contains several sub categories such as Traffic Control Prevailing Wage, Federal Wage Rates, and the like.

#### Procedure

For design-build, the process of verifying labor compliance is the same as defined in the design-bid-build MnDOT Contract Administration Manual.  The following provides a quick reference list of the labor compliance processes to be followed for MnDOT projects:

Wage compliance checks

Certified payroll verification

Monitoring the payroll tracking system

Confirmation appropriate forms are filed

Employee interviews

Poster board confirmation

Request to sublet

#### Useful Tips/Lessons Learned

##### Payrolls:  Do not log any payrolls into Document Control, they are addressed in the Payroll Tracking System.

##### Payroll Tracking System:  Ensure that the appropriate forms are being submitted in accordance with the MnDOT Contract Administration Manual

##### Employee interviews:  Be sure to use the proper forms, and file them in the MnDOT Library and the MnDOT Document Control system (TRACS)

##### Poster Boards:  Be sure to check with compliance to verify where the Labor Law notices need to be posted if multiple project offices are established

##### Sublets:

###### The verification team must ensure that the information for sublet employees is entered into TRACS by the Contractor

###### Ensure that the Multiple Trucking Company (MTO) form is properly completed and on file for applicable sublets

#### References

##### MnDOT Contract Administration Manual, Section 2

##### RFP Book 1, Section 7

##### RFP Book 1, Exhibit F

##### http://www.dot.state.mn.us/const/labor/civil-rights-labor.html

##### http://www.dot.state.mn.us/civilrights/index.html

##### MnDOT Labor Compliance Field Review Form

#### Attachments/Exhibits

Field Compliance Review Labor Provisions

Request to Sublet Form Summary

1.2.2.E-1  Field Compliance Review on Labor Provisions

1.2.2.E-2  Request to Sublet Summary

### EEO/DBE Compliance

#### Purpose

It is the policy of MnDOT that Disadvantaged Business Enterprises (DBE), as defined in 49 C.F.R. Part 26, and other small businesses be provided the maximum feasible opportunity to participate in contracts financed in whole or in part with public funds.

This section describes the MnDOT verification process for monitoring and reporting the context of the Contractor’s compliance with the DBE requirements, and defines the steps that the MnDOT Contract Administration Team will take to recommend action, as appropriate, if the Contractor fails to comply.

#### Procedure

In design-build the process and procedures for EEO and DBE or Targeted Group Business (TGB) is not materially different than for traditional design-bid-build projects.  Section 7 of Book 1 of the RFP includes contractual information on the Project’s EEO/DBE requirements.  Exhibits D and E in Book 1 provide additional details with regard to TGB requirements.

##### If issues or questions arise regarding compliance with EEO/DBE requirements, the following must take place:

###### The MnDOT Contract Administration Team reports any issues regarding DBEs to the Project Manager.

###### The MnDOT Project Manager contacts the MnDOT Civil Rights Office.

##### If a DBE issue is determined by the MnDOT Civil Rights Office to be a Non-Compliance, the Contractor and USDOT will be notified as follows:

###### Failure of the Contractor to carry out DBE requirements specified in the contract constitutes breach of contract.  The Contractor and the USDOT will be notified of such breach, including notification that the breach may result in termination of the contract or imposition of other appropriate sanctions.

#### Useful Tips/Lessons Learned

##### It is important to remember that in design-build there is a value aspect of the selection process and this could include the approach the Contractor gave with regard to DBE and EEO.  Before allowing changes to DBE commitments, the Contract Administration Team must verify that the change or alteration would not have resulted in a different evaluation of the Contractors Proposal (i.e., that such a change would not have resulted in selection of another design-build team).

##### Use the Forms provided in Exhibits D and E of Book 1

##### Use the following website links to get additional information for MnDOT DBE and EEO programs respectively:

http://www.dot.state.mn.us/civilrights/dbe.html

http://www.dot.state.mn.us/civilrights/eeo.html

http://www.dot.state.mn.us/civilrights/

http://www.dot.state.mn.us/const/labor/civil-rights-labor.html

#### References

##### Book 1, Section 7

##### Book 1, Exhibits D and E

#### Attachments/Exhibits

None

## Contract Revisions (Change Orders)

One of the benefits of design-build is that there are fewer contract revisions than under a traditional design-bid-build project.  Under design-build, the owner is able to transfer risk to the Contractor through the contract.  The Contractor then prices risk associated with the Work, reducing the need for price revisions.  Section 13 of Book 1 defines “Changes in the Work,” defining the (presumed rare) situations where an adjustment to the contract price would be allowed/justified.

Some typical design-bid-build contract revisions become less common in design-build such as:

Differing site conditions

Change in quantity

However, there are new contract revisions that arise in design-build, such as:

Changes in Key Personnel

Change of a Major Participant

Change in Basic Configuration

Section 13 of Book 1 defines in detail the Contractor’s rights regarding Changes in Work.

#### Purpose

This section outlines the procedures for processing Change Orders.  This procedure is meant to define the steps necessary to process the change order after it has been agreed upon that a Change Order is necessary.

Change Orders are classified into two categories, Level 1 and Level 2, defined as follows:

Level 1 Approvals

For changes that do not affect contract value, completion date, or significant contractual terms (examples below).

Signatures Required

Assistant District Engineer

MnDOT Project Manager

Contractor

FHWA for Projects of Division Interest

Types of Work(Changes that Require a Level 1 Approval)

Revised method of measurement (very rare in design-build)

Document unacceptable Work or materials (unless it is of such a significance that it affects the overall “performance” of the Project, in which case a more formalized corrective action plan should be documented)

Document incentive (bonus) payments authorized by the contract and for which funds have already been encumbered (Bonus payments made to the Contractor from incentives in the contract are processed as Level 1 change orders)

Substitution of materials (if a material was specified)

Substitution of methods or equipment at Contractor’s request (this is rare in design-build)

Document changes in new standards (if contract value or completion date are not affected)

Document increased or decreased quantities (if contract value not affected and only for items that are tied to quantity in payment).  Measuring quantities is rare in design-build, however can occur.

Alterations in scope of work (if contract value and completion date are not affected, and if change is not outside general parameters of RFP and contract which would require Level 2)

Minor adjustments to special provisions and specifications that do not alter contract value, completion date or legal responsibility of the contractor

Clarifications to contract language (this is to be used primarily for clarification of technical information; input from MnDOT Contract Management and Attorney General should be sought on interpreting the contract “legal” language)

Level 2 Approvals

For changes to contract value, completion date, or significant contractual terms.

Signatures Required

- Assistant District Engineer

- MnDOT Project Manager

- Contractor

- Commissioner of Transportation

- Commissioner of Administration (or MnDOT Contract Management if delegated by Department of Administration)

- Finance (only if funds are encumbered)

- FHWA for Projects of Division Interest

Types of Work (Work Changes that Require a Level 2 Approval)

- Changes in Work if change is outside general Parameters of RFP and contract, or any change to Basic.

- Significant alterations to special provisions and specifications

- Changes in contract time

- Revisions to the pavement structural section

- Major revisions to geometric design

- Incorporation of Alternative Technical Concepts (ATC) from other proposing design-build teams

#### Procedure

##### The entire Design/Build Change Order Approval Process can be found at the following link:
http://www.dot.state.mn.us/const/tools/documents/DBChangeOrderGuidelines.pdf

##### The Contractor should document the reason why a Change Order is needed and clearly demonstrate to MnDOT why an item is not covered in the scope. All change orders must have a contract reference for the change.

#### Useful Tips/Lessons Learned

##### Review Section 13 of Book 1 for an understanding of the differences between design-build and design-bid-build change processes.

##### For an MnDOT-directed change, the MnDOT Contract Administration Team should document in writing why the change is needed, referencing any portion of the contract that relates to the change, specifically the contract allowance of directed changes.

##### Change orders and potential change orders should be part of the weekly meeting agenda.  This will help all parties appreciate the importance of early communication of any perceived changes, and foster a collaborative spirit and trust between parties.

##### Resolve change orders quickly and escalate if needed.  The MnDOT Contract Administration Team should define the timelines for advancing to each level of the escalation ladder in conjunction with Section 19 of Book 1

##### If a significant owner-directed change is proposed, consider allowing sufficient time for fully vetting risk, contingencies and schedule impacts. Hold workshops if necessary to ensure all parties understand the scope and expectations for the change.  Remember it is difficult for a contractor to price and determine schedule impacts for even relatively small change orders.

##### MNDOT has a policy, defined in Book 1 Section 13, Table 1, which allows the Contractor to price risk in a change order.  When evaluating what to allow for additional profit due to risk, the MnDOT Contract Administration Team should review Book 1 and consider the following:

It is common practice to expect that a contractor will have less risk in pricing change orders. There are exceptions to this, including:

      - If the change affects several Work items, it may be difficult to thoroughly analyze, in a short timeframe, the effects on schedule

      - If a change impacts the timing of long-lead-time procurement orders

      - If a change results in a need to provide additional geotechnical exploration and monitoring (e.g., for settlement or vibrations)

Where the Work is simple and easily defined, often it can be performed with little to no risk.  For example, identifying a need for a longer guardrail, or changing a sidewalk or mixed-use path width with no effects on grading.

The MnDOT Contract Administration Team should justify what percentage of profit to use based on risk on a case-by-case basis.  On larger change orders, consider paying for additional exploration prior to agreeing to additional profit percentage or contingency.

##### Book 1 provides additional information on  the timelines associated with Contractor change order related submittals, as well as more guidance for MnDOT staff on reviewing Requests for Cost Proposals and Notices of Change

##### There are several additional items inherent to design-build contracting that need to be considered when reviewing change orders:

###### The Contractor is the engineer of record so they need to include their design costs in change order cost proposals

###### There are more warranties in design-build, so the Contractor may include a markup to account for warranty risk

###### Because the Contractor is also the engineer of record, there is more schedule risk inherent in changes (because design and the design review process must be completed before construction).

#### Change Orders must be tracked in a log (Exhibit 1.3.E-1 provides a sample) to provide a record of scope, schedule, and price changes.  References

##### RFP Book 1, Section 13

##### Library Procedures

##### MnDOT Contract Administration Manual

##### Book 1, particularly Section 13.

#### Attachments/Exhibits

Change Order Log Sample

Change Order Form

Exhibit 1.3.E-1  Change Order Log (sample)

Exhibit 1.3.E-2  Change Order Form

Exhibit 1.3.E-2  Change Order Form (continued)

## Documentation

The purpose of this section is to provide an understanding of the MnDOT Contract Administration Team’s role with respect to documentation on design-build Projects, including the following:

Contract Records – Security and Confidential Documents

Document Control

Progress Meeting Notes

### Contract Records (Security/Confidential Documents)

#### Purpose

The purpose of this section is to explain the process for accepting and reviewing security and confidential documents, and to outline the process for keeping these documents secure.

The need to manage security-related and other confidential documents is not common, and is restricted to Bridges as defined by the MnDOT Bridge Group.

#### Procedure

##### Security documents as defined by the MnDOT Bridge Group are submitted on hardcopy only and sent via mail or other non-electronic shipping method.  In no case are the documents to be submitted electronically.  Each security document is marked “CONFIDENTIAL”.

##### Security documents are not entered into the TRACS system, but are kept by the MnDOT Bridge Office in a secure location after review and acceptance of the Documents.

##### MnDOT’s Document Control Manager, or designated representative, makes hard copies of the original for review.  Hard copies made of the original security document are hand numbered and distributed only to those who need to review the Document, as determined by MnDOT.

##### MnDOT reviewers comment directly on the hardcopy of the document, and return their hardcopy to MnDOT’s Document Control Manager, or designated representative.

##### When all hardcopies have been returned, all comments are then transferred to the original security document and the hardcopies are shredded.

##### MnDOT comments are then forwarded via mail or other non-electronic shipping method to the author of the security document.  Comments are not disseminated by electronic means.

##### The author of the security document must respond to each MnDOT comment via phone call or hardcopy.

##### After the author of the security document has reviewed and responded to the comments, a comment resolution meeting is scheduled to discuss any unresolved comments.

##### Following resolution of all comments, the author of the security document submits final security documents for review and MnDOT signature in accordance with the Final RFC Procedure of this Manual (Section 1.7.4.3).

#### Useful Tips/Lessons Learned

##### If it is suspected that a structure or element of the project may be subject to security concerns, confer with the MnDOT Bridge Group

#### References

##### Released for Construction – Contractor Quality Manual

#### Attachments/Exhibits

None

### Document Control

#### Purpose

This section provides guidance on the document control processes to be used on design-build projects.

The MnDOT Contract Administration Team provides and operates a Document Control System to support the project office and to manage, document, and store the project paperwork and electronic submittals.

The MnDOT Contract Administration Team provides the necessary personnel for the Document Control Center, which is the location where hard copies of documents are stored.

This section does NOT apply for CONFIDENTIAL or SECURITY ITEMS, discussed above in Section 1.4.1.

The MnDOT Contract Administration Team is responsible for ensuring that the document control process is functioning properly.  It is important to provide proper training to all personnel responsible for transmitting and receiving documents and data on the project.

#### Procedure

##### Document Control Start-up procedures are as follows:

###### Hold a meeting with the Contractor’s Document Control staff and MnDOT Document Control staff

Establish a list of documents to be controlled and identify the person responsible for each document

Establish the file structure for electronic and hard copies

Establish a naming convention for documents not already pre-defined by contract

Establish where final hard copies will reside and what individual MnDOT departments require copies (e.g., the Bridge Office for all documents related to structures)

###### Establish TRACS access for all individuals responsible to provide input to or receive documents from TRACS

###### Establish the process for providing documents to non-TRACS users, internal and third parties

###### Establish protocols for confirming documents are incorporated properly into the system through a combination of reports generated by TRACS, and regular reviews by appropriate personnel

##### For each project, a Document Control Center shall be set up and maintained as follows:

###### The document control center for the project is generally located at the co-located office if there is co-location; otherwise it is located at the MnDOT Resident Engineer’s office (e.g., Golden Valley, Mendota Heights, District 2

###### The Document Control center is supported by document control specialists responsible for logging, indexing, scanning, distributing, collecting, filing, and maintaining incoming and outgoing correspondence and documents

###### Documents obtained in the field (e.g., on-site or at field offices) must be processed through the Document Control Center

##### Document Storage procedures include:

###### All documents sent through Document Control are stored electronically and in hard copy, when hard copies are required by contract.

###### Electronic versions are stored in the TRACS system

###### Hard copies are stored in accordance with the format shown in Exhibit 1.4.2.E-1

###### Final storage of hard copies is defined at the Document Control start-up meeting.

##### Procedures for Receiving and Distributing Documents from the Contractor:

###### All submittals and documents received for the project (excluding over the shoulder reviews) are delivered to the Document Control Center

Verification staff receiving submittal documents directly from Contractor staff need to forward them to Document Control

Verification staff receiving email correspondence containing approvals, acceptance, directives, disputes, or other pertinent project-related materials, shall forward the email to Document Control

###### Document Control verifies that the submittal document contains the appropriate number of hard copies and that an electronic version is uploaded into TRACS.

###### Document Control logs each document the Contractor uploads into the TRACS system.  The process includes:

The Contractor assigning a unique sequential Document Control number to each document

The Contractor assigning the appropriate document type in TRACS (e.g., submittal, transmittal, etc.)

The Contractor attaching the electronic file to the TRACS Document Control number.

If hard copy only is provided, Document Control scans the document and enters it into TRACS (excluding confidential/security documents).

Document Control distributes the information in the format needed via a routing slip attached as Exhibit 1.4.2.E-4; hard copies are routed to the individuals shown in Exhibit 1.4.2.E-1.

Document Control stores the hard copy in the file cabinet according to the Document Management System File Number Descriptions shown in Exhibits 1.4.2.E-2 and 1.4.2.E-3.  If a CD is provided, Document Control files the CD in the CD Library and provides a hard copy of the TRACS document output in the file cabinet.

##### Outgoing Documents shall be handled as follows:

###### All outgoing documents to the Contractor or any other third party (e.g., utility, city, stakeholder) are sent by MnDOT Document Control

###### Document Control scans the document, logs the document into TRACS, and attaches the scanned file

###### For transmittals to the Contractor.

Document Control prepares a transmittal cover sheet generated from the TRACS Transmittal Tab in the DMS Module

All Transmittals are addressed to the Contractor’s Project Manager (additional recipients can be copied, and must be listed on the distribution list in the transmittal cover sheet)

All Transmittals are listed on the form as being from MnDOT’s Project Manager

Document Control is encouraged to provide additional guidance or comments in the Remarks section of the TRACS transmittal, so that the Contractor knows why it was sent and whether any action is required

Document Control scans the transmittal cover sheet and attached documents, logs the transmittal into TRACS and links the scanned document(s).

Document Control stores the hard copy in the file cabinet according to the Document Management System File Number Descriptions shown in Exhibit 1.4.2.E-2 and 1.4.2.E-3.

###### Letters to external stakeholders shall be handled as follows:

The Contract Administration Team staff reviews the contents of the letter with the MnDOT Project Manager.

Contract Administration Team verification staff provides a cover letter, or may request that Document Control draft a cover letter for signature

Document Control sends the letter to the addressee, and to ‘cc’ and ‘bc’ recipients (to the latter with no transmittal cover) using standard MnDOT mailing procedures

Document Control scans the document, logs the document into TRACS, and links the scanned file

Document Control stores the hard copy in the file cabinet according to the Document Management System File Number Descriptions shown in Exhibit 1.4.2.E-2 and 1.4.2.E-3.

##### Library Documents – the following hard copy documents are kept in the Document Control Library located at the MnDOT Document Control area:

Final RFC Documents

        - Field Design Changes (FDC)

        - Notice of Design Changes (NDC)

        - RFIs

Change Order Books

Invoice Books

Field Reports

        - Material Testing Reports

        - Inspection Testing Reports

        - Lab Reports

        - Field Wage Checks

###### Final RFC Documents:

Upon receipt of any hard copy RFC Documents stamped “Release For Construction,” Document Control confirms the Contractor has scanned the RFC Document, logged the document into TRACS, and linked the scanned file

Document Control develops a log of each RFC Package submitted, in accordance with Exhibit 1.4.2.E-5 (RFC Log)

A hard copy of the log is kept with the RFC packages in the Document Control Library

Document Control stores the hard copy of the RFC Documents in 11 x 17 inch three-ring binders, with tab delineators between each RFC Package as necessary

If NDC or FDC are submitted, Document Control will perform the following actions:

        - Confirm that the Contractor has scanned the NDC or FDC document, logged the document into TRACS, linked the scanned file, and updated to RFC package in TRACS with any revised drawings

        - Log the NDC and FDC into the RFC log

        - File the NDC and FDC in the Library next to the corresponding RFC Package

###### Change Order Books:

Change Orders are processed in accordance with the contract revisions process of this Manual (Section 1.3)

Document Control maintains three-ring binders of all outstanding and fully executed Change Orders; these are kept in the Document Control Library

Document Control maintains a log of the Change Orders (see Exhibit 1.4.2.E-7), which is kept in the three-ring-binders

Supporting documentation used to develop the Change Order is stored in the three-ring binders

Document Control scans and logs Change Orders transmitted for signature in Document Control and TRACS.  Hard copies of the transmittals are stored in the library.   Note that supporting documentation is not scanned and placed into TRACs until the Change Order has been fully executed

Upon receipt of a fully executed Change Order, Document Control will perform the following actions:

        - Scan the Change Order and all supporting documentation, log the Change Order into TRACS as a fully executed change Order, and attach the scanned file

        - Route the Change Order via the routing process identified in accordance with Section B.3 of this procedure to the following:

Project Manager

Construction Manager

Change Order/Invoicing lead

        - Store the hard copy in the MnDOT Document Control Library

###### Invoice Books are managed as follows:

The  MnDOT Project Manager usually designates a Project Office Manager who provides final invoices to the document control manager (invoices are prepared in accordance with Sections 1.5 and 1.6 of this Manual)

Document Control scans the invoice, logs the invoice into TRACS using File Number 03.11, and places the hard copy in the Library

###### Field Reports are handled as follows:

Document Control works with the Project Office Manager to determine which documents are classified within this category

If a document is classified in the Field report category, Document Control logs the document into TRACS and identifies which type of document it is if not defined by the originator

Document Control distributes copies to the individuals indicated on the distribution list (refer to Exhibit 1.4.2.E-4)

Document Control stores the hard copy documents in the Library, sorted by type (e.g. Material Testing Report, lab report, field wage check) and by date.

Document Control provides tabbed dividers between types

##### Procedures for Ingoing/Outgoing Reporting:

###### At the end of each work day, Document Control produces a pdf log of each document logged into TRACS during the day.  The report is generated using the Document Management System (DMS) procedure of the TRACS manual.

###### Document Control e-mails the list to all pre-determined MnDOT Contract Administration Team members.

#### Useful Tips/Lessons Learned

##### It is critical to ensure that everyone follows the document control processes at the start of the project – everyone must make it a habit for the process to be successful

##### Have a document control kick off meeting explaining the naming convention of documents (as defined in the approved Quality Manual), locations of stored materials, particularly project logs, etc.

###### Note the Quality Manual template provided with the RFP includes a sample basic naming convention that the Contractor can use or modify

##### Document Control staffing concerns:

###### It is better to err by having too many document control personnel at the start of the project, than to try to catch up when document management gets behind.  Once document control is functioning properly, resource needs can be reviewed and staffing adjusted as needed

###### It is important to remember that document control staff does not want to slow down the project, particularly at the beginning of a project, document control staff will need extra direction in identifying document types and understanding distribution and storage procedures for each.

###### Given that many projects take multiple construction seasons, or experience staff changes, written records are critical

##### When preparing project-specific processes to help ensure consistent document control and review processes, it is important to identify reviewers by name and provide timelines.  Adjust the process as applicable based on project-specific factors including, but not limited to:

###### The results of process review audits

###### Whether the project is using co-location or not, e.g., will there be two repositories for hard copies (to be consolidated at the end of the project), will networks allow one electronic file management location, etc.

##### It is important to set it up the file naming convention so that when a search is conducted all relevant results are found.  For example, all submittals for a particular package should have an identifier that ties them together.

#### References

##### Section 1.3 Contract Revisions (Change Orders)

##### Section 1.4.1 Contract Records (Security/Confidential Documents)

##### Section 1.5 Schedule Review

##### Section 1.6 Invoice Review

#### Attachments/Exhibits

Document Control Distribution

Document Management System File Number Descriptions, Option 1

Document Management System File Number Descriptions, Option 2

Routing Slip

Transmittal Cover Sheet

RFC Log

Change Order Log

Exhibit 1.4.2.E-1  Document Control Distribution (sample)

| Category | Sub Category | Distribution List |
| --- | --- | --- |
| Plan Submittals (NOT RFC) | Bridge Plans and Bridge Reports |  |
|  | Roadway Plans Utility Plans Traffic Plans Drainage Plans MOT Plans |  |
|  | Environmental Plans and Permits |  |
|  | Geotechnical Reports |  |
|  | Noise Walls |  |
|  | Retaining Walls |  |
| Construction Documents | Lab Tests Field Design Changes (FDCs) RFIS Released for Construction Plans Non-Conformance Reports Material Reports |  |
| Misc. Reports | Change Orders Invoices Claims |  |
|  | Public Relations |  |

Exhibit 1.4.2.E-2  Document Management System File Number Descriptions – Option 1

| {Contractor} | XXXX Design-Build Project DOCUMENT MANAGEMENT PLAN |
| --- | --- |
| Doc. No.: DMP201 | Rev. 0 | [date} | Page 1 of 8 |

ELECTRONIC FILE NAMING CONVENTION

All electronic project documents should be named according to the following Naming Convention:

CCC-DDD-yyyymmdd-(ssss)nn.DOC

Where …

| CCC |  | 3 letter document type – See list below |  |
| --- | --- | --- | --- |
| DDD |  | 2 or 3 letter discipline – See list below |  |
| yyyy |  | 4 digit year |  |
| mm |  | 2 digit month |  |
| dd |  | 2 digit day |  |
| ssss |  | Optional Subject |  |
| nn |  | 2 digit sequential number |  |

| Document Type | Discipline |
| --- | --- |
| MEM Memo | DRG Drainage |
| ROC Record of Conversation | RDY Roadway |
| LTR Letter | RWL Roadway – Walls |
| FAX Facsimile | TRF Traffic |
| TRN Letter of Transmittal | STR Structures |

Exhibit 1.4.2.E-2  Document Management System File Number Descriptions – Option 1 (continued)

| Document Type | Discipline |
| --- | --- |
| RPT |  | Reports | UTY | Utilities |
| AGN |  | Agenda | ITS | Intelligent Transportation Systems |
| MIN |  | Meeting Minutes | VQA | Visual Quality/Aesthetics |
| EML |  | Email | GEO | Geotechnical |
| OTH |  | Other | ENV | Environmental Compliance |
| ADT |  | Audit | PIN | Public Involvement |
|  |  |  | SVY | Survey |
|  |  |  | CQ | Construction Quality |
|  |  |  | DQA | Design Quality Assurance |
|  |  |  | DQC | Design Quality Control |
|  |  |  | DC | Document Control |
|  |  |  | PM | Project Management |

Exhibit 1.4.2.E-3  Document Management System File Number Descriptions – Option 2

Excerpt below.  See embedded pdf file below for full list of codes.

Exhibit 1.4.2.E-4  Routing Slip (sample)

Exhibit 1.4.2.E-5  Transmittal Cover Sheet (sample)

Exhibit 1.4.2.E-6  RFC Log

Exhibit 1.4.2.E-7  Change Order Log (sample)

### Progress Meeting Notes

#### Purpose

The purpose of this section is to establish an approach for recording, storing and retrieving meeting minutes for a design-build project.

#### Procedure

##### Meeting minutes are required for all meetings, excluding Over-the-Shoulder (OTS) review meetings

###### Meeting notes from OTS meetings are not officially transmitted

##### The Contractor is responsible for recording minutes of all meetings

##### Minutes must include a list of attendees

##### The Contractor submits draft meeting minutes to all attendees for review

##### MnDOT submits suggested revisions to the minutes to the Contractor (or informs the Contractor that no changes are necessary)

###### MnDOT may respond to draft meeting minutes via e-mail (no need to transmit through Document Control and TRACS)

##### The Contractor incorporates changes as it sees fit, and submits the final meeting minutes to Document Control.  However, disagreements should be reviewed before meeting minutes are finalized.

##### Document Control uploads final meeting minutes in TRACS under “File Description Meeting and Minutes”

##### Document Control makes an electronic copy and attaches it to the TRACS Document Number.

##### Document Control places the hard copy of the meeting minute transmittal into the document file

##### Document Control staff distributes minutes to MnDOT staff as described Section 1.4.2.B.4 (Document Control).

#### Useful Tips/Lessons Learned

##### Refer to Book 2 Section 5 as well as individual Book 2 Sections to confirm what meetings are mandatory.

##### It is critical to set expectations of the preparing party, timeliness and content of meeting minutes early in a project.  Late meeting minutes result in less accurate meeting minutes. General information presented in meeting minutes does not provide the accuracy needed if minutes are later used for confirming decisions, or following up on action items. The Contractor must be concise and accurate with meeting minute content. Elaboration on a complicated topic is sometimes warranted, followed by a concise result or conclusion.

##### Encourage the Contractor to provide an agenda for all meetings, to help keep the meeting focused.

#### References

##### TRACS User’s Manual

##### TRACS File Number Descriptions

##### Document Control Procedure (From Contractors Quality Manual or Part 9 of Volume 4 of the Quality Manual Template)

#### Attachments/Exhibits

None

## Schedule Review

#### Purpose

This section provides an understanding of scheduling and process reporting, and describes the process by which the MnDOT Contract Administration Team:

Reviews the schedule provided with the proposal

Reviews the preliminary schedule

Reviews and controls the baseline schedule

Evaluates subsequent schedule submittals

Manages and reports project performance

Issues payment

This section covers schedule submittals during the project lifecycle (design-construction-closeout); it does not include guidelines for developing schedules.

The Contractor conducts all Work necessary to meet the requirements of Schedule Management as detailed in Book 2, Section 2.

The MnDOT Contract Administration Team’s role is critical in ensuring, prior to approval, that submitted schedules and schedule updates are representative of the actual Work performed, and are achievable.

Schedule review is particularly important in design-build contracts, because payments are based on project milestones, and not on quantities as is common in design-bid-build projects.  Knowing the expected length of a schedule item helps estimate the percentage of completion for payment.  .

#### Procedure

##### All schedules are prepared and maintained in Primavera 6 (P6), unless otherwise allowed by the contract.

###### The Contractors should be encouraged to prepare proposal schedules in MnDOT’s P6 system – this approach results in less rework of the schedule after award

###### If MnDOT’s P6 system is used, Preliminary schedules reviewed before NTP1 can be progressed further

##### The MnDOT Contract Administration Team reviews the schedule submitted with the proposal.

##### After selection, schedules are approved as detailed in Book 2 Section 2. The process generally includes the following:

###### Prior to any payment on non-management items:

Compare the submitted schedule to the schedule presented with the Proposal identifying, additional activities, differing activity durations, logic differences, float differences and reconciles as necessary.

Compare the schedule of prices to the price sheet provided with the proposal to ensure subtotals of  price sheet do not change without an authorized change order

###### Review and approval of the preliminary schedule, prior to NTP 1, includes:

Identifying any logic inconsistencies

A review of Float and other schedule attributes, such as predecessor and successor task relationships, to see if they seem consistent with standard construction sequences

###### Reviews of the baseline schedule and resources to make sure that the payment items on the CPM are reasonable.  This work is performed with project staff or by other functional areas of MnDOT.

Set up payment and schedule of price sub amounts upon approval

###### Reviews of the original payment breakdown to ensure the payments (schedule of price items) are made at a reasonable time within the schedule and are not front-loaded, including a review of design costs. Some items to look for include:

Early designed construction items for disproportional costs, such as foundations and fills.  Are there adequate design costs allocated for post-design support of FDCs, NDCs and As-Builts

For early design packages such as MOT and foundations look for effort levels

Foundation costs should be proportional to the type of bridge

Prices for walls that are constructed early should be consistent with historical prices accounting for site condition and uses

###### Document the reasons why the costs are reasonable or unreasonable and provide feedback to the Contractor on items which are not deemed reasonable.  Keep comments in the MnDOT library.

###### Formally notify the Contractor in writing (processed through Document Control) when the baseline schedule has been accepted.

##### Monthly (unless modified by the contract), and with each subsequent schedule update submittal, the MnDOT Contract Administration Team will review the schedule following Section 2.3.2.7 of Book 2, including the following activities:

###### Compare changes to previous approved payment and to previous accepted schedules.  The latter is done via schedule analysis modules within TRACS software.

###### Review each schedule to ensure it meets the project requirements, as detailed in Book 2 Section 2. Specific items to look for include:

Check that change orders have their own Schedule Of Value

The totals of Schedule Of Value’s continue to match the proposal (unless modified by a change order)

Are logic changes identified and discussed in narrative form

Are any duration changes or start/finish date changes discussed in narrative form

###### Provide written comments back to the Contractor in TRACS on any objections to the submitted schedule.

###### Formally notify the Contractor of the approved schedule.

###### Review the payment requests in accordance with the Design Invoice Review Procedures and Construction and Non-Design Invoice Review Procedures to ensure they are representative of the updated schedule.

##### Once all schedule and invoice comments have been resolved with the Contractor, the Contractor submits the schedule through TRACS.

##### The invoice is signed by the MnDOT Project Manager.

##### The MnDOT Project Manager or designated representative e-mails the signed invoice to CPG for payment.

##### The MnDOT Project Manager or designated representative provides all invoice documentation to the project Document Control staff for storage in TRACS and the MnDOT Library.

#### Useful Tips/Lessons Learned

##### For initial schedule reviews:

###### If MnDOT’s P6 system was used in the proposal phase by the Contractor, encourage the Contractor to progress the Preliminary Schedule further to vet logic, design integration and other items traditionally more difficult to progress from Preliminary Schedule to Baseline schedule Approval.

###### Watch out for front-loaded cost items that have a high cost and an early completion deadline (e.g. early design packages, foundations, MOT phase 1).

###### Ensure design activities tie to the construction of items and that there is review time included. A meeting to confirm this early in the project can give a better feel if design and construction are being properly coordinated.

###### Look for post-design services from the designer. This is a good way to ensure that they will remain engaged and responsive after the RFC plans have been accepted.  These fees are typically broken out from As-Built fees.

##### The following are helpful when reviewing schedule documentation:

###### Remember the schedule is only updated after the payment is approved.

###### To document completion of a task for payment, use TRACS to tie in diary entries to specific pay items.

###### For payment of material on hand, refer to Book 1, Section 11.  Pay only upon proof of payment, not on invoices.

##### The following is helpful to ensure the Schedule ties to NTP1 and NTP2 properly:

###### Remember approval of the Preliminary schedule is usually a requirement for NTP1, verify with Book 1

###### Approval of the Baseline schedule is a requirement of NTP2, verify with Book 1

##### Remember MnDOT is on the critical path for payment.  There are defined timelines for payment once all approvals are recorded.   Schedule and other invoice review processes should take place with minimal delay.  In the long run, delays in payment of invoices leads to higher costs, as MnDOT consultants and contractors must typically borrow money to meet payroll obligations prior to receiving payment for work completed.

#### References

##### RFP Book 2 Section 2

##### Section 1.6.1 Design Invoice Review

##### Section 1.6.2 Construction and Non-Design Invoice Review

##### RFP Book 1 Section 11 (Material on Hand)

#### Attachments/Exhibits

None

## Invoice Review

### Design Invoice Review

#### Purpose

This section outlines the procedures for processing payments for design services provided as part of a design-build contract.  Invoices for design services come through the cost-loaded CPM schedule provided by the Contractor.

Approval of invoices should always be based factually on the latest approved updated baseline schedule.

#### Procedure

##### Document Control distributes the Contractor’s Invoice/Schedule update to the Project Manager for processing.

##### The Project Manager prepares the invoice in Excel format for MnDOT review.  See Exhibit 1.6.1.E-2 for a sample.

##### MnDOT’s schedule team (part of the Contract Administration Team) provides a breakdown of the engineering service payments requested on each invoice.  The request for payment is distributed to the following MnDOT Contract Administration Team individuals:

###### Project Manager

###### Design Manager

###### Construction Manager (only for Shop Drawing review and other construction phase design services)

##### The individuals in B.3 or their designees review the request for design payments.

##### MnDOT staff involved with the activities for which payment requests have been made, assess the validity of the requested payment against the design payment guidelines presented in Exhibit 1.6.1.E-1.  Each invoice may be reviewed by different individuals.

##### MnDOT Contract Administration Team staff should confirm that the payment is not in excess of, nor does the payment breakdown roll up in excess of the Schedule of Prices submitted with the Proposal. Exhibit 1.6.1.E-3 provides a sample contractor pay estimate.

##### For variances in payment which cannot be readily justified, or which vary significantly from the guidelines established in 1.6.1.E-1. Use the comments section in Exhibit 1.6.1.E-2 (add as necessary) to document the reason for payment.

##### MnDOT Contract Administration Team staff makes a recommendation for design payment based upon their design reviews and in accordance with the attached payment guidelines (Exhibit 1.6.1.E-1).

##### The MnDOT Project Manager or designated representative meets with the Contractor’s invoice personnel to resolve any differences between the Contractor’s request for payment and the MnDOT justification for payment.  The MnDOT Project Manager may modify the MnDOT justification percentages in consultation with MnDOT staff that reviewed the invoice in response to the meeting with the Contractor’s personnel.

##### Invoices are processed through the Schedule Analysis procedures covered in Section 1.5 of this manual.

B.11	The breakdown of requested payments and MnDOT’s responses must be documented and loaded into Document Control. This documentation must be sufficient to explain the Contractor’s request and MnDOT’s responses to financial reviewers (and auditors) who are unfamiliar with the project.

#### Useful Hints/Lessons Learned

##### Be sure to review the submittal and commitments log and the RFC logs – these will help determine the status of much of the design

##### Review the schedule to help identify items that should be ready for payment according to the approved schedule

##### Review shop drawing logs for payment regarding post-design services associated with shop drawings

##### Review NCR and corrective action reports for design packages that may require withholding payments

##### Encourage the Contractor’s design team to hold OTS meetings; these meetings help properly identify design progress

##### Review the contract to see if there is withholding for post-design services or if they are required to show the work in appropriate schedule activities and the payment breakdowns

##### Be sure to remind the Contractor of any withholding requirements with the first invoice

##### Be sure to remind the Contractor of designer responsibilities with As-Built drawings and other post-design roles and learn how they will be kept engaged and available

#### References

##### Section 1.5 Schedule Review

#### Attachments/Exhibits

Design Payment Guidelines

Sample Contractor Pay Estimate Worksheet

Sample Contractor Pay Estimate

Sample Voucher

Exhibit 1.6.1.E-1  Design Payment Guidelines (sample)

| Activity Type | Complete | Comments |
| --- | --- | --- |
| Preliminary Design Related Activities | 0-30% | No OTS Reviews, but brief overview has been provided |
|  | 30% | One OTS, Cut Sheets |
|  | 30-100% | Verf. Team validates progress |
| MnDOT Review Activities | 0% | No Submittal |
|  | 50% | Submitted for Acceptance |
|  | 100% | Comments Resolved |
| Final Design Activities or Issue RFC Packages | 0% | Prelim Design Activity not at 100% |
|  | 0-75% | At least one OTS |
|  | 75-90% | Submitted for Acceptance |
|  | 100% | Accepted |
| Construction Activities | 0-100% | Prorate over duration |
| Preliminary Bridge Plans Reports / Analysis | 0-75% | No OTS reviews, but overview has been provided |
|  | 75% | OTS Review |
|  | 75-90% | More than one OTS |
|  | 90% | Submitted for Acceptance |
|  | 100% | Accepted |

Exhibit 1.6.1.E-1  Design Payment Guidelines (sample) - continued

| Activity Type | Complete | Comments |
| --- | --- | --- |
| As-Built | 100% | As-Built Accepted |
| Shop Drawings | 0-70% | No OTS reviews, but brief overview has been provided |
|  | 70% | OTS Review |
|  | 90% | Submitted for Acceptance |
|  | 100% | Accepted |
| On Site Design Coordination / Eng Sup. | 0-100% | Prorated over duration |
| Surveys | 0-100% | Based on verification staff assessment of completeness |
| 30% Design Packages | 100% | At Least one OTS |
| 60% Design Packages | 0-100% | Plans have made progress since 30%, more than one OTS |
| 90% Design Packages | 0-75% | Plans are mostly complete |
|  | 100% | Submitted for Acceptance |
| 100% Design Packages | 100% | Accepted |

Exhibit 1.6.1.E-2  Sample Contractor Pay Estimate Worksheet

Exhibit 1.6.1.E-3  Sample Contractor Pay Estimate

Excerpt below.  Click on embedded pdf file below for full sample invoice.

Exhibit 1.6.1.E-4  Sample Pay Voucher

Excerpt below.  Click on embedded pdf file below for full sample pay voucher.

### Construction and Non-Design Invoice Review

#### Purpose

This section outlines the procedures for processing payments for construction and non-design services provided as part of a design-build contract.

Non-design related services include:

Management Items

Construction Items

Includes pavement repair

Includes other maintenance items

Geotechnical Items

Survey Items

Other unique items such as

Hazardous or regulated material disposal or hauling’

Well-sealing

Incentives

Instrumentation

Invoices for construction services come through the cost loaded CPM schedule provided by the Contractor.

Approval of invoices should always be based factually on the latest approved updated baseline schedule and the bid file (as amended for contract modifications, e.g. current schedule activities that are in the payment breakdown.

#### Procedure

##### Document Control will receive each invoice through the Voucher process.  Payments are not processed from reports generated by TRACS.

##### MnDOT’s schedule team (part of the Contract Administration Team) provides a breakdown of the non-design service payments requested on each invoice.  The request for payments are then distributed to the following MnDOT Contract Administration Team individuals:

###### Project Manager

###### Construction Manager

###### Inspection Lead Bridge

###### Inspection Lead Civil

##### The Project Manager prepares the invoice in Excel format for MnDOT review.  See Exhibit 1.6.1.E-1 of the Design Invoice Review Section for a sample contractor pay estimate.

##### The Project Manager determines the payments for management items and survey items based upon the pro-rated schedule.

##### Document Control forwards the construction items to the individuals listed in B.2 to review.  These individuals review the requested amount from the Contractor and either concur or provide a percent complete based upon MnDOT’s evaluation of the site conditions.  The MnDOT Project Manager meets with the Contractor regarding the construction items and resolves any differences between the Contractor’s requested payments and MnDOT’s assessment.  Upon resolution of these items, the Project Manager returns the spreadsheet and supporting documentation to Document Control.  The spreadsheet and supporting documentation must be sufficient to explain the Contractor’s request and MnDOT’s responses to financial reviewers (and auditors) who are unfamiliar with the project.

###### For material on hand or any form of payment prior to work, pay is based on documentation of payment, not on invoices.

##### Invoices are processed through the Schedule Analysis procedure covered in Section 1.5 of this manual.

#### Useful Tips/Lessons Learned

##### It is important for those reviewing the invoice to visit the site with the Contractor to review the status of constructed items

##### Review the schedule to help identify items that should be ready for payment according to the approved schedule

##### Always review NCRs, corrective actions and audit results before approving payment for an activity

##### Review data in TRACS and ensure the data will support the agreed-to progress.  If reports are not in TRACS do not pay for the activity.

##### Be sure to remind the Contractor of any withholding requirements with the first invoice.

#### References

##### Section 1.5, Schedule Review

##### RFP Book 1 Section 11 Material on Hand

#### Attachments/Exhibits

None

## Design

The purpose of this section is to provide an understanding of the MnDOT design oversight team’s role during a design-build project with respect to:

Design Oversight Roles

Quality Manual

Design Oversight Meetings

Design Oversight Reviews

Over-the-Shoulder Reviews

Release for Construction – Review

Release for Construction – Final

Design Process Reviews

Right of Way (R/W)

### Design Oversight Roles

#### Purpose

This section provides an introduction to the overall design oversight role of the MnDOT Contract Administration Team, defining the team members and their roles. It also describes a Contractor’s typical design team structure, and the interaction needs between them.

The following information will assist the MnDOT Contract Administration Team understand typical design oversight roles during a project.

#### Procedure

The following are typical roles on MnDOT and Contractor design staff.

##### MnDOT design oversight staff roles:

###### Oversight design manager:  may be the MnDOT Project Manager or other person responsible for organizing and reviewing design comments before they are entered into TRACS.

###### Discipline review leads:  technical leads that have expertise in their discipline (e.g., roadway, drainage, structures, geotechnical, traffic, etc.) to review the Contractor’s design for conformance to standards and the contract.

###### CPM Schedule reviewer:  will review schedule updates to confirm design is on schedule and logic is maintained in the schedule.

###### Environmental Compliance manager:  will review designs for compliance with applicable permits. The MnDOT Contract Administration Team may include a regulated waste specialist or other specialists, refer to Section 1.9 of this manual.

##### Contractor Design staff roles:

###### Design Manager:   the designer’s representative that coordinates all design activities

###### Discipline or Task lead:  personnel responsible for each discipline (the engineer of record for each discipline)

###### Designer:  individuals doing design for each discipline

#### Useful Hints/Lessons Learned

##### It is very helpful to have a single person other than those providing design review comments to review all comments to verify there is a contract reference and to verify that MnDOT comments do not reflect preferences or include duplications, before they are entered into TRACS

###### It is important to not require the Contractor to respond to MnDOT Contract Administration Team staff comment preferences.  However, that does not mean preferences cannot be pursued. Often if a contractor can implement a preference without cost or schedule impacts they will. These preferences should be presented informally outside of TRACS, generally in an OTS setting or at Task Force meetings.

###### It is important to not enforce preferences, such enforcement can be misconstrued as a request for a Change Order, opening up the project to schedule and cost changes.

##### Understand that depending on the size of the project, the number of personnel involved on both teams can vary.

###### Sometimes multiple roles are covered by one person on small projects

###### On larger projects, two people may fill one role such as environmental compliance, traffic maintainer, etc.

##### Be aware that the Design Manager for the Contractor may not be the contact for design reviews. The contact may be a discipline lead or the design quality manager. Regardless, the Contractor must follow the contract. It is important to define these interaction paths early.

##### Consider preparing project-specific processes that will ensure consistent review processes.  Adjust this process as deemed necessary for co-location versus not co-located

###### Identifying specific reviewers by name helps overall interaction, allowing designers to contact commenters for further clarification.

###### Consider defining all review times. Don’t entertain inconsistent review times, all reviews of a given type should be modified if one is modified.

###### If the designers and reviewers are co-located, synergy can be realized by timely pre-review meetings, Over-the-Shoulder reviews, etc. to reduce overall design review comments. This ultimately may speed up reviews and provide some project float.

##### It is helpful to have MnDOT Contract Administration Team members with construction and environmental expertise at project meetings that are primarily for or during design.

##### It is helpful to learn how the Contractor’s design team will be engaged in the post-design (construction) work.  It is essential that these personnel are available during the construction phase to develop or approve field changes and answer design related questions.

#### References

##### RFP Book 2 Section 5

#### Attachments/Exhibits

Typical Design Oversight Organization Chart – Option 1

Typical Design Oversight Organization Chart – Option 2

Typical Contractor Design Organization Chart

Exhibit 1.7 - E.1  Design Oversight Organization Chart – Option 1

Exhibit 1.7.1.E-2  Design Oversight Organization Chart – Option 2

Exhibit 1.7.1E-3  Contractor Design Organization Chart

### Quality Manual

#### Purpose

The purpose of this section is to provide an understanding of the MnDOT Contract Administration Team’s role during a design-build project with respect to:

Approving the design portions of the Quality Manual

Overseeing the Quality Manual design commitments

#### Procedure

##### Approval of the Quality Manual

###### The approval process for the Quality Manual is outlined in Book 2 Section 5

###### The Quality Manual is reviewed and approved early in the project. See Book 1 to understand if approval is required of any portion of the Quality Manual prior to NTP 2

###### The MnDOT Project Manager is responsible for approving the Quality Manual. The MnDOT Project Manager will generally have function leaders of the MnDOT Contract Administration Team participate in the review and approval

###### Where specific processes and roles are defined in the Quality Manual, ensure they are consistent with the contract.

##### Overseeing the Implementation of the Quality Manual

###### The MnDOT Contract Administration Team should not perform design reviews prior to the approval of the design portion of the Quality Manual.

###### The design oversight team performs Process Reviews according to Section 1.2 of this manual.

###### The design oversight team performs design reviews as outlined in the accepted Quality Manual.

###### Design oversight reviews confirm the design is compliant with the contract.  Reviews are not an opportunity to express MnDOT staff preferences – as long as the design is compliant with contract requirements, it is acceptable.  Preferences may be assumed to be MnDOT requests for a Change Order.

#### Useful Tips/Lessons Learned

##### Review of the Quality Manual:

###### Use of the template provided in the RFP is not mandatory; the template provided is simply a guide and does not need to be used.  However the Quality Manual must meet the requirements of Book 2 Section 5.

###### Review the Quality Manual to ensure it provides the necessary guidance to reviewers to ensure they understand the sequence of reviews.  Between the Quality Manual and the schedule, reviewers should be able to easily follow the review process requirements, specifically each review that is required..

###### Review the Quality Manual to check that the roles of all Quality personnel for the Contractor are defined.

###### Review the Quality Manual to ensure the Design QC processes are defined sufficiently to allow an audit to confirm a process is followed.  For this reason, ambiguous terms must not be used (e.g. may, should instead of must, will). The Quality Manual must present commitments and documentation requirements in a format that can be audited.

##### It is highly beneficial to identify all the design reviews that will occur.  There are required design reviews; however there are situations that would justify additional reviews from a contractor or MnDOT position such as phased release, specialty design, etc.

##### The Quality Manual Approval Process is defined in Book 2 Section 5; however it is common to approve the document in sections with the Design section being approved early.

##### Oversight of the Quality Manual:

###### Perform process reviews soon after NTP to help establish expectations of following the Quality Manual.

###### To modify the Quality Manual, the modifications must be appropriate for the project, reviewed by MnDOT and approved.

#### References

##### Contractors Quality Manual

##### MnDOT Quality Manual Template

#### Attachments/Exhibits

None

### Design Oversight Meetings

#### Purpose

This section defines typical meetings the design oversight staff will attend.

Meetings are critical to proper design progression. It is important to remember design is iterative and the design at proposal submittal is not complete. It is important for the MnDOT Contract Administration Team to know the Contractor will want to complete the design presented in the proposal. Design meetings help all parties understand what the Contractor has considered in the design process leading up to award and post-award to help streamline reviews and comments.  It is also important that design meetings and reviews include all needed disciplines, such as roadway, structures, environmental, MOT etc..

Regular interaction between MnDOT and Contractor design staff is important to a project’s schedule and quality.  Some of the recommended meetings and review processes are described in the subsections below.  In addition, informal collaboration is encouraged to ensure a better understanding of MnDOT goals, as well as to reduce review time.  A formal design submittal and review process is essential, however this process traditionally results in multiple, often conflicting, comments coming from different MnDOT departments, which can take a long time to resolve. This is directly in contrast to one of the main benefits of design-build, to reduce schedule by streamlining design and overlapping it with construction.  In contrast, in-person meetings, and one-on-one informal interactions provide opportunities to resolve issues quickly, before submittal, and promote collaborative working relationships.

#### Procedure

The MnDOT Contract Administration Team should implement a consistent interaction protocol that includes frequent and regularly scheduled communication. The more consistent this process is across the project, generally results in more consistent reviews.

The following are typical design oversight meetings:

##### Task Force or Work Group meetings (weekly/bi-weekly) to review progress of individual disciplines or project components, and to facilitate discussion of acceptable performance (Book 2) interpretations and decisions.

##### Weekly Design progress meetings to review the status of design, keep management apprised of progress and potential upcoming issues, and to provide decisions needed by any party.

##### Over-the-Shoulder design review meetings to facilitate informal review of design concepts prior to official submittal and review. The intent is to facilitate consensus of design intent and adherence to the contract to reduce the need for design review comments. These meetings are called as needed by the Contractor or MnDOT.

##### Comment resolution meetings held to resolve comments made by the design oversight team.  Typically held with each submittal to discuss how each comment was resolved, designer disagreements with comments, or designer need for additional information on the genesis of the comment.

#### Useful Hints/Lessons Learned

##### Use the Contractor’s organizational chart and the MnDOT staff to set the appropriate level of interactions for the project.  Connecting MnDOT staff at all levels to their counterparts on the Contractor’s design staff, allows questions and problems to be resolved at a lower level (that is, without having to run everything by the Design Lead or the Project Manager).

##### Limit attendance at task force or work group meetings to MnDOT and Contractor staff from that specific discipline. The Design Manager, Contractor Project Manager, Oversight Design Lead do not need to attend all these meetings, the intent is to delegate authority and decision making to the lower levels.

##### If Task Force or work group representatives cannot agree, elevate the decision to the next level as defined by the Partnering process outlined in Book 1 and established for the project. The following is an example of an escalation ladder by position or role:

| Level | Position |
| --- | --- |
| 1 | Designer – roadway lead |
| 2 | Management level 1 – Design Manager |
| 3 | Management level 2 – PM |

##### Consider holding a weekly MnDOT-only meeting (inclusive of the entire MnDOT Contract Administration Team) to discuss issues that arose in Task Force meetings.

##### It is helpful to have MnDOT Contract Administration Team members from construction and environmental at project meetings that are primarily for design.

##### It is helpful to be proactive in discussing how As-Built documents are to be generated; discussing these in early meetings helps everyone be prepared for providing these documents.

#### References

None

#### Attachments/Exhibits

None

### Design Oversight Reviews

Design oversight reviews are performed to assure the design prepared by the Contractor meets the contract requirements.  There are three defined review types as presented below.

Over-the-Shoulder Reviews:  Section 1.7.4.1

Released for construction reviews:  Section 1.7.4.2

Submittal for signature reviews:  Section 1.7.4.3

The following subsections define the reviews the design oversight staff will participate in, and provide procedures and guidelines for each review.

### 1.7.4.1	Over-the-Shoulder Reviews (OTS)

#### Purpose

The purpose of Over the Shoulder reviews are  to establish an informal process by which the Contractor and MnDOT can discuss and resolve design issues during the development of the plans prior to formal RFC submittals. This section details the Contract Administration Team’s role in these reviews.

#### Procedure/Guidelines

##### OTS reviews are informal meetings between the Contractor and the MnDOT Contract Administration Team.  OTS review meetings are scheduled through appropriate MnDOT or Contractor discipline leads.

##### The Contractor may provide any information to MnDOT it deems appropriate for the OTS review.  It is acceptable for the Contractor to submit documents via e-mail.  The MnDOT Contract Administration Team representative may request additional information in order to make the review more effective.  It is the Contractor’s choice whether to provide the additional information requested at the OTS meeting.

Note:  RFC packages are NOT submitted via e-mail and must go through the project’s Document Control.

##### The MnDOT Contract Administration Team is responsible for recording and keeping all notes in their own files as necessary.  OTS review documentation is NOT to be submitted to Document Control.

#### Useful Tips/Lessons Learned

##### Co-locating in general makes this process even more successful because OTS reviews tend to occur naturally, and arranging other reviews generally is easier as team members are dedicated to the project.

##### If there is no co-location, properly scheduling meetings becomes more critical to ensure the proper team members attend.

##### While not required, OTS are highly recommended.  Consider including this during Quality Manual development and discuss during project kickoff meetings.

##### Audit the process after the first OTS of each discipline to set up a standard expectation moving forward. This audit should consist of interviewing those that participated to obtain feedback if the OTS was helpful. Provide training if the OTS does not obtain expected results.

##### Comments related to oversight must not be personal or arbitrary

##### Preferential comments (which differ from personal and arbitrary) regarding the design are acceptable comments at an OTS, but be sure to advise the Contractor they are preferential, and not required. For example, the municipality would like to have a wider boulevard between curb and trails (contract only dictates a minimum width, which is what the Contractor typically proposes).  Additional width would be preferred for snow storage/sign placement, but the comment is preferential and not contractual, and thus it remains the Contractor’s decision whether to add width beyond what is contractually required.

##### Reviewing the needs of As-Built documents early can be help assure proper documentation is maintained to prepare these important documents.

#### References

##### Section 1.7.4.2 Released for Construction – For Review

##### Section 1.7.4.3 Released for Construction – Final

#### Attachments/Exhibits

None

### 1.7.4.2	Released for Construction – For Review

#### Purpose

The initial formal review of design packages is the Released for Construction – for review. This review is intended to be a thorough review of the design and contract requirements.  The purpose of this procedure is to document the process for accepting and reviewing Released for Construction (RFC) packages for review and comment.   This procedure does not include Over-the-Shoulder (OTS) reviews.

#### Procedure

##### All RFC – For Review documents need to be submitted via Document Control.

##### Each RFC – For Review package submitted to Document Control will include the following:

###### Cover Sheet with Submittal Description and Schedule Activity ID

###### Form DQP 418FA signed by each of the Contractor employees identified on the form (or a designated representative).

###### Form DQP 418FA signed by the Contractor’s Quality Manager identifying the quality processes have been followed

###### Hard-copies (refer to Section 5 of the RFP for each discipline, may vary) of the following:

Structures and Geotech

Overhead Signs

Roadway and Other Misc. Items

###### Electronic files (uploaded to TRACS) containing:

One Adobe .pdf  file of the full submittal

Excel Spreadsheet with Drawing Index

Dgn file

Reports

Calculations

Specifications

Material Testing Quantities

##### The Contractor’s Document Control personnel uploads the Excel Drawing Index into TRACS in accordance with the TRACS Procedure Manual.

##### Document Control distributes hard copies of each RFC – For Acceptance Package to the individuals listed in Section 1.4.2, Document Control Procedure Exhibit 1.4.2.E-4, in the format requested by each individual.

##### MnDOT reviewers upload comments on the RFC – For Acceptance Review into TRACS software using the Submittal Control Module procedures set up in the TRACS Procedure Manual.

##### MnDOT personnel should always perform reviews within the timelines defined in Book 2 Section 5. Faster, when possible, for high-priority or critical path items.  Typical packages with specific time definitions include:

Preliminary Bridge Submittal

RFC Submittal

Early Construction Submittal

RFI Submittal

Note: refer to Book 2 Section 5 of the RFP for changes to review times.

##### After the review time is over, no additional comments should be made.

##### The MnDOT Project Manager or designated representative is responsible for monitoring the submittal schedule to ensure that MnDOT meets the above deadlines.

##### When all MnDOT comments have been entered into TRACS, the individual identified above in B.8 notifies Document Control, who will notify the Contractor via e-mail that MnDOT has concluded its comments on that RFC package (e.g., comments are closed according to TRACS).

##### The Contractor needs to respond to each MnDOT comment using the Submittal Control Module in TRACS.  It is the Contractor’s responsibility to notify the MnDOT Design Manager via e-mail when the Contractor has responded to all of the comments.

##### After the Contractor has reviewed and responded to the comments (and responses are closed according to TRACS) The Contractor has the responsibility to schedule a comment resolution meeting to discuss unresolved comments, if any, and agree to a resolution.

##### Following the comment resolution meeting, the Contractor revises responses, as needed, in TRACS.

##### MnDOT representatives responsible for producing comments will confirm that they have been incorporated as agreed to at the comment resolution meeting by reviewing plans and the TRACS comment resolution form before they are submitted for signature, or at a minimum at the time they are submitted for signature.

##### Following resolution of all comments, the Contractor is responsible to submit final RFC packages for review and MnDOT signature in accordance with the Final RFC Procedure of this Manual (Section 1.7.4.3).  This review process may be repeated if the submittal requires formal resubmittal due to an extensive design change driven by a comment or comments.  Otherwise, at this point the package would be submitted for Acceptance and signature as stated above.

Note:  RFC packages are NOT submitted via e-mail and must go through the MnDOT Document Control.

#### Useful Tips/Lessons Learned

##### MnDOT defines clearly “what” the requirement is in the RFP/contract, but it is up to the Contractor to define the “how” (that is, the method or design they will use to meet the requirement for MnDOT’s acceptance).

##### Always provide a contract reference for a design item not meeting the contract.  If the comment is preferential be sure to make it clear the Contractor is not obligated to modify the design. These should be discussed in task force/work group meetings or OTS reviews prior to RFC submittal whenever possible.

##### Fostering a partnering approach to reviews, OTS reviews and task force/work group meetings can assist in reducing actual package review times without officially changing the allocated time.

##### Remind the Contractor they can view comments in the TRACS Submittal Control Module in real-time as comments are being made by MnDOT.

##### Be open and foster innovation.  If a MnDOT functional group rejectgs a design because they have never designed it that way in design-bid-build, push them to find out if there are circumstances under which the approach is acceptable.

##### Be a good partner.  If a design meets the contract, but will make a situation worse, the team can and should work to find a solution that meets the contract and improves the situation.  But remember since the design met the contract, the “right” solution maybe the preference and should be treated as such. Try to have a “We” attitude, not just focusing on what MnDOT may like.  Fostering all parties to have win-win solutions early in the project can lead to better collaboration throughout. ,.

##### The MnDOT Project Manager or designated representative attends meetings, but should manage the Contract Administration Team design oversight staff in such a way that responsibilities are delegated to the functional expert for acceptance.

##### For comments it is helpful to have the final comment be “Schedule comment resolution meeting.”, Also “Submit for signature” should be the final comment if there are no comments that require re-submittal.

##### It may be helpful to schedule a review of the plan just prior to submittal for signature to confirm that comments have been incorporated as agreed to at the comment resolution meeting. See above procedure Step B.13.  The earlier this confirmation, the better.

##### Provide comments on packages in a timely manner that meets the requirements of the contract.  Delays in reviews can result in delays in Project completion.

#### References

##### Section 1.7.4.3 Released for Construction – Final

#### Attachments/Exhibits

1.7.4.2.E-1	Sample Drawing Index

1.7.4.2.E-1	TRACS Manual

Exhibit 1.7.4.E-1  Sample Drawing Index

Click on embedded excel file below to view full sample index.

Exhibit 1.7.4.E-2  TRACS Manual

Exerpt below.  Click on embedded pdf file below to view entire manual.

### 1.7.4.3	Released for Construction-Final

#### Purpose

This section documents the process for accepting and processing Released for Construction (RFC) packages ready to be released for field staff.

#### Procedure

##### The Contractor is responsible for responding to all comments submitted by MnDOT during the Release for Construction – For Review process.

##### After all comments have been resolved, the Contractor is required to submit a final RFC package for MnDOT Acceptance.

##### The Contractor is required to submit final RFC – For Acceptance packages to Document Control.  E-mailed copies will not be accepted.

##### Each RFC – For Acceptance package submitted to Document Control must contain the following:

###### Cover Sheet with Submittal Description and Schedule Activity ID

###### Form DQP 418FA signed by the each of the Contractor employees identified on the form (or a designated representative)

###### Signed comment resolution form from TRACS

###### Hard-copies signed (generally electronically signed) by the Engineer of Record, for the following documents:

Structures and Geotech

Overhead Signs

Roadway and Other Misc. Items

###### Following acceptance, the Contractor uploads RFC plans and applicable electronic design files to TRACS, including:

One Adobe “.pdf”  file of full submittal

Microstation “.dgn” files

Reports that support the package

Calculations for elements represented in the package

Specifications or special provisions

Material Testing Quantities

##### Document Control distributes the hard-copy of each RFC – Final package to the MnDOT Design Manager for Acceptance.

##### If the RFC package is acceptable, the following procedure will occur:

###### Except for the front sheet of the plan, each sheet will have a signature block for MnDOT to sign and Accept the sheet.

The Design Manager will determine exact language to demonstrate acceptance, “MnDOT Acceptance” is adequate. Consistency is critical throughout the project.

###### There are a limited number of individuals within MnDOT who can sign plan sets.  Be sure to verify who they are on your Project.

Consultants working for MnDOT do not have authority to sign RFC plans.

###### After each page is signed, the front sheet is stamped “MnDOT has reviewed this deliverable and determined that it appears to meet the requirements of the Contract Documents” This stamp will require a MnDOT signature from an individual that is authorized to sign for the Project.

###### The signed and stamped plan set is then returned to Document Control.

###### Document Control prepares a transmittal for the Contractor indicating that the RFC package has been accepted.

###### Document Control returns the plan to the Contractor Design Coordinator or other designated representatives to stamp each page “Released for Construction.”

###### The Contractor’s Document Control scans the RFC documents and logs the RFC package into TRACS and attaches the scanned file (pdf) and all supporting information listed in Sections B4.5 above.

###### The Contractors Document Control delivers one hard copy to Document Control.

###### MnDOT’s Document Control makes the appropriate number of copies and distributes to the individuals identified in Exhibit 1.4.2.E-4 (routing slip).

###### Document Control files the RFC drawing in the RFC Library in accordance with the Library Procedures of this Construction Administration Manual (see Section 1.4).

##### If the RFC Package is not accepted, MnDOT submits comments to the Contractor via Document Control and repeats the Released for Construction – For Review procedure of this manual. Comments at this stage may be given verbally, if the quantity of unresolved comments is limited and simple to correct.

#### Useful Tips/Lessons Learned

##### It may be helpful to schedule a review of the plan just prior to submittal for signature to confirm that comments have been incorporated as agreed to at the Comment Resolution Meeting

##### Holding a review meeting prior to formal submittal for signature will reduce the possibility of a package being returned to the Contractor for additional modifications

##### Set up electronic file transfers using an FTP and electronic signatures, if needed

##### Electronic signatures can help speed the signing process if set up properly

##### Standardize the design packages or at least make sure MnDOT receives an index or table of contents

##### Consider holding an early coordination meeting to decide the structure and number of design packages

##### Limit the amount of information stored in TRACS to avoid version confusion. See the TRACS user manual provided as an Exhibit in this Manual (Exhibit 1.7.4.E-2).

#### References

##### Section 1.7.4.2 Released for Construction – For Review Procedure

#### Attachments/Exhibits

None

### Design Process Reviews

See Section 1.2

### Right of Way (R/W)

#### Purpose

Due to the timelines involved in acquiring R/W or easements, MnDOT typically performs this process. However, a design-build RFP may require the Contractor to acquire part or all of the R/W at their risk and cost.

Throughout this section, the term “R/W” includes all types of new R/W needed to construct a project:

Permanent acquisition of entire properties or portions of properties

Permanent easements

Temporary easements

In design-bid-build, design is typically complete or near-complete before R/W is acquired.  Under design-build, R/W acquisition is always underway before design is completed.

This section provides guidance to the MnDOT Contract Administration Team on completing R/W for typical projects and provides a process for situations where the Contractor acquires R/W or easements.

#### Procedure/Guidelines

Procedures for R/W are given below for two scenarios:

- Projects for which R/W and easements are acquired by MnDOT

- A project where the contractor, at risk elects to purchase R/W to accommodate a design element

##### Contractor not allowed to acquire R/W or easements:

###### As noted above, R/W acquisition should already be started during the design-build RFP writing process.  Ideally, a schedule of when the actual R/W will be available for Contractor access (right of entry) should be included in the design-build RFP.  Where this is not possible, an addendum to the RFP can be issued to allow proposers to refine their schedule assumptions.

###### The MnDOT Contract Administration Team should review the proposal schedule, and subsequently, the Contractor’s preliminary schedule and baseline schedule, to determine the available float in MnDOT’s contractually-obligated R/W delivery.

This is done to determine the level of impact that R/W process delays (which are not uncommon) could have on the overall project schedule.  If the Contractor plans for design and early construction tasks to take place on portions of the project requiring R/W prior to when MnDOT can obtain Right of Entry, the Contractor must change the schedule.

###### Review schedule updates (during the project) to properly track float as acquisition proceeds.

###### Conduct meetings with the MnDOT R/W unit to ensure the MnDOT Contract Administration Team is providing all information needed for the MnDOT R/W unit to perform their function expeditiously. This information may also include Contractor design exhibits indicating the extent of R/W needed.

##### Contractor allowed to acquire R/W or easement

###### R/W acquisition required by the Contractor will be done at their cost and will be their schedule risk, unless mutually agreed otherwise.

###### If the Contractor’s design requires the acquisition of less R/W than that specified in the RFP, if known early MnDOT may be able to alter the acquisition strategy.

###### If the Contractor’s design requires the acquisition of land parcels, portions of land parcels, or easements that are not included in the RFP (and not specifically included in the approved environmental documents) the R/W acquisition process, performed by the MnDOT R/W unit must abide by environmental process concerns, including the following:

NEPA documentation:  a Contractor wishing to acquire a property or easement cannot simply purchase the property.  In most cases, the approved environmental documents would need to be revised, which would trigger public review, notification requirements and other actions that could impact the schedule.

Valuation:  for federally-funded projects, the valuation of the property would need to be reviewed for compliance with federal law, regardless of the property owner’s willingness to agree on a price.

Municipal consent may be needed for publicly-owned land

Utility Agreements may need to be changed

Land Owner’s willingness to sell the property or grant an easement needs to be considered, as the process of condemnation adds significant schedule risk

Environmental Permits may need to be updated

###### Confirm with the MnDOT R/W unit to identify any potential additional complications and outline a schedule for the acquisition.

###### Confirm that the Contractor’s proposed acquisition schedule is acceptable to the MnDOT R/W unit.

#### Useful Tips/Lessons Learned

##### For projects that receive Federal funding, make sure that Right of Entry Easements and Temporary Easements receive FHWA approval

##### The MnDOT Contract Administration Team needs to continually check the current schedule for progress on the R/W process to avoid R/W delay claims

##### If the Contractor wants to attempt to add R/W after MnDOT’s acquisition schedule is complete, MnDOT should engage the property owners and give a perspective for the property owners for how the change would look like from their property.

##### Contact information should be shared between appropriate Contractor staff and R/W staff to ensure there are no delays in sharing information that would impact R/W acquisition

#### References

##### MnDOT’s ROE permit form

#### Attachments/Exhibits

None

## Construction

The purpose of this section is to provide an understanding of the MnDOT Contract Administration Team’s role during a design-build project with respect to:

Construction Inspection and Testing Roles

Quality Manual

Critical Activity Points

Construction Inspection and Testing

Construction Process Reviews

Request For Information

Field Design Change

Notice of Design Change

This section is organized into subsections as listed above for ease in finding a specific topic.

### Construction Inspection and Testing Roles

#### Purpose

This section provides an introduction to the overall construction verification role of the MnDOT Contract Administration Team, and defines the roles of typical verification team members. It also describes a Contractor’s typical construction quality team, and the interaction needs between them.

##### Roles of MnDOT Construction Verification Team:

###### Quality Manager:  oversees that the inspection and verification procedures are being followed, and develops updates to the procedures as needed (on smaller projects this role is generally filled by one of the other leads).

###### Bridge Head (Lead) Inspector:  must be a person with skill in structures inspection including knowledge of weld procedures, bolt tensioning and reinforcement.  Works with the Contractor’s Quality Control Manager at Structures Critical Activity Points (review points).

###### Highway Head (Lead) Inspector:  Must be a person with skill in heavy civil work. Works with the Contractors Quality Control Manager at Civil Critical Activity Points.

###### Materials Tester:  Performs verification testing as deemed appropriate.

###### Plant Inspector Concrete and Bituminous:  Performs standard MnDOT inspections at batch plants. For Contractor Batch Plants on-site, the inspector(s) will coordinate with the Contractor’s plant personnel.

###### CPM Schedule Reviewer:  reviews the Contractor’s schedule updates as detailed in Section 1.5.

###### Environmental Compliance Manager:  reviews construction activities for compliance with applicable permits including BMPs (refer to Section 1.9 for additional detail).

###### Environmental specialists:   individuals with specific specialized expertise who assist the Environmental Compliance Manager in carrying out his/her responsibilities.  These roles will vary according to the needs of the project (e.g., asbestos removal, hazardous materials inspectors, stormwater management inspectors).  Confer with OES to determine environment-related staffing needs.

##### Roles of the Contractor’s Construction QC Team

###### The Contractor’s approved Quality Management Plan will define the specific roles for the project.

###### Section 3 of Volume 1 of the Quality Manual Template provided with the RFP in Section 5 of Book 2 lists typical roles of the Contractor’s Quality Organization, which include:

Quality Manager

Construction Quality Manager

Lead Inspector

Quality Control Inspectors

Quality Control Testers

Critical Activity Point Manager

Utility Coordinator

Contract Environmental Compliance Officer – works directly with the MnDOT Environmental Compliance Manager

#### Procedure

This section provides guidelines for the interaction between the MnDOT construction verification team and the Contractor’s construction QC team.  The specific type and number of interactions can be adjusted to adapt to the needs of each project, and to different phases of individual projects.  As with Design team interactions described in Section 1.7.1, maintaining open lines of communication between the Contractor’s quality team and the MnDOT verification team of the Contract Administration Team is important in maintaining schedule and improving quality.

##### The Quality Managers of both organizations should meet on a monthly basis to collaborate, and to have the Contractor’s quality leaders sign Form QM740FB or similar indicating the quality program is functioning

##### For all Critical Activity Points, the Contractor’s construction foreman Critical Activity Point Manager and the MnDOT oversight representative signs Form CQP202F or similar indicating the Critical Activity was properly completed

##### Material testing is typically performed by the Contractor’s testing personnel.  Exceptions where testing is performed by MnDOT, are as follows:

MnDOT testers will provide verification testing as deemed appropriate on any item

MnDOT performs testing at off-site batch plants where similar testing is typically performed by MnDOT on design-bid-build projects

##### Typically inspections are performed by MnDOT with the exception of the following inspections performed by the Contractor:

Inspections of on-site batch plants.

Inspections of specialty construction items such as soil nail walls, post tensioning, prestressing, temporary works such as false work, shoring and the like.

##### Early in the construction phase, use the Contractor’s organization chart to connect MnDOT verification staff to their counterparts on the Contractor’s staff.  This will enable decision-making to take place more quickly at a lower level, without having to escalate questions and decisions to the Quality Managers and the Project Managers.

##### The Quality managers for MnDOT and the Contractor are responsible for ensuring that the various interactions required by the Quality Manual are taking place.

#### Useful Hints/Lessons Learned

##### The MnDOT lead inspectors upload their reports to TRACS

##### The interaction between the Contractor’s foreman and the MnDOT inspector is different in design-build compared to a traditional design-bid-build project.  The Contractor’s quality team fills the role traditionally performed by the MnDOT inspector, leaving MnDOT’s Lead Inspector to provide a verification role (checking that the Contractor’s quality team is following the procedures required by the Quality Manual.

##### In conjunction with traditional roles stated above, MnDOT Inspectors are typically “problem solvers” in the field on design-bid-build projects.  On design-build projects, MnDOT Contract Administration Team staff must be careful not to direct the Contractor or take responsibility for the Contractor’s design omissions.

###### If something arises in the field that causes a change from the design, the Contractor is responsible for checking with their designers and proposing a solution, either through NDC or FDC as appropriate

###### MnDOT staff may offer suggestions, but cannot direct solutions, as that may be interpreted as a Change Order, which would open up the contract to schedule and price changes

###### MnDOT’s role is to ensure that the contract requirements are being met, not to specify preferences as to how those requirements are to be met

##### Be careful to not perform the Contractor’s quality duties, don’t become The Contractor’s QC

###### If during inspections, systematic issues are identified, be sure to inform the Contractor’s Quality Manager to address the issue

###### Don’t mark striping

###### Don’t mark signal pole locations

###### Don’t mark sign locations

###### Don’t allow verification testing to become the Contractor’s QC for test rolling confirmation, density testing, etc.

##### It is helpful to have MnDOT Contract Administration Team members from design and environmental disciplines at project meetings that are primarily for or during construction

##### The MnDOT Quality Manager must be fully able to meet the demands of the job and stay committed throughout the project:

###### Due to tight schedule requirements, the Quality Manager must be available when needed – for example, when a Critical Activity Point is reached or if there is a quality problem discovered that needs immediate attention.  These issues can arise at any time of the day or week, including in inclement weather.  For this reason, location (or willingness to co-locate) should be considered in selecting personnel for this role.

#### References

##### RFP Book 2 Section 5 Exhibits, Quality Manual Template

##### Contractor’s approved Quality Manual

#### Attachments/Exhibits

Typical construction Oversight Organization Chart – Option 1

Typical construction Oversight Organization Chart – Option 2

Exhibit 1.8.1.E-1  Typical Construction Oversight Organization Chart – Option 1

Exhibit 1.8.1.E-2  Typical Construction Oversight Organization Chart – Option 2

### Quality Manual

#### Purpose

The purpose of this section is to provide an understanding of the MnDOT Contract Administration Team’s role during a design-build project with respect to:

##### Approving the non-design portion of the Quality Manual

##### Overseeing the Quality Manual non-design commitments

#### Procedure

##### Approval of the non-design portion of the Quality Manual

###### The approval process for the Quality Manual is outlined in Book 2 Section 5.

###### The Quality Manual is reviewed and approved early in the project. See Book 1 to understand any time requirements for approval.

###### The MnDOT Project Manager is responsible for approving the Quality Manual. The MnDOT Project Manager will generally engage the Resident Engineer and other construction leads to participate in the review and approval.

##### Overseeing the Quality Manual

###### The construction verification team performs process reviews according to Section 1.2 of this manual

###### Process reviews over the course of the project are performed on all aspects of the Quality Manual

###### The MnDOT Contract Administration Team, in collaboration with the Contractor, prepare corrective action reports for sections of the Quality Manual that are systematically not being followed

#### Useful Tips/Lessons Learned

##### Review of the Quality Manual

###### Use of the Template provided in the RFP is not mandatory; the Template provided is simply a guide.  However the Quality Manual must meet the requirements of Book 2 Section 5.

###### Review the Quality Manual to ensure it is easy to follow and provides the necessary guidance to inspectors, testers and constructors regarding the required testing, inspection and hold points, such as:

Special inspection or testing needs

Critical activity points are identified

Ability of MnDOT to confirm quality for specialty or one off items

###### Review the Quality Manual to ensure the roles of all Quality personnel for the Contractor are well-defined.  This will enable future review of Contractor Quality personnel to ensure that they are carrying out their responsibilities.

Refer to Section 1.8.1 for typical roles to be filled by the Contractor’s construction team.

Proactively engage the Contractor’s Quality Manager during reviews to ensure he or she is actively performing required tasks.

Proactively work with the Critical Activity Point Manager during review to ensure they properly understand the critical nature of documentation to be provided at each Critical Activity Point meeting. Review CQP 202 with the Critical Activity Point Manager.

###### Review the Quality Manual to ensure the QC processes are defined sufficiently to allow an audit.  To confirm that a process is being followed as intended, ambiguous terms must not be used (e.g., “may,” “should”). The Quality Manual must be completed with commitments that can be easily verified during an audit.

###### Review the Quality Manual to ensure the quality verification is performed adequately on items that may require warranty:

Common warranty items such as pavement, structural concrete, embankments, painting and others also have critical activity points.  Properly defining Critical Activity Points (to correlate with warranty starting points) will assist in implementing the Warranty.

Improper documentation of Work elements can result in difficulty in enforcing manufacturer’s warranties.

###### Critical Activity Points are a great benefit to all parties in confirming the quality of Work.  Providing suggestions of omitted or additional Critical Activity Points is advisable during the review of the Quality Manual. Refer to Book 2 Section 5 of the RFP for any contractually-mandated Critical Activity Points.  Be sure to provide proper care when reviewing these to ensure they are properly defined.

###### The non-design Quality Manual Approval Process is defined in Book 2 Section 5; however it is common to approve the document in sections (e.g., design, management, and construction) as outlined in Book 1 Section 4.2.2.

##### Oversight of the implementation of the Quality Manual:

###### Always perform process reviews soon after NTP to help establish expectations of following the Quality Manual.

###### Strongly consider having a MnDOT Quality Manager as part of the oversight team to lead the Quality Manual enforcement efforts versus assigning the role on a part time basis to another project team member.

###### Any proposed modifications to the Quality Manual must be appropriate for the project, and reviewed and approved by MnDOT.

#### References

##### Section 1.8.1 Construction Inspection and Testing Roles

##### Section 1.2 Audits and Reviews

##### RFP Book 2 Section 5

##### RFP Book 1

#### Attachments/Exhibits

None

### Critical Activity Points

#### Purpose

This section defines the importance of the Critical Activity Points in design-build delivery, and describes the role of the MnDOT Construction verification staff and Contractor staff in performing Critical Activity Points. Proper adherence to the development and execution of Critical Activity Points during construction is essential to confirming quality on a Project for both MnDOT and the Contractor, and for ensuring the design intent is met in the field.  They assist not only in confirming quality at the time of the on-site meeting, but also in confirming that all the proper documentation is available for record documents.

#### Procedure

##### Critical Activity Points are not mile markers.  They are an enforceable checkpoint that if failed should be used to stop an activity.    The Contractor cannot proceed with Work on an element with a failing Critical Activity Point.

##### In preparation of the Quality Manual the Contractor will define all Critical Activity Points, with review and concurrence from MnDOT, (refer to Book 2 Section 5 for Project required Critical Activity Points).

##### The Contractor will schedule Critical Activity Point meetings when Work reaches the hold point defined by the Critical Activity Point.

##### The following personnel are typically represented at a Critical Activity Point:

Construction Quality Manager (CQM) of the Contractor

Critical Activity Point Manager (CAPM) of the Contractor, if different than the CQM

Contractor’s foreman, if different from the CAPM

Representative of the MnDOT verification team

##### At each Critical Activity Point meeting, the Contractor must provide testing and inspection documentation that indicates the Work has been accomplished in accordance with the contract.

##### A Critical Activity Point meeting is also scheduled and held for the first time a material is used:

###### The Contractor will collect material certifications or other documentation indicating the material is suitable for use and provide important items such as material storage requirements to ensure continued compliance prior to incorporation of the material into the Work.

##### Form CQP202F must be signed by the Contractor’s foreman and Critical Activity Point Manager and signed and Accepted by the MnDOT verification team member to satisfactorily accomplish a Critical Activity Point, thereby allowing the Work to proceed.

##### If the Critical activity is marked unsatisfactory by the MnDOT verification team member, the Contractor may be assessed a penalty as defined in Book 2 Section 5 or Book 1.

##### Critical Activity Point data must be loaded into TRACS by the Contractor.

##### If non-conforming Work is noted during a Critical Activity Point, the Contractor must address any non-conforming Work identified at the Critical Activity Point prior to moving forward, and the Critical Activity Point must be re-scheduled.

##### The Critical Activity Point must eventually be checked Acceptable and signed by the MnDOT verification team representative.

#### Useful Hints/Lessons Learned

##### Refer to Book 2 Section 5 for defined Critical Activity Points for the project.

##### The field staff should be proactive and be prepared for upcoming Critical Activity Points to help with enforcement, scheduling and invoice payment based on completion.

##### During pre-activity meetings it is advisable to identify required Critical Activity Points and discuss any unique aspects related to the Work.

##### MnDOT inspectors are traditionally “problem solvers” in the field on design-bid-build projects.  On design-build projects, MnDOT inspectors must be careful not to direct the Contractor or take responsibility for their design omissions.  If something arises in the field that causes a change from the design, the Contractor is responsible for checking with their designers and proposing a solution, either through NDC or FDC as appropriate

##### The typical process associated with a Critical Activity Point or other identified quality concern is that the Contractor’s Quality Manager identifies the quality concern and follows it through by requiring the Contractor to resolve the quality concern.  MnDOT Contract administration Team verification staff are the second line of identifying and following through on quality concerns.

###### MnDOT staff may offer suggestions, but cannot direct solutions, as that may be interpreted as a Change Order, which would open up the contract to schedule and price changes

###### MnDOT’s role is to ensure that the contract requirements are being met, not to specify preferences as to how those requirements are to be met

#### References

##### Typical Design Oversight Organization Charts in Section 1.7

##### RFP Book 2 Section 5

#### Attachments/Exhibits

Construction TRACS Manual

Exhibit 1.8.3.E-1  Construction TRACS Manual

Excerpt below.  Click on embedded pdf file below to view entire manual.

### Construction Process Reviews

See Section 1.2

### Requests for Information (RFI)

#### Purpose

Design-build projects, like design-bid-build projects, rely on contract documents and plans that are not always fully understood.  For this reason RFIs are used to obtain clarification of design and contract meaning.  Because in design-build, design is generally on a faster track, and may have multiple disciplines designing concurrently that would typically be more linear, there is an increased likelihood of having a larger number of design related RFIs.  Design RFIs on design-build projects are typically between the Contractor and the Contractor’s designer, but can also be to MnDOT with regard to the RFP   to obtain clarification on construction inspection and testing needs, specifications, or other contractual ambiguities.

#### Procedure

The procedures below outline the process for receiving and responding to Requests for Information from the Contractor.

##### The Contractor submits an RFI to MnDOT regarding the contract.

##### Document Control will follow the process of 1.4.2.B.3 for incoming RFIs.

##### The technical lead assigned to review the RFI (the MnDOT Project Manager or other designated project member) will review the contract and formulate a response.

##### All answers of RFIs are required to have a peer review.  The MnDOT Project Manager reviews all RFI responses prepared by others, and will select a person with skills and knowledge of the subject to review RFI responses they prepare themselves.

##### Document Control staff are required to follow the process of 1.4.2.B.4 for outgoing responses of RFIs.

##### All RFIs are maintained in the Library.

#### Useful Tips/Lessons Learned

##### Be sure that all RFIs are reviewed against, and responses reference, the contractual section that applies.

##### Whenever possible, provide timely responses to RFIs to avoid project delays.

##### Responses to RFIs should provide interpretation of the contract documents.  RFI responses may suggest solutions, but must be worded to make it clear that this is a suggestion, not a demand.  As noted in other sections, MnDOT staff must be careful not to direct the Contractor, in order to avoid initiating a Change Order.

#### References

##### Section 1.4.2 Document Control

##### The Contractor’s Quality Manual

#### Attachments/Exhibits

None

### Field Design Changes

#### Purpose

During construction there are numerous situations that require changes to design to accommodate existing or as constructed conditions, enhance constructability or improve quality. This section describes procedures for submitting and reviewing Field Design Changes on design-build projects.

#### Procedure

  - The Contractor’s procedure for issuing Field Design Changes is identified in the Contractor’s Quality Manual.

  - A Field Design Change (FDC) is issued when MnDOT or the Contractor’s Construction Manager identifies a field change condition. FDCs most often do not result in a Change Order; rather they are implemented to account for a modified approach to construction for one of various reasons.  Reasons for field changes include:

###### Existing conditions vary from those assumed in the plans (e.g., utilities are discovered to be in a different location from that represented by Subsurface Utility Engineering information)

###### As constructed conditions require a change in construction of the next element

###### Constructability can be enhanced by a change in construction approach

###### Quality can be improved by a change in construction

###### Alternate materials that the Contractor wishes to use (e.g., for reasons of cost or availability) can achieve equal or better quality

##### The Contractor, MnDOT Construction Manager, and the Construction Quality Manager together determine the level of the FDC. The pre-defined FDC levels are described below.  Note that the Contractor’s Quality Manual may modify these descriptions if approved by MnDOT during review of the Quality Manual:

###### Level 1 – Request for Existing Conditions Adjustment: These revisions are adjustments to match project elements with conditions encountered in the field.  They are limited to dimensional and layout adjustments to Released for Construction documents and do not impact future construction and installation.

###### Level 2 – Request for Adjustments to Match As-Constructed Details: These accommodate specific details of Work elements already constructed by the Contractor.  They are limited to dimensional and layout adjustments to Released for Construction documents and do not impact future construction and installation.

###### Level 3 – Request for Revision to modify Released for Construction Documents:  These are revisions to the Released for Construction documents to address design or construction discrepancies and/or changes.  They may involve revisions to dimensions and layout, or material changes to conform to contract requirements.

###### Level 4 – Request for Deviation from Project Requirements:  Any deviation from project requirements shall be formally processed for MnDOT concurrence, in the same manner as design submittals.  The proposed revisions shall involve an isolated part of the project, and shall be fully justified by the Contractor and approved by MnDOT prior to incorporation.

##### MnDOT typically has four individuals who have authority to assign a level to FDCs:

###### Construction Manager

###### Design Manager

###### Lead Bridge inspector

###### Lead Civil Inspector

##### Once the level of the FDC is determined, the Contractor completes Phase I of the Field Design Change (FDC) Form CQP201FA (see Exhibit 1.8.6.E-1).

##### The Contractor’s Document Control assigns an FDC number and enters this FDC number into the FDC log CQP201FB (see Exhibit 1.8.6.E-2).

##### For FDC Levels 1 and 2, the following process is followed unless modified by the Contractor’s Quality Manual and approved by MnDOT in the review process:

###### Level 1 and 2 FDCs do not require involvement from the MnDOT Design Manager.

###### The MnDOT Construction Manager agrees on the resolution with Contractor.

###### The MnDOT Construction Manager signs Phase II of the FDC Form after the Contractor has successfully filled out and described the design change.

###### The Contractor’s Document Control forwards the final FDC to MnDOT’s Document Control. Document Control distributes in accordance with the Document Control Procedure.

###### The revised plans are placed in the MnDOT library in accordance with the Document Control Procedure.

##### For FDC Levels 3 and 4, the following process is followed unless modified by the Contractor’s Quality Manual and approved by MnDOT in the review process:

###### Requires involvement from the MnDOT Design Manager.

###### The MnDOT Construction Manager and MnDOT Design Manager confirm that the FDC meets contract requirements and agrees on the resolution with Contractor.

###### MnDOT typically has two Design Managers with authority to approve the resolution of an FDC:

Design Manager

Bridge lead

###### The Contractor submits new Design Calculations for the MnDOT Design Manager’s review.

###### The MnDOT Design and Construction Manager sign Phase II of the FDC Form after the following take place:

MnDOT has reviewed and agreed with the new Design Calculations and Resolution.

The Contractor has successfully filled out and described the design change on this form.

##### The Contractor’s Document Control forwards the final FDC to Document Control.  MnDOT’s project Document Control staff then distributes in accordance with the Document Control Procedure.

##### The revised plans, if required by the FDC level are then placed in the MnDOT library in accordance with the Document Control Procedure.  IIf revised plans are not required for construction, the As-Builts will document the change.

#### Useful Tips/Lessons Learned

##### Always review FDCs against the contract and any project change orders.  Be sure to find a reference section that allows for the proposed resolution or does not restrict it by other contract language.

##### Use field design changes as a check when reviewing As-Builts to assure the Contractor’s designer incorporated them.

##### Field design changes are one of the reasons it is important the Contractor keeps the designer engaged in the Project post-design.

##### Field design changes for existing conditions that vary do not always result in a change order. Some conditions for field design changes that would and would not result in a change order are provided below:

###### No change order

Boring logs reveal a soft zone of 8 ft. on one side of the bridge and 12 ft. at the other side and Contractor finds a zone of 16 ft. at the bent when finishing GMOI required borings.  If the Contractor interpreted the soft zone based on the two borings, this was at their risk as generally MnDOT will only warrant the boring profile at the location of the borings and extrapolation between borings is a contractor risk.

A pipe is not located where depicted but located within the limits of SUE degree of accuracy.

###### Change order possibly warranted if additional costs are realized for the field design change solution:

A boring reveals 8 ft. of soft soils, and during subexcavation the Contractor finds 20 ft., requiring additional design work, and/or more expensive foundations

A pipe is not located within the degree of accuracy represented by the SUE in the contract, leading to additional design work, and additional construction expense.

Note that if the solution proposed by an approved FDC reduces costs for the Contractor and does not impact the schedule, then there may be no need for a Change Order.

#### References

##### Section 1.4.2 Document Control Procedures

##### The Contractor’s approved Quality Manual

#### Attachments/Exhibits

CQP201FA – Field Design Change (FDC) of Quality Manual Template

CQP201FB – Field Design Change (FDC) Log of Quality Manual Template

Exhibit 1.8.6.E-1  FDC of Quality Manual Template

Exhibit 1.8.6.E-2  FDC Log of Quality Manual Template

### Notices of Design Change

#### Purpose

The purpose of this section is to describe procedures for Notices of Design Change.

#### Procedure

##### The Contractor’s procedure for issuing Notices of Design Change is identified in Contractor’s Quality Manual.

##### When the Contractor or MnDOT identifies a potential design change, it should be immediately reported to one of the following MnDOT Design Managers:

Bridge

Roadway

##### The MnDOT Design Manager discusses the potential design change with the Contractor’s Design Manager.

##### The Contractor’s Document Control assigns an NDC number and enters this NDC number into the NDC log DQP505FB (see Exhibit 1.8.7.E-1).

##### The Contractor should immediately notify the MnDOT Construction Manager by filling out and processing through Document Control a Notice of Design Change Form DQP505FA (see Exhibit 1.8.7.E-2); including the reason for the change, the scope of the change, and the estimated time to respond to the design issues.

##### Document Control distributes the Notice of Design Change to the appropriate staff in accordance with the Document Control Procedure.

##### The Contractor makes the necessary plan changes. These changes will be annotated and updated in the revision blocks.

##### Over-the-Shoulder Reviews may be conducted for NDCs in accordance with the Over-the-Shoulder procedures (see Section 1.7.4.1).

##### The Contractor submits NDCs as Released for Construction drawings in accordance with Section 1.7.

###### For more complicated NDCs the process is typically to submit for RFC review.

###### For simple NDCs it is common to submit straight to RFC for signature (RFC – Final).

##### The revised plans are placed in the MnDOT library, replacing the previous RFC document.  The revised drawings will be accompanied by a copy of the original NDC form.

#### Useful Hints/Lessons Learned

##### It is important that the same QC process be followed for NDCs as are followed for design.

##### Notices of Design Changes are one reason it is important for the Contractor to keep the designer engaged in post design.

##### NDCs should always result in re-released plans. However, review all NDCs to assure As-Builts depict them.

#### References

##### Section 1.4.2 Document Control Procedure

##### Section 1.7.4.1 Over-the-Shoulder Reviews Procedure

##### Section 1.7.4.3 Released for Construction – Final

#### Attachments/Exhibits

DQP505FB – Notice of Design Change Log

DQP505FA – Notice of Design Change

Exhibit 1.8.7.E-1  DQP505FB – Notice of Design Change Log

Exhibit 1.8.7.E-2  DQP505FA – Notice of Design Change

## Environmental

#### Purpose

The MnDOT Office of Environmental Stewardship (OES) is responsible for administering environmental programs related to MnDOT construction activities that use state and federal funds. Programs related to environmental stewardship include permitting, regulated materials, air and water quality, erosion control, and stormwater management construction activities. The environmental requirements and commitments for every project are unique.  Responsibility for carrying out these commitments varies based on how the contract is written.  Refer to Book 2 Section 4 and Book 3 Special Provisions for a project’s environmental requirements and commitments.

#### Procedure

The following steps should be followed to ensure that construction activities are carried out in compliance with environmental commitments and requirements:

##### Have a meeting with the MnDOT Environmental Compliance Manager to review the RFP requirements as stipulated in Book 2 Section 4 and Book 3, Special Provisions.  Lay out expectations on the project and determine communication protocol (e.g., who to call if there are hazardous waste spills or discoveries of archeological artifacts). This meeting should take place before NTP 1. This meeting can also be used to identify environment-related commitments and deliverables.

##### Prior to NTP1, meet with MnDOT OES specialists to confirm the requirements of permits and the responsibilities of the verification and oversight team, as well as expectations on what types of Environmental Specialists may be needed to carry out Quality/verification work.  Some potential project-specific needs include:

The Contractor’s responsibility for managing or removing contamination will vary by contract; review these requirements with OES representatives.

The Project commitment to large birds and other species may also vary; review these requirements with OES representatives.

##### Have a meeting with the Contractor to:

Review the Environmental requirements for the project.

Develop the list of contacts from the Contractor and MnDOT Environmental Compliance Manager. Refer to Section 4 for specific project requirements.

Schedule Environmental Training Program for all necessary parties.

##### Ensure the Contractor and the MnDOT Environmental Compliance Manager lay out the contacts and the lines of communication. The MnDOT Environmental Compliance Manager is responsible for the contacts on the MnDOT environmental side.

##### Confirm that all items in Book 2 Section 4.5.1 are completed prior to NTP2 and are submitted to the MnDOT Environmental Compliance Manager and the MnDOT environmental group at Central Office.

#### Useful Tips/Lessons Learned

##### Keep the functional office (OES) involved in Over-the-Shoulder reviews. Although thorough communication with OES is critical, specific areas of interest typically include:

- Regulated materials

- Staging

- Grading

##### Use the list of contacts for individuals to be invited to the environmental pre-construction kick-off meeting.  Make sure the field staff is included in the meeting

##### Not all of the requirements of Book 2 Section 4 fall under the traditional Environmental Compliance Manger role, such as Noise Wall design requirements. Make sure that that the MnDOT Environmental Compliance Manager or another oversight staff member is assigned to champion each requirement of Book 2 Section 4. If the MnDOT Environmental Compliance Manager does not have the specific expertise of the subject matter, make sure coordination happens with the person with that expertise

##### Develop a list of required permits to ensure they are obtained when required, The RFP Book 2 Section 4 may be used as the starting point for the list.

##### Be sure to engage the MnDOT Environmental Compliance Manager from OES to help manage environmental needs on the project.

#### References

##### Section 1.2.1 Process Reviews

##### RFP Book 2 Section 4

#### Attachments/Exhibits

Example Environmental Compliance Management Team.

Exhibit 1.9.E-1	Office of Environmental Stewardship Contacts for MnDOT Environmental Compliance Management Team (sample from the St. Croix Bridge Crossing Project)

| Contact | Cell Phone Number | Issues |
| --- | --- | --- |
| Peter Leete | 651 xxx-xxxx | Invasive species, mussels, wildlife, Work within water |
| Dan Sullivan | 651- xxx-xxxx | MPCA NPDES construction stormwater permit |
| Dwayne Stenlund | 612-xxx-xxxx | Erosion control, stormwater management BMPs |
| Jason Alcott | 651-xxx-xxxx | Invasive species, mussels, wildlife |
| Nick Tiedeken | 651-xxx-xxxx (desk) | COE permits Permit modifications Floodplains |
| Kristen Zschomler | 651-xxx-xxxx (desk) 763- xxx-xxxx (cell) | Section 106/Historical properties – buildings (including remains), archaeological sites, burials, structures, objects. |
| Patti Strohmayer – 1st contact David Larson – 2nd contact | 651- xxx-xxxx (desk) 651- xxx-xxxx (desk) | All landscaping – current tree protection, soil placement, and future planting areas. |
| Sarma Straumanis | 651-xxx-xxxx 651-xxx-xxxx (BWSR) | Wetlands Wetland Conservation Act |
| Mark Vogel | 651-xxx-xxxx | Regulated material management – material handling and disposal |
| Keri Aufdencamp | 651-xxx-xxxx | Contaminated soil and groundwater, spills |
| Paul Voigt | 651-xxx-xxxx (desk) | Existing vegetation, MDA quarantines |
| Marilyn Jordahl-Larson | 651-xxx-xxxx (desk) | Noise and air impacts |

## Contacts with the Public, Media or Attorneys

#### Purpose

Contacts from residents or public officials with inquiries, concerns or complaints about Project activities may be received from any number of sources, including telephone, mail or personal contact.  Additionally, throughout the project, information will be disseminated to various stakeholders. These contacts should be handled as described below.

#### Procedure

The procedures below are divided into three sections:

Contact with media and attorneys

Contact with the public

Contractor contact with the public and stakeholders.

MnDOT strives to be responsive to all of these groups, but protocols must be followed to ensure consistency of message.  Review Book 2 Section 3 of the RFP for project-specific alterations or additions to these procedures

##### The following procedures should be used when communicating with the media or legal counsel:

###### MnDOT Contract Administration Team members are not to respond to media or legal counsel inquiries unless approved by the MnDOT Project Manager or Project Public Affairs coordinator for the Project.

###### Unexpected visits to the project site should be referred to the MnDOT Project Manager or Public Affairs representative for the project as defined in Book 2 Section 3.  A MnDOT Contract Administration Team member is not to comment either on or off the record until instructions or authorization has been given by Project public affairs, or their designated representative.

###### Verification staff should avoid discussions of controversial topics in which comments can be taken out of context.  Questions or comments on such topics should be referred to MnDOT Public Affairs.

##### The following procedures should be used when dealing with the public in general:

###### Provide factual information when addressed by the public, if warranted; then provide a summary of your discussions to the MnDOT Project Manager and MnDOT Public Affairs staff.

###### The Contractor and MnDOT Public Affairs will be the first line for dealing with complaints received from the hotline (if used), website, or other sources.  If necessary, verification staff will be required to assist these groups with responding to individual citizen complaints.

##### The following procedures should be used in engaging the Contractor with public stakeholders:

###### The Contractor should not be involved in media relations without authorization of the MnDOT Project Manager.

###### The Contractor should provide exhibits for public meetings as outlined in Book 2, Section 3.

###### The Contractor can be beneficial at public meetings to discuss schedule, construction sequences and approaches.

#### Useful Tips/Lessons Learned

##### Information about the project given to the public should be fact rather than opinion.  It is good to have pre-prepared, one-page handouts for this purpose.

##### Use a positive attitude that is supportive of the project.

##### Verification staff should avoid discussions of controversial topics in which comments can be taken out of context.  Questions or comments on such topics should be referred to MnDOT Public Affairs.

##### Do not allow media, legal, or public access to the site without the consent of the MnDOT Project Manager and/or the MnDOT Public Affairs group. Refer them to the Project office, hotline or website as available.

##### Generally try to refer anyone inquiring about the project to the hotline (if used), website or public affairs coordinator for the project.

##### Include Contractor representatives where appropriate to provide specific project information.

#### References

##### RFP Book 2 Section 3

#### Attachments/Exhibits

None

## Third Parties

### Utilities

#### Purpose

In design-bid-build projects MnDOT traditionally will relocate utilities prior to the project.  In design-build projects, MnDOT may elect to move high risk utilities before entering the contract with the Contractor.  However, generally utilities are relocated during the Contractor’s contract timeframe with many relocated by the Contractor.

For all projects, design-bid-build and design-build, the MnDOT Office of Utility Agreements and Permits is responsible for administering utility agreements, and issues Notice and Orders. They also enforce the Utility Accommodations Policy on MnDOT Right of Way by helping to resolve any outstanding utility issues.

Utility agreements and responsibilities for coordination and relocation are the primary differences in design-build projects.

The utility requirements and commitments for every design-build project vary based on how the contract is written.  Refer to Book 2 Section 6, UIS sheets and Book 3 Special Provisions for the utility requirements and commitments.

#### Procedure

The supplement for design-build from the Utility Accommodation and Coordination Manual can be found at the link below.  The focus of Section 6 is the implementation of the design-build contract and identifies the steps that should be followed by MnDOT and the Contractor.

http://www.dot.state.mn.us/utility/guidance.html

This supplement covers design-build procurement and RFP development, as well as aspects of contract management, listed below:

Utility Work Plan

Utility Identification

Utility Conflict Analysis

Utility Coordination

Performing the Utility Work

Recurring Utility Meetings

Reimbursement/Responsibility for Cost

Inspection

Close-Out

#### Useful Tips/Lessons Learned

The following useful tips and lessons learned should be kept in mind when managing Utility issues in a design-build project:

##### It is the Contractor’s responsibility to field verify that the utility is located in the field at the location on the plans provided by the Utility Company and/or the RFC Drawings prepared by the Contractor.

##### Have a utility kick-off meeting to discuss utility information and, even though they are non-contractual, the UIS sheets.  Become familiar with the timeframes in Book 2 and the UIS sheets for Utility Companies performance of work.

##### Meeting minutes are required.  Actively require and request meeting minutes within 24 hours of the meeting.

##### It is important to remember that the MnDOT Contract Administration Team is an overseer, not an active designer.  It is the Contractor’s design and coordination staff that must work with the Utilities on design issues.

##### Any additional design work or construction costs arising from differences from the expected location are the responsibility of the Contractor, and cannot be used to justify a change order.

##### Check Book 2 Section 6 to see if the Utility Tracking Report is required.  If it is, review with the Contractor at the kick-off meeting referred to in C.2 above, and enforce providing the report throughout the duration of the project.

##### The contract may also include an outline of the coordination process as an Exhibit to Book 2 Section 6 (Template “MnDOT PM Prompt”). Check to see if it is included and review at the kick-off and enforce it if it is.

##### Perform process reviews to assure utility requirements are being followed.

#### References

##### MnDOT design build supplement to the Utility Accommodation and Coordination Manual (http://www.dot.state.mn.us/utility/guidance.html)

#### Attachments/Exhibits

Utility Tracking Report

Exhibit 1.11.1 - E.1  Utility Tracking Report

### Railroad

#### Purpose

The MDOT Office of Freight and Commercial Vehicle Operations (OFCVO) is responsible for administering railroad agreements. The railroad requirements for each project can vary, and are defined in Book 2 Section 21 of the RFP (additional requirements may appear in Book 3 Special Provisions).

#### Procedure

##### Any required Work near railroad facilities should be given particular attention during reviews:

###### Ensure Design reviewers consider the railroad agreement when reviewing design packages

###### Ensure Construction oversight staff has access to railroad agreements for reference

#### Useful Tips/Lessons Learned

##### Recommend having a kick off meeting with design and construction personnel to allow discussion of Work near and over/under railroad operations. This may be a requirement of the Railroad Agreement.

##### Engage the railroad early to allow for timely agreements.

##### Be sure to proactively encourage the Contractor to engage the railroad in design reviews as needed and to provide schedule updates during construction to allow for proper planning by the railroad.

#### References

##### RFP Book 2 Section 21

#### Attachments/Exhibits

None

## Final Acceptance/Project Close-Out

#### Purpose

The purpose of this section is to provide an understanding of the MnDOT Contract Administration Team’s role with Final Project Closeout Processes in preparation of the warranty period which follows project close-out.

Prior to closing out a project, the FHWA may conduct process reviews and periodic project inspections during the course of the project in accordance with the MnDOT/FHWA Stewardship Agreement.  The MnDOT Project Manager should coordinate these reviews with the FHWA contact designated to the project.  As part of these inspections, MnDOT and the FHWA should develop punch list items.

For the most part project close-out is similar to design-bid-build projects.  However in design-build projects the contractor is also the engineer of record and therefore has some duties associated with that.  Also, payment is not generally by quantity, therefore there are some specific requirements associated with closeout in design-build.  These are detailed in Section 20 of Book 1 and described below.

#### Procedure

The following procedures will be used to close out a project.  This is not an all-inclusive list of requirements, but it covers the major items that need to be addressed during project close-out.

##### It is the Contractor’s obligation to request Final Acceptance.  The Contractor submits a sworn Affidavit of Final Completion in accordance with Book 1, Sections 20.2.1.3 and 20.2.1.2 to initiate this process.

##### Payment retainage should only be released according to the contract. Upon receipt of the Affidavit of Final Completion, the MnDOT Project Manager:

###### Performs a pre- Final Inspection walk through of the project and makes sure the punch list items are complete. Punch lists are not to be overlapped with warranty requirements.

During the final walk-through and follow up meeting, reviews warranty requirements with the Contractor.  These items, once agreed upon by both parties, should be uploaded in TRACS as warranty watch items.

###### Review the project with the OCIC Project Review Engineer and obtain his/her inspection report.

###### Verifies that the requirements outlined in Book 1 Section 20.2.1.2 have been met.

###### Verifies with MnDOT Utility Agreements Unit that there are no outstanding issues with utilities.

###### Verifies with MnDOT Municipal Agreements units that there are no outstanding issues.

###### Verifies with OCIC that there are no outstanding labor holds on the project.

###### Completes all other tasks that may be necessary.

##### If the Contractor has fulfilled the contract requirements and the above conditions have been met, MnDOT will issue a Notice of Final Acceptance in the format of a letter to the Contractor signed by the MnDOT Project Manager.

###### The letter should contain:

Language regarding overpayment obligations (Book 1 Section 20.2.3)

Record retention requirements of Book 1, Section 22

Notification that the Contractor needs to submit an Application for Final Payment in accordance with Book 1, Section 11.6.1

Any other language deemed necessary by the Project Manager

###### MnDOT’s Project Manager must prepare the project final acceptance letter according to MnDOT’s Contract Administration Manual

##### Before Final Payment can be made, the following items must be submitted by the Contractor:

###### A properly prepared Application for Final Payment as per Book 1, Section 11.6.1.

###### A release of claims and conditions outlined in Book 1, Section 11.6.2.1.  The release needs to be accompanied by an affidavit certifying the conditions in Book 1 Section 11.6.2.1.

###### Demonstrates that Minn Stat 290.92 has been met (withholding of State income tax paid to Contractor’s employees) as per Book 1 Section 11.6.2.2.  This can be done via form IC-134.

###### Additional requirements outlined in the MnDOT design-bid-build Contract Administration Manual, described below:

Contractor has submitted federal form PR-47 (Statement of Materials and Labor used by Contractors on Highway Construction Involving Federal Funds).

Contractor has submitted the Final DBE Report

When the Contractor has fulfilled the requirements listed above and when the MnDOT Office of Civil Rights reviews and concurs with the Final DBE Report, the MnDOT Project Manager processes the Final Voucher in accordance with Sections 2.2 and 2.11 of the MnDOT Contract Administration Manual.  The Overrun and Underrun Report may not be necessary for design-build projects.

Upon signature of the Certification of Construction Acceptance (as outlined in the MnDOT Contract Administration Manual) by the Assistant District Engineer or designated representative, the MnDOT Project Manager sends the final to OCIC as per the procedures in the MnDOT Contract Administration Manual.  OCIC forwards the final voucher to the MnDOT Finance unit.

The FHWA will grant MnDOT Final Acceptance of the project at the end of the Warranty Period.  Please note that the FHWA definition of Final Acceptance is different from the contract language.

Upon FHWA Final Acceptance, MnDOT Finance sends the final voucher to the FHWA for approval.

#### Useful Tips/Lessons Learned

##### Do not release retainage prematurely, often retainage is a good incentive for Contractors to finish items timely.

##### Final Acceptance and financial Closeout can and should occur prior to the end of the warranty period.  Retainage cannot be used to ‘motivate’ contractor action regarding warranty items; if funds are necessary they should be withdrawn from the Contractor’s warranty bond.  Furthermore, Federal funds cannot be left unspent on an inactive project.

##### Before subcontractor retainage is released it is prudent to inspect the work with both the subcontractor and contractor present.

##### Double check that the Critical Activity Points are all checked Acceptable.

##### Confirm there are no outstanding NCRs.

##### As-Built documents are commonly a requirement of the contract and ensuring they are accurate is important. The following lessons learned are provided in project close-out to confirm these documents will provide value to MnDOT in the long run:

###### The Contractor’s designer is best suited to prepare As-Built documents

###### Be sure they incorporate changes affected by NCRs, Corrective Actions, FDCs and other design changes or field changes.

###### Require that the Contractor tie As-Built stationing into previous MnDOT stationing and notify MnDOT of any required equations/etc.

C.6.4	Once As-Builts are received, follow the process in Exhibit 1.12.E-1 to post them to eDOCS.

#### References

##### MnDOT Contract Administration Manual

##### RFP Book 1 Section 20

#### Attachments/Exhibits

1.12.E-1	As-Built Plan eDOCS Upload Procedure

Exhibit 1.12 - E.1  As-Built Plan eDOCS Upload Procedure

Step by Step Saving Design Build Construction Plans to eDOCS Procedure

Procedure (Design Build Plans)

- CADD Files are saved to Project Wise

- The electronic copy of the plan is imported to EDMS as a “PDF” file.

- The EDMS profile is filled out according to the EDMS Plans Profile Example below.

- The Document Status Field is set to “As Built”.

- The Document Date is set at the date signed in the “Certified Signature” area.

EDMS Profile for Trunk Highway Plans

- Document Name:  Trunk Highway, [Between…and…] (from top of title page)

- Category:  DESIGN

- Doc. Type:  PLAN

- Doc. Status:  As Built

- Doc. Date: Date that appears with the last signature on title sheet

- Description:  Description of plan from top of title sheet, e.g. Concrete Paving & Shouldering.

- Stewardship Location:  [District shown on title page (without A or B designation). If it shows District 5 or 9, use Metro]

- Function:  Design

- Unit: N/A

- State Project No.:  Fill in this field from info. on title sheet. Use the table to add multiple SP’s

- District: Fill in this field from info. on title sheet.

- County:  Fill in this field from info. on title sheet.

- Control Section:  Fill in this field from info. on title sheet (first four digits of S.P. #).

- Trunk Highway:  Fill in this field from info. on title sheet.

- Beginning Ref. Post and End Ref. Post:  Fill in if available on title sheet.  Look on the plan to see that they are connected.

Change Document Security

Note you must change the security and add Guests-Outside of MnDOT in order for it to display on the external MnDOT Web Site.

From the document profile Click Edit in the Access Control area.

Select Guests-Outside of MnDOT > arrow them to the Current Trustees > Select Read Only > OK (to change security) > OK to update the profile.

Import New Version from File

Once the Contractor provides the PDF file of the As-Built Plans import the file as a new version of the place holder file / document.

Search for and select the target file / PDF > Right Mouse and Select Versions and Attachments

Right mouse on the latest version > Select Import Version from File > OK

Browse to where the file is stored > select Open to import. A new version of the file will be imported.

When information seekers use the MnDOT Web Site the new version will be automatically delivered via the eDOCS Dynamic web link process.

## Warranty Enforcement

#### Purpose

The purpose of this section is to provide an understanding of the MnDOT Contract Administration Team’s role with project warranties.  All MnDOT projects contain warranties for various items. In design-build projects there may be extended warranties or different warranties than a traditional design-bid-build project.  The Contract Administration Team will not stay in place for the entire warranty period.  Therefore there will be a hand-off at some point to a team/person that will administer the warranty.

This section provides the Contract Administration Team procedures and additional guidance in administering a project to have a seamless transition to the warranty period and also provides guidance for the team/person that will administer the warranty period.

#### Procedure

##### The Project Manager assigns one person to be the Single Point Of Contact to administer the Warranty Requirements of the contract.  The SPOC must be a MnDOT Employee.

##### The Project Manager provides the SPOC’s name to the Contractor as part of Final Acceptance.

##### The duties of the SPOC are as follows:

###### The SPOC is responsible for coordinating, typically on a yearly basis, the walkthrough of the Project with the Contractor (see B.4 of this section).

###### The SPOC enforces the warranty in accordance with Book 1 Section 21 of the contract.  This includes coordinating reviews and reporting with the MnDOT functional groups such as the MnDOT Materials Office and MnDOT Bridge Office.

###### The SPOC is responsible for reviewing the items flagged in TRACS as warranty watch items.

###### The SPOC notifies the MnDOT Project Manager after each review of the Project.  The SPOC notifies the MnDOT Project Manager if corrective action is required.

###### The SPOC notifies the MnDOT Project Manager if a dispute arises with the Contractor.

###### If the MnDOT Project Manager is not available, the SPOC will inform the MnDOT District Engineer in the above-referenced cases.

###### If the SPOC is unable to fulfill his/her duties during the life of the Warranty, the SPOC will notify the District Engineer and a new SPOC will be identified for the Project.

##### The SPOC will recall the Contractor to perform warranty inspections and Work as outlined by the following process:

###### On the pre-arranged time coordinate warranty meeting on-site

###### Review items identified in Book 1 for warranty conditions

###### Provide a list of required warranty Work and obtain signatures of both SPOCs (as part of Close-Out, the Contractor will designate a Single Point of Contact of their own).

###### Establish the acceptable timeline for warranty Work identified to be completed.

###### Schedule and perform follow up inspections, repeat steps B.4.3 and B.4.4 until Work is accepted.

##### Engaging the Warranty Bond Surety for Work.

###### If the Contractor is non-responsive for performing defined warranty Work, the MnDOT SPOC engages the District Engineer.  Defer to District Engineer direction for this activity.

#### Useful Tips/Lessons Learned

##### It is helpful from time to time after project award to remind Contractors that there are warranties on a project, not intending to apply Owner pressure but to help them be mindful of contractual obligations

##### During the final walk-through and follow up meeting, review warranty requirements with the Contractor

##### Be sure to review the warranty meeting (reviews) and walk through (inspection) process at the start of the project and periodically throughout as a reminder to the Contractor there are items that have a warranty and a warranty period for the Project

##### Each SPOC will arrange for warranty reviews and inspections

##### Be consistent in warranty enforcement, talk to Resident Engineers and SPOCs that have enforced warranties in the past to form a consistent approach

##### Consider assigning a warranty when signing off on an NCR if Work is in question or difficult to properly inspect

#### References

##### RFP Book 1 Section 21

##### RFP Book 1 Exhibit C

#### Attachments/Exhibits

None

# Text boxes

design-build

Minnesota Department of Transportation

Contract Management

Administration Manual

June 2015