## POC COMMENTS
T.H. 61 Hastings Bridge Design-Build Project
S.P. 1913-64
POC Oversight Documentation
Date | No. | Observation | Recorded by: | Action
2009-10-05 | 1 | Added Joe Campbell as an auditor of the process. Joe is acting bridge design-build engineer. | Jay J Hietpas | Joe was at the kick-off meeting. No additional action required
2009-10-05 | 2 | Reassigned #9 to Steve Kordosky | Jay J Hietpas | None
2009-10-05 | 3 | Added Chuck Howe to assist with evaluation of the vibration monitoring expert. Chuck will share SOQ's with Rich Lamb. | Jay J Hietpas | Amber to brief Chuck on DB Process
2009-10-05 | 4 | Added Tom Sytrbicki and Petra Dewall as Technical Advisors | Jay J Hietpas | Amber to brief Tom and get a copy of SOQ's to him.
2009-10-05 | 5 | Following members were not in attendance at the 10/5/2009 kickoff meeting: Joe Showers, Phil Forst, Kevin Kliethermes, Tom Strybicki, Gary Person, Chuck Howe, Betsy Hayes, Jim Cownie, Lisa Akerman | Jay J Hietpas | Betsy Hayes does not need to be briefed unless called into process. Jim Cownie and Lisa Akerman will be briefed on Friday, Oct 9 by JJH as part of the legal review. Amber will need to brief Dan Dorgan, Joe Showers, Tom Strybicki, Gary Person and Chuck Howe before they recieve proposls. Kevin Kliethermes from the FHWA will brief Phil Forst if necessary.
2009-10-05 | 6 | Interview times were randomly selected by JJH. Jay put all 5 teams names ina copu and drew them out starting with the earliest time and progressing to the last time. | Jay J Hietpas | Steve to notify the teams on times.
2009-10-05 | 7 | Briefed Gary Person on SOQ Evalution process. | Amber Blanchard | Gary missing blue folder. Need to get it to him.
2009-10-06 | 8 | Gave Kevin Kliethermes SOQ number 17. | Amber Blanchard | No action required.
2009-10-12 | 9 | Briefed Joe Showers on the SOQ Evaluation process. | Amber Blanchard | No action required.
2009-10-13 | 10 | Briefed Petra DeWall on the SOQ evaluation process. Gave Petra SOQ number 13. | Amber Blanchard | No action required.
2009-10-14 | 11 | Briefed Chuck Howe on the SOQ evaluation process. | Amber Blanchard | No action required.
2009-10-14 | 12 | Provided Gary Person with blue folder. | Amber Blanchard | No action required.
2009-10-14 | 13 | Briefed Tom Styrbicki on the SOQ Evaluation process. | Amber Blanchard | No action required.
2009-10-15 | 14 | Dan Dorgan removed himself from the SOQ Evaluation process. | Amber Blanchard | See e-mail in file
2009-10-20 | 15 | Reminded TRC that federal rules prohibit favoritism towards local contractors | Jay J Hietpas | No action required.
2009-10-20 | 16 | Recorded may have forgotten to push the "record" button for the Walsh interview. It may be possible that all interviews were taped, except for Walsh. | Jay J Hietpas | Check video tapes to see if this did happen
2009-10-21 | 17 | TRC agreed that all proposers met the minimum pass/fail requirements | Jay J Hietpas | No action required.
2009-10-20 | 18 | TRC (via Jay Hietpas), sent clarifications to Walsh, Flatiron, and Jensen. TRC was instructed to ignore the second paragraph of the Figg cover letter. | Jay J Hietpas | See legal file for each team
2009-10-21 | 19 | Amber briefed the TRC on the responses requested in #18. TRC was instructed to ignore the second paragraph of Figg Cover letter. Jay indicated to TRC that Flatiron had a typo in their paragraph. | Jay J Hietpas | No action required.
2009-10-21 | 20 | Jay updated TRC on recent reference checks recieved. | Jay J Hietpas | Update legal/pass fail summary
2009-10-21 | 21 | Scores were finalized. TRC was asked to initial the final scoring sheet indicating that these were their scores and recommendation. Lynn Clarkowski forgot to sign before she left. | Jay J Hietpas | Send an e-mail to Lynn asking her to confirm her scores. See final scoring file.
2009-10-21 | 22 | Rich Lamb, Gary Peterson and Chuck Howe brief the TRC on the strengths/weeknesses of the Geotechnical Engineering Team and Vibration Monitoring Manager. Petra Dewall briefed the TRC on the qualifications of the bridge scour engineer. | Jay J Hietpas | No action required.

## MANUALLOG
TH 61 Hastings Bridge Design-Build Project
SOQ Review Process
Name | Proposal # | Evaluation Manual # | Role | Confidentiality Form | Agenda | SOQ Eval Manual (double sided) | RFQ w/ Clarifiactions (double sided) | Five (5) Sets of Qualitative Eval Forms (single sided) | Five (5) Submitter Evaluations Sheets (single sided) | Five (5) Sets of Appendix B (single sided) | SOQ Evaluation Summary Sheet
Kevin Western | 1 | 1 | TRC | X | X | X | X | X | X
Dave Miller | 2 | 2 | TRC | X | X | X | X | X | X
Lynn Clarkowski | 3 | 3 | TRC | X | X | X | X | X | X
Amr Jabr | 4 | 4 | TRC | X | X | X | X | X | X
Paul Kivisto | 5 | 5 | TRC | X | X | X | X | X | X
Keith Farquhar | 6 | 6 | TA | X | X | X | X
Joe Showers | 7 | 7 | TA | X | X | X | X
Rich Lamb | 8 | 8 | TA | X | X | X | X
Gary Person | 9 | 9 | TA | X | X | X | X
Dan Dorgan | 10 | 10 | TA | X | X | X | X
Jim Cownie | 11 | 11 | TA | X |  | X | X |  |  | X
Lisa Ackerman | 12 | 12 | TA | X |  | X | X |  |  | X
Kevin Kliethermes | 13 | 13 | POC | X | X | X | X
Phil Forst | 14 | 14 | POC | X | X | X | X
Jay Hietpas | 15 | 15 | POC | X | X | X | X |  |  | X
Amber Blanchard | 16 | 16 | POC | X | X | X | X |  |  | X | X
| 17 | 17
| 18 | 18
| 19 | 19
| 20 | 20

## Team Listing
TH 61 HASTINGS BRIDGE SOQ SUBMITTALS
Submitter | Ames/Lunda | Walsh | Flatiron-Kiewit | PCL/Kraemer | Jensen Johnson Cramer
Major Participants / Subs | Parsons Transportation Group | Buckland and Taylor, Ltd | T.Y. Lin International | HDR | Figg
| Michael Baker Corporation | AECOM | IBT | PB Americas | TKDA
| Dan Brown and Associates | Vibra-Tech Engineers | M+M | Huitt-Zollars | Braun Intertec
| Braun Intertec |  | PBS&J | Braun Intertec | Ayres Associates
| Touchstone Architecture |  | Braun Intertec
| Ayres Associates |  | Terracon
| HZ United |  | Wenck
| Illumination Arts |  | Rani Engineering
| Himle Horner, Inc |  | U of Minnesota
Project Manager | Dolye Honstad | Tom Warren | Peter Sanderson | Jeff Morore | Brian West
Construction Manager | David Duke | Dave Singleton | Bryan Bahl | Lynn Davis | Mark Buller/Zvonko Juric
Vibration Monitoring Manager | Chris Kehl | Mohamad Sharif | Christopher Kehl | Mathew Ruble | Chris Kehl
Quality Manager | Ben Fardi | Joe Hosanna | Tracy Martin | Gregory Bauer | Chad Widup
Independent Bridge Check Engineer | Bob Bondi | Wally R Burn | Daniel Tassin / Dr. John Kulicki | Charles Quade | Chris Burgess
Design Quality Manager | Eddie He | Jeffrey Wetmore | Dennis Jang | James Unruh | Jose Rodriguez
Construction Quality Manager | Ben Fardi | Frank Raymond | Frank Mydlinski | Gregory Bauer | Chad Widup
Design Manager | Vince Gastoni | John Wallace Jordan | Amir Kangari | John Yadlosky | Jay Rohleder
Lead Bridge Design Engineer | Martin Furrer | Don Bergman | David Goodyear | Michael Abrahams | Denney Pate
Bridge Hydraulics Engineer | John Hunt | Ryan M Edsion | Joel Toso | John Engel | Lyle Zevenbergen
Geotechnical Engineering Team | Dan Brown | Chia K Tan | Jeff Gebhard | Mathew Ruble | Jebb Gebhard
| Jeff Gebhard |  | Steve Laverson | Jeff Gebhard

## Lessons Learned
1 | Make sure we require page numbers in the proposal and in the appendix (A-1, A-2…).
2 | Inform Mn/DOT staff well of information that will be disclosed as part of Form 8 and make them aware well in adavnce of any information.
3 | Develop a "silvert-bullet" if there is a fatal flaw
4 | RFP requirements identified as enhancements should be scored as a weakness.
5