Design-Build Contract

BOOK 1

MINNESOTA DEPARTMENT OF TRANSPORTATION

District

Design-Build Project

S.P.

Federal Project No.

{May, 2011}

Table of Contents

Recitals	1

1	CONTRACT COMPONENTS; INTERPRETATION OF CONTRACT DOCUMENTS	2

1.1	Certain Definitions	2

1.2	Contract Documents	2

1.3	Order of Precedence	2

1.4	Interpretations	2

1.5	Referenced Standards and Specifications	3

1.6	Omission of Details; Clarification by Mn/DOT	3

1.7	Computation of Periods	3

1.8	Standard for Approvals	3

1.9	Federal Requirements	4

1.10	American Recovery and Reinvestment Act (ARRA) Section 902	Error! Bookmark not defined.

2	OBLIGATIONS OF CONTRACTOR	5

2.1	Performance Requirements	5

2.1.1	Performance of Work	5

2.1.2	Performance Standards	5

2.1.3	Performance as Directed	5

2.2	General Obligations of Contractor	5

2.3	Representations, Warranties and Covenants	6

2.3.1	Maintenance of Professional Qualifications	6

2.3.2	Evaluation of Constraints	6

2.3.3	Feasibility of Performance	6

2.3.4	Review of Site Information	6

2.3.5	Governmental Approvals	7

2.3.6	Progression of Work	7

2.3.7	Design and Engineering Personnel	7

2.3.8	Organization	7

2.3.9	Authorization	7

2.3.10	Legal, Valid and Binding Obligation	8

2.3.11	False or Fraudulent Statements and Claims	8

2.4	Design Requirements	8

2.4.1	Required Acceptance	8

2.4.2	Design Review Process; Compliance with Design	8

2.4.3	Ownership of Design	9

3	INFORMATION SUPPLIED TO CONTRACTOR; RESPONSIBILITY FOR DESIGN; DISCLAIMER	10

3.1	Information Supplied	10

3.2	Responsibility for Design	10

3.3	Reliance of Specified RID Information	10

3.3.1	No Other Liability Regarding RID	10

3.3.2	No Representation or Warranty Regarding Basic Configuration and RID	10

3.4	Professional Licensing Laws	11

4	TIME WITHIN WHICH PROJECT SHALL BE COMPLETED; SCHEDULING	12

4.1	Time of Essence	12

4.2	Notices to Proceed	12

4.2.1	Issuance of NTP1	12

4.2.2	Issuance of NTP2	12

4.3	Completion Deadlines	12

4.3.1	Substantial Completion Deadline	12

4.3.2	Final Acceptance Deadline	13

4.3.3	No Time Extensions	13

4.4	Contract Schedule	13

4.5	Prerequisites for Start of Construction	13

4.6	Limitation of Operations	13

5	CONTROL OF WORK	14

5.1	Control and Coordination of Work	14

5.2	Safety	14

5.3	Process to be Followed for Discovery of Certain Site Conditions	14

5.3.1	Notification to MnDOT	14

5.3.2	Further Investigation and Necessary Actions	14

5.3.3	Recommence Work	15

5.4	Obligation to Minimize Impacts	15

5.5	Quality Management	15

5.5.1	Contractor Quality Management	15

5.5.2	Oversight, Inspection, and Testing by Mn/DOT and Others	15

5.5.3	Obligation to Uncover Finished Work	15

5.6	Effect of Oversight, Spot Checks, Audits, Tests, Acceptances, and Approvals	16

5.6.1	Oversight and Acceptance	16

5.6.2	No Estoppel	16

5.7	Nonconforming Work	16

5.7.1	Rejection, Removal and Replacement of Work	16

5.7.2	Acceptance of Nonconforming Work	16

6	ACCESS TO SITE; Utility relocations; environmental mitigation	18

6.1	Access to Site	18

6.1.1	Access to Right of Way Identified on R/W Work Map	18

6.1.2	Access to Right of Way Not Identified on R/W Work Map	18

6.1.3	Sharing of Cost Savings For Avoided Right of Way Acquisitions	19

6.2	Utility Relocations	19

6.2.1	Accuracy of Design and Data	19

6.2.2	Change in Allocation of Responsibility	20

6.2.3	Added Utility Work	21

6.2.4	Betterments	21

6.2.5	Utility Delays	22

6.2.6	Certain Obligations of Contractor; Utility-Related Right of Way Costs	23

6.2.7	Additional Restrictions on Change Orders	24

6.3	Environmental Compliance	24

6.3.1	Mitigation Requirements	25

6.3.2	New Environmental Approvals	25

7	EQUAL EMPLOYMENT OPPORTUNITY; SUBCONTRACTS; LABOR	26

7.1	Equal Employment Opportunity	26

7.1.1	Equal Employment Opportunity Policy	26

7.1.2	Inclusion in Subcontracts	26

7.2	Disadvantaged Business Enterprises	26

7.2.1	Disadvantaged Business Enterprises Policy	26

7.2.2	Inclusion in Subcontracts	26

7.3	Subcontracting Requirements	26

7.3.1	Major Participants	26

7.3.2	Assignment of Subcontract Rights	26

7.3.3	Subcontract Terms	26

7.3.4	Subcontract Data	27

7.3.5	Responsibility for Work by Subcontractors	27

7.3.6	Subcontract Work	27

7.3.7	Debarred Subcontractors	27

7.4	Key Personnel; Character of Workers	27

7.4.1	Key Personnel	27

7.4.2	Representations, Warranties and Covenants	28

7.4.3	Employee Performance Requirements	28

8	SURETY BONDS	29

8.1	Payment and Performance Bond	29

8.2	Warranty Bond	29

8.3	Utility Work	29

8.4	Guaranty	29

8.5	No Relief of Liability	30

9	INSURANCE	31

9.1	General Insurance Requirements	31

9.1.1	Evidence of Insurance	31

9.1.2	A.M. Best Rating	31

9.1.3	Full Force and Effect	31

9.1.4	No Recourse	31

9.1.5	Indemnification	31

9.1.6	Commercial Unavailability of Required Coverages	31

9.1.7	Primary and Non-Contributory	31

9.1.8	 Governmental Immunity	32

9.2	Contractor-Provided Insurance	32

9.2.1	Worker’s Compensation and Employer’s Liability Coverage	32

9.2.2	Commercial General Liability Insurance	32

9.2.3	Automobile Liability Insurance	33

9.2.4	Excess (Umbrella) Liability Insurance	33

9.2.5	Contractor’s Pollution Liability Coverage	33

9.2.6	Professional Liability Insurance	34

9.2.7	Builder’s Risk	34

10	risk of loss	36

10.1	Site Security	36

10.2	Maintenance and Repair of Work and On-Site Property	36

10.2.1	Responsibility of Contractor	36

10.2.2	Landscape Establishment	36

10.2.3	Relief from Liability for Maintenance	36

10.3	Damage to Off-Site Property	36

10.4	Title	37

11	PAYMENT	38

11.1	Contract Price	38

11.1.1	Contract Price	38

11.1.2	Items Included in Contract Price	38

11.1.3	Delay in Issuance of NTP1	38

11.1.4	Fuel Cost Escalation	38

11.2	Invoices and Payment	39

11.3	Limitations on Payment	39

11.3.1	Delay in Issuance of NTP1	39

11.3.2	Payment Schedule	39

11.3.3	NTP1 Payment Cap	39

11.3.4	Unincorporated Materials (Materials on Hand)	39

11.3.5	Materials Ineligible for Payment	40

11.3.6	Nonconforming Work	40

11.4	Not Used	41

11.5	Deductions	41

11.6	Final Payment	41

11.6.1	Application for Final Payment	41

11.6.2	Payment	42

11.7	Payments to Subcontractors	42

11.8	Interest on Late Payments	42

11.9	Disputes	43

12	Contract Incentives	44

12.1	Early Completion Incentives	44

12.2	Other Incentives	44

13	CHANGES IN THE WORK	45

13.1	Circumstances under which Change Orders May Be Issued	45

13.1.1	Definition of and Requirements Relating to Change Orders	45

13.1.2	Directive Letter as Condition Precedent to Claim That a Mn/DOT-Directed Change Has Occurred	46

13.1.3	Significant Changes in the Character of Work	46

13.2	Procedure for Mn/DOT-Initiated Change Orders	46

13.2.1	Request for Change Proposal	46

13.2.2	Unilateral Change Orders	47

13.2.3	Changes in Law	47

13.3	Procedure for Contractor Initiated Change Orders	47

13.3.1	Eligible Changes	47

13.3.2	Conditions Precedent	49

13.3.3	Performance of Disputed Work	51

13.4	Contents of Change Orders	51

13.4.1	Not Used	51

13.4.2	Scope of Work, Cost Estimate, Delay Analysis, and Information Regarding Change	51

13.4.3	Not Used	52

13.4.4	Contractor Representation	52

13.5	Certain Limitations	52

13.5.1	Limitation on Contract Price Increases	52

13.5.2	Limitation on Delay and Disruption Damages	53

13.5.3	Limitation on Time Extensions	53

13.6	Negotiated Price Change Orders	54

13.6.1	Not Used	54

13.6.2	Unit Price Change Orders	54

13.6.3	Added Work	54

13.6.4	Deleted Work	54

13.6.5	Work Both Added and Deleted	54

13.7	Time and Materials Change Orders	54

13.7.1	Determination of Costs	55

13.7.2	Time and Materials Records	55

13.7.3	 Compliance with the Federal Acquisition Regulation	56

13.8	Differing Site Conditions	56

13.8.1	Responsibilities of Mn/DOT	56

13.8.2	Burden of Proof	57

13.9	Certain Events	57

13.10	Contaminated Materials Management	57

13.11	Matters Not Eligible for Change Orders	57

13.12	Waiver	58

13.13	Disputes	58

13.14	No Release or Waiver	58

13.14.1	Extension of Time for Performance	58

13.14.2	No Change Order Based on Course of Conduct or Order by Unauthorized Person	59

14	SUSPENSION OF WORK	60

14.1	Suspension for Convenience	60

14.2	Suspension for Cause	60

14.3	Contractor Responsibilities During Suspension	60

15	TERMINATION FOR CONVENIENCE	61

15.1	Notice of Termination	61

15.2	Contractor’s Responsibilities Upon Termination	61

15.3	Responsibility After Notice of Termination	62

15.4	Negotiated Termination Settlement	62

15.4.1	Settlement Proposal	62

15.4.2	Negotiated Settlement Amount	62

15.5	Determination of Settlement Amount If Negotiations Fail	63

15.5.1	Payment Amount	63

15.5.2	Maximum Compensation	63

15.5.3	Excluded Items	64

15.5.4	Payment of Termination Amount	64

15.6	Partial Termination	64

15.7	Reduction in Amount of Claim	64

15.8	Partial Payments	64

15.9	Inclusion in Subcontracts	64

15.10	Limitation on Payments to Subcontractor	64

15.11	No Unearned Profits or Consequential Damages	65

15.12	No Waiver	65

15.13	Dispute Resolution	65

15.14	Allowability of Costs	65

15.15	Suspension of Work	65

15.16	Termination Due to Non-Appropriation of Funds	65

15.16.1	Availability of Funds	65

15.16.2	Anticipated Appropriations	65

15.16.3	Remedy for Failure To Appropriate	65

16	DEFAULT	67

16.1	Default By Contractor	67

16.1.1	Events of Default	67

16.1.2	Right to Cure	68

16.2	Remedies	68

16.2.1	Rights of Mn/DOT	68

16.2.2	Liability of Contractor	69

16.3	Right to Stop Work If Undisputed Payment Is Not Made	70

16.4	Notice and Opportunity to Cure Other Types of Mn/DOT Breaches	70

17	DAMAGES	71

17.1	Liquidated Damages and Disincentives	71

17.1.1	Failure to Meet Completion Deadlines	71

17.1.2	Reasonableness of Liquidated Damage Amounts	71

17.2	Offset; Waiver	72

17.2.1	Offset	72

17.2.2	Waiver of Liquidated Damages	72

17.3	Payment of Liquidated Damages	72

18	INDEMNIFICATION	73

18.1	Indemnifications by Contractor	73

18.1.1	General Indemnities	73

18.1.2	Design Defects	73

18.1.3	Losses Due to Negligence of Indemnified Parties	74

18.1.4	Claims by Employees	74

18.1.5	Reliance on Contractor’s Performance	74

18.2	Responsibility of Mn/DOT for Certain Contaminated Materials	74

18.2.1	Pre-Existing Site Contamination	74

18.2.2	Generator Number for Hazardous Waste Materials	74

18.3	No Effect on Other Rights	75

18.4	CERCLA Agreement	75

18.5	Intent of Indemnity for Breach of Contract	75

19	PARTNERING, CLAIMS FOR ADJUSTMENT AND DISPUTES	76

19.1	Partnering	76

19.2	Disputes	79

19.3	Costs	79

19.4	Claims for Compensation Adjustment and Disputes	79

20	ACCEPTANCE OF PROJECT	80

20.1	Substantial Completion	80

20.1.1	Notice by Contractor	80

20.1.2	Correction of Defects	80

20.1.3	Notice of Substantial Completion	81

20.2	Final Acceptance	81

20.2.1	Conditions to Final Acceptance	81

20.2.2	Inspection and Issuance of Notice of Final Acceptance	82

20.2.3	Overpayments; No Relief from Continuing Obligations	82

20.3	Opening of Sections of Project to Traffic	82

20.3.1	Plan for Opening to Traffic	82

20.3.2	Direction to Open Following Contractor Failure to Perform	83

20.3.3	No Waiver	83

20.4	Assignment of Causes of Action	83

21	WARRANTIES	84

21.1	Warranties by Contractor	84

21.1.1	Project Warranties	84

21.1.2	Project Warranty Term	84

21.1.3	Additional Warranty Requirements	84

21.1.4	Corrective Work	84

21.1.5	Costs of Correction of Work	85

21.2	Warranty of Corrected Work	85

21.3	Subcontractor Warranties	86

21.3.1	Assignment	86

21.3.2	Enforcement	86

21.4	No Limitation of Liability	86

21.5	Warranty Beneficiaries	86

21.6	Remedies for Breach of Warranty	86

21.7	Disputes	86

22	DOCUMENTS AND RECORDS	87

22.1	Escrowed Proposal Documents	87

22.1.1	Review of EPD	87

22.1.2	Property of Contractor	87

22.1.3	Representation and Warranty	87

22.1.4	Contents of EPD	88

22.1.5	Format of EPD	88

22.1.6	Review by Mn/DOT	88

22.1.7	Confidentiality Agreement	88

22.2	Subcontractor Pricing Documents	88

22.3	Project Records	89

22.3.1	Maintenance of Records	89

22.3.2	Audit and Inspection Rights	89

22.3.3	Audit of Time and Materials Work	89

22.3.4	Change Order Pricing Data	89

22.3.5	Claims Audits	89

22.4	Retention of Records	90

22.5	Minnesota Government Data Practices Act	91

22.5.1	Applicability of Act	91

22.5.2	Confidential Materials	91

22.5.3	Contractor to Defend Against Disclosure Request	91

23	MISCELLANEOUS PROVISIONS	92

23.1	Amendments	92

23.2	Waiver	92

23.2.1	No Waiver of Subsequent Rights	92

23.2.2	Custom Does not Constitute Waiver	92

23.2.3	Waivers Must Be in Writing	92

23.3	Independent Contractor	92

23.4	Successors and Assigns	92

23.4.1	Assignment by Mn/DOT	93

23.4.2	Assignment by Contractor	93

23.5	Designation of and Cooperation with Representatives	93

23.5.1	Designation of Representatives	93

23.5.2	Cooperation	93

23.6	Officials not to Benefit	93

23.7	Survival	93

23.8	Limitation on Third-Party Beneficiaries	94

23.9	No Personal Liability	94

23.10	Notices and Communications	94

23.10.1	Delivery of Notices	94

23.10.2	Receipt of Notices	95

23.10.3	Copies of Correspondence to Mn/DOT	95

23.11	Further Assurances	95

23.12	Severability	95

23.13	Headings	96

23.14	Governing Law	96

23.15	Limit of Liability	96

23.16	Entire Agreement	96

23.17	Counterparts	96

Exhibits

Exhibit A	Acronyms and Definitions

Exhibit B	Certificate to Commissioner of Transportation

Exhibit C	Additional Warranty Requirements

Exhibit D	EEO Special Provisions

Exhibit E	Disadvantaged Business Enterprise (DBE) Special Provisions for Design-Build Projects

Exhibit F	Federal and State Prevailing Wage Requirements and Additional Federal Requirements

Exhibit F-1	Traffic Control Prevailing Wage Coverage

Exhibit F-2	Federally Funded Construction Contracts; Special Provisions Division A – Labor

Exhibit F-3	Federal Wage Rates

Exhibit F-4	State Wage Rates

Exhibit F-5	Not Used

Exhibit F-6	Steel and Iron Materials (SP2000-22)

Exhibit F-7	Notice of Certification of Truck Rental Rates

Exhibit G	Key Personnel

Exhibit H	Limitation on Use of Contract Funds for Lobbying

Exhibit I	Debarment and Suspension

{Note to authors:  Exhibits E, F-1, F-2, F-3, F-6, H, and I are only required on federally funded projects.}  Put “Not Used” next to these exhibit names for state-funded only projects.

THIS Design-Build Contract is entered into by and between the State of Minnesota through its Commissioner of Transportation (“Mn/DOT”) and       (“Contractor”), effective as of the last date set forth on the signature page hereto, with reference to the definitions contained in Exhibit A hereto and the following facts:

# Recitals

A.	The Project is located in       County, Minnesota, within the city limits of      .  The Project limits include      .  The Project scope is to design and construct      .  The proposed construction includes      . The Project also includes      .

B.	The parties intend for the Contract to be a lump-sum design-build Contract obligating Contractor to perform all work necessary to complete the Project by the deadlines specified herein, for the Contract Price, subject only to certain specified limited exceptions. To allow Mn/DOT to budget for the Project and to reduce the risk of cost overruns, the Contract includes restrictions affecting Contractor’s ability to make claims for an increase to the Contract Price or an extension of the Completion Deadlines. Contractor has agreed in the Contract to assume such responsibilities and risks and has reflected the assumption of such responsibilities and risks in the Contract Price.

C.	If Contractor fails to complete the Project within the time limitations set forth in the Contract Documents, then Mn/DOT will suffer substantial losses and damages. The Contract Documents therefore provide that Contractor shall pay Mn/DOT substantial Liquidated Damages if such completion is delayed.

D.	Mn/DOT has provided the Basic Configuration to Contractor for the purpose of defining certain aspects of the Project. Mn/DOT has also provided Reference Information Documents (RID) to Contractor. Contractor has no right to rely on the RID except to the extent specifically permitted in the Contract Documents. Mn/DOT and Contractor both intend for Contractor to assume full responsibility and liability with respect to the design of the Project, including correction of any Errors in the Basic Configuration or RID, and Mn/DOT and Contractor both intend for Contractor to indemnify and hold harmless Mn/DOT and others with respect to any defects in the Project which may relate to Errors in the Basic Configuration or RID.

NOW, THEREFORE, in consideration of the sums to be paid to Contractor by Mn/DOT, the foregoing premises and the covenants and agreements set forth herein, the parties hereto hereby agree as follows.

# 1	CONTRACT COMPONENTS; INTERPRETATION OF CONTRACT DOCUMENTS

## 1.1	Certain Definitions

Exhibit A hereto contains the meaning of various terms used in the Contract Documents.

## 1.2	Contract Documents

The term “Contract Documents” shall mean the documents listed in Section 1.3, including all exhibits thereto.

## 1.3	Order of Precedence

Each of the Contract Documents is an essential part of the Contract, and a requirement occurring in one is as binding as though occurring in all. The Contract Documents are intended to be complementary and to describe and provide for a complete Contract. In the event of any conflict among the Contract Documents, the order of precedence shall be as set forth below:

(a)	Change Orders and Contract amendments

(b)	Book 1, as executed by Mn/DOT and Contractor (Design-Build Contract)

(c)	Book 2 (Project Requirements)

(d)	Book 3 (Applicable Standards)

(e)	The Proposal, except if the Proposal includes statements that can reasonably be interpreted as offers to provide higher quality items than otherwise required by the Contract Documents or to perform services in addition to those otherwise required, or otherwise contains terms that are more advantageous to Mn/DOT than the requirements of the Contract Documents, as determined by Mn/DOT, Contractor’s obligations hereunder shall include compliance with all such statements, offers and terms.

(f)	The Statement of Qualifications, except if the Statement of Qualifications includes statements that can reasonably be interpreted as offers to provide higher quality items than otherwise required by the Contract Documents or to perform services in addition to those otherwise required, or otherwise contains terms that are more advantageous to Mn/DOT than the requirements of the Contract Documents, as determined by Mn/DOT, Contractor’s obligations hereunder shall include compliance with all such statements, offers, and terms.

In the event of conflicting requirements involving any requirement established by reference contained in the Contract Documents, Mn/DOT shall have the right to determine, in its sole discretion, which requirement applies.

Contractor shall request Mn/DOT’s determination respecting the order of precedence among conflicting provisions promptly upon becoming aware of any such conflict.

## 1.4	Interpretations

In the Contract Documents, where appropriate: the singular includes the plural and vice versa; references to statutes or regulations include all statutory or regulatory provisions consolidating, amending, or replacing the statute or regulation referred to; the words “including,” “included,” “includes,” and “include” are deemed to be followed by the words “without limitation”; unless the context requires otherwise, in phrases involving performance by a Person, the word “shall” indicates a requirement imposed on the Person; unless otherwise indicated, references to sections, appendices and exhibits are to the document which contains such references; words such as “herein,” “hereof,” and “hereunder” refer to the entire document in which they are contained and not to any particular provision or section; words not otherwise defined that have well-known technical or construction industry meanings are used in accordance with such recognized meanings; references to Persons include their respective permitted successors and assigns and, in the case of Governmental Persons, Persons succeeding to their respective functions and capacities; and words of any gender used herein include each other gender where appropriate. Unless otherwise specified, lists contained in the Contract Documents defining the Project or the Work shall not be deemed all-inclusive. Contractor further acknowledges and agrees that it has independently reviewed the Contract Documents with legal counsel, and that it has the requisite experience and sophistication to understand, interpret, and agree to the particular language of the Contract Documents. Accordingly, in the event of an ambiguity in or dispute regarding the interpretation of the Contract Documents, the Contract Documents shall not be construed against the Person who prepared them, and instead other rules of interpretation shall be used. Mn/DOT’s final answers to the questions posed during the proposal process for the Contract shall in no event be deemed part of the Contract Documents and shall not be relevant in interpreting the Contract Documents except as they may clarify provisions otherwise considered ambiguous.

## 1.5	Referenced Standards and Specifications

Except as otherwise specified in the Contract Documents or otherwise directed by Mn/DOT, Work specified by the number, symbol, or title of any standard established by reference to a described publication affecting any portion of the Project shall comply with the latest edition or revision thereof and amendments and supplements thereto in effect on the Proposal Due Date.

## 1.6	Omission of Details; Clarification by Mn/DOT

Contractor shall not take advantage of any apparent Error in the Contract. Should it appear that the Work to be done or any matter relative thereto is not sufficiently detailed or explained in the Contract Documents, Contractor shall apply to Mn/DOT in writing for such further written explanations as may be necessary and shall conform to the explanation provided. Contractor shall promptly notify Mn/DOT of all Errors which it may discover in the Contract Documents, and shall obtain specific instructions in writing regarding any such Error before proceeding with the Work affected thereby. The fact that the Contract Documents omit or misdescribe any details of any Work which are necessary to carry out the intent of the Contract Documents, or which are customarily performed under similar circumstances, shall not relieve Contractor from performing such omitted Work or misdescribed details of the Work, and they shall be performed as if fully and correctly set forth and described in the Contract Documents, without entitlement to a Change Order hereunder except as specifically allowed under Section 13.

## 1.7	Computation of Periods

References to “days” or “Days” contained in the Contract Documents shall mean Calendar Days unless otherwise specified, provided that if the date to perform any act or give any notice specified in the Contract Documents (including the last date for performance or provision of notice “within” a specified time period) falls on a non-Working Day, such act or notice may be timely performed on the next succeeding day which is a Working Day. Notwithstanding the foregoing, requirements contained in the Contract Documents relating to actions to be taken in the event of an emergency, requirements contained in Section 5.3 and any other requirements for which it is clear that performance is intended to occur on a non-Working Day, shall be required to be performed as specified, even though the date in question may fall on a non-Working Day.

## 1.8	Standard for Approvals

In all cases where approvals, acceptances, or consents are required to be provided by Mn/DOT or Contractor hereunder, such approvals, acceptances, or consents shall not be withheld unreasonably except in cases where a different standard (such as sole discretion) is specified, and shall not be unreasonably delayed if no response time is specified. In cases where sole discretion is specified, the decision shall not be subject to dispute resolution or other legal challenge; provided, however, the issue of whether the decision was arbitrary or capricious shall be subject to dispute resolution hereunder.

## 1.9	Federal Requirements

Notwithstanding anything to the contrary contained herein, in the event of any conflict between any Federal Requirement and the other requirements of the Contract Documents, the Federal Requirements shall prevail, take precedence and be in force over and against any such conflicting provisions.

# 2	OBLIGATIONS OF CONTRACTOR

## 2.1	Performance Requirements

### 2.1.1	Performance of Work

All materials, services and efforts necessary to achieve Substantial Completion and Final Acceptance on or before the applicable Completion Deadline shall be Contractor’s sole responsibility, except as otherwise specifically provided in the Contract Documents. Subject to the terms of Section 13, the costs of all such materials, services and efforts are included in the Contract Price.

### 2.1.2	Performance Standards

Contractor shall furnish the design of the Project and shall construct the Project as designed, in accordance with all professional engineering principles and construction practices generally accepted as standards of the industry in the State (but at least meeting the requirements of the Contract Documents), in a good and workmanlike manner, free from defects (except to the extent that such defects are inherent in prescriptive specifications included in the Contract Documents unless (a) Contractor has actual or constructive knowledge of such defects, and (b) Contractor fails to request a change thereto by Mn/DOT), and in accordance with the terms and conditions set forth in the Contract Documents.

### 2.1.3	Performance as Directed

At all times during the term hereof, including during the course of, and notwithstanding the existence of, any dispute, Contractor shall perform as directed by Mn/DOT in a diligent manner and without delay, shall abide by Mn/DOT’s decision or order, and shall comply with all applicable provisions of the Contract Documents. If a dispute arises regarding such performance or direction, the dispute shall be resolved in accordance with Section 19.

## 2.2	General Obligations of Contractor

Contractor, in addition to performing all other requirements of the Contract Documents, shall perform the following:

(a)	Furnish all design and other services, provide all materials and labor and undertake all efforts necessary or appropriate (excluding only those services, materials and efforts which the Contract Documents specify will be undertaken by other Persons): (i) to construct the Project and maintain it during construction in accordance with the requirements of the Contract Documents, all Governmental Rules, all Governmental Approvals, and all other applicable safety, environmental, licensing and other requirements, taking into account the R/W Work Map and other constraints affecting the Project, so as to achieve, Substantial Completion and Final Acceptance by the applicable Completion Deadlines; and (ii) otherwise to do everything required by and in accordance with the Contract Documents.

(b)	At all times provide Contractor’s Project Manager, Approved by Mn/DOT, who (i) will have full responsibility for the prosecution of the Work, (ii) will act as agent and be a single point of contact in all matters on behalf of Contractor, (iii) will be present (or its Approved designee will be present) at the Site at all times that Work is performed, and (iv) will have authority to bind Contractor on all matters relating to the Project.

(c)	Obtain all Governmental Approvals (other than the Environmental Approvals and certain New Environmental Approvals as provided in Section 6.3).

(d)	Comply with all conditions imposed by and undertake all actions required by and all actions necessary to maintain in full force and effect, all Governmental Approvals, including implementation of all environmental mitigation measures required by the Contract Documents, except to the extent that such responsibility is expressly assigned in the Contract Documents to another Person.

(e)	Provide such assistance as is reasonably requested by Mn/DOT in dealing with any Person and/or in prosecuting and defending lawsuits in any and all matters relating to the Project, which may include providing information and reports regarding the Project, executing declarations and attending meetings and hearings, but which shall in no event be deemed to require Contractor to provide legal services.

(f)	Comply with all requirements of all Governmental Rules, including: (i) the Environmental Laws, including all environmental mitigation and monitoring measures required for the Project, including those set forth in Book 2, Section 4, and requirements regarding the handling, generation, treatment, storage, transportation and disposal of Contaminated Materials; (ii) the Americans with Disabilities Act of 1990 (ADA), 42 U.S.C. § 12101 et seq., including any amendments, as well as all applicable regulations and guidelines; and (iii) the Federal Requirements.

(g)	Comply with the Quality Manual requirements in Book 2, Section 2.4.

(h)	Cooperate with Mn/DOT and Governmental Persons with jurisdiction over the Project in the review and oversight of the Project and other matters relating to the Work.

(i)	Supervise and be responsible to Mn/DOT for acts and omissions of all Contractor-Related Entities, as though all such Persons were directly employed by Contractor.

(j)	Mitigate delay to the Project and mitigate damages due to delay to the extent possible, including by resequencing, reallocating or redeploying Contractor’s forces to other work, as appropriate.

(k)	Pay all applicable federal, State and local sales, consumer, use and similar taxes, property taxes and any other taxes, fees, charges or levies imposed by a Governmental Person, whether direct or indirect, relating to, or incurred in connection with, the performance of the Work.

## 2.3	Representations, Warranties and Covenants

Contractor represents, warrants and covenants for the benefit of Mn/DOT as follows:

### 2.3.1	Maintenance of Professional Qualifications

Contractor and its design Subcontractor(s) have maintained, and throughout the term of the Contract and its design Subcontract(s) shall maintain, all required authority, license status, professional ability, skills and capacity to perform the Work, and shall perform them in accordance with the requirements of the Contract Documents.

### 2.3.2	Evaluation of Constraints

Contractor has evaluated the constraints affecting delivery of the Project, including the R/W Work Map and Basic Configuration as well as the conditions of the Environmental Approvals and has reasonable grounds for believing and does believe that the Project can be delivered within such constraints.

### 2.3.3	Feasibility of Performance

Contractor has evaluated the feasibility of performing the Work within the time specified herein and for the Contract Price, and has reasonable grounds for believing and does believe that such performance (including achievement of Substantial Completion and Final Acceptance by the applicable Completion Deadlines, for the Contract Price) is feasible and practicable.

### 2.3.4	Review of Site Information

Contractor has, prior to submitting its Proposal, in accordance with prudent and generally accepted engineering and construction practices, reviewed the boring logs provided by Mn/DOT in Book 2 and undertaken other appropriate activities sufficient to familiarize itself with surface conditions and subsurface conditions discernible from the surface affecting the Project, to the extent Contractor deemed necessary or advisable for submittal of a Proposal. Said activities have included inspection and examination of the Site and surrounding locations, to the extent possible.  Based on its review, inspection, examination and other activities, Contractor is familiar with and accepts the physical requirements of the Work, subject to the right to receive a Change Order for Differing Site Conditions as specified herein. Before commencing any Work on a particular aspect of the Project, Contractor shall verify all governing dimensions and conditions at the Site and shall examine all adjoining work which may have an impact on such Work. Contractor shall be responsible for ensuring that the Design Documents and Construction Documents accurately depict all governing and adjoining dimensions and conditions.

### 2.3.5	Governmental Approvals

Contractor has no reason to believe that any Governmental Approval required to be obtained by Contractor will not be granted in due course and thereafter remain in effect so as to enable the Work to proceed in accordance with the Contract Documents. If any Governmental Approvals required to be obtained by Contractor must formally be issued in the name of Mn/DOT, Contractor shall undertake all efforts to obtain such approvals, subject to Mn/DOT’s reasonable cooperation with Contractor, including execution and delivery of appropriate applications and other documentation in a form Approved by Mn/DOT. Contractor shall assist Mn/DOT in obtaining any Governmental Approvals which Mn/DOT may be obligated to obtain, including providing information requested by Mn/DOT and participating in meetings regarding such approvals.

### 2.3.6	Progression of Work

Contractor shall at all times schedule and direct its Work to provide an orderly progression of the Work to achieve Substantial Completion and Final Acceptance by the applicable Completion Deadlines and in accordance with the Contract Schedule, including furnishing such employees, materials, facilities and equipment and working such hours (including extra shifts and overtime operations) as may be necessary to achieve such goals, all at Contractor’s own expense, except as otherwise specifically provided in Section 13.

### 2.3.7	Design and Engineering Personnel

All design and engineering Work furnished by Contractor shall be performed by or under the supervision of Persons licensed to practice architecture, engineering or surveying (as applicable) in the State, and by personnel who are careful, skilled, experienced and competent in their respective trades or professions, who are professionally qualified to perform the Work in accordance with the Contract Documents, and who shall assume professional responsibility for the accuracy and completeness of the Design Documents and Construction Documents prepared or checked by them.

### 2.3.8	Organization

Contractor is a      duly organized and validly existing under the laws of the State of       with all requisite power to own its properties and assets and carry on its business as now conducted or proposed to be conducted. Contractor is duly qualified to do business, and is in good standing, in the State, and will remain in good standing throughout the term of the Contract and for as long thereafter as any obligations remain outstanding under the Contract Documents.

### 2.3.9	Authorization

The execution, delivery and performance of the Contract have been duly authorized by all necessary actions of Contractor, and, if applicable, Contractor’s members, and will not result in a breach or a default under the organizational documents of any such Person or any indenture, loan, credit agreement, or other material agreement or instrument to which any such Person or any Guarantor is a party or by which their properties and assets may be bound or affected.

### 2.3.10	Legal, Valid and Binding Obligation

The Contract constitutes the legal, valid and binding obligation of Contractor and, if applicable, of each member of Contractor, enforceable in accordance with its terms. If applicable, each Guaranty constitutes the legal, valid and binding obligation of Guarantor, enforceable in accordance with its terms.

### 2.3.11	False or Fraudulent Statements and Claims

Contractor recognizes that the requirements of the Program Fraud Civil Remedies Act of 1986, as amended, 31 U.S.C. § 3801 et seq. and the USDOT regulations, “Program Fraud Civil Remedies,” 49 C.F.R. Part 31, apply to its actions hereunder. Accordingly, by signing the Contract, Contractor certifies or affirms the truthfulness and accuracy of any statement it has made, it makes, or it may make pertaining to the Contract. In addition to other penalties that may be applicable, Contractor also acknowledges that if it makes a false, fictitious, or fraudulent claim, statement, submission, or certification, the federal government reserves the right to impose the penalties of the Program Fraud Civil Remedies Act of 1986, as amended, on Contractor to the extent the federal government deems appropriate.

Contractor recognizes that the Minnesota False Claims Act (Minnesota Statutes Chapter 15C) applies to any requests  or demands made by the Contractor under this Contract and that the Contractor may be civilly liable to the State (including treble damages and attorney fees) for violations of the Act.

## 2.4	Design Requirements

### 2.4.1	Required Acceptance

Acceptance by Mn/DOT is required prior to commencing any Work that would necessitate a modification in the Basic Configuration, regardless of whether the modification is required by a Governmental Approval, is desired by Contractor for its benefit or for any other reason. Contractor acknowledges and agrees that constraints set forth in the Contract Documents, as well as Site conditions, the R/W Work Map and the requirement to obtain Acceptance, will impact Contractor’s ability to revise the Basic Configuration.

### 2.4.2	Design Review Process; Compliance with Design

#### 2.4.2.1	Design Review Process

Contractor shall furnish the Released for Construction Documents and other Design Documents to Mn/DOT in accordance with Book 2, Section 2.4. Contractor shall obtain Mn/DOT’s Acceptance of the Released for Construction Documents in accordance with Book 2, Section 2.4 and, if required, shall obtain Mn/DOT’s Acceptance or Approval of the other Design Documents (as applicable) in accordance with Book 2. Mn/DOT shall have the right to review and comment on all Released for Construction Documents and other Design Documents for compliance with the requirements of the Contract Documents in accordance with Book 2, Section 2.4. Contractor shall notify Mn/DOT in writing within 14 Days after receipt of any such comments if Contractor believes incorporation of the comments would cause the Released for Construction Documents, other Design Documents or any Contract Documents to contain Errors in any respect or which would otherwise adversely affect in any manner the design or construction of the Project or the Contract Schedule, and Mn/DOT shall have the right to modify its comments. Any failure of Contractor to so notify Mn/DOT shall constitute Contractor’s full acceptance of all responsibility for changes made to the Released for Construction Documents and other Design Documents in response to such Mn/DOT comments and will be treated for all purposes hereunder as if Contractor had initiated such changes. Within 14 Days of receipt of comments (including modifications to previous comments) or such longer period as may be allowed by Mn/DOT, Contractor shall revise and modify all such documents or materials so as to fully reflect all such comments.

#### 2.4.2.2	Third Party ATC Approvals

Contractor acknowledges that any approvals from Persons other than Mn/DOT required to implement Approved ATCs incorporated in the Contract Documents are Contractor’s sole responsibility to obtain and may be disapproved for any reason (or for no stated reason). Contractor agrees that if Contractor fails to obtain any such approval, Contractor shall comply with the corresponding baseline requirements (unmodified by the ATC) without any increase in the Contract Price or extension of the Completion Deadlines.

#### 2.4.2.3	Design Reviews Required by Third Parties

Contractor, working with Mn/DOT, shall be responsible for giving and obtaining all design reviews required by Utility Owners, Regulatory Agencies, Railroad owners and any other Persons other than Mn/DOT, as applicable.

#### 2.4.2.4	Compliance with Contract Documents and Design

Contractor shall deliver the Project in accordance with and otherwise meet the requirements of the Contract Documents and Design Documents. To the extent of any conflicts between the Contract Documents and the Design Documents, the Contract Documents shall have precedence over the Design Documents.

### 2.4.3	Ownership of Design

Released for Construction Documents and other Design Documents become Mn/DOT’s property upon preparation. Other documents prepared or obtained by Contractor in connection with the performance of its obligations under the Contract, including Construction Documents, studies, manuals, as-built drawings, calculations, technical and other reports and the like, become Mn/DOT’s property upon Contractor’s preparation or receipt, thereof.

# 3	INFORMATION SUPPLIED TO CONTRACTOR; RESPONSIBILITY FOR DESIGN; DISCLAIMER

## 3.1	Information Supplied

Mn/DOT has made available to Contractor information which is described in the Contract Documents and certain Reference Information Documents regarding the Project, and has allowed Contractor access to the Site for purposes of inspection and testing.

## 3.2	Responsibility for Design

Contractor agrees that it has full responsibility for the design of the Project and that Contractor shall furnish the design of the Project, regardless of the fact that certain conceptual design work occurred and was provided to Contractor prior to the date of execution of the Contract. Contractor specifically acknowledges and agrees that:

(a)	The Basic Configuration is preliminary and conceptual in nature.

(b)	Contractor is not entitled to rely on and has not relied on (i) the RID or (ii) any other documents or information provided by Mn/DOT, except to the extent specifically permitted in the Contract Documents.

(c)	Contractor is responsible for correcting any Errors in the Basic Configuration through the design and/or construction process as set forth in Book 2 without any increase in the Contract Price or extension of a Completion Deadline, subject only to the right to a Change Order for Necessary Basic Configuration Changes.

(d)	Contractor’s Warranties and indemnities hereunder cover Errors in the Project even though they may be related to Errors in the Basic Configuration or RID.

## 3.3	Reliance of Specified RID Information

### 3.3.1	No Other Liability Regarding RID

Contractor understands and agrees that Mn/DOT shall not be responsible or liable in any respect for any loss, damage, injury, liability, cost or cause of action whatsoever suffered by any Contractor-Related Entity by reason of any use of any information contained in the RID or any action or forbearance in reliance thereon, except to the extent that Mn/DOT has specifically agreed herein that Contractor shall be entitled to an increase in the Contract Price and/or extension of a Completion Deadline with respect to such matter. Contractor further acknowledges and agrees that (a) if and to the extent Contractor or anyone on Contractor’s behalf uses any of said information in any way, such use is made on the basis that Contractor, not Mn/DOT, has approved and is responsible for said information, and (b) Contractor is capable of conducting and obligated hereunder to conduct any and all studies, analyses and investigations as it deems advisable to verify or supplement said information, and that any use of said information is entirely at Contractor’s own risk and at its own discretion.

### 3.3.2	No Representation or Warranty Regarding Basic Configuration and RID

Mn/DOT DOES NOT REPRESENT OR WARRANT THAT THE INFORMATION CONTAINED IN THE RID IS EITHER COMPLETE OR ACCURATE OR THAT SUCH INFORMATION CONFORMS WITH THE REQUIREMENTS OF THE CONTRACT DOCUMENTS. THE FOREGOING SHALL IN NO WAY AFFECT Mn/DOT’S AGREEMENT HEREIN TO ISSUE CHANGE ORDERS IN ACCORDANCE WITH SECTION 13.

## 3.4	Professional Licensing Laws

Mn/DOT does not intend to contract for, pay for, or receive any design services which are in violation of any professional licensing laws, and by execution of the Contract, Contractor acknowledges that Mn/DOT has no such intent. It is the intent of the parties that Contractor is fully responsible for furnishing the design of the Project, although the fully licensed design firm(s) or individuals designated herein will perform the design services required by the Contract Documents. Any references in the Contract Documents to Contractor’s responsibilities or obligations to “perform” the design portions of the Work shall be deemed to mean that Contractor shall “furnish” the design for the Project. The terms and provisions of this Section 3.4 shall control and supersede every other provision of the Contract Documents.

# 4	TIME WITHIN WHICH PROJECT SHALL BE COMPLETED; SCHEDULING

## 4.1	Time of Essence

Time is of the essence of the Contract.

## 4.2	Notices to Proceed

### 4.2.1	Issuance of NTP1

Contractor shall begin performance of certain limited Work as directed and described in NTP1 issued by Mn/DOT. Limited Work may include non-permanent construction that does not impact traffic such as preliminary design, final design if specifically authorized in writing by Mn/DOT, tree removal, clearing and grubbing, Utility coordination, soil borings, temporary construction, and other items specifically authorized in writing by Mn/DOT. This limited Work shall not commence until all the following events have been fully satisfied with respect to the Work proposed to be constructed.

(a)	Contractor has notified Mn/DOT in writing of the Work to be performed and has received Mn/DOT Approval, which may require Released for Construction Plans with Mn/DOT Acceptance.

(b)	All Governmental Approvals necessary for construction of such portion of the Project have been obtained and all conditions of such Governmental Approvals that are a prerequisite to commencement of such construction have been performed.

(c)	All insurance policies and bonds required to be delivered to Mn/DOT hereunder have been received and Accepted or Approved by Mn/DOT as applicable and remain in full force and effect.

(d)	All necessary rights of access for such portion of the Project have been obtained.

(e)   Acceptance of the Preliminary Schedule in accordance with Book 2, Section 2.

### 4.2.2	Issuance of NTP2

Contractor shall begin performance of the remainder of the Work as directed and described in NTP2 issued by Mn/DOT. Mn/DOT shall issue NTP2 upon the occurrence of all of the following:

(a)    Approval of the Original Payment Breakdown.

(b)    Approval of the Contractor’s Quality Manual.  To expedite construction activities, the Contractor may request that Mn/DOT Approve sections of the Quality Manual to obtain NTP2.

(c)   Approval of the environmental items listed in Book 2, Section      .

(d)   Acceptance of the preliminary Utility Tracking Report.

(e)	Approval of the Traffic Management Plan.

(f)	Approval of the insurance policies, endorsements, and/or certificates required under Section 9.

## 4.3	Completion Deadlines

### 4.3.1	Substantial Completion Deadline

Contractor shall achieve Substantial Completion by      . Said deadline for Substantial Completion, is referred to herein as the “Substantial Completion Deadline.”

#### 4.3.1.1	Intermediate Completion Deadlines {Use as applicable}

The Contractor shall complete       by      .

### 4.3.2	Final Acceptance Deadline

Contractor shall achieve Final Acceptance within 200 Calendar Days following Substantial Completion.  See Section 11.3 on Limitations on Payment.  Said deadline for Final Acceptance, as it may be extended hereunder, is referred to herein as the “Final Acceptance Deadline.”

### 4.3.3	No Time Extensions

Except as otherwise specifically provided in Section 12 and Section 13, Mn/DOT shall have no obligation to extend any Completion Deadline. Contractor shall not be relieved of its obligation to comply with the Contract Schedule and achieve Substantial Completion and Final Acceptance by the applicable Completion Deadlines for any reason.

## 4.4	Contract Schedule

Contractor shall deliver the Project, including planning, design, construction, management, development and completion, in accordance with the Contract Schedule, as described in Book 2, Section 2.3. Such schedule shall also be the basis for determining the amount of monthly progress payments to be made to Contractor.

## 4.5	Prerequisites for Start of Construction

Contractor shall not start construction (or recommence construction following any suspension) of any portion of the Project, except Work specifically authorized under NTP1, until all the following events have been fully satisfied with respect to the Work proposed to be constructed.

(a)	Mn/DOT has issued a Notice to Proceed authorizing such Work.

(b)	All requirements of the Quality Manual that are a condition to construction have been met.

(c)	Contractor has furnished the Released for Construction Documents to Mn/DOT and has received Mn/DOT’s Acceptance thereof in accordance with Book 2, Section 2.4 relating to such portion of the Project, unless waived in writing by Mn/DOT.

(d)	All Governmental Approvals necessary for construction of such portion of the Project have been obtained and all conditions of such Governmental Approvals or the application to the Government entities which allow construction to proceed during the application process, that are a prerequisite to commencement of such construction, have been performed.

(e)	All insurance policies and bonds required to be delivered to Mn/DOT hereunder have been received and Accepted or Approved by Mn/DOT as applicable and remain in full force and effect.

(f)	All necessary rights of access for such portion of the Project have been obtained.

(g)	Contractor has furnished to Mn/DOT and Mn/DOT has Accepted the drawings set forth in Book 2, Section 14.

(h)	Any additional conditions for construction set forth in the Contract Documents.

## 4.6	Limitation of Operations

The Contractor shall not perform construction operations on Sundays or State holidays, unless specifically authorized in writing by Mn/DOT.  See Book 2, Section 4 for noise restrictions.

# 5	CONTROL OF WORK

## 5.1	Control and Coordination of Work

Contractor shall be solely responsible for and have control over the construction means, methods, techniques, sequences, procedures and Site safety, and shall be solely responsible for coordinating all portions of the Work under the Contract Documents, subject, however, to all requirements contained in the Contract Documents.

## 5.2	Safety

Contractor shall take all reasonable precautions to prevent damage, injury, or loss to, all persons on the Site or who would reasonably be expected to be affected by the Work, including individuals performing Work, employees of Mn/DOT and its consultants, visitors to the Site and members of the public who may be affected by the Work.  Contractor shall at all times comply with the Safety Management Plan (SMP) when an SMP is required by the Contract.  Contractor shall immediately notify Mn/DOT if Contractor believes that any Contract requirement creates a safety risk.

## 5.3	Process to be Followed for Discovery of Certain Site Conditions

### 5.3.1	Notification to MnDOT

#### 5.3.1.1	Discovery of Certain Site Conditions

If Contractor becomes aware of (a) any on-Site material that Contractor believes may contain Contaminated Materials that are required to be removed or treated, (b) any archeological, paleontological, cultural or biological resources, or (c) any Differing Site Conditions, as a condition precedent to Contractor’s right to a Change Order, Contractor shall immediately notify Mn/DOT via telephone or in person, to be followed immediately by written notification. In such event, Contractor shall immediately stop Work in the affected area and secure the affected area pending receipt of direction from Mn/DOT.   Mn/DOT will view the location within two Working Days of receipt of such notification and will advise Contractor at that time whether to resume work or whether investigation is required.   Any delay resulting from Mn/DOT viewing the location up to two Working Days shall not be considered a Mn/DOT-Caused Delay.

#### 5.3.1.2	Identified Conditions; Alternative Procedure

Notwithstanding the foregoing, Contractor shall not be obligated to stop Work upon discovery of any materials, resources, species or conditions which the Contract Documents indicate are present in the location in question. Furthermore, if any Governmental Approval specifies a procedure to be followed which differs from the procedure set forth herein, Contractor shall follow the procedure set forth in the Governmental Approval.

### 5.3.2	Further Investigation and Necessary Actions

Contractor shall promptly conduct such further investigation as Mn/DOT deems appropriate.

If Differing Site Conditions are discovered, the Contractor shall advise Mn/DOT within one Working Day after the initial notice to Mn/DOT of any action recommended to be taken regarding the situation.  Mn/DOT then will determine whether Contractor’s findings and proposed actions are acceptable within three Working Days of receipt of Contractor’s notice and either Approve, or require modification of, Contractor’s proposed actions.  The development and execution of any recommended action plan will only be considered a Mn/DOT-Caused Delay to the extent that these items affect the Critical Path.

Contaminated Materials requirements are further described in Book 2, Section 4.

If paleontological, cultural, or biological resources are present, Mn/DOT will determine and perform the necessary actions to address impacts to these resources or direct the Contractor to perform any necessary actions pursuant to a Change Order issued under Section 13.6 or 13.7.   The impacts of any necessary actions to address these resources will only be considered a Mn/DOT-Caused Delay to the extent that these items affect the Critical Path.

### 5.3.3	Recommence Work

Mn/DOT shall have the right to require Contractor to recommence Work in the area at any time, even though an investigation may still be ongoing (so long as such Work is not in violation of any Governmental Rules or Governmental Approvals). Contractor shall promptly recommence Work in the area upon receipt of notification from Mn/DOT to do so. On recommencing Work, Contractor shall follow all applicable procedures contained in the Contract Documents and all other Governmental Rules with respect to such Work, consistent with Mn/DOT’s determination or preliminary determination regarding the nature of the material, resources, species or condition.

## 5.4	Obligation to Minimize Impacts

Contractor shall ensure that all of its activities and the activities of all Contractor-Related Entities are undertaken in a manner that will minimize the effect on surrounding property and the public to the maximum extent practicable.

## 5.5	Quality Management

### 5.5.1	Contractor Quality Management

Contractor shall perform the quality management necessary for Contractor to comply with its obligations under the Contract Documents.

### 5.5.2	Oversight, Inspection, and Testing by Mn/DOT and Others

All materials and each part or detail of the Work shall also be subject to oversight, inspection and testing by Mn/DOT and other Persons designated by Mn/DOT. When any Utility Owner is to accept or pay for a portion of the cost of the Work, its respective representatives have the right to oversee, inspect and test the Work. Such oversight, inspection and/or testing does not make such Person a party to the Contract nor will it change the rights of the parties hereto. Contractor hereby consents to such oversight, inspection and testing. Upon request from Mn/DOT, Contractor shall furnish information to such Persons as are designated in such request and shall permit such Persons access to the Site and all parts of the Work.

### 5.5.3	Obligation to Uncover Finished Work

At all times before Final Acceptance, Contractor shall remove or uncover such portions of the finished construction Work as directed by Mn/DOT. After examination by Mn/DOT and any other Persons designated by Mn/DOT, Contractor shall restore the Work to the standard required by the Contract Documents. If the Work exposed or examined is not in conformance with the requirements of the Contract Documents, then uncovering, removing and restoring the Work and recovery of any delay to the Critical Path occasioned thereby shall be at Contractor’s expense and Contractor shall not be entitled to a time extension. Furthermore, any Work done or materials used without notice to and opportunity for prior inspection by Mn/DOT as provided in Book 2, Section 2.4 may be ordered uncovered, removed or restored at Contractor’s expense and without a time extension, even if the Work proves acceptable after uncovering. Except with respect to Work done or materials used as described in the foregoing sentence, if Work exposed or examined under this Section 5.5.3 is in conformance with the requirements of the Contract Documents, then any delay in the Critical Path from uncovering, removing and restoring Work shall be considered a Mn/DOT-Caused Delay, and Contractor shall be entitled to a Change Order for the cost of such efforts and recovery of any delay to the Critical Path occasioned thereby, subject to the provisions of Section 13.

## 5.6	Effect of Oversight, Spot Checks, Audits, Tests, Acceptances, and Approvals

### 5.6.1	Oversight and Acceptance

Contractor shall not be relieved of its obligation to perform the Work in accordance with the Contract Documents, or any of its other obligations under the Contract Documents, by oversight, spot checks, audits, reviews, tests, inspections, acceptances or approvals by any Persons, or by any failure of any Person to take such action. The oversight, spot checks, audits, reviews, tests, inspections, acceptances and approvals by any Person do not constitute Final Acceptance of the particular material or Work, or waiver of any legal or equitable right with respect thereto. Mn/DOT may reject or require Contractor to remedy any Nonconforming Work and/or identify additional Work that must be done to bring the Project into compliance with Contract requirements at any time prior to Final Acceptance, whether or not previous oversight, spot checks, audits, reviews, tests, inspections, acceptances or approvals were conducted by any Person.

### 5.6.2	No Estoppel

Mn/DOT shall not be precluded or estopped, by any measurement, estimate or certificate made either before or after Final Acceptance and payment therefor, from showing that any such measurement, estimate or certificate is incorrectly made or untrue, or from showing the true amount and character of the Work performed and materials furnished by Contractor, or from showing that the Work or materials do not conform in fact to the requirements of the Contract Documents. Notwithstanding any such measurement, estimate or certificate, or payment made in accordance therewith, Mn/DOT shall not be precluded or estopped from recovering from Contractor and its Surety(ies) such damages as Mn/DOT may sustain by reason of Contractor’s failure to comply or to have complied with the terms of the Contract Documents.

## 5.7	Nonconforming Work

### 5.7.1	Rejection, Removal and Replacement of Work

Subject to Mn/DOT’s right, in its sole discretion, to Accept or reject Nonconforming Work, Contractor shall remove and replace rejected Nonconforming Work so as to conform with the requirements of the Contract Documents, at Contractor’s expense and without any time extension; and Contractor shall promptly take all action necessary to prevent similar deficiencies from occurring in the future. The fact that Mn/DOT may not have discovered the Nonconforming Work shall not constitute an Acceptance of such Nonconforming Work. If Contractor fails to correct any Nonconforming Work within five Days of receipt of notice from Mn/DOT requesting correction (or, for Nonconforming Work that cannot be corrected within five Days, if Contractor fails to provide to Mn/DOT a schedule for correcting any such Nonconforming Work Approved by Mn/DOT within such five-Day period, begin correction within such five-Day period and thereafter diligently prosecute such correction in accordance with such Approved schedule to completion), then Mn/DOT may cause the Nonconforming Work to be remedied or removed and replaced, and may deduct the cost of doing so from any moneys due or to become due Contractor and/or obtain reimbursement from Contractor for such cost.

### 5.7.2	Acceptance of Nonconforming Work

Mn/DOT may, in its sole discretion, Accept any Nonconforming Work without requiring it to be fully corrected, and shall be entitled to a pay adjustment (or reimbursement of a portion of the Contract Price, if applicable). In certain events, it may not be possible for the Nonconforming Work to be made to conform to the requirements of the Contract Documents, including, without limiting the foregoing, Contractor’s failure to perform such items to be paid in equal monthly amounts indicated in Book 2, Section 2.2 during a required time period. In general, the pay adjustment (or reimbursement) shall equal, at Mn/DOT’s election, (a) Contractor’s cost savings associated with its failure to perform the Work in accordance with the Contract requirements or (b) the amount deemed appropriate by Mn/DOT to provide compensation for impacts to affected parties such as future maintenance and/or other costs relating to the Nonconforming Work. In certain events, Mn/DOT shall be entitled to a pay adjustment (or reimbursement) as expressly set forth elsewhere in the Contract Documents.

# 6	ACCESS TO SITE; Utility relocations; environmental mitigation

## 6.1	Access to Site

### 6.1.1	Access to Right of Way Identified on R/W Work Map

#### 6.1.1.1	Obligation to Provide Access to Right of Way

Mn/DOT will provide access to the Right of Way identified on the R/W Work Map.

#### 6.1.1.2	Right of Way Access Requirements

Concurrently with review of the Baseline Schedule, Contractor and Mn/DOT shall discuss the access requirements for the Right of Way identified on the R/W Work Map associated with the scheduled activities, mutually determine which parcels are on the Critical Path and establish dates to be included in the Baseline Schedule for activities associated with provision of access. Contractor shall be provided access to those parcels identified on the R/W Work Map that have not been obtained by the Proposal Due Date no later than the deadline specified in Book 2, Section 7. For Approval, the Baseline Schedule must be structured to provide reasonable work-arounds to progress the Project until these parcels become available, and reasonably minimize dependence on these parcels.

#### 6.1.1.3	Delay in Providing Access

If Mn/DOT at any time determines it will be unable to provide access to a particular parcel by the scheduled date (on the Contract Schedule), Mn/DOT shall notify Contractor regarding the revised projected date for delivery of access. Contractor shall take appropriate action to minimize any cost and time impact and shall work around such parcel until access can be provided, including rescheduling and resequencing Work so as to avoid any delay to the Project. Subject to Section 6.1.1.4, to the extent that a delay to the Critical Path cannot be avoided, such delay to the Critical Path shall be considered a Mn/DOT-Caused Delay.

#### 6.1.1.4	Obligation to Provide Written Notice

In addition to the requirements of Section 6.1.1.3, and as a necessary condition for obtaining any increase in the Contract Price or extension of a Completion Deadline related to Mn/DOT’s delivery of access to the parcels identified on the R/W Work Map, Contractor shall provide Mn/DOT with a 30-Day written notice when lack of availability of a given parcel will result in an impact to the cost or schedule.

### 6.1.2	Access to Right of Way Not Identified on R/W Work Map

#### 6.1.2.1	Unidentified Right of Way as a Result of a Mn/DOT-Directed Change

Any Right of Way not identified on the R/W Work Map that is required as the result of a Mn/DOT-Directed Change will be addressed in the respective Change Order for the Mn/DOT-Directed Change.

#### 6.1.2.2	Right of Way Associated with a Contractor Initiated Change Order

The cost of obtaining any Right of Way not identified on the R/W Work Map associated with a Contractor Initiated Change Order will be considered in determining the Contract Price adjustment under Section 13.

#### 6.1.2.3	Reimbursement of Mn/DOT Costs

Subject to Mn/DOT Approval, Contractor shall reimburse Mn/DOT for any costs (including attorneys’, accountants’ and expert witness fees and costs) of acquiring any real property that is not Mn/DOT’s responsibility under Sections 6.1.1.1, 6.1.2.1 or 6.1.2.2 which Contractor determines is necessary or advisable in order to complete the Project, including obtaining any Construction Easements. Mn/DOT may deduct such amounts from payments otherwise owing hereunder, or may invoice Contractor. Contractor shall reimburse Mn/DOT for any such amounts paid by Mn/DOT within 10 Days after receipt of an invoice from Mn/DOT therefor.

#### 6.1.2.4	Additional Requirements

Additional requirements applicable to Contractor are set forth in Book 2, Section 7.

### 6.1.3	Sharing of Cost Savings For Avoided Right of Way Acquisitions

Contractor is encouraged to evaluate design alternatives that would avoid the need to acquire Right of Way. If any such design alternative is Approved, resulting in reduction of Mn/DOT’s costs, change in the Contract Price will be negotiated.

## 6.2	Utility Relocations

This Section 6.2 describes how the risk of increased costs and delays associated with the Utility Work is allocated between Mn/DOT and Contractor through the Change Order process, and contains certain additional terms relating to Utility Work to supplement those set forth in Book 2, Section 6. Contractor agrees that (a) the Contract Price covers all of the Relocations and other Utility Work to be furnished or performed by Contractor described in Book 2, Section 6 and in this Section 6.2, and (b) it is feasible to obtain and/or perform all necessary Utility Work within the time deadlines of the Contract Documents. Accordingly, Contractor shall be entitled to receive a Change Order for additional costs and delays associated with the Utility Work only as permitted by this Section 6.2 or in circumstances for which such a Change Order is otherwise permitted under Section 13 (such as for Mn/DOT-Directed Changes which increase the Utility Work to be furnished or performed by Contractor). A deductive Change Order for reductions in the Utility Work to be furnished or performed by Contractor shall be issued only when permitted by this Section 6.2 or in circumstances for which a deductive Change Order is otherwise permitted under Section 13. Notwithstanding the foregoing, Contractor’s entitlement to any Change Orders pursuant to Section 13 relating to the Utility Work shall be subject to any applicable limitations and restrictions set forth in this Section 6.2, and Contractor’s entitlement to any Change Orders pursuant to this Section 6.2 shall be subject to the limitations, restrictions and procedures set forth in Section 13.

### 6.2.1	Accuracy of Design and Data

#### 6.2.1.1	Inaccuracy Increasing the Work

In general, if any existing underground Utility identified in Book 2, Section 6 as part of the Work (or any portion of such Utility) is not indicated at all in the Certified SUE Plans or Test Hole Matrices showing Verified Utility Information provided in Book 2 or is not indicated with “reasonable accuracy” (as defined in Section 6.2.1.3) therein, then, upon Contractor’s fulfillment of all applicable requirements of Section 13, and subject to the limitations contained therein, Mn/DOT shall be responsible for, and agrees to issue a Change Order to (a) compensate Contractor for additional costs and/or (b) extend the applicable Completion Deadlines as the result of any delay in the Critical Path of the Utility Work (other than Betterments added to the Work pursuant to Section 6.2.4) to be furnished or performed by Contractor which are directly attributable to such lacking or incorrect information.  Notwithstanding the foregoing, Contractor shall be responsible for, and no Change Order shall be issued under this Section 6.2.1.1 with respect to any of the following:

(i)	Any Utility (or portion thereof) which a surface inspection of the area would have shown the existence or the likelihood of existence thereof in the correct location and/or size, as applicable, by reason of above-ground facilities such as buildings, meters, junction boxes or identifying markers

(ii)	Service Lines

(iii)	Any costs or delays associated with the performance of Incidental Utility Work by Contractor or by any Utility Owner

#### 6.2.1.2	Inaccuracy Decreasing the Work

If any existing underground Utility identified in Book 2, Section 6 as part of the Work (or any portion of such Utility) is not indicated with “reasonable accuracy” in the Certified SUE Plans or Test Hole Matrices showing Verified Utility Information provided in Book 2, then Mn/DOT shall have the right to issue a Change Order reducing the Contract Price and/or Completion Deadlines to reflect the value of any reduction in the costs and/or duration of the Utility Work (other than Betterments added to the Work pursuant to Section 6.2.4) to be furnished or performed by Contractor which is directly attributable to the correction of such information. The amount of any such Change Order shall be determined in accordance with Section 13.

#### 6.2.1.3	“Reasonable Accuracy” Defined

6.2.1.3.1	Reasonable Accuracy

For purposes of Sections 6.2.1.1 and 6.2.1.2, a Utility shall be deemed indicated with reasonable accuracy if:

(a)	with respect to the “Quality Level A” Utility information provided by Mn/DOT (as indicated therein), the Utility’s actual location is within 2 feet of the indicated horizontal and vertical locations at the “xyz” coordinates in the Certified SUE Plans or Test Hole Matrices showing Verified Utility Information in Book 2; or

(b)	with respect to the “Quality Level B” Utility information provided by Mn/DOT (as indicated therein), the Utility’s actual location is within 2 feet of the indicated horizontal location at the “xy” coordinates in the Certified SUE Plans or Test Hole Matrices showing Verified Utility Information in Book 2 (with no limitation on vertical location).

(c) with respect to the “Quality Level D” Utility information Mn/DOT makes no guarantee to its “xyz” accuracy.  The Utility’s actual location shall be verified by the Contractor in the field.

6.2.1.3.2	Inconsistency Among Verification Data Sheets

If there is any inconsistency between any two or more Certified SUE Plans or Test Hole Matrices showing Verified Utility Information cited in Section 6.2.1.3.1, the most accurate of the indications will be used for purposes of Section 6.2.1.3.1.

6.2.1.3.3	Contractor Acknowledgment Regarding RID

Contractor acknowledges that statements in the RID as to the extent or nature of the work required to Relocate any Utility shall have no relevance to the determination of reasonable accuracy, and shall not be considered in calculating the amount of the Change Order, if any, to which either party is entitled pursuant to this Section 6.2.1.

#### 6.2.1.4	Partial Inaccuracy

If only a portion of an existing underground Utility identified in Book 2, Section 6 is not indicated at all in the Certified SUE Plans or Test Hole Matrices showing Verified Utility Information provided in Book 2 or is not indicated with “reasonable accuracy” therein, then a Change Order pursuant to Sections 6.2.1.1 or 6.2.1.2 shall be allowed only for the resulting increased or decreased costs (respectively) of the Utility Work incurred by Contractor with respect to that portion of such Utility (subject, in the case of any increase in the Contract Price, to the restrictions set forth in clauses (i), (ii) and (iii) of Section 6.2.1.1).

### 6.2.2	Change in Allocation of Responsibility

#### 6.2.2.1	Change in Allocation of Responsibility Increasing the Work

The scope of the Work with respect to Utilities may be increased pursuant to either of the following:

(a)	The scope of the Work may be increased pursuant to Book 2, Section 6 (i.e., Contractor to perform Utility Work otherwise assigned to the Utility Owner pursuant to Book 2, Section 6); or

(b)	Upon Approval or direction by Mn/DOT, design and/or construction of Utility Relocations not identified in Book 2, Section 6 may be added to the Work by Change Order.

Upon Contractor’s fulfillment of all applicable requirements of Section 13, and subject to the limitations contained therein, Contractor shall be entitled to an increase in the Contract Price to compensate Contractor for its additional costs directly attributable to any increase in the scope of the Work pursuant to this Section 6.2.2.1; provided, however, that if Mn/DOT determines in its sole discretion that Mn/DOT is entitled to reimbursement by the Utility Owner for the cost of such Relocation, then the amount of such resulting increase in the Contract Price shall instead be determined in the same manner as that provided in Section 6.2.4 for a Betterment, subject to the requirements of any applicable Utility Agreement. Contractor is responsible for scheduling all Utility Work so as to meet all applicable Completion Deadlines, without regard to whether such Utility Work is performed by Contractor or the affected Utility Owner; accordingly, Contractor shall not be entitled to an extension of any Completion Deadline on account of any increase in the scope of the Work pursuant to this Section 6.2.2.1 unless Mn/DOT determines that the Utility Work is beyond the Contractor’s reasonable control.

#### 6.2.2.2	 Change in Allocation of Responsibility Decreasing the Work

Any Utility Work initially included in the scope of the Work may be deleted from the scope of the Work pursuant to either of the following:

(a)	The scope of the Work may be reduced pursuant to Book 2, Section 6; or

(b)	Upon Approval or direction by Mn/DOT, design and/or construction of Utility Relocations identified in Book 2, Section 6 or Incidental Utility Work may be removed from the Work.

#### Mn/DOT shall be entitled to a reduction in the Contract Price to reflect any reduction in the scope of the Work pursuant to this Section 6.2.2.2. The amount of any such deductive Change Order shall be determined in accordance with Section 13. Any reduction in the scope of the Work pursuant to this Section 6.2.2.2 shall not be considered a Mn/DOT-Directed Change.

### 6.2.3	Added Utility Work

Upon Contractor’s fulfillment of all applicable requirements of Section 13, and subject to the limitations contained therein, Contractor shall be entitled to (a) an increase in the Contract Price to compensate Contractor for its additional costs and/or (b) an extension of the applicable Completion Deadlines as the result of any delay in the Critical Path directly attributable to any Utility Work added after the Proposal Due Date in accordance with Book 2, Section 6.

### 6.2.4	Betterments

Utility Betterments not already identified in Book 2, Section 6 to be included in the Contractor’s Work may be added to the Work pursuant to this Section 6.2.4 and Book 2, Section 6.4.6.

#### 6.2.4.1	Procedure

Any Utility Owner may request Mn/DOT to permit Contractor to perform work relating to Betterments as a part of the Work, at the Utility Owner’s expense. If Mn/DOT Approves any such request, Contractor will have the obligation to perform such work, with the right to receive additional payment and an extension of any affected Completion Deadline to the extent that any delay in the Critical Path is directly attributable to the Betterment. The price charged by Contractor for such Betterment shall either be a lump sum amount negotiated with the Utility Owner or determined on a time and materials cost basis as specified below. Any extension of any Completion Deadline(s) or Contract Price increase requested for any Betterment shall be subject to the requirements of Sections 6.2 and 13, as applicable.

6.2.4.1.1	Pricing

If a Utility Owner requests that Contractor design and/or construct a Betterment, Contractor shall use its best efforts to negotiate a lump sum price or unit prices for such work with the Utility Owner, in good faith. If Contractor and the Utility Owner are unable to agree on a lump sum price or unit prices, then Mn/DOT will direct Contractor to perform such work with compensation determined in accordance with the agreements entered into with the Utility Owner, provided that the conditions set forth in Section 6.2.4.1.3 are satisfied.

6.2.4.1.2	Change Order Increasing the Contract Price

A proposed Betterment will be added to the scope of the Work if Approved by Mn/DOT pursuant to Section 6.2.4.1.3. Mn/DOT agrees to issue a Change Order increasing the Contract Price on account of any Betterment added to the Work pursuant to this Section 6.2.4.1. The amount of any Change Order issued under this Section 6.2.4.1 shall be a direct pass-through of the lump sum price negotiated by Contractor and the Utility Owner (with no additional mark-ups) or, if no such price has been negotiated, an amount determined in accordance with the agreement entered into with the Utility Owner. Contractor shall not request or accept any payment directly from the Utility Owner for any Betterment added to the Work.

6.2.4.1.3	Mn/DOT’s Approval of Betterments

Mn/DOT will Approve the addition of a Betterment to the scope of the Work under this Section 6.2.4.1 only if: (a) the Utility Owner has agreed to the addition of such Betterment to the Work, (b) such Betterment is compatible with the Project, (c) the Utility Owner has agreed to reimburse Mn/DOT for all the costs thereof, (d) the Utility Owner has agreed as to the method (e.g., negotiated lump sum amount, unit prices or time and materials cost basis) of pricing such Work, and (e) it is feasible to separate the cost/pricing of the Betterment work from that for any related Utility Work being furnished or performed by Contractor. Contractor shall provide Mn/DOT with such information, analyses and certificates as may be requested by Mn/DOT in connection with its Approval.

6.2.4.1.4	Change Order Reducing the Contract Price

If any Betterment has been added to the Work and the Contract Price has been increased accordingly by Change Order, but subsequently for any reason the Betterment is deleted from the Work, or the scope of Contractor’s Work with regard to such Betterment is materially reduced, then Mn/DOT shall be entitled to issue a Change Order reducing the Contract Price to reflect the value of any reduction in the costs of the Work that is directly attributable to such deletion or reduction. Such Change Order shall be equal to the lump sum amount added to the Contract Price pursuant to Section 6.2.4.1.2, if applicable and if the entire Betterment has been deleted from the Work; otherwise, the amount of such Change Order shall be determined in accordance with Section 13.

6.2.4.1.5	Betterment Not Considered Mn/DOT-Directed Change

Any change in the scope of the Work pursuant to this Section 6.2.4 shall not be considered a Mn/DOT-Directed Change.

### 6.2.5	Utility Delays

Contractor shall give written notice to Mn/DOT of any circumstance which may lead to a claim under this Section 6.2.5 within 10 Days after Contractor’s becoming aware that such circumstance has occurred or is likely to occur.

#### 6.2.5.1	Allocation of Risk

The Contractor shall bear the risk of schedule impacts associated with the first four Days of Utility Delays per Utility Owner for the Project.  Subject to the limitations and conditions set forth herein, if aggregate Utility Delays caused by a particular Utility Owner exceed four Days, then any Completion Deadline(s) affected thereby shall be extended for one Day for every Day of Utility Delay caused by such Utility Owner in excess of the initial aggregate of four Days of Utility Delay caused by such Utility Owner so long as the Utility Delay impacts the Project’s Critical Path.   The Contractor will receive no extensions to the Completion Deadline(s) if the Project’s Critical Path is not impacted.

Failure of the parties to reach agreement regarding Contractor’s entitlement to an extension due to Utility Delays shall be a Dispute to be resolved in accordance with Section 19.  Contractor shall not be entitled to any extension of any Completion Deadline on account of any Utility Delay except as provided in this Section 6.2.5.1.

#### 6.2.5.2	Conditions to Extensions for Utility Delays

With respect to each Utility Delay claimed by Contractor, Contractor shall not be entitled to any extension of any Completion Deadline(s) pursuant to Section 6.2.5.1, and such Utility Delay shall not be counted toward the four-Day cap on Contractor’s risk per Utility Owner set forth in Section 6.2.5.1, unless all of the following conditions are satisfied:

(a)	Contractor has provided evidence reasonably satisfactory to Mn/DOT that (i) Contractor has fulfilled its obligation under the applicable Utility Agreement(s) to coordinate with the Utility Owner to prevent or reduce such delays, and (ii) Contractor has otherwise made diligent efforts to obtain the timely cooperation of the Utility Owner but has been unable to obtain such timely cooperation;

(b)	If Contractor is responsible for the Relocation, Contractor has provided a reasonable Relocation plan to the Utility Owner and Contractor has obtained, or is in a position to timely obtain, all applicable approvals, authorizations, certifications, consents, exemptions, filings, leases, licenses, permits, registrations, options and/or rulings required by or with any Governmental Person in order to design and construct such Relocation; and

(c)	No circumstances exist which have delayed or are delaying the affected Relocation, other than those which fit within the definition of a Utility Delay.

#### 6.2.5.3	Concurrent Delays

To the extent one or more Utility Delays is or are concurrent with another delay to the Critical Path which is Contractor’s responsibility hereunder but which is not a Utility Delay, then such Utility Delay(s) shall not be considered in calculating any four-Day cap on Contractor’s risk pursuant to Section 6.2.5.1. Furthermore, to the extent two or more Utility Delays occur concurrently with each other (whether caused by the same Utility Owner or by different Utility Owners), then only one of such Utility Delays shall be considered in calculating a four-Day cap on Contractor’s risk pursuant to Section 6.2.5.1 (in selecting between two or more Utility Owners for such purpose, the Utility Delay caused by the Utility Owner with the least amount of accrued Utility Delay shall be selected and applied to the four-Day cap on Contractor’s risk for such Utility Owner).

### 6.2.6	Certain Obligations of Contractor; Utility-Related Right of Way Costs

#### 6.2.6.1	Multiple Relocations of the Same Utility

Contractor shall endeavor to avoid multiple Relocations of the same Utility, whether by the Utility Owner or by Contractor (pursuant to Section 6.2.2.1). Accordingly, after a Utility has been Relocated once in order to accommodate the Project, Contractor shall be responsible for all costs incurred by either Contractor or the Utility Owner in order to subsequently Relocate such Utility to accommodate the Project. If the Utility Owner performs such subsequent Relocation at Mn/DOT’s expense, then Contractor shall reimburse Mn/DOT for all amounts paid by Mn/DOT to such Utility Owner in reimbursement for such subsequent Relocation. If Contractor performs such subsequent Relocation, then Contractor shall not receive any extension of any Completion Deadline or increase in the Contract Price on account of the performance of such subsequent Relocation.

#### 6.2.6.2	Minimizing Mn/DOT’s Reimbursement Obligation

In designing and constructing the Project, Contractor shall take all reasonable steps to minimize costs to the Utility Owners which will be subject to reimbursement by Mn/DOT, to the extent practicable and otherwise consistent with other requirements of the Contract Documents.

#### 6.2.6.3	Utility-Related Right of Way Costs

6.2.6.3.1	Mn/DOT’s Responsibility

With respect to Utility Easements other than those described in Section 6.2.6.3.2, Mn/DOT shall be responsible for any compensation required to be paid to Utility Owners for relinquishing their Utility Easements.

6.2.6.3.2	Contractor’s Responsibility

With respect to Utility Easements resulting from a change in Basic Configuration, Contractor shall be responsible for, and shall reimburse Mn/DOT within 10 Days after receiving an invoice therefor, any compensation which Mn/DOT may be obligated to pay to the Utility Owners for relinquishing such Utility Easements.

### 6.2.7	Additional Restrictions on Change Orders

In addition to all of the other requirements and limitations contained in this Section 6.2 and in Section 13, the entitlement of Contractor to any Change Order under this Section 6.2 shall be subject to the restrictions and limitations set forth in this Section 6.2.7.

#### 6.2.7.1	Burden of Proof

Contractor shall provide adequate support, by documentation acceptable to Mn/DOT, to prove that the amount of any additional costs and/or time incurred by Contractor are both necessary and reasonable. For Relocations, Contractor shall also bear the burden of proving that the Relocation cannot reasonably be avoided.

#### 6.2.7.2	Incremental Costs Only

Any Change Order increasing the Contract Price pursuant to this Section 6.2 shall include only the incremental costs arising from the circumstances giving rise to such Change Order.

#### 6.2.7.3	Coordination Costs

Contractor shall not be entitled to an increase in the Contract Price for any costs of coordinating with Utility Owners or for assisting Mn/DOT in coordinating with Utility Owners.

#### 6.2.7.4	Voluntary Action by Contractor

If Contractor elects to make payments to Utility Owners or to undertake any other efforts which are not required by the terms of the Contract Documents, Contractor shall not be entitled to a Change Order in connection therewith. Contractor shall promptly notify Mn/DOT of the terms of any such arrangements.

## 6.3	Environmental Compliance

In performance of the Work, Contractor shall comply with all requirements of all applicable Environmental Laws and Governmental Approvals issued thereunder, whether obtained by Mn/DOT or Contractor. Contractor acknowledges and agrees that it will be responsible for all fines and penalties that may be assessed in connection with any failure to comply with such requirements.

### 6.3.1	Mitigation Requirements

Contractor shall perform all environmental mitigation measures (which term shall be deemed to include all requirements of the Environmental Approvals and similar Governmental Approvals, regardless of whether such requirements would be considered to fall within a strict definition of the term) for the Project. The Contract Price includes compensation for Contractor’s performance of all such mitigation measures and for performance of all mitigation measures arising from New Environmental Approvals which Section 6.3.2 designates as Contractor’s responsibility as well as the cost of all activities to be performed by Contractor as described in Book 2, Section 4.

### 6.3.2	New Environmental Approvals

#### 6.3.2.1	Approvals To Be Obtained by Mn/DOT

Mn/DOT shall be responsible for obtaining any New Environmental Approvals necessitated by a Mn/DOT-Directed Change, Mn/DOT-Caused Delay, change in a Governmental Rule under Section 13.3.1.2(d)(v), or Force Majeure event. Contractor shall provide support services to Mn/DOT with respect to obtaining any such New Environmental Approval. Any Change Order covering a Mn/DOT-Directed Change, Mn/DOT-Caused Delay, or Force Majeure event may include compensation to Contractor for any changes in the Work (including performance of additional mitigation measures but excluding performance of such support services) resulting from such New Environmental Approvals, as well as any time extension necessitated by the Mn/DOT-Directed Change, or Force Majeure event, subject to the conditions and limitations contained in Section 13.

#### 6.3.2.2	Approvals To Be Obtained by Contractor

If a New Environmental Approval becomes necessary for any reason other than those specified in Section 6.3.2.1, Contractor shall be fully responsible for obtaining the New Environmental Approval and any other Environmental Approvals that may be necessary, and for all requirements resulting there from, as well as for any litigation arising in connection therewith. Mn/DOT will reasonably assist Contractor in obtaining any New Environmental Approvals. If the New Environmental Approval is associated with a Contractor Initiated Change Proposal, the Contractor shall be responsible for obtaining the approval and the costs of obtaining and complying with the terms of the New Environmental Approval shall be considered in determining the Contract Price adjustment under Section 13.

# 7	EQUAL EMPLOYMENT OPPORTUNITY; SUBCONTRACTS; LABOR

## 7.1	Equal Employment Opportunity

### 7.1.1	Equal Employment Opportunity Policy

Contractor shall comply with the Equal Employment Opportunity (EEO) requirements set forth in Exhibits D and F.

### 7.1.2	Inclusion in Subcontracts

Contractor shall include Exhibits D and F in every Subcontract over $10,000 (including purchase orders), and shall require that they be included in all Subcontracts over $10,000 at lower tiers, so that such provisions will be binding upon each Subcontractor.

## 7.2	Disadvantaged Business Enterprises {Use only on projects with DBE goals}

### 7.2.1	Disadvantaged Business Enterprises Policy

Contractor shall comply with the requirements set forth in Exhibit E.

### 7.2.2	Inclusion in Subcontracts

Contractor shall include Exhibit E in every Subcontract (including purchase orders), and shall require that they be included in all Subcontracts at lower tiers, so that such provisions will be binding upon each Subcontractor.

## 7.3	Subcontracting Requirements

Contractor shall comply with all applicable requirements of the Contract Documents relating to Subcontracts (including Exhibits D, E, F and I), and shall ensure that its Subcontractors (at all tiers) comply with all applicable requirements of the Contract Documents relating to subcontracting (including Exhibits D, E, F and I.).

### 7.3.1	Major Participants

Contractor shall not add, delete, or change the role of, any Major Participant as set forth in its Proposal without the prior Approval of Mn/DOT.

### 7.3.2	Assignment of Subcontract Rights

Each Subcontract shall provide that, pursuant to terms in form and substance satisfactory to Mn/DOT, (a) Mn/DOT is a third party beneficiary of the Subcontract and shall have the right to enforce all terms of the Subcontract for its own benefit, (b) all guarantees and warranties, express and implied, shall inure to the benefit of Mn/DOT, its successors and assigns, as well as Contractor, and (c) the rights of Contractor under such instrument are assigned to Mn/DOT contingent upon delivery of written request from Mn/DOT following default by Contractor or termination or expiration of the Contract, allowing Mn/DOT to assume the benefit of Contractor’s rights with liability only for those remaining obligations of Contractor accruing after the date of assumption by Mn/DOT, but shall not release or relieve Contractor from its obligations or liabilities under the assigned Subcontract.

### 7.3.3	Subcontract Terms

Each Subcontract shall include terms and conditions sufficient to ensure compliance by the Subcontractor with all applicable requirements of the Contract Documents, and shall include provisions addressing the following requirements as well as any other terms that are specifically required by the Contract Documents to be included therein:

(a)	Each Subcontract involving fuel in material quantities shall specify how such Subcontractor’s share of the price adjustment under Section 11.1.4 will be determined.

(b)	Each Subcontract shall include terms that are substantially similar to those terms required by Sections 5.1, 5.2, 5.3, 5.4, 7.1, 7.2, 7.3.1, 7.4.3, 10.1, 13.7, 14, 15, 19, 20.3 and 23.6 and Exhibits D , E, and F, specifically including an agreement by the Subcontractor to be joined in any dispute resolution proceeding pursuant to Section 19 if such joinder is reasonably necessary to resolve the dispute; and each Subcontract other than Subcontracts with Suppliers shall include terms that are substantially similar to those contained in Sections 2.2(e), 2.2(f), 2.2(h), 2.3.1, 21.3, 22.2, 22.3 and 22.4 and Standard Specification 1505.

### 7.3.4	Subcontract Data

Contractor shall notify Mn/DOT, in writing, of the name and address of, licenses held by, and any insurance documents required pursuant to Section 9 of, each Subcontractor (excluding Suppliers), as soon as the potential Subcontractor has been identified by Contractor, but in no event less than 14 Days prior to the scheduled initiation of Work by such proposed Subcontractor.

Contractor shall provide requests to sublet any portion of the Contract to Mn/DOT on a form provided by Mn/DOT, at least 10 Days in advance of the date on which the Subcontractor intends to start work.  Contractor shall allow Mn/DOT access to all Subcontracts and records regarding Subcontracts within 7 Days following receipt of Mn/DOT’s request.  All Subcontracts shall be in writing and shall include design costs (if applicable).

### 7.3.5	Responsibility for Work by Subcontractors

Notwithstanding any Subcontract or agreement with any Subcontractor, Contractor shall be fully responsible for all of the Work. Mn/DOT shall not be bound by any Subcontract, and no Subcontract shall include a provision purporting to bind Mn/DOT. Each Subcontract shall include the following provision:

Nothing contained herein shall be deemed to create any privity of contract between the State of Minnesota through its Commissioner of Transportation (Mn/DOT) and Subcontractor, nor does it create any duties, obligations or liabilities on the part of Mn/DOT to Subcontractor except those allowed under Minnesota law. In the event of any claim or dispute arising under this Subcontract and/or Contractor’s contract with Mn/DOT, Subcontractor shall look only to Contractor for any payment, redress, relief or other satisfaction. Subcontractor hereby waives any claim or cause of action against Mn/DOT arising out of this Subcontract or otherwise arising in connection with Subcontractor’s work.

### 7.3.6	Subcontract Work

Contractor shall coordinate the Work performed by Subcontractors.

### 7.3.7	Debarred Subcontractors

Contractor shall not enter into any Subcontracts with any Person then debarred or suspended from submitting bids by any agency of the State.  See Exhibit I.

## 7.4	Key Personnel; Character of Workers

### 7.4.1	Key Personnel

Exhibit G hereto identifies certain key positions for the Project. Mn/DOT shall have the right to review the qualifications and character of each individual to be assigned to a key position (including personnel employed by Subcontractors) and to Approve or disapprove use of such key person in such key position prior to the commencement of any Work by such individual or during the prosecution of the Work. Contractor shall notify Mn/DOT in writing of any proposed changes in any Key Personnel, and shall not change any Key Personnel without the prior written Approval of Mn/DOT.

### 7.4.2	Representations, Warranties and Covenants

Contractor acknowledges and agrees that the award of the Contract by Mn/DOT to Contractor was based, in large part, on the qualifications and experience of the personnel listed in the Proposal and Contractor’s commitment that such individuals would be available to undertake and perform the Work. Contractor represents, warrants and covenants that such individuals are available for and will fulfill the roles identified for them in the Proposal in connection with the Work. Unless otherwise agreed to by Mn/DOT in writing, individuals filling key personnel roles shall devote a sufficient amount of their time for the applicable role with respect to the prosecution and performance of the Work and Contractor shall document such commitment to Mn/DOT’s satisfaction upon Mn/DOT’s request.

### 7.4.3	Employee Performance Requirements

All individuals performing the Work shall have the skill and experience and any licenses or certifications required to perform the Work assigned to them. If Mn/DOT determines in its sole discretion that any Person employed by Contractor or by any Subcontractor is not performing the Work properly and skillfully, or who is intemperate or disorderly, then, at the written request of Mn/DOT, Contractor or such Subcontractor shall remove such Person and such Person shall not be re-employed on the Project without the prior Approval of Mn/DOT in its sole discretion. If Contractor or the Subcontractor fails to remove such Person(s) or fails to furnish skilled and experienced personnel for the proper performance of the Work, then Mn/DOT may, in its sole discretion, suspend the affected portion of the Work by delivery of written notice of such suspension to Contractor. Such suspension shall in no way relieve Contractor of any obligation contained in the Contract Documents or entitle Contractor to a Change Order or time extension. Once compliance is achieved, Contractor shall be entitled to and shall promptly resume the Work.

Surveys performed to progress the construction activities on the project are covered by the contract labor requirements.

# 8	SURETY BONDS

Contractor shall provide to Mn/DOT and maintain at all times during the term of the Contract security for performance of the Work as described below (or other assurance satisfactory to Mn/DOT in its sole discretion). Each bond required hereunder shall be provided by a Surety licensed as surety and qualified to do business in the State. The Surety shall have a “Best’s Rating” of A- or better and Financial Size Category of VIII or better by A.M. Best Co.

## 8.1	Payment and Performance Bond

Contractor has provided to Mn/DOT and shall maintain in full force and effect the Payment and Performance Bond in the amount of $      [100% of the Contract Price] under Part A and the amount of $      [100% of the Contract Price] under Part B.  The Contractor shall use the Payment and Performance Bond form provided by Mn/DOT.

## 8.2	Warranty Bond

Contractor shall provide a warranty bond which shall guarantee performance of all Warranty obligations of Contractor under the Contract Documents.  The warranty bond (a) shall be in an amount equal to four percent of the Contract Price period ending two years following Substantial Completion and shall be in amount equal to two percent of the Contract Price during the third year following Substantial Completion.  The Contractor shall use the warranty bond form provided by Mn/DOT.

{Or}

Contractor shall provide a warranty bond which shall guarantee performance of all Warranty obligations of Contractor under the Contract Documents.  The warranty bond (a) shall be in an amount equal to       ending two years following Substantial Completion and shall be in amount equal to      during the third year following Substantial Completion.  The Contractor shall use the warranty bond form provided by Mn/DOT.

## 8.3	Utility Work

The Utility Work furnished or performed by Contractor hereunder will automatically be covered by the Payment and Performance Bond and any warranty bond or other security to be provided by Contractor pursuant to Section 8.2. At their request, Utility Owners whose Utilities are being Relocated by Contractor shall be added as additional obligees to the Payment and Performance Bond (as their interests may appear), as well as to such replacement bond or other security (as their interests may appear), to the limited extent of the amount of the Utility Work required on behalf of the Utility Owner.  The Payment and Performance Bond shall be provided in their full amount, however, on behalf of Mn/DOT, with no riders that reduce Mn/DOT’s potential of recovery based on the Utility Owner’s limited obligee amounts.  Alternatively, Contractor may provide separate bonds satisfactory to the Utility Owners. Contractor shall provide all information necessary for such coverage to the surety(ies) providing such bonds. All cost estimates required to be provided under the Contract Documents with respect to Utility Work furnished or performed by Contractor shall include the cost of bond premiums.

## 8.4	Guaranty

Contractor has provided to Mn/DOT and shall maintain in full force and effect the Guaranty (if required).  Each Guarantor (if any) shall have a credit rating for senior unsecured debt of at least Baa1 by Moody’s Investors Services or BBB+ by Standard & Poors Corporation.

## 8.5	No Relief of Liability

Notwithstanding any other requirements of the Contract Documents, performance by a Surety or any Guarantor of any of the obligations of Contractor shall not relieve Contractor of any of its obligations hereunder.

# 9	INSURANCE {Discuss requirements with Dept. of Administration for each project as dollar amounts AND COVERAGE will change}

## 9.1	General Insurance Requirements

### 9.1.1	Evidence of Insurance

Contractor shall provide evidence of insurance as proof of compliance for all insurance requirements contained in this Section 9. The evidence of insurance shall provide for 30 Days written notice of cancellation. A Certificate of Insurance indicating certain specified amendments and attachments shall be acceptable, but Mn/DOT reserves the right to request a complete certified copy of the policy, at Mn/DOT’s sole discretion. No Work shall start until compliance with insurance requirements has been approved by Mn/DOT.

### 9.1.2	A.M. Best Rating

All insurance companies providing policies obtained to satisfy the insurance requirements must have an A.M. Best rating of A- X or better, and be authorized to do business in the State of Minnesota.

### 9.1.3	Full Force and Effect

All policies will remain in full force and effect throughout the term of the Contract and, when there is an extended reporting period, shall remain in effect for the time stipulated.

### 9.1.4	No Recourse

There shall be no recourse against the State for payment of premiums or other amounts with respect to the insurance provided by Contractor, or for deductibles under these policies.

### 9.1.5	Indemnification

The insurance coverage provided hereunder shall support, but is not intended to limit, Contractor’s indemnification obligations under Section 18.

### 9.1.6	Commercial Unavailability of Required Coverages

If, through no fault of Contractor, any of the coverages required in this Section 9 (or any of the required terms of such coverages, including policy limits) become unavailable or are available only with commercially unreasonable premiums, Mn/DOT will consider in good faith alternative insurance packages and programs proposed by Contractor, with the goal of reaching agreement on a package providing coverage equivalent to that specified herein. Contractor must demonstrate to Mn/DOT’s reasonable satisfaction that it has used diligent efforts in the global insurance markets to place the required insurance coverages, and shall advise Mn/DOT of the specific results of those efforts. Contractor shall not be entitled to any increase in the Contract Price for increased costs resulting from the unavailability of coverage and the requirement to provide acceptable alternatives. Mn/DOT shall be entitled to a reduction in the Contract Price if it agrees to accept alternative policies providing less than equivalent coverage, with the amount to be determined by extrapolation using the insurance quotes included in the EPD (or based on other evidence of insurance premiums as of the Proposal Due Date if the EPD does not provide adequate information).

### 9.1.7	Primary and Non-Contributory

For claims covered by the insurance specified herein, said insurance coverage shall be primary insurance with respect to the insureds, additional insureds, and their respective members, directors, officers, employees, agents and consultants, and shall specify that coverage continues notwithstanding the fact that Contractor has left the Site.  Any insurance or self-insurance beyond that specified in this Contract that is maintained by an insured, additional insured, or their members, directors, officers, employees, agents and consultants shall be excess of such insurance and shall not contribute with it.

### 9.1.8	 Governmental Immunity

Insurance companies providing policies as required hereunder shall waive their rights to assert the immunity of the State of Minnesota as defense to any claims arising out of this Contract.

## 9.2	Contractor-Provided Insurance

Contractor shall procure, at its own expense, insurance acceptable to Mn/DOT, as described herein, and shall maintain such insurance, as specified herein, in accordance with the requirements stated in Section 9.1, or as otherwise Approved by Mn/DOT at its sole discretion.

### 9.2.1	Worker’s Compensation and Employer’s Liability Coverage

Contractor shall provide Worker’s Compensation coverage that is in compliance with all Governmental Rules (including Minn. Stat. Ch. 176) and Employer’s Liability with minimum limits of $     by disease each person, $      by disease aggregate, and $      each person by accident. The policy must be endorsed to include:

(a)	Coverage C:  Other states’ coverage, except monopolistic states.

(b)	Voluntary Compensation Endorsement: (i) Applies to all volunteers and employees not subject to applicable worker’s compensation law at the discretion of Insureds; (ii) Designated law in state of hire. Delete exclusion C.2 (Intentional Injury), unless such deletion is commercially unavailable. Limit $1 million.

(c)	Alternative Employer Endorsement.

(d)	Federal Employers Liability Act Coverage (WC 00 01 01A) (if any basis).

(e)	USL&H, Maritime, Jones Act and Foreign Coverage.

(f)   A waiver of subrogation in favor of the State of Minnesota.

### 9.2.2	Commercial General Liability Insurance

Contractor shall provide Commercial General Liability broad form coverage for Bodily Injury, Property Damage, Personal Injury, Advertising Liability and Blanket Contractual Liability written on an occurrence form that shall be no less comprehensive or more restrictive than the coverage provided by Insurance Services office (ISO) form CG 00 01 12 04 or its equivalent.

(a)	Limits of liability. General liability:

$      – each occurrence

$      – general aggregate (annually)

$      – personal and advertising injury

$      – blanket contractual liability

$      – products/completed operations liability

$      – fire hazard liability (any one fire)

$      – medical expense (any one person per occurrence)

The aggregate limits shall apply separately to the Project (Endorsement CG-25-03).

(b)	Such insurance shall include, by its terms or appropriate endorsements, Bodily Injury, Property Damage, Fire Hazard Liability, Personal and Advertising Injury, Blanket Contractual Liability, Independent Contractors, Premises and Operations and Products and Completed Operations.  Products and completed operations coverage shall be maintained for a minimum of ten years from Final Acceptance.

1.	Shall include blanket coverage of Explosion, Collapse, and Underground (XCU) hazards.

2.	Shall contain endorsement(s) deleting any restrictions for work performed within 50 feet of railroad Right of Way.

3.	The policy shall be on an Occurrence Coverage basis.  The Contractor shall provide Certificates of Insurance showing that it maintains such occurrence Coverage for a minimum of 10 years from Final Acceptance.

4.	The following shall be additional insured(s) by endorsement, ISO forms CG 20 10 07 04  and CG 20 37 07 04 or their equivalent with respect to liability arising out of acts or omissions of any Contractor-Related Entity, whether on or off of the Site: State of Minnesota.

5.   Shall include a waiver of subrogation in favor of the State of Minnesota.

6.	Shall include a Pollution exclusion with standard exception as per Insurance Service Office (ISO) Commercial General Liability Coverage From – CG 00 01 12 04 or equivalent.

### 9.2.3	Automobile Liability Insurance

Contractor shall provide comprehensive automobile liability insurance covering the ownership, maintenance and use of all owned/leased, non-owned and hired vehicles used in the performance of Work, both on and off the Site, including loading and unloading.

The following limits of liability and other requirements shall apply:

(a)	$      combined single limit for bodily injury and property damage liability.

(b)	Coverage shall be provided on ISO form number CA.00 01 or equivalent.

(c)	The policy will include uninsured and underinsured, and Minnesota No-Fault, in compliance with Minnesota law.

(d)	   The policy shall be endorsed to include Motor Carrier Act endorsement – Hazardous Materials Cleanup (MCS-90) and Pollution Liability – Broadened endorsement CA 9948 09 02 or equivalent.

(e)   Shall include a waiver of subrogation in favor of the State of Minnesota.

### 9.2.4	Excess (Umbrella) Liability Insurance

An Umbrella or Excess Liability insurance policy may be used to supplement the Contractor's policy limits to satisfy the full policy limits required by the Contract.

### 9.2.5	Contractor’s Pollution Liability Coverage

(a)	Contractor shall provide pollution liability coverage for the Project.  Such insurance shall include bodily injury, property damage, environmental damage, loss of use of property, governmental ordered cleanup cost, completed operations and defense including costs, charges and expenses incurred in the investigation, adjustment or defense of claims for damages. Coverage shall also be provided for transport of waste and non-owned disposal sites, if Contractor is disposing of waste. Contractual liability shall be included.

(b)	The following limits and conditions shall apply:

1.	The limit of liability shall be $      per occurrence and $      annual aggregate.

2.	The State of Minnesota shall be named as an additional insured.

3.	A “claims made” form will be acceptable. The retroactive or prior acts date of such coverage shall not be after the effective date of this Contract and Contractor shall maintain such insurance for a period of at least 10 years, following Substantial Completion.  If Contractor discontinues such coverage, then extended reporting period coverage must be purchased to fulfill this requirement.

4.   Shall include a waiver of subrogation in favor of the State of Minnesota.

### 9.2.6	Professional Liability Insurance

Contractor, or a Major Participant providing professional services, shall provide Professional Liability Coverage:

(a)	Limits of Liability shall be $      per claim and an annual aggregate of $     .

(b)	The policy shall be renewed for five years after the Final Acceptance Date

(c)	The policy shall provide coverage for any negligent act, error or omission arising out of design or engineering activities with respect to the Project.

(d)   Prior acts or retroactive effect date of coverage shall not be subsequent to the effective date of the Contract.

### 9.2.7	Builder’s Risk

The Contractor shall purchase and maintain “All Risk” or equivalent Builder’s Risk policy insuring the interest of Mn/DOT, the Contractor, and any tier of Subcontractor. Coverage on an “All Risk” or equivalent basis shall include the perils of flood, earthquake, and pollution cleanup expense. The limit of insurance required shall represent the total completed construction value of the Project, including potential redesign. Any deductible shall be the sole responsibility of the Contractor and shall not exceed $      for flood and earthquakes and shall not exceed $      for all other covered risks without the written approval of Mn/DOT.  The Builder’s Risk Policy may include minimum sub-limits of $      for perils of flood and $      for perils of earthquakes.

(a)	The Builder’s Risk policy shall cover all materials, supplies, and equipment that are intended for construction and specific installation in the Project while such materials, supplies, and equipment are located at the Project Site, in transit, and while temporarily located away from the Project Site for the purpose of repair, adjustment, or storage at the risk of one of the insured parties.

(b)	Any property not covered by the Builder’s Risk policy, such as the Contractor’s or any tier of Subcontractor’s licensed motor vehicles, or personal property, including job trailers, machinery, tools, equipment, and property of a similar nature not destined to become a part of the Project, shall be the responsibility of the Contractor or Subcontractor at any tier, and such person or organization may self insure or provide other insurance at its option for the same.

(c)	Waiver of Liability: Absent Mn/DOT’s sole negligence or breach of specific contractual duty specifically and logically related to the damage or loss, Mn/DOT will not be responsible for loss or damage to property of any kind owned, borrowed, rented, or leased by the Contractor, Subcontractors and/or the Contractor’s/Subcontractors’ employees, servants, or agents.

(d)	All losses and claims shall be immediately reported to the Contractor, Mn/DOT, and applicable insurance carrier, under loss notice procedures as directed by the Contractor.

(e)	Any loss insured under Section 9.2.9 is to be adjusted with the Contractor and made payable to the Contractor as trustee for all insured parties, as their interests may appear, subject to the requirements of any applicable mortgage clause. The Contractor shall pay Mn/DOT a just share of any insurance moneys received, and by appropriate agreement, written where legally required for validity, shall require the Contractor to make just share payments to the Subcontractors in similar manner.

(f)	Partial occupancy or use shall not commence until the insurance company or companies providing property insurance have consented to such partial occupancy or use by endorsement or otherwise.

(g)	Boiler and Machinery Insurance:  The Contractor shall purchase and maintain boiler and machinery insurance, if applicable, which shall specifically cover such insured objects during installation and until Final Acceptance by Mn/DOT; this insurance shall include interests of Mn/DOT, Contractor and Subcontractors in the Work, and Mn/DOT and Contractor shall be named insureds.

(h)	Waivers of Subrogation:  Mn/DOT and Contractor waive all rights against each other and any of their Subcontractors of all tiers for damages caused by fire or other causes of loss to the extent covered by the property insurance obtained pursuant to the provisions of this Section 9.2.9 or other property insurance applicable to the Work, except such rights as they have to proceeds of such insurance held by Mn/DOT or Contractor as fiduciary.  The policies shall provide such waivers of subrogation by endorsement or otherwise.  A waiver of subrogation shall be effective as to a Person or entity even though that Person or entity would otherwise have a duty of indemnification, contractual or otherwise, did not pay the insurance premium directly or indirectly, and whether or not the Person or entity had an insurable interest in the property damage.

# 10	risk of loss

## 10.1	Site Security

Contractor shall provide appropriate security for the Site, including securing any buildings from entry, and shall take all reasonable precautions and provide protection to prevent damage, injury or loss to the Work and materials and equipment to be incorporated therein, as well as all other property at the Site, whether owned by Contractor, Mn/DOT, or any other Person. Contractor shall at all times keep the Site in a neat and clean condition, including performing litter removal, removal of graffiti and weed control.

## 10.2	Maintenance and Repair of Work and On-Site Property

### 10.2.1	Responsibility of Contractor

Contractor shall maintain, rebuild, repair, restore, or replace all Work (including Design Documents, Construction Documents, materials, equipment, supplies and maintenance equipment which are purchased for permanent installation in, or for use during construction of, the Project, regardless of whether Mn/DOT has title thereto under the Contract Documents) that is injured or damaged prior to the date of Acceptance of maintenance liability by Mn/DOT or third parties as specified in Section 10.2.3. All such work shall be at no additional cost to Mn/DOT except to the extent that Mn/DOT is responsible for such costs as provided in Section 13. Contractor shall also have full responsibility during such period for rebuilding, repairing and restoring all other property at the Site, whether owned by Contractor, Mn/DOT or any other Person. Additional requirements regarding maintenance of highways during construction are set forth in Book 2, Section 19.

For damage within the Site that Mn/DOT would typically seek compensation from the insurance company of the responsible party, Mn/DOT will subrogate its right to seek said financial reimbursement to the Contractor. Mn/DOT will provide copies of accident reports, when they exist, to the Contractor. Mn/DOT makes no guarantee that the Contractor will be able to obtain any financial reimbursement based on this subrogation of Mn/DOT’s rights.

### 10.2.2	Landscape Establishment

Notwithstanding anything to the contrary in Section 10.2, requirements regarding maintenance of trees, shrubs, vines and perennials furnished under the Contract Documents are set forth in Standard Specification 2571.

### 10.2.3	Relief from Liability for Maintenance

Effective as of the date on which Substantial Completion occurs, Mn/DOT shall be considered to have Accepted maintenance liability for all elements of the Project which are 100 percent complete as of such date and placed in service. All remaining elements of the Project shall be considered Accepted for maintenance purposes as of the date on which Final Acceptance occurs. Notwithstanding the foregoing, all elements of the Work which will be owned by Persons other than Mn/DOT (such as Utility facilities) will be considered accepted for purposes of maintenance responsibility only as of the date of acceptance of maintenance responsibilities by such Persons.

## 10.3	Damage to Off-Site Property

Contractor shall take all reasonable precautions and provide protection to prevent damage, injury, or loss to property adjacent to the Site or likely to be affected by the Work. Contractor shall restore damaged, injured or lost property caused by an act or omission of any Contractor-Related Entity to a condition similar or equal to that existing before the damage, injury or loss occurred.

## 10.4	Title

Contractor warrants that it owns, or will own, and has, or will have, good and marketable title to all materials, equipment, tools and supplies furnished, or to be furnished, by it and its Subcontractors that become part of the Project or are purchased for Mn/DOT for the operation, maintenance, or repair thereof, free and clear of all Liens. Title to all of such materials, equipment, tools and supplies which shall have been delivered to the Site shall pass to Mn/DOT, free and clear of all Liens, upon the sooner of (a) incorporation into the Project, or (b) payment by Mn/DOT to Contractor of invoiced amounts pertaining thereto. Notwithstanding any such passage of title, and subject to Section 10.1, Contractor shall retain sole care, custody and control of such materials, equipment, tools and supplies, and shall exercise due care with respect thereto as part of the Work until Final Acceptance or until Contractor is removed from the Project.

# 11	PAYMENT

## 11.1	Contract Price

### 11.1.1	Contract Price

As full compensation for the Work and all other obligations to be performed by Contractor under the Contract Documents, Mn/DOT shall pay to Contractor a lump sum amount of $     (such amount, as it may be adjusted from time to time to account for Change Orders, is referred to herein as the “Contract Price”). The Contract Price shall be increased or decreased only by a Change Order issued in accordance with Section 13, by a Contract amendment or as specifically provided elsewhere in the Contract Documents.

### 11.1.2	Items Included in Contract Price

Contractor acknowledges and agrees that, subject only to Contractor’s rights under Section 13, the Contract Price includes:

(a)	performance of each and every portion of the Work;

(b)	all designs, equipment, materials, labor, insurance and bond premiums, home office, jobsite and other overhead, profit and services relating to Contractor’s performance of its obligations under the Contract Documents (including all Work, Warranties, equipment, materials, labor and services provided by Subcontractors and intellectual property rights necessary to perform the Work);

(c)	the cost of obtaining all Governmental Approvals (except for approvals which are the responsibility of Mn/DOT, as specifically provided elsewhere in the Contract Documents);

(d)	all costs of compliance with and maintenance of the Governmental Approvals and compliance with Governmental Rules; and

(e)	payment of any taxes, duties, and permit and other fees and/or royalties imposed with respect to the Work and any equipment, materials, labor, or services included therein.

### 11.1.3	Delay in Issuance of NTP1

#### 11.1.3.1	Delays beyond 60 Days after Public Opening Date

If Mn/DOT has not issued NTP1 on or before 60 Days after the Public Opening Date due to no fault of Contractor, Contractor may seek to negotiate a Change Order including an extension in the time allowed to Mn/DOT for issuance of NTP1 and an increase in the Contract Price mutually acceptable to Contractor and Mn/DOT. If Contractor does not wish to seek a Change Order as provided above or Mn/DOT fails to issue a Change Order acceptable to Contractor, then Contractor’s sole remedy shall be to terminate the Contract by delivery of notice of termination to Mn/DOT, with the right to receive payment as specified in Section 15.

#### 11.1.3.2	Allocation of Price Increase

Any price increase under this Section 11.1.3 shall be amortized proportionally over all Work remaining to be performed, and shall be evidenced by a Change Order.

### 11.1.4	Fuel Cost Escalation

Price adjustments will be made as specified in DBS-1910. The “date of letting” as used in said provision shall mean the Public Opening Date.   To request additional payment, the Contractor shall submit a Request for Change Order to Mn/DOT in accordance with Section 13.  The request must include a breakdown of quantities and fuel cost adjustment calculations.

For fuel escalation credits, Mn/DOT will request a Mn/DOT initiated Change Order in accordance with Section 13.2.   Upon Mn/DOT request, the Contractor shall provide a breakdown of quantities and fuel cost credit calculations.

For earthwork items, 2106 items will be used as the basis for fuel escalation payments/credits.

## 11.2	Invoices and Payment

Requirements relating to invoicing are set forth in Section 2.2 of Book 2. Within 30 Days after receipt by Mn/DOT of each invoice, Mn/DOT shall pay Contractor the amount of the invoice Approved for payment less any amounts which Mn/DOT is entitled to withhold.

## 11.3	Limitations on Payment

In no event shall Mn/DOT have any obligation to pay Contractor any amount which would result in (a) payment for any activity in excess of the value of the activity times the completion percentage of such activity, or (b) aggregate payments hereunder in excess of the overall completion percentage for the Project times the Contract Price. Furthermore, Mn/DOT shall have the right to withhold payment up to $500,000 of the Contract Price until Final Acceptance is achieved.  The withholding will occur on the last $500,000 due to the Contractor and may be in addition to any other withholding, disincentives, liquidated damages or other monetary deductions allowed in the Contract.

### 11.3.1	Delay in Issuance of NTP1

Not used.

### 11.3.2	Payment Schedule

Not used. {Use if applicable}

Payments, including mobilization, but not including payments for Change Order Work not included in the Payment Schedule, are limited by a cumulative cap on payments as set forth in the Payment Schedule. In other words, at no time shall Contractor’s cumulative total progress payments (exclusive of payments for Change Order Work) exceed the cumulative total expenditure permitted by the Payment Schedule. Payment of any amounts included in an invoice which are in excess of the maximum aggregate amount payable under the Payment Schedule shall be deferred until such deferred amounts can be paid without aggregate payments exceeding the Payment Schedule. {Use if applicable}

### 11.3.3	NTP1 Payment Cap

Not used. {Use if applicable}

The amount of funds available to pay Contractor prior to issuance of NTP2 is limited to the amount of the NTP1 Payment Cap. Mn/DOT has no obligation to make any payment to Contractor in excess of this amount until such time (if any) as NTP2 is issued. If Contractor performs any Work in excess of the NTP1 Payment Cap, it does so at its own risk. {Use if applicable}

### 11.3.4	Unincorporated Materials (Materials on Hand)

Mn/DOT will not pay for materials associated with a progressed activity prior to their incorporation into the Project, except under the circumstances described in this Section 11.3.4.

#### 11.3.4.1	Delivery of Materials

Materials shall be delivered to the Site, or delivered to Contractor and promptly stored by Contractor in storage Approved by Mn/DOT. Materials that have not been delivered to or adjacent to the Site will be eligible for payment only if they were specifically manufactured or produced for the Project, and then only after being irrevocably assigned to Mn/DOT. As a condition to inclusion of such materials in any invoice, Contractor shall submit certified bills for such materials with its invoice. Payment will not be made when the invoice value of such materials, as determined by Mn/DOT, amounts to less than $2,000 or if materials are to be stored less than 30 Days.

#### 11.3.4.2	Title to Materials

All such materials so delivered shall become the property of Mn/DOT. Payment for stockpiled materials will not constitute final acceptance of such materials. At Mn/DOT’s request, Contractor at its own expense shall promptly execute, acknowledge and deliver to Mn/DOT actual bills of sale or other instruments in a form acceptable to Mn/DOT, conveying and assuring to Mn/DOT title to such materials included in any invoice, free and clear of all Liens. Contractor at its own expense shall conspicuously mark such materials as the property of Mn/DOT, shall not permit such materials to become commingled with non-Mn/DOT-owned property and shall take such other steps, if any, as Mn/DOT may require or regard as necessary to vest title to such materials in Mn/DOT free and clear of Liens. The required invoice, billing, title, or assignment documents, furnished by Contractor, shall contain complete material description and identification data.

#### 11.3.4.3	Deductions

The amount shown in an invoice for material which is subsequently lost, damaged or unsatisfactory will be deducted from succeeding invoices until the material is repaired or replaced (at Contractor’s expense). In case any Supplier claims against Contractor remain (for materials so paid for) unsatisfied for more than 30 Days following issuance of payment to Contractor, the applicable payment may be canceled on the next invoice.

#### 11.3.4.4	Not to Exceed Amount

Payment for material furnished and delivered as indicated in this Section 11.3.4 will not exceed the amount paid by Contractor as evidenced by a bill of sale supported by paid invoice, or 75 percent of the in-place price, whichever is less.

### 11.3.5	Materials Ineligible for Payment

#### 11.3.5.1	Equipment

Mn/DOT will not pay directly for equipment costs. Payment for equipment, whether new, used or rented, and to the extent not included in the mobilization payments under Book 2, Section 2.2, will be allocated to and paid for as part of the activities with which the equipment is associated, in a manner which is consistent with the requirements of Section 13.7.3.

#### 11.3.5.2	Perishable Materials

Mn/DOT will make no partial payment on living or perishable materials until incorporated as specified in the Contract.

#### 11.3.5.3	Contractor’s Election

Mn/DOT will make no payment for materials brought onto the Site at Contractor’s election that may be incorporated into the Project such as fuels, supplies, metal decking forms, ties or supplies used to improve efficiency of operations.

### 11.3.6	Nonconforming Work

Mn/DOT will make no payment for Nonconforming Work, except as provided under Section 5.7.

## 11.4	Not Used

## 11.5	Deductions

Mn/DOT may deduct from any amounts otherwise owing to Contractor, including each progress payment and the final payment, the following:

(a)	any anticipated or accrued losses, liability, Liquidated Damages or other damages for which Contractor is responsible hereunder;

(b)	the estimated cost of remedying any Nonconforming Work or otherwise remedying any breach of contract by Contractor;

(c)	any amounts that Mn/DOT deems advisable, in its sole discretion, to cover any existing or threatened claims, Liens and stop notices by Subcontractors, Suppliers, laborers, Utility Owners or other third parties relating to the Project;

(d)	any sums expended by Mn/DOT in performing any of Contractor’s obligations under the Contract which Contractor has failed to perform; and

(e)	any other sums which Mn/DOT is entitled to recover from Contractor under the terms of the Contract.

Mn/DOT’s failure to deduct from a progress payment any amount which Mn/DOT is entitled to recover from Contractor under the Contract shall not constitute a waiver of Mn/DOT’s right to such amounts.  Contractor shall be entitled to any excess amounts being withheld by Mn/DOT at the time of Contractor’s final payment.

## 11.6	Final Payment

Final payment will be made in accordance with this Section 11.6.

### 11.6.1	Application for Final Payment

On or about the date of delivery of its Affidavit of Final Completion, Contractor shall prepare and submit a proposed Application for Final Payment to Mn/DOT showing the proposed total amount due Contractor. In addition to meeting all other requirements for invoices hereunder, the Application for Final Payment shall list all outstanding or pending Change Notices and all existing or threatened claims, Liens and stop notices by Subcontractors, laborers, Utility Owners or other third parties relating to the Project, including any notices filed or to be filed with the Affidavit of Final Completion, stating the amount at issue associated with each such notice. The Application for Final Payment shall be accompanied by (a) complete and legally effective releases or waivers of Liens and stop notices satisfactory to Mn/DOT, from all Persons legally eligible to file Liens and stop notices in connection with the Work, (b) consent of Surety(ies) to final payment, (c) the release and affidavit required by Section 11.6.2, (d) Minnesota Department of Revenue Form IC-134 and (e) such other documentation as Mn/DOT may reasonably require. Prior applications and payments shall be subject to correction in the proposed Application for Final Payment. Change Notices filed concurrently with the Application for Final Payment must be otherwise timely and meet all requirements under Sections 13 and 19. If a Subcontractor refuses to furnish a release or waiver required by Mn/DOT, Contractor may furnish a bond satisfactory to Mn/DOT to indemnify Mn/DOT against such Lien.

Mn/DOT will review Contractor’s proposed Application for Final Payment, and changes or corrections will be forwarded to Contractor for correction.

### 11.6.2	Payment

#### 11.6.2.1	Release and Affidavit as Condition to Final Payment

As a condition to its obligation to make payment to Contractor based on the Application for Final Payment, Mn/DOT shall have received an executed release from Contractor for any and all claims arising from the Work, releasing and waiving any claims against the Indemnified Parties, excluding only those matters identified in any Change Notices listed as outstanding in the Application for Final Payment, and otherwise satisfactory in form and content to Mn/DOT.

The release shall be accompanied by an affidavit from Contractor certifying:

(a)	that it has resolved any claims made by Subcontractors, Utility Owners and others against Contractor or the Project;

(b)	that it has no reason to believe that any Person has a valid claim against Contractor or the Project which has not been communicated in writing by Contractor to Mn/DOT as of the date of the certificate; and

(c)	that all guarantees and warranties are in full force and effect.

The release and the affidavit shall survive final payment. The payment amount will be reduced by any amounts deductible under Section 11.5.

#### 11.6.2.2	Compliance with Withholding as Condition to Final Payment

Before final payment is made, Contractor shall also demonstrate compliance with the provisions of Minn. Stat. Section 290.92 requiring the withholding of State income tax from wages paid to Contractor's employees for Work performed under the Contract. Contractor can satisfy this requirement by obtaining a Certificate of Compliance from the Commissioner of Revenue and providing the certificate to Mn/DOT. Contractor is advised that, before the Commissioner of Revenue can issue the certificate, Contractor must first place on file with the Commissioner of Revenue, an affidavit stating compliance with the provisions of Minn. Stat. Section 290.92. The required affidavit form will be supplied by the Commissioner of Revenue upon request.

#### 11.6.2.3	Partial Estimates and Payments Subject to Correction

All prior partial estimates and payments shall be subject to correction in the final payment.

## 11.7	Payments to Subcontractors

Within 10 Days after receipt of payment from Mn/DOT, Contractor shall pay each Subcontractor, out of the amount paid to Contractor on account of such Subcontractor, all undisputed amounts (less any retainage and any other offsets and deductions provided in the Subcontract or by law) due and owing in accordance with the Subcontract. Within 10 Days after satisfactory completion of all Work to be performed by a Subcontractor, including provision of appropriate releases, certificates and other evidence of the Subcontractor’s compliance with all applicable requirements of the Contract Documents, Contractor shall return any moneys withheld in retention from the Subcontractor. Contractor shall, by appropriate agreement with each Subcontractor, require each Subcontractor to make payments to its lower tier Subcontractors in a similar manner. Mn/DOT shall have no obligation to pay or to see to the payment of money to a Subcontractor, except as may otherwise be required by law.

## 11.8	Interest on Late Payments

All amounts owing by Contractor to Mn/DOT under the Contract shall earn interest from the date on which such amount is owing at the lesser of (i) 10 percent per annum or (ii) the maximum rate allowable under Governmental Rules.

## 11.9	Disputes

Subject to Mn/DOT’s right to withhold from progress payments any amounts in dispute, and except as expressly stated otherwise in this Section 11, any disagreement between Mn/DOT and Contractor relating to this Section 11 shall be subject to Section 19. Failure by Mn/DOT to pay any amount in dispute shall not alleviate, diminish or modify in any respect Contractor’s obligation to perform under the Contract Documents, including Contractor’s obligation to achieve Final Acceptance in accordance with the Contract Documents, and Contractor shall not cease or slow down its performance under the Contract Documents on account of any such amount in dispute. Contractor shall proceed as directed by Mn/DOT pending resolution of the dispute. Upon resolution of any such dispute each party shall promptly pay to the other any amount owing.

# 12	Contract Incentives

## 12.1	Early Completion Incentives

Not used. {Use if applicable}

In the event that the Contractor achieves Substantial Completion in advance of the  as described in Section 4.3.1, the Contractor will receive an incentive payment of $      for each Calendar Day that the Work required to meet is completed prior to the . The total incentive shall not exceed $     . {Use if applicable}

## 12.2	Other Incentives

See Book 3, Section 5 (Design-Build Special Provisions).

# 13	CHANGES IN THE WORK

This Section 13 sets forth the requirements for obtaining all Change Orders under the Contract. Contractor hereby acknowledges and agrees that the Contract Price constitutes full compensation for performance of all of the Work, subject only to those exceptions specified in this Section 13, and that Mn/DOT is subject to constraints which limit its ability to increase the Contract Price or extend the Completion Deadlines. Contractor hereby waives the right to make any claim for a time extension or for any monetary compensation in addition to the Contract Price and other compensation specified in the Contract, except as set forth in this Section 13. To the extent that any other provision of this Contract expressly provides for a Change Order to be issued, such provision is hereby incorporated into this Section 13.

## 13.1	Circumstances under which Change Orders May Be Issued

### 13.1.1	Definition of and Requirements Relating to Change Orders

#### 13.1.1.1	Change Orders

The term “Change Order” shall mean a written amendment to the terms and conditions of the Contract Documents issued in accordance with this Section 13. Mn/DOT may issue unilateral Change Orders as specified in Section 13.2. A Change Order shall not be effective for any purpose unless executed by Mn/DOT, as specified herein. As used herein, execution of a Change Order by Mn/DOT shall mean that the Change Order has been fully executed with all the required signatures by Mn/DOT and any other necessary parties of the State. Change Orders may be requested by Contractor only pursuant to Section 13.3. Change Orders may be issued for the following purposes (or combination thereof):

(a)	to modify the scope of the Work;

(b)	to revise a Completion Deadline;

(c)	to revise the Contract Price; and

(d)	to revise other terms and conditions of the Contract Documents.

#### 13.1.1.2	Issuance of Directive Letter

Mn/DOT may at any time issue a Directive Letter to Contractor in the event of any desired change in the Work or of any Dispute regarding the scope of the Work. The Directive Letter will state that it is issued under this Section 13.1.1.2, will describe the Work in question and will state the basis for determining compensation, if any. Contractor shall proceed immediately with the Work as directed in the letter, pending the execution of a formal Change Order (or, if the letter states that the Work is within the original scope of the Work, Contractor shall proceed with the Work as directed but shall have the right pursuant to Section 13.3 to request that Mn/DOT issue a Change Order with respect thereto).

#### 13.1.1.3	Performance of Changed or Extra Work

As a condition precedent to Contractor’s right to receive additional payment or an extension of a Completion Deadline for changed or extra work, Contractor shall have received either a Directive Letter from Mn/DOT stating that it is issued pursuant to Section 13.1.1.2 or a Change Order for such work executed by Mn/DOT. To the extent that Contractor undertakes any such work without receiving a Directive Letter or Change Order executed by Mn/DOT, Contractor shall be deemed to have performed such work voluntarily and shall not be entitled to a Change Order in connection therewith. In addition, Contractor may be required to remove or otherwise undo any such work, at its sole cost.

### 13.1.2	Directive Letter as Condition Precedent to Claim That a Mn/DOT-Directed Change Has Occurred

In addition to provision of a Change Notice and subsequent Request for Change Order pursuant to Section 13.3.2, receipt of a Directive Letter from Mn/DOT is a condition precedent to Contractor’s right to claim that a Mn/DOT-Directed Change has occurred, provided that no Directive Letter shall be required for alleged Mn/DOT-Directed Changes directly attributable to delays caused by bad faith actions, active interference, gross negligence or comparable tortious conduct by Mn/DOT. The fact that a Directive Letter was issued by Mn/DOT shall not be considered evidence that in fact a Mn/DOT-Directed Change occurred. The determination whether a Mn/DOT-Directed Change in fact occurred shall be based on an analysis of the original Contract requirements and a determination whether the Directive Letter in fact constituted a change in those requirements. The foregoing requirements shall not imply that a Directive Letter would be required in order for Contractor to have the right to receive compensation for Work within its original scope for which additional compensation is specifically allowed under this Section 13.

### 13.1.3	Significant Changes in the Character of Work

If a Mn/DOT-Directed Change significantly changes the character of the Work, whether the alterations or changes included in such direction are in themselves significant changes to the character of the Work or by affecting other Work cause such other Work to become significantly different in character, an adjustment, excluding anticipated profit, will be made to the Contract. The basis for the adjustment shall be agreed upon prior to performance of such Work. If a basis cannot be agreed upon, then an adjustment will be made either for or against Contractor in such amount as Mn/DOT may determine to be fair and equitable, subject to resolving the Dispute in accordance with Section 19. The term “significant change” shall be construed to apply only when (a) the changes materially modify the general definition of the Project or the design-build character of the Work, or (b) Mn/DOT requires Work to be performed that is physically remote from the original Project and not necessary for completion of the original Project. Changes that are specifically contemplated by the Contract shall not be considered significant changes in the character of the Work. If the changes do not significantly change the character of the Work to be performed under the Contract, the altered Work will be paid for as provided elsewhere in the Contract.

## 13.2	Procedure for Mn/DOT-Initiated Change Orders

This Section 13.2 concerns Change Orders issued by Mn/DOT following a Request for Change Proposal and Change Orders unilaterally issued by Mn/DOT.

### 13.2.1	Request for Change Proposal

#### 13.2.1.1	Issuance of Request

If Mn/DOT desires to issue a Mn/DOT-Directed Change or to evaluate whether to initiate such a change, then Mn/DOT may, at its discretion, issue a Request for Change Proposal.

#### 13.2.1.2	Initial Consultation

Within two Days after Contractor’s receipt of a Request for Change Proposal, Mn/DOT and Contractor shall consult to define the proposed scope of the change. Within seven Days after the initial consultation, Mn/DOT and Contractor shall consult concerning the estimated cost and time impacts. Contractor shall provide data regarding such matters as requested by Mn/DOT.

#### 13.2.1.3	Notification by Mn/DOT

Within seven Days after the second consultation and provision of any data as described in Section 13.2.1.2, Mn/DOT shall notify Contractor whether Mn/DOT:

(a)	wishes to issue a Change Order;

(b)	wishes to request Contractor to prepare a Change Order form as discussed at the meeting; or

(c)	no longer wishes to issue a Change Order.

Mn/DOT may at any time, in its sole discretion, require Contractor to provide two alternative Change Order forms, one of which shall provide for a time extension and any additional costs permitted hereunder, and the other of which shall show all Acceleration Costs associated with meeting the original Completion Deadlines, as well as any additional costs permitted hereunder.

#### 13.2.1.4	Submittal of Change Order Form

If so requested, Contractor shall, within 21 Days after receipt of the notification described in Section 13.2.1.3, prepare and submit to Mn/DOT for review and Approval by Mn/DOT a Change Order form for the requested change, complying with all applicable requirements of Section 13.4, and incorporating and fully reflecting all requests made by Mn/DOT. Contractor shall bear the cost of developing the Change Order form, including any modifications thereto requested by Mn/DOT, except that costs of design and engineering work required for preparation of plans or exhibits necessary to the Change Order form and pre-authorized by Mn/DOT shall be included in the Change Order as reimbursable items. If the Change Order is Approved, the design and engineering costs will be included within the Change Order, otherwise, they shall be separately reimbursed through a separate Change Order.

#### 13.2.1.5	Order To Proceed

If Mn/DOT and Contractor agree that a change in the requirements relating to the Work has occurred but disagree as to whether the change justifies additional compensation or time or disagree as to the amount of any change to be made to the Contract Price or a Completion Deadline, Mn/DOT may, in its sole discretion, order Contractor to proceed with the performance of the Work in question notwithstanding such disagreement. Such order may, at Mn/DOT’s option, be in the form of:

(a)	a Time and Materials Change Order as provided in Section 13.7; or

(b)	a Directive Letter as described in Section 13.1.1.2.

### 13.2.2	Unilateral Change Orders

Mn/DOT may issue a Change Order at any time, regardless of whether it has issued a Request for Change Proposal.

#### 13.2.2.1	Additive and Deductive Change Orders

Additive unilateral Change Orders shall state that Contractor shall be entitled to compensation in accordance with Section 13.7 for the additional Work required thereby. The Change Order may contain a price deduction deemed appropriate by Mn/DOT, and Contractor shall have the right to submit the amount of such price deduction to dispute resolution in accordance with Section 19.

### 13.2.3	Changes in Law

Mn/DOT shall be entitled to a decrease in the Contract Price for any change in Governmental Rules that reduces the cost of the Work, if and to the extent that the change (a) allows a material modification in the design of the Project resulting in a net cost savings or (b) reduces the requirements of complying with environmental approvals.

## 13.3	Procedure for Contractor Initiated Change Orders

### 13.3.1	Eligible Changes

This section outlines instances whereby Contractor shall submit Change Notice and subsequent Request for Change Orders to Mn/DOT.

#### 13.3.1.1	Time Extension

Contractor may submit a Request for Change Order to extend a Completion Deadline, subject to certain limitations, only for the following excusable delays changing the duration of the Critical Path:

(a)	Mn/DOT-Caused Delays;

(b)	delays directly attributable to Differing Site Conditions, to the extent permitted by Section 13.8;

(c)	delays directly attributable to Force Majeure events, to the extent permitted by Section 13.9;

(d)	certain delays relating to Contaminated Materials, as described in Section 13.10, to the extent permitted therein and Section 5.3;

(e)	certain delays relating to Utilities, as described in Section 6;

#### 13.3.1.2	Contract Price Increase

Contractor may submit a Request for Change Order to increase the Contract Price, subject to certain limitations, including with respect to delay damages, as specified in Section 13.5.2, only for increased costs in the Work as follows:

(a)	additional costs directly attributable to additional Work resulting from Mn/DOT-Directed Changes for which Mn/DOT has not submitted a Change Order or a Request for Change Proposal;

(b)	additional costs directly attributable to Mn/DOT-Caused Delays;

(c)	additional costs directly attributable to Differing Site Conditions, to the extent provided in Section 13.8;

(d)	additional costs directly attributable to the following, to the extent provided in Section 13.9:

(i)	an earthquake;

(ii)	any rebellion, war, riot, terrorism or civil commotion;

(iii)	the discovery at, near, or on the Site of any paleontological, cultural or biological resources or any species presently or in the future listed as threatened or endangered under the federal or state endangered species act, provided that the existence of such resources was not disclosed in the RFP documents;

(iv)	the suspension, termination, interruption, denial, failure to obtain, nonrenewal or amendment of any Environmental Approval or New Environmental Approval, except as otherwise provided in Section 6.3; and

(v)	any change in a Governmental Rule, change in the judicial interpretation of a Governmental Rule, or adoption of any new Governmental Rule, which is materially inconsistent with Governmental Rules in effect on the Proposal Due Date (excluding any such change or new Governmental Rule which was passed or adopted but not yet effective as of the Proposal Due Date), and which (A) requires a material modification in the Project design, (B) requires Contractor to obtain a major State or federal environmental approval not previously required for the Project or (C) specifically targets the Project or Contractor;

(e)	certain additional costs relating to Contaminated Materials, as described in Section 13.10, to the extent provided therein;

(f)	adjustments as specified in Section 11.1.4, to the extent provided therein; and

(g)	additional costs directly attributable to uncovering, removing, and restoring Work, to the extent provided in Section 5.5.3.

#### 13.3.1.3	Contractor Initiated Change Proposal

Contractor at any time may submit a Request for Change Order to Mn/DOT that proposes changes to the scope of work of the Contract.  Proposals can include changes to add or reduce the scope of work or implement changes to the contract that are “equal to or better” than the underlying requirements. Provisions of Section 13.3.2 regarding delivery of Change Notice do not apply to a Contractor initiated change proposal.

### 13.3.2	Conditions Precedent

The requirements set forth in this Section 13.3.2 constitute conditions precedent to Contractor’s entitlement to request and receive a Change Order in all circumstances except those involving a Request for Change Proposal by Mn/DOT, a share of cost savings under Section 6.1.3, or a price increase under Section 11.1.3 or 11.1.4. Contractor agrees that the filing of Change Notices and subsequent filing of Requests for Change Orders with Mn/DOT pursuant to this Section 13.3.2 are necessary in order to begin the administrative process for Contractor-initiated Change Orders. Contractor understands that it shall be forever barred from recovering against Mn/DOT under this Section 13 if it fails to give notice of any act, or failure to act, by Mn/DOT or any of its representatives or the happening of any event, thing or occurrence pursuant to a proper Change Notice, and thereafter complies with the remaining requirements of this Section 13.3.

#### 13.3.2.1	Delivery of Change Notice

Contractor shall deliver to Mn/DOT written notice (“Change Notice”) stating that an event or situation has occurred within the scope of Section 13.3.1.1 and/or 13.3.1.2 and shall state which subsection thereof is applicable. The first notice shall be labeled “Change Notice No. 1” and subsequent notices shall be numbered sequentially.

13.3.2.1.1	Importance of Prompt Delivery

Each Change Notice shall be delivered as promptly as possible after the occurrence of such event or situation. If any Change Notice is delivered later than five Days after Contractor first discovered (or should have discovered in the exercise of reasonable prudence) the occurrence which is described therein, Contractor shall be deemed to have waived the right to collect any and all costs incurred prior to the date of delivery of the Change Notice, and shall be deemed to have waived the right to seek an extension of any Completion Deadline with respect to any delay in the Critical Path which accrued prior to the date of delivery of the written notice. Furthermore, if any Change Notice concerns any condition or material described in Section 5.3, Contractor shall be deemed to have waived the right to collect any and all costs incurred in connection therewith to the extent that Mn/DOT is not afforded the opportunity to inspect such material or condition before it is disturbed. Contractor’s failure to provide a Change Notice within 30 Days after Contractor first discovered (or should have discovered in the exercise of reasonable prudence) the occurrence of a given event or situation shall preclude Contractor from any relief, unless Contractor can show, based on a preponderance of the evidence, that (a) Mn/DOT was not materially prejudiced by the lack of notice, or (b) Mn/DOT’s designated representative specified in accordance with Section 23.5.1 had actual knowledge (including items (a) through (e) of Section 13.3.2.1.2), prior to the expiration of the 30-Day period, of the event or situation and that Contractor believed it was entitled to a Change Order with respect thereto. A Change Notice shall be deemed delivered only if it fully conforms to the requirements of Section 13.3.2.1.2.

13.3.2.1.2	Contents of Change Notice

The Change Notice shall: (a) state in detail the facts underlying the potential Change Order, the reasons why Contractor believes additional compensation or time will or may be due and the date of occurrence; (b) state in detail the basis that the work is not required by the Contract, if applicable; (c) identify particular elements of Contract performance for which additional compensation may be sought under this Section 13; (d) identify any potential Critical Path impacts; (e) provide an estimate of the time within which a response to the notice is required to minimize cost, delay, or disruption of performance; and (f) time impact analysis.

13.3.2.1.3	Facts Supporting Objection to Decision

If the Change Notice relates to a decision which the Contract leaves to the discretion of a Person or as to which the Contract provides that such Person’s decision is final, the Change Notice shall set out in detail all facts supporting Contractor’s objection to the decision, including all facts supporting any contention that the decision was capricious or arbitrary or is not supported by substantial evidence.

13.3.2.1.4	Notices Under Other Contract Provisions

The written notification under Section 5.3 may also serve as a Change Notice provided it meets the requirements for Change Notices.

13.3.2.1.5	Failure to Provide Information

Any adjustments made to the Contract shall not include increased costs or time extensions for delay resulting from Contractor’s failure to provide requested additional information under this Section 13.3.2.1.

#### 13.3.2.2	Delivery of Requests for Change Orders

Contractor shall deliver a Request for Change Order to Mn/DOT within 30 Days after delivery of the Change Notice. Mn/DOT may require design and construction costs to be covered by separate Request for Change Orders, in which case Contractor shall deliver each such Request for Change Order to Mn/DOT within 30 Days after delivery of the Change Notice. If Contractor requests a time extension, then Mn/DOT, in its sole discretion, may require Contractor to provide two alternative Request for Change Orders within 30 Days after delivery of the Change Notice, one of which shall provide for a time extension and any additional costs permitted hereunder, and the other of which shall show all Acceleration Costs associated with meeting the original Completion Deadlines, as well as any additional costs permitted hereunder. If Contractor fails to deliver a complete Request for Change Order or submits incomplete Request for Change Order meeting all the requirements of Section 13.3.2.3 within the appropriate time period, Contractor shall be required to provide a new Change Notice before it may submit a Request for Change Order.

#### 13.3.2.3	Incomplete Change Orders

Each Request for Change Order provided under Section 13.3.2.2 shall meet all requirements set forth in Section 13.4; provided that if any such requirements cannot be met due to the nature of the occurrence, Contractor shall provide an incomplete Request for Change Order which shall:

(a)	comply with all requirements capable of being met;

(b)	include a list of requirements which are not fulfilled together with an explanation reasonably satisfactory to Mn/DOT stating why such requirements cannot be met;

(c)	provide such information regarding projected impact on the Critical Path as is requested by Mn/DOT; and

(d)	in all events include sufficient detail to ascertain the basis for the proposed Change Order and for any price increase associated therewith, to the extent such amount is then ascertainable.

Contractor shall furnish, when requested by Mn/DOT, such further information and details as may be required to determine the facts or contentions involved. Contractor agrees that it shall give Mn/DOT access to any and all of Contractor’s books, records and other materials relating to the Work, and shall cause its Subcontractors to do the same, so that Mn/DOT can investigate the basis for such Request for Change Order. Contractor shall provide Mn/DOT with a monthly update to all outstanding incomplete Requests for Change Order, describing the status of all previously unfulfilled requirements and stating any changes in projections previously delivered to Mn/DOT, time expenditures to date and time anticipated for completion of the activities for which the time extension is claimed. Mn/DOT may reject Contractor’s claim at any point in the process. Once a complete Request for Change Order is provided, Mn/DOT’s failure to respond thereto within 14 Days of delivery of the request shall be deemed a rejection of such request. Although Mn/DOT intends to review incomplete Request for Change Orders for the purposes described in Section 13.3.2.4, Mn/DOT shall have no obligation to review the back-up associated with any Request for Change Order until a complete Request for Change Order is provided.

#### 13.3.2.4	Importance of Timely Delivery

Contractor acknowledges and agrees that, due to the limited availability of funds for the Project, timely delivery of notification of such events and situations and Request for Change Orders and updates thereto are of vital importance to Mn/DOT. Mn/DOT is relying on Contractor to evaluate, promptly upon the occurrence of any event or situation, whether the event or situation will affect schedule or costs and, if so, whether Contractor believes a time extension and/or price increase is required hereunder. If an event or situation occurs which may affect the Contract Price or a Completion Deadline, Mn/DOT will evaluate the situation and determine whether it wishes to make any changes to the definition of the Project so as to bring it within Mn/DOT’s funding and time restraints.

The following matters (among others) shall be considered in determining whether Mn/DOT has been prejudiced by Contractor’s failure to provide timely notice:

(a)	the effect of the delay on alternatives available to Mn/DOT (that is, a comparison of alternatives which are available at the time notice was actually given and alternatives which would have been available had notice been given when required under the Contract); and

(b)	the impact of the delay on Mn/DOT’s ability to obtain and review objective information contemporaneously with the event.

#### 13.3.2.5	Subcontractor Claims

All claims shall be submitted through Contractor.  Submission of claims directly from Subcontractors shall constitute a waiver of that portion of the claim.

### 13.3.3	Performance of Disputed Work

If Mn/DOT refuses to issue a Change Order based on Contractor’s request, Contractor shall nevertheless perform all work as specified in an appropriate Directive Letter, with the right to submit the issue of entitlement to a Change Order to Dispute Resolution in accordance with Section 19. Contractor shall maintain and deliver to Mn/DOT, upon request, contemporaneous records, meeting the requirements of Section 13.7.2, for all work performed which Contractor believes constitutes extra work (including non-construction work), until all Disputes regarding entitlement or cost of such work are resolved.

## 13.4	Contents of Change Orders

### 13.4.1	Not Used

### 13.4.2	Scope of Work, Cost Estimate, Delay Analysis, and Information Regarding Change

Contractor shall prepare a scope of work, cost estimate, delay analysis and other information as required by this Section 13.4.2 for each Request for Change Order.

#### 13.4.2.1	Scope of Work

The scope of work shall describe in detail satisfactory to Mn/DOT all activities associated with the Request for Change Order, including a description of additions, deletions and modifications to the existing Contract requirements.

#### 13.4.2.2	Cost Estimate

The cost estimate shall set out the estimated costs in such a way that a fair evaluation can be made. It shall include a breakdown for labor, materials, equipment, overhead (which includes all indirect costs) and profit, unless Mn/DOT agrees otherwise. The estimate shall include costs allowable under Section 13.5.2, if any. If the work is to be performed by Subcontractors and if the work is sufficiently defined to obtain Subcontractor quotes, Contractor shall obtain quotes (with breakdowns showing cost of labor, materials, equipment, overhead and profit) on the Subcontractor’s stationery and shall include such quotes as back-up for Contractor’s estimate. No mark-up shall be allowed in excess of the amounts allowed under Sections 13.5.2 and 13.7. Contractor shall identify all conditions with respect to prices or other aspects of the cost estimate, such as pricing contingent on firm orders being made by a certain date or the occurrence or non-occurrence of an event.

#### 13.4.2.3	Impacted Delay Analysis

If Contractor claims that such event, situation or change affects the Critical Path, it shall provide an impacted delay analysis indicating all activities represented or affected by the change, with activity numbers, durations, predecessor and successor activities, resources and cost, and with a narrative report, in form satisfactory to Mn/DOT, which compares the proposed new schedule to the Baseline Schedule or Revised Baseline Schedule, as appropriate. The revision to the Contract Schedule associated with the time extension shall not modify the “early and late start cost curves” of the Contract Schedule, except with respect to activities which have been impacted by the event which justifies the extension. Contractor may reschedule activities not otherwise affected by the event, in order to take advantage of additional Float available as the result of the time extension. Any such rescheduling shall be reflected in the Contract Schedule.

#### 13.4.2.4	Other Supporting Documentation

Contractor shall provide such other supporting documentation as may be required by Mn/DOT.

### 13.4.3	Not Used

### 13.4.4	Contractor Representation

Each Change Order (other than Change Orders issued unilaterally by Mn/DOT) shall contain a sworn certification in form acceptable to Mn/DOT by Contractor that the amount of time and/or compensation requested includes all known and anticipated impacts or amounts, direct, indirect and consequential, which may be incurred as a result of the event or matter giving rise to such proposed change and that Contractor has no reason to believe and does not believe that the factual basis for the Change Order is falsely represented.

The Contractor acknowledges that a false representation in connection with a change order may subject the Contractor to civil liability to the State (including treble damages and attorney fees) under the Minnesota False Claims Act.

## 13.5	Certain Limitations

### 13.5.1	Limitation on Contract Price Increases

Any increase in the Contract Price allowed hereunder shall exclude:

(a)	costs caused by the breach of contract or fault or negligence, or act or failure to act of any Contractor-Related Entity;

(b)	costs which could reasonably have been avoided by Contractor, including by resequencing, reallocating or redeploying its forces to other portions of the Work or to other activities unrelated to the Work (including any additional costs reasonably incurred in connection with such reallocation or redeployment); and

(c)	costs for any rejected Work which failed to meet the requirements of the Contract Documents and any necessary remedial Work.

### 13.5.2	Limitation on Delay and Disruption Damages

#### 13.5.2.1	Acceleration Costs; Delay and Disruption Damages

Acceleration Costs shall be compensable hereunder only with respect to Change Orders issued by Mn/DOT as an alternative to allowing an extension of a Completion Deadline as contemplated by Sections 13.2.1.3 and 13.3.2.2. Other delay and disruption damages shall be compensable hereunder only in the case of a delay which qualifies as a Mn/DOT-Caused Delay to the extent that it entitles Contractor to an extension of a Completion Deadline. Without limiting the generality of the foregoing, costs of rearranging Contractor’s work plan to accommodate Mn/DOT-Directed Changes not associated with an extension of a Completion Deadline shall not be compensable hereunder.

#### 13.5.2.2	Other Limitations

Delay and disruption damages shall be limited to direct costs directly attributable to the delays described in Section 13.5.2.1 and mark-ups thereon in accordance with Section 13.7 and any additional field office and jobsite overhead costs incurred by Contractor directly attributable to such delays. In addition, before Contractor may obtain any increase in the Contract Price to compensate for extended overhead, Acceleration Costs or other damages relating to delay, Contractor shall have demonstrated to Mn/DOT’s satisfaction that:

(a)	its schedule which defines the affected Critical Path in fact set forth a reasonable method for completion of the Work;

(b)	the change in the Work or other event or situation which is the subject of the requested Change Order has caused or will result in an identifiable and measurable disruption of the Work which impacted the Critical Path activity;

(c)	the delay or damage was not due to any breach of contract or fault or negligence, or act or failure to act of any Contractor-Related Entity, and could not reasonably have been avoided by Contractor, including by resequencing, reallocating or redeploying its forces to other portions of the Work or other activities unrelated to the Work (subject to reimbursement for additional costs reasonably incurred in connection with such reallocation or redeployment);

(d)	the delay for which compensation is sought is not concurrent with any other delay excluding Mn/DOT-Caused Delays; and

(e)	Contractor has suffered or will suffer actual costs due to such delay, each of which costs shall be documented in a manner satisfactory to Mn/DOT.

### 13.5.3	Limitation on Time Extensions

Any extension of a Completion Deadline allowed hereunder shall exclude any delay to the extent that it:

(a)	did not impact the Critical Path;

(b)	was due to the fault or negligence, or act or failure to act of any Contractor-Related Entity; or

(c)	could reasonably have been avoided by Contractor, including by resequencing, reallocating or redeploying its forces to other portions of the Work (provided that if the request for extension involves a Mn/DOT-Caused Delay, Mn/DOT shall have agreed, if requested to do so, to reimburse Contractor for its costs incurred, if any, in resequencing, reallocating or redeploying its forces).

Contractor shall be required to demonstrate to Mn/DOT’s satisfaction that the change in the Work or other event or situation which is the subject of the request for Change Order seeking a change in a Completion Deadline has caused or will result in an identifiable and measurable disruption of the Work which has impacted the Critical Path activity.

## 13.6	Negotiated Price Change Orders

Mn/DOT and Contractor (on its own behalf and on behalf of its Subcontractors) shall endeavor to negotiate, in good faith, a reasonable cost for each Change Order. In general, the price of a Change Order shall be negotiated in accordance with this Section 13.6 or shall be based on time and materials records pursuant to Section 13.7.

### 13.6.1	Not Used

### 13.6.2	Unit Price Change Orders

Instead of negotiating the price for a Change Order in accordance with Section 13.6.3, 13.6.4 or 13.6.5, Mn/DOT and Contractor may agree to negotiate unit prices for changed Work. Measurement of unit-priced quantities will be as specified in the Change Order. The unit prices shall be deemed to include all costs for the Work, including labor, material, overhead, markups and profit, and shall not be subject to change regardless of any change in the estimated quantities. Unit-priced Change Orders shall initially include an estimated increase in the Contract Price based on estimated quantities. The final price of a Change Order may be lump sum or may be based upon a final determination of the quantities.

### 13.6.3	Added Work

When the Change Order adds Work to Contractor’s scope, the increase in the Contract Price shall be negotiated based on estimated costs of labor, material and equipment, or shall be based on actual costs in accordance with Section 13.7. Mark-ups for profit and overhead shall be as provided in Section 13.7, and risk associated with the Work described in the Change Order shall be addressed through an additional amount agreed to by Mn/DOT and Contractor not to exceed 8 percent of the total Change Order amount (excluding the amount allocated to risk).

### 13.6.4	Deleted Work

When the Change Order deletes Work from Contractor’s scope (including deletion of any Work contained in the Contract that is found to be unnecessary), the amount of the reduction in the Contract Price shall be based upon a current estimate including a bill of material, a breakdown of labor and equipment costs and overhead and profit associated with the deleted work. Credits for mark-up for profit and overhead shall be as provided in Section 13.7.  Mn/DOT reserves the right to request a credit for risk up to 8 percent of the total Change Order amount (excluding amount allocated to risk).  When a deduction is involved, documented cancellation and restocking charges may be included in costs and subtracted from the price deduction.

### 13.6.5	Work Both Added and Deleted

When the Change Order includes both added and deleted Work, Contractor shall prepare separate cost breakdowns for Added Work and Deleted Work in accordance with Section 13.6.3 and 13.6.4.

(a)	The cost (or credit) amount of the Change Order shall be the difference between the cost Added Work and Deleted Work cost breakdowns.

(b)	If the change results in a net change of zero, there will be no change in the Contract Price.

## 13.7	Time and Materials Change Orders

Mn/DOT may at its discretion issue a Time and Materials Change Order whenever Mn/DOT determines that a Time and Materials Change Order is advisable. The Time and Materials Change Order shall instruct Contractor and designer to perform the Work, indicating expressly the intention to treat the items as changes in the Work, and setting forth the kind, character, and limits of the Work as far as they can be ascertained, the terms under which changes to the Contract Price will be determined and the estimated total change in the Contract Price anticipated thereunder. Upon final determination of the allowable costs, Mn/DOT shall issue a modified Change Order setting forth the final adjustment to the Contract Price. The following costs and mark-ups (and no others) shall be used for calculating the change in the Contract Price. No direct compensation will be allowed for other miscellaneous costs for which no specific allowance is provided in this Section 13.7.

### 13.7.1	Determination of Costs

Compensation for Time and Materials Change Orders shall be in accordance with Mn/DOT Standard Specification 1904 and this Section 13.7.

#### 13.7.1.1	Non-Construction Labor Costs

The cost of labor for non-construction-related Work (including designers), whether provided by Contractor or a Subcontractor, will equal the sum of the following:

(a)	Actual unburdened wages (i.e., the base wage paid to the employee exclusive of any fringe benefits), plus

(b)	Unless already included in the wage rates paid, the actual Mn/DOT Approved labor-related costs incurred by reason of subsistence and travel allowances, plus

(c)	A labor surcharge of 140 percent of actual unburdened wages, which shall constitute full compensation for all state and federal payroll, unemployment and other taxes, insurance and bond premiums, fringe benefits (including health insurance, retirement plans, vacation, sick leave and bonuses) and all other payments made to, or on behalf of, the worker, as well as overhead and profit.

If non-construction labor costs are performed by Subcontractors, the Contractor is entitled to the allowances under Mn/DOT Standard Specification 1904 to cover administration, general superintendence, additional bond, and other overhead expenses not otherwise recoverable.

#### 13.7.1.2	Excessive Cost

If the cost of materials is, in the opinion of Mn/DOT, excessive, then the cost of such materials shall be deemed to be the lowest current wholesale price at which such materials were available, in the quantities needed and delivered to the Site.

#### 13.7.1.3	Evidence of Cost

If Contractor, designer or any Subcontractor (as applicable) does not furnish satisfactory evidence of the cost of such materials from the actual supplier thereof within 60 Days after the date of delivery of the material, Mn/DOT reserves the right to establish the cost of such materials at the lowest current wholesale prices at which such materials were available, in the quantities needed and delivered to the Site.

#### 13.7.1.4	Permit Fees

Contractor will be reimbursed for the cost of any additional permit fees payable as the result of the change in the Work. Back-up documentation supporting each cost item for this category shall be provided by Contractor and Approved by Mn/DOT prior to any payment authorization being granted.

#### 13.7.1.5	Credit Items

Where Contractor’s or any Subcontractor’s portion of a change involves credit items, or the proposed change is a net deductive change, Contractor shall include all Contractor’s and Subcontractor’s overhead and profits in computing the value of the credit.

### 13.7.2	Time and Materials Records

#### 13.7.2.1	Collection and Maintenance of Data

Contractor shall maintain its records in such a manner as to provide a clear distinction between (a) the direct cost of Work for which it is entitled (or for which it believes it is entitled) to an increase in the Contract Price and (b) the costs of other operations. Contractor shall contemporaneously collect, record in writing, segregate and preserve (y) all data necessary to determine the costs described in this Section 13.7 with respect to all Work which is the subject of a Change Order or a requested Change Order, specifically including costs associated with design Work as well as Utility Relocations, but specifically excluding all negotiated Change Orders, and (z) all data necessary to show the actual impact (if any) of the change on the Critical Path with respect to all Work which is the subject of a Change Order or a proposed Change Order, if the impact on the Contract Schedule is in dispute. Such data shall be provided Mn/DOT, and its authorized representatives as directed by Mn/DOT, on forms Approved by Mn/DOT. The cost of furnishing such reports is included in Contractor’s predetermined overhead and profit mark-ups.

#### 13.7.2.2	Daily Reports

Contractor shall furnish daily reports, on forms Approved by Mn/DOT, of Time and Materials Change Order Work. The cost of furnishing such reports shall be included in Contractor’s overhead and fee percentages. The reports shall include:

(a)	name, classification, date, daily hours, total hours, rate, and extension for each worker (including both construction and non-construction personnel) and foreman;

(b)	designation, dates, daily hours, total hours, rental rate, and extension for each unit of machinery and equipment;

(c)	quantities of materials, prices and extensions;

(d)	transportation costs of materials, machinery, and equipment; and

(e)	invoices for materials used and for transportation charges.

The reports shall also state the total costs to date for the Time and Materials Change Order Work.

#### 13.7.2.3	Reports As Basis for Payment

All Time and Materials Change Order reports shall be signed by Contractor’s Project Manager. Mn/DOT will compare its records with Contractor’s reports, make the necessary adjustments and compile the costs of Time and Materials Change Order Work. When such reports are agreed upon and signed by both parties, they will become the basis of payment, but shall not preclude subsequent adjustment based on a later audit. Contractor’s (and each Subcontractor’s) cost records pertaining to Work paid for on a time and materials basis shall be open, during all regular business hours, to inspection or audit by representatives of Mn/DOT during the life of the Contract and for a period of not less than seven years after Final Acceptance, and Contractor (and each Subcontractor) shall retain such records for that period. If an audit is to be commenced more than 60 Days after Final Acceptance, Contractor will be given a 20 Day notice of the time when such audit is to begin.

### 13.7.3	 Compliance with the Federal Acquisition Regulation

Reimbursable expenses under Time and Materials Change Orders shall be limited to and comply with the FAR. Expenses excluded by the FAR shall not be reimbursed. If FHWA asserts that any claimed reimbursable expenses are not reimbursable under FAR, Mn/DOT will allow Contractor the opportunity to respond to FHWA and defend the allowability of the expenses.

## 13.8	Differing Site Conditions

### 13.8.1	Responsibilities of Mn/DOT

Upon Contractor’s fulfillment of all applicable requirements of Sections 5.3 and 13, and subject to the limitations contained therein, Mn/DOT shall be responsible for, and agrees to issue Change Orders, (a) to compensate Contractor for additional costs directly attributable to changes in the scope of the Work arising from Differing Site Conditions, and (b) to extend the Completion Deadlines as the result of any delay in the Critical Path caused by any such conditions.

### 13.8.2	Burden of Proof

Contractor shall bear the reasonable burden of proving that a Differing Site Condition exists and that it could not reasonably have worked around the Differing Site Condition so as to avoid additional cost. Each request for a Change Order relating to a Differing Site Condition shall be accompanied by a statement signed by a qualified professional setting forth all relevant assumptions made by Contractor with respect to the condition of the Site, justifying the basis for such assumptions, explaining exactly how the existing conditions differ from those assumptions, and stating the efforts undertaken by Contractor to find alternative design or construction solutions to eliminate or minimize the problem and the associated costs.

## 13.9	Certain Events

Upon Contractor’s fulfillment of all applicable requirements of Section 13, and subject to the limitations contained therein, Mn/DOT shall be responsible for, and agrees to issue Change Orders, (a) to compensate Contractor for additional costs directly attributable to the events set forth in Section 13.3.1.2(d) and/or (b) to extend the applicable Completion Deadlines as the result of any delay in the Critical Path caused by a Force Majeure event.

## 13.10	Contaminated Materials Management

See Book 2, Section 4.

## 13.11	Matters Not Eligible for Change Orders

Contractor acknowledges and agrees that no increase in the Contract Price or extension of a Completion Deadline is available except in circumstances expressly provided for in the Contract, that such price increase and time extension shall be available only as provided in this Section 13, and that Contractor shall bear full responsibility for the consequences of all other events and circumstances. Matters which are Contractor’s exclusive responsibility include the following:

(a)	Errors in the Design Documents and Construction Documents (including Errors directly attributable to Errors in the RID which are not guaranteed in Section 3.3);

(b)	subject to Sections 13.3.1.2(d)(iv) and (v), any design changes required by Mn/DOT as part of the process of Accepting the Design Documents for consistency with the requirements of the Contract Documents, the Governmental Approvals and/or Governmental Rules;

(c)	defective or incorrect schedules of Work or changes in the planned sequence of performance of the Work (except to the extent arising from causes which otherwise give rise to a right to a Change Order);

(d)	action or inaction of Contractor’s employees, Suppliers, Subcontractors or any Contractor-Related Party (unless arising from causes which otherwise give rise to a right to a Change Order);

(e)	groundwater levels or subsurface moisture content;

(f)	untimely delivery of equipment or material, or unavailability, defectiveness, or increases in costs of material, equipment or products specified by the Contract Documents (except to the extent arising from causes which otherwise give rise to a right to a Change Order);

(g)	delays not on the Critical Path;

(h)	costs covered by insurance proceeds received by or on behalf of Contractor;

(i)	correction of Nonconforming Work and oversight and related activities in connection therewith by Mn/DOT (including rejected design submittals);

(j)	failure by Contractor to comply with Contract requirements;

(k)	all other events beyond the control of Mn/DOT for which Mn/DOT has not agreed to assume liability hereunder, and;

(l)	any situations (other than Force Majeure events) which, while not within one of the categories delineated above, were or should have been anticipated because such situations are referred to elsewhere in the Contract or arise out of the nature of the Work.

Contractor hereby assumes responsibility for all such matters, and acknowledges and agrees that assumption by Contractor of responsibility for such risks, and the consequences, costs and delays resulting therefrom, is reasonable under the circumstances of the Contract and that contingencies included in the Proposal Price in Contractor’s sole judgment, constitute sufficient consideration for its acceptance and assumption of said risks and responsibilities.

## 13.12	Waiver

CONTRACTOR HEREBY EXPRESSLY WAIVES ALL RIGHTS TO ASSERT ANY AND ALL CLAIMS BASED ON ANY CHANGE IN THE WORK, DELAY OR ACCELERATION (INCLUDING ANY CHANGE, DELAY, SUSPENSION OR ACCELERATION WHICH, BUT FOR THE EXPRESS TERMS OF THE CONTRACT DOCUMENTS, COULD BE INFERRED OR IMPLIED AT LAW) FOR WHICH CONTRACTOR FAILED TO PROVIDE PROPER AND TIMELY NOTICE OR FAILED TO PROVIDE A TIMELY REQUEST FOR CHANGE ORDER, AND AGREES THAT CONTRACTOR SHALL BE ENTITLED TO NO COMPENSATION OR DAMAGES WHATSOEVER IN CONNECTION WITH THE WORK EXCEPT TO THE EXTENT THAT THE CONTRACT DOCUMENTS EXPRESSLY SPECIFY THAT CONTRACTOR IS ENTITLED TO A CHANGE ORDER OR OTHER COMPENSATION OR DAMAGES.

## 13.13	Disputes

If Mn/DOT and Contractor agree that a request to increase the Contract Price and/or extend any Completion Deadline by Contractor has merit, but are unable to agree as to the amount of such price increase and/or time extension, Mn/DOT agrees to mark up the Change Order request or Change Order form, as applicable, provided by Contractor to reduce the amount of the price increase and/or time extension as deemed appropriate by Mn/DOT. In such event, Mn/DOT will execute and deliver the marked-up Change Order to Contractor within a reasonable period after receipt of a request by Contractor to do so, and thereafter will make payment and/or grant a time extension based on such marked-up Change Order. The failure of Mn/DOT and Contractor to agree to any Change Order under this Section 13 (including agreement as to the amount of compensation allowed under a Time and Materials Change Order and the disputed amount of the increase in the Contract Price and/or extension of a Completion Deadline in connection with a Change Order as described above) shall be a Dispute to be resolved pursuant to Section 19. Except as otherwise specified in the Change Order, execution of a Change Order by both parties shall be deemed accord and satisfaction of all claims by Contractor of any nature arising from or relating to the Work covered by the Change Order. Contractor’s Claim and any award by the dispute resolver shall be limited to the incremental costs incurred by Contractor with respect to the disputed matter (crediting Mn/DOT for any corresponding reduction in Contractor’s other costs) and shall in no event exceed the amounts allowed by Section 13.7 with respect thereto.

## 13.14	No Release or Waiver

### 13.14.1	Extension of Time for Performance

No extension of time granted hereunder shall release Contractor’s Surety or any Guarantor from its obligations. Mn/DOT shall not be deemed to have waived any rights under the Contract (including its right to abrogate the Contract for abandonment or for failure to complete within the time specified, or to impose and deduct damages as may be provided herein) as the result of any grant of an extension of time beyond the date fixed for the completion of any part of the Work, any acceptance of performance of any part of the Work after a Completion Deadline, or the making of any payments to Contractor after such date.

### 13.14.2	No Change Order Based on Course of Conduct or Order by Unauthorized Person

No course of conduct or dealings between the parties nor express or implied acceptance of alterations or additions to the Work, and no claim that Mn/DOT has been unjustly enriched shall be the basis for any claim, request for additional compensation or extension of a Completion Deadline. Further, Contractor shall undertake, at its risk, work included in any request, order or other authorization issued by a person in excess of that person’s authority as provided herein, or included in any oral request. Contractor shall be deemed to have performed such work as a volunteer and at its sole cost. In addition, Mn/DOT may require Contractor to remove or otherwise undo any such work, at Contractor’s sole cost.

# 14	SUSPENSION OF WORK

## 14.1	Suspension for Convenience

Mn/DOT may, at any time and for any reason, by written notice, order Contractor to suspend all or any part of the Work required under the Contract Documents for the period of time that Mn/DOT deems appropriate for the convenience of Mn/DOT. Contractor shall promptly comply with any such written suspension order. Contractor shall promptly recommence the Work upon receipt of written notice from Mn/DOT directing Contractor to resume Work. Suspensions related to seasonal or climatic conditions, or Force Majeure events shall not be considered Mn/DOT-Caused Delays.

## 14.2	Suspension for Cause

Mn/DOT has the authority by written order to suspend the Work without liability to Mn/DOT wholly or in part for Contractor’s failure to:

(a)	correct conditions unsafe for the Project personnel or general public;

(b)	comply with any Governmental Approval, Governmental Rule or otherwise carry out the requirements of the Contract;

(c)	carry out orders of Mn/DOT duly given; or

(d)	comply with environmental requirements or requirements for developing and implementing the Quality Manual.

Contractor shall promptly comply with any such written suspension order. Contractor shall promptly recommence the Work upon receipt of written notice from Mn/DOT directing Contractor to resume Work.

## 14.3	Contractor Responsibilities During Suspension

During periods that Work is suspended, Contractor shall continue to be responsible for the Work and shall prevent damage or injury to the Project and other facilities in the Project vicinity, provide for drainage, obtain and maintain compliance with all Governmental Approvals, maintain all Contractor-provided insurance and bonds and erect necessary temporary structures, signs or other facilities required to maintain the Project and other facilities in the Project vicinity. During any suspension period, unless otherwise directed by Mn/DOT, Contractor shall continue to be responsible for maintenance of traffic in accordance with the requirements of the Contract, for plant and landscape maintenance in accordance with Section 14 of Book 2 and for maintenance during construction in accordance with Section 19 of Book 2. If the suspension is for Mn/DOT’s convenience, the additional work performed by Contractor during the suspension period shall be considered Mn/DOT-Directed Changes.

# 15	TERMINATION FOR CONVENIENCE

## 15.1	Notice of Termination

Mn/DOT may terminate the Contract and the performance of the Work by Contractor if Mn/DOT determines, in its sole discretion, that a termination is in the best public, State or national interest to do so. Mn/DOT shall notify Contractor of its decision to terminate by delivering to Contractor a written Notice of Termination specifying the extent of termination and its effective date. Termination of the Contract shall not relieve any Surety or Guarantor of its obligation for any claims arising out of the Work performed.

## 15.2	Contractor’s Responsibilities Upon Termination

After receipt of a Notice of Termination, and except as otherwise directed by Mn/DOT, Contractor shall immediately proceed as follows, regardless of any delay in determining or adjusting any amounts due under this Section 15.

(a)	Stop Work as specified in the notice;

(b)	Communicate such notice to all affected Subcontractors and that their Subcontracts are not to be further performed unless otherwise authorized in writing by Mn/DOT;

(c)	Place no further Subcontracts or orders for materials, services or facilities, except as necessary to complete the continued portion of the Work, if any, or for mitigation of damages;

(d)	Terminate all Subcontracts to the extent that they relate to the Work terminated;

(e)	Assign to Mn/DOT in the manner, at the times, and as and to the extent directed by Mn/DOT, all of the right, title and interest of Contractor under the Subcontracts so terminated, in which case Mn/DOT will have the right, in its sole discretion, to accept performance, settle or pay any or all claims arising out of the termination of such Subcontracts;

(f)	Subject to the prior Approval of Mn/DOT, settle all outstanding liabilities and claims arising out of such termination of Subcontracts;

(g)	Provide Mn/DOT with an inventory list of all materials previously produced, purchased or ordered from Suppliers for use in the Work and not yet used in the Work, including its storage location, as well as any documentation or other property required to be delivered hereunder which is either in the process of development or previously completed but not yet delivered to Mn/DOT, and such other information as Mn/DOT may request; and transfer title and deliver to Mn/DOT, in the manner, at the times, and as and to the extent, if any, directed by Mn/DOT (i) fabricated or unfabricated parts, the Work in process, completed Work, supplies and other material produced or acquired for the Work terminated; and (ii) the Design Documents, Construction Documents and all other completed or partially completed drawings (including plans, elevations, sections, details and diagrams), specifications, records, samples, information and other property that would have been required to be furnished to Mn/DOT if the Work had been completed;

(h)	Complete performance in accordance with the Contract Documents of all Work not terminated;

(i)	Take all action that may be necessary, or that Mn/DOT may direct, for the safety, protection and preservation of (a) the public, including public and private vehicular movement, (b) the Work and (c) the equipment, machinery, materials and property related to the Contract Documents that is in the possession of Contractor and in which Mn/DOT has or may acquire an interest;

(j)	As authorized by Mn/DOT in writing, use its best efforts to sell, in a manner, at the times, to the extent, and at the price or prices directed or authorized by Mn/DOT, any property of the types referred to in Section 15.2(g); provided, however, that Contractor (i) is not required to extend credit to any purchaser, and (ii) may acquire the property under the conditions prescribed and at prices Approved by Mn/DOT. The proceeds of any transfer or disposition will be applied to reduce any payments to be made by Mn/DOT under the Contract Documents or paid in any other manner directed by Mn/DOT;

(k)	If requested by Mn/DOT, withdraw from the portions of the Site designated by Mn/DOT and remove such materials, equipment, tools and instruments used by, and any debris or waste materials generated by, Contractor and any Subcontractor in the performance of the Work as Mn/DOT may direct; and

(l)	Take other actions directed by Mn/DOT.

## 15.3	Responsibility After Notice of Termination

Contractor shall continue to be responsible for damage to materials after issuance of the Notice of Termination, except as follows:

(a)	Contractor’s responsibility for damage to materials for which partial payment has been made as provided herein shall terminate when Mn/DOT certifies that those materials have been stored in the manner and at the locations directed by Mn/DOT.

(b)	Contractor’s responsibility for damage to materials purchased by Mn/DOT subsequent to the issuance of the notice that the Contract is to be terminated shall terminate when title and delivery of those materials has been taken by Mn/DOT.

Immediately after Mn/DOT determines that Contractor has completed the Work directed to be completed prior to termination and such other work as may have been ordered to secure the Project for termination, Contractor will not be required to provide for continuing safety, security and maintenance at the Site.

## 15.4	Negotiated Termination Settlement

### 15.4.1	Settlement Proposal

After receipt of a Notice of Termination, Contractor shall submit a final termination settlement proposal to Mn/DOT in the form and with the certification prescribed by Mn/DOT. Contractor shall submit the proposal promptly, but no later than 60 Days from the effective date of termination, unless Contractor has requested a time extension in writing within such 60-Day period and Mn/DOT has agreed in writing to allow such an extension. Mn/DOT will then review Contractor’s termination settlement proposal and will act upon it, return it with comments or reject it. If Contractor fails to submit the proposal within the time allowed, Mn/DOT may determine, on the basis of information available to it, the amount, if any, due Contractor because of the termination and shall pay Contractor the amount so determined.

### 15.4.2	Negotiated Settlement Amount

Contractor and Mn/DOT may agree, as provided in Section 15.4.1, upon the whole or any part of the amount or amounts to be paid to Contractor by reason of the total or partial termination of Work pursuant to this Section 15. Such negotiated settlement may include a reasonable allowance for profit solely on Work which has been completed as of the termination date and subsequently Accepted by Mn/DOT. Such agreed amount(s), exclusive of settlement costs, shall not exceed the total Contract Price as reduced by the amount of payments otherwise made and as further reduced by the Contract Price of Work not terminated. Upon determination of the settlement amount the Contract will be amended accordingly, and Contractor will be paid the agreed amount. Nothing in Section 15.5, prescribing the amount to be paid to Contractor in the event that Contractor and Mn/DOT fail to agree upon the whole amount to be paid to Contractor by reason of the termination of Work pursuant to this Section 15, shall be deemed to limit, restrict or otherwise determine or affect the amount(s) which may be agreed upon to be paid to Contractor pursuant to this Section 15.4. Mn/DOT’s execution and delivery of any settlement agreement shall not affect any of its rights under the Contract Documents with respect to completed Work, relieve Contractor from its obligations with respect thereto, including Warranties, or affect Contractor’s rights under the Payment and Performance Bond and Payment as to such completed or non-terminated Work.

## 15.5	Determination of Settlement Amount If Negotiations Fail

If Contractor and Mn/DOT fail to agree, as provided in Section 15.4.2, upon the whole amount to be paid to Contractor by reason of the termination of Work pursuant to this Section 15, the amount payable (exclusive of interest charges) shall be determined by Mn/DOT in accordance with the following, but without duplication of any amounts agreed upon in accordance with Section 15.4.

### 15.5.1	Payment Amount

Mn/DOT will pay Contractor the sum of the following amounts for Work performed prior to the effective date of the Notice of Termination, as such amounts are determined by Mn/DOT:

(a)	Contractor’s actual reasonable out-of-pocket cost (without profit, and including equipment costs only to the extent permitted by Section 13) for all Work performed, including mobilization, demobilization and work done to secure the Project for termination, including reasonable overhead and accounting for any refunds payable with respect to insurance premiums, deposits or similar items, as established to Mn/DOT’s satisfaction. In determining the reasonable cost, deductions will be made for the cost of materials to be retained by Contractor, amounts realized by the sale of materials and for other appropriate credits. Deductions will also be made for the cost of damaged materials. When, in the opinion of Mn/DOT, the cost of an item of Work is excessively high due to costs incurred to remedy or replace defective or rejected Work, the reasonable cost to be allowed will be the estimated reasonable cost of performing that Work in compliance with the requirements of the Contract Documents and the excessive actual cost will be disallowed.

(b)	As profit on clause (a) above, a sum determined by Mn/DOT to be fair and reasonable; provided, however, that if it appears that Contractor would have sustained a loss on the entire Contract had it been completed, no profit shall be included or allowed under this Section 15.5.1 and an appropriate adjustment shall be made by reducing the amount of the settlement to reflect the indicated rate of loss.

(c)	The cost of settling and paying claims arising out of the termination of Work under Subcontracts as provided in Section 15.2(f), exclusive of the amounts paid or payable on account of supplies or materials delivered or services furnished by the Subcontractor prior to the effective date of the Notice of Termination under the Contract, which amounts shall be included in the cost on account of which payment is made under clause (a) above.

(d)	The reasonable out-of-pocket cost (including reasonable overhead) of the preservation and protection of property incurred pursuant to Section 15.2(i) and any other reasonable out-of-pocket cost (including overhead) incidental to termination of Work under the Contract, including the reasonable cost to Contractor of handling material returned to the vendor, delivered to Mn/DOT or otherwise disposed of as directed by Mn/DOT, and including a reasonable allowance for Contractor’s administrative costs in determining the amount due to Contractor as the result of the termination of Work under the Contract.

(e)	If the termination occurs prior to issuance of NTP2, the stipend amount.

### 15.5.2	Maximum Compensation

Contractor acknowledges and agrees that it shall not be entitled to any compensation in excess of the value of the Work performed (determined as provided in Section 15.5.1) plus its settlement costs, and that items such as lost or anticipated profits, unabsorbed overhead and opportunity costs shall not be recoverable by it upon termination of the Contract. However, the total amount to be paid to Contractor, exclusive of costs described in Sections 15.5.1(c), (d) and (e), may not exceed the total Contract Price less the amount of payments previously made and less the Contract Price of any Work not terminated. Furthermore, if any refund is payable with respect to insurance or bond premiums, deposits or similar items which were previously passed through to Mn/DOT by Contractor, such refund shall be paid directly to Mn/DOT or otherwise credited to Mn/DOT. If the Contract includes an NTP1 Payment Cap as described in Section 11.3, the total amount payable to Contractor shall in no event exceed the NTP1 Payment Cap if termination occurs prior to issuance of NTP2.

### 15.5.3	Excluded Items

Except for normal spoilage, and except to the extent that Mn/DOT will have otherwise expressly assumed the risk of loss, there will be excluded from the amounts payable to Contractor under Section 15.5.1, the fair value, as determined by Mn/DOT, of equipment, machinery, materials and property which is destroyed, lost, stolen or damaged so as to become undeliverable to Mn/DOT, or to a buyer pursuant to Section 15.2(j). The amount set forth in the Proposal by Contractor for the Work terminated shall be a factor to be analyzed in determining the value of the Work terminated.

### 15.5.4	Payment of Termination Amount

Upon determination of the amount of the termination payment, the Contract shall be amended to reflect the agreed termination payment, and Contractor shall be paid the agreed amount.

## 15.6	Partial Termination

If a termination hereunder is partial, the Contract Price for the remainder of the Work shall be adjusted as appropriate to account for the change in the overall scope of the Project.

## 15.7	Reduction in Amount of Claim

The amount otherwise due Contractor under this Section 15 shall be reduced by (a) all unliquidated advance or other payments made to or on behalf of Contractor applicable to the terminated portion of the Contract, (b) the amount of any claim which Mn/DOT may have against any Contractor-Related Entity in connection with the Contract, (c) the agreed price for, or the proceeds of the sale of, any property, materials, supplies or other things acquired by Contractor or sold, pursuant to the provisions of this Section 15, and not otherwise recovered by or credited to Mn/DOT, (d) amounts that Mn/DOT deems advisable, in its sole discretion, to retain to cover any existing or threatened claims, Liens and stop notices relating to the Project, including claims by Utility Owners, (e) the cost of repairing any Nonconforming Work and (f) any amounts due or payable by Contractor to Mn/DOT.

## 15.8	Partial Payments

Mn/DOT may, from time to time, under such terms and conditions as it may prescribe and in its sole discretion, make partial payments on account against costs incurred by Contractor in connection with the terminated portion of the Contract, whenever in the opinion of Mn/DOT the aggregate of such payments shall be within the amount to which Contractor will be entitled under this Section 15. If the total of such payments is in excess of the amount finally agreed or determined to be due under this Section 15, such excess shall be payable by Contractor to Mn/DOT upon demand together with interest thereon as set forth in Section 11.8.

## 15.9	Inclusion in Subcontracts

Contractor shall insert in all Subcontracts a requirement that the Subcontractor shall stop Work on the date and to the extent specified in a Notice of Termination from Mn/DOT in accordance with this Section 15, and shall require Subcontractors to insert the same provision in each Subcontract at all tiers.

## 15.10	Limitation on Payments to Subcontractor

For the purposes of Sections 15.4.2 and 15.5, upon termination under Section 15.2(d) of Work under any Subcontract, Contractor will not be entitled to reimbursement for that portion of the termination settlement with any such Subcontractor which constitutes anticipatory or unearned profit on Work not performed, or which constitutes consequential damages on account of the termination or partial termination.

## 15.11	No Unearned Profits or Consequential Damages

Under no circumstances shall Contractor be entitled to anticipatory or unearned profits or consequential or other damages as a result of a termination or partial termination under this Section 15. The payment to Contractor determined in accordance with this Section 15 constitutes Contractor’s sole and exclusive remedy for a termination under this Section 15.

## 15.12	No Waiver

Anything contained in the Contract to the contrary notwithstanding, a termination under this Section 15 shall not waive any right or claim to damages which Mn/DOT may have, and Mn/DOT may pursue any cause of action which it may have at law or in equity or under the Contract.

## 15.13	Dispute Resolution

The failure of the parties to agree on amounts due under this Section 15 shall be a Dispute to be resolved in accordance with Section 19.

## 15.14	Allowability of Costs

All costs claimed by Contractor under this Section 15 shall, at a minimum, be allowable, allocable and reasonable in accordance with the cost principles and procedures of 48 CFR Part 31.

## 15.15	Suspension of Work

In the event of any suspension of Work by Mn/DOT, after issuance of NTP1, for more than 180 consecutive Days, Contractor shall have the right to consider the Contract to have been terminated for convenience under this Section 15. Contractor shall notify Mn/DOT of such election by delivering to Mn/DOT a written notice of termination due to such suspension specifying its effective date. Upon delivery by Contractor to Mn/DOT of a notice of termination due to suspension, the provisions of this Section 15 shall apply.

## 15.16	Termination Due to Non-Appropriation of Funds

### 15.16.1	Availability of Funds

The obligation of Mn/DOT to make any payments to Contractor hereunder is contingent upon funds being appropriated, budgeted, allocated and otherwise made available by Mn/DOT in amounts to meet its funding obligations for the Contract. Contractor is not obligated to perform Work, and correspondingly is not entitled to any compensation for Work performed, in any fiscal year beyond the amount, if any, appropriated and made available by Mn/DOT in amounts to meet its funding obligations for the Contract.

### 15.16.2	Anticipated Appropriations

Mn/DOT anticipates that sufficient funds will be authorized to allow Mn/DOT to make all payments owing hereunder.

### 15.16.3	Remedy for Failure To Appropriate

If funds are not budgeted, allocated or otherwise made available by Mn/DOT or the State or federal Legislature fails to make an appropriation, resulting in stoppage of Work, Contractor agrees to resume performance of the Work without any modification to the terms and conditions hereof, provided that an appropriation therefor is approved or funds are made available within 60 Days after Contractor stops Work under Section 15.16.1. Any such Work stoppage shall be considered a suspension for convenience under Section 14.1. If funds are not appropriated or made available before expiration of such 60-Day period, either party may terminate the Contract.

# 16	DEFAULT

## 16.1	Default By Contractor

### 16.1.1	Events of Default

Contractor shall be in breach under the Contract upon the occurrence of any one or more of the following events or conditions:

(a)	Contractor fails to promptly begin the Work under the Contract Documents following issuance of a Notice to Proceed authorizing such work;

(b)	Contractor fails to perform the Work with sufficient resources to ensure the prompt completion thereof (i.e., Contractor fails to execute remedial action in accordance with the Quality Manual and Book 2, Section 2.4);

(c)	Contractor fails to perform the Work in accordance with the Contract Documents, refuses to remove and replace rejected materials or Nonconforming or unacceptable Work, or fails to remove and replace workers as directed by Mn/DOT under Section 7.4.3;

(d)	Contractor discontinues or suspends the prosecution of the Work (exclusive of Work stoppage due to [i] termination by Mn/DOT, [ii] a Force Majeure event or suspension by Mn/DOT, or [iii] nonpayment by Mn/DOT not related to a breach by Contractor);

(e)	Contractor fails to resume performance of Work which has been suspended or stopped, within a reasonable time after receipt of notice from Mn/DOT to do so or (if applicable) after cessation of the event preventing performance;

(f)	Contractor breaches any other agreement, representation or warranty contained in the Contract Documents, or Contractor fails to perform any other obligation under the Contract Documents, including EEO and DBE requirements;

(g)	Contractor fails to provide and maintain the required insurance;

(h)	Contractor fails to provide and maintain the required payment and performance bond or Contractor assigns or transfers the Contract Documents or any right or interest therein, except as expressly permitted under Section 23.4.2;

(i)	Contractor fails, absent a valid dispute, to make payment when due for labor, equipment or materials in accordance with its agreements with Subcontractors and applicable law, fails to comply with any Governmental Rule or Governmental Approval; or fails reasonably to comply with the instructions of Mn/DOT consistent with the Contract Documents;

(j)	Contractor fails to discharge or obtain a stay within 10 Days of any final judgment(s) or order for the payment of money against it in excess of $100,000 in the aggregate arising out of the prosecution of the Work (provided that, for purposes hereof, posting of a bond in the amount of 125 percent of such judgment or order shall be deemed an effective stay);

(k)	Contractor shall have become insolvent, generally does not pay its debts as they become due, admits in writing its inability to pay its debts, or makes an assignment for the benefit of creditors;

(l)	Insolvency, receivership, reorganization or bankruptcy proceedings shall have been commenced by or against Contractor, any Guarantor or any Major Participant and not dismissed within 60 Days;

(m)	Any representation or warranty made by Contractor or any Guarantor in the Contract Documents or in any certificate, schedule, instrument or other document delivered pursuant to the Contract Documents shall have been false or materially misleading when made;

(n)	Contractor or any Guarantor is a party to fraud;

(o)	Any Guarantor revokes or attempts to revoke its obligations under the Guaranty, or otherwise takes the position that such instrument is no longer in full force and effect; or

(p)  Any Guarantor shall have become insolvent, generally does not pay its debts as they become due, admits in writing its inability to pay its debts, or makes an assignment for the benefit of creditors.

### 16.1.2	Right to Cure

Mn/DOT agrees to allow Contractor and Surety 15 Days notice and opportunity to cure any breach before declaring an Event of Default, provided that the notice and cure period shall only be three days for a breach under Section 16.1.1(g) and no such notice and opportunity to cure is required for any breach which by its nature cannot be cured. If a breach for which a 15-Day cure period is provided is curable but by its nature cannot be cured within 15 Days, as determined by Mn/DOT, Mn/DOT agrees not to declare an Event of Default provided that Contractor commences such cure within such 15-Day period and thereafter diligently prosecutes such cure to completion; provided, however, that in no event will such cure period exceed 60 Days in total. Contractor hereby acknowledges and agrees that the events described in Sections 16.1.1(h), (k), (m), (n) and (o) are not curable. Notwithstanding the foregoing, if Mn/DOT believes a condition affecting the Project poses an immediate and imminent danger to public health or safety, Mn/DOT may, without notice and without awaiting lapse of any cure period, rectify the condition at Contractor’s cost, and so long as Mn/DOT undertakes such action in good faith, even if under a mistaken belief in the occurrence of such default, such action shall not expose Mn/DOT to liability to Contractor and shall not entitle Contractor to any other remedy, it being acknowledged that Mn/DOT has a paramount public interest in providing and maintaining safe public use of and access to the Project. Mn/DOT’s good faith determination of the existence of such danger shall be deemed conclusive in the absence of clear and convincing evidence to the contrary.

## 16.2	Remedies

### 16.2.1	Rights of Mn/DOT

If an Event of Default occurs, then, in addition to all other rights and remedies provided by law or equity or available under the Contract or otherwise, including the rights to recover Liquidated Damages and to seek recourse against the surety bonds required hereby, any Guaranty and/or other performance security, Mn/DOT shall have the following rights and remedies, without further notice, and without prejudice to any of its other rights or remedies and without waiving or releasing Contractor from any obligations, and Contractor shall have the following obligations (as applicable):

(a)	Mn/DOT may order Contractor to suspend or discontinue the Work or any portion of the Work;

(b)	Mn/DOT may terminate the Contract or a portion thereof, in which case, the provisions of Sections 15.2 and 15.3 shall apply;

(c)	If and as directed by Mn/DOT, Contractor shall withdraw from the Site; and shall remove such materials, equipment, tools and instruments used by, and any debris or waste materials generated by, any Contractor-Related Entity in the performance of the Work;

(d)	Contractor shall deliver to Mn/DOT possession of any or all facilities of Contractor located on the Site as well as any or all Design Documents, Construction Documents and all other completed or partially completed drawings (including plans, elevations, sections, details and diagrams), specifications, records, information, schedules, samples, shop drawings and other documents, that Mn/DOT deems necessary for completion of the Work;

(e)	Contractor shall confirm the assignment to Mn/DOT of the Subcontracts requested by Mn/DOT, and Contractor shall terminate, at its cost, all other Subcontracts;

(f)	Mn/DOT may deduct from any amounts payable by Mn/DOT to Contractor such amounts payable by Contractor to Mn/DOT, including Liquidated Damages or other damages payable to Mn/DOT under the Contract Documents;

(g)	Mn/DOT shall have the right, but not the obligation, to pay such amount and/or perform such act as may then be required;

(h)	Mn/DOT, without incurring any liability to Contractor, shall have the rights (i) to take the performance of all or a portion of the Work from Contractor (either with or without the use of Contractor’s materials, equipment, tools and instruments) and enter into an agreement with another Person for the completion of such Work; or (ii) to use such other methods, as in the opinion of Mn/DOT, will be required for the completion of the Project; and/or

(i)	If Mn/DOT exercises any right to perform any obligations of Contractor, in the exercise of such right Mn/DOT may, but is not obligated to, among other things: (i) perform or attempt to perform, or cause to be performed, such work; (ii) spend such sums as Mn/DOT deems necessary and reasonable to employ and pay such architects, engineers, consultants and contractors and obtain materials and equipment as may be required for the purpose of completing such work; (iii) execute all applications, certificates and other documents as may be required for completing the work; (iv) modify or terminate any contractual arrangements; (v) take any and all other actions which it may in its sole discretion consider necessary to complete the Work; and (vi) prosecute and defend any action or proceeding incident to the Work.

### 16.2.2	Liability of Contractor

#### 16.2.2.1	Occurrence of an Event of Default

If an Event of Default has occurred, Contractor and Surety shall be jointly and severally liable to Mn/DOT (in addition to any other damages under the Contract Documents other than those costs intended to be covered by Liquidated Damages payable hereunder) for all costs reasonably incurred by Mn/DOT or any party acting on Mn/DOT’s behalf in completing the Work or having the Work completed by another Person (including any re-procurement costs, throw away costs for unused portions of the completed Work and increased financing costs). Upon the occurrence of an Event of Default, Mn/DOT shall be entitled to withhold all or any portion of further payments to Contractor until such time as Mn/DOT is able to determine how much (if any) remains owing to Contractor. Promptly upon such determination, Mn/DOT shall notify Contractor in writing of the amount, if any, that Contractor shall pay Mn/DOT or that Mn/DOT shall pay Contractor with respect thereto. All costs and charges incurred by Mn/DOT, including attorneys’, accountants’ and expert witness fees and costs, together with the cost of completing the Work under the Contract Documents, will be deducted from any moneys due or which may become due to Contractor. If such expense exceeds the sum which would have been payable under the Contract, then Contractor and its Surety(ies) and any Guarantor shall be liable and shall pay to Mn/DOT the amount of such excess.

#### 16.2.2.2	Assurance of Future Performance

It is recognized that if a default under Section 16.1.1(k) or (l) occurs, such event could impair or frustrate Contractor’s performance of the Work. Accordingly, it is agreed that upon the occurrence of any such event, Mn/DOT shall be entitled to request of Contractor, or its successor in interest, adequate assurance of future performance in accordance with the terms and conditions hereof. Failure to comply with such request within 10 Days of delivery of the request shall entitle Mn/DOT to terminate the Contract and to the accompanying rights set forth above. Pending receipt of adequate assurance of performance and actual performance in accordance therewith, Mn/DOT shall be entitled to proceed with the Work with its own forces or with other contractors on a time and material or other appropriate basis, the cost of which will be credited against and deducted from Mn/DOT’s payment obligations hereunder. The foregoing shall be in addition to all other rights and remedies provided by law or equity and such rights and remedies as are otherwise available under the Contract, any Guaranty and Payment and Performance Bond.

#### 16.2.2.3	Alternative to Terminating the Contract and Completing the Work

In lieu of the provisions of this Section 16.2 for terminating the Contract and completing the Work, Mn/DOT may pay Contractor for the parts already done according to the provisions of the Contract Documents and may treat the parts remaining undone as if they had never been included or contemplated by the Contract. No claim under this provision will be allowed Contractor for prospective profits on, or any other compensation relating to, Work uncompleted by Contractor.

#### 16.2.2.4	Termination Deemed to Constitute a Termination for Convenience

If the Contract is terminated for grounds which are later determined not to justify a termination for default, such termination shall be deemed to constitute a termination for convenience pursuant to Section 15.

#### 16.2.2.5	Damages Resulting From Contractor’s Breach or Failure to Perform

If Mn/DOT suffers damages as a result of Contractor’s breach or failure to perform an obligation under the Contract Documents, then Mn/DOT shall be entitled to recovery of such damages from Contractor regardless of whether the breach or failure that gives rise to the damages ripens into an Event of Default.

#### 16.2.2.6	Cumulative Remedies

The exercise or beginning of the exercise by Mn/DOT of any one or more rights or remedies under this Section 16.2 shall not preclude the simultaneous or later exercise by Mn/DOT of any or all other rights or remedies, each of which shall be cumulative.

#### 16.2.2.7	Continued Liability of Contractor and Surety

Contractor, any Guarantor and Surety shall not be relieved of liability for continuing Liquidated Damages on account of a default by Contractor hereunder or by Mn/DOT’s declaration of an Event of Default, or by actions taken by Mn/DOT under this Section 16.2.

## 16.3	Right to Stop Work If Undisputed Payment Is Not Made

Contractor shall have the right to stop Work if Mn/DOT fails to make an undisputed payment due hereunder within 30 Days after receipt of notice of nonpayment. Any such Work stoppage shall be considered a suspension under Section 14.1. Contractor shall not have the right to terminate the Contract for default as the result of any failure by Mn/DOT to make an undisputed payment due hereunder, but Contractor shall have the right to declare a termination for convenience under Section 15 upon meeting the requirements of Section 15.15.

## 16.4	Notice and Opportunity to Cure Other Types of Mn/DOT Breaches

In the event of any breach of the Contract by Mn/DOT other than a failure to make payments to Contractor, Contractor shall provide to Mn/DOT a written notice describing the breach and the opportunity to cure such breach. Mn/DOT shall be entitled to 30 days notice and opportunity to cure any such breach; provided that if such breach is capable of cure but by its nature cannot be cured within 30 days, Mn/DOT shall have such additional period of time as may be reasonably necessary to cure the breach so long as Mn/DOT commences such cure within such 30-day period and thereafter diligently prosecutes such cure to completion. Contractor shall have no right to exercise any remedies to which it may be entitled at law or in equity until the foregoing notice is delivered and the foregoing cure period lapses without cure of the breach.

# 17	DAMAGES

## 17.1	Liquidated Damages and Disincentives

### 17.1.1	Failure to Meet Completion Deadlines

Contractor understands and agrees that if Contractor fails to complete the Work in accordance with the Contract Documents, Mn/DOT will suffer substantial losses and damages. Contractor agrees that it shall be liable for all such losses and damages. Contractor acknowledges and agrees that because of the unique nature of the Project, the fact that it is an essential part of the Minnesota State highway system and the fact that inconvenience to the traveling public will be one of the significant impacts of any completion delay, it is impracticable and extremely difficult to ascertain and determine the actual damages which would accrue to Mn/DOT and the public in the event of Contractor’s failure to achieve Substantial Completion, Intermediate Completion Deadline and/or Final Acceptance by the applicable Completion Deadlines. Therefore, Contractor and Mn/DOT have agreed to stipulate the amount payable by Contractor in the event of its failure to meet a Completion Deadline. Contractor acknowledges and agrees that such Liquidated Damages are intended to compensate Mn/DOT solely for Contractor’s failure to meet the Completion Deadlines, and shall not excuse Contractor from liability from any other breach of Contract requirements, including any failure of the Work to conform to applicable requirements. The fact that Mn/DOT has agreed to accept Liquidated Damages as compensation for its damages associated with any delay in meeting a Completion Deadline shall not preclude Mn/DOT from exercising its other rights and remedies respecting the delay set forth in Section 16.2 other than the right to collect other damages due to the delay, except that Mn/DOT agrees not to exercise such other rights and remedies respecting the delay so long as Contractor diligently performs the Work in accordance with said schedule.

If Contractor fails to achieve Substantial Completion, Final Acceptance, or perform work required to meet and Intermediate Completion Deadline by the applicable Completion Deadline, Contractor agrees to pay Mn/DOT Liquidated Damages in the following amounts:

(a)	$      per Day for Contractor’s failure to achieve Substantial Completion by the Substantial Completion Deadline, until the date Contractor achieves Substantial Completion.

(b)	$      per Day for Contractor’s failure to perform all work required to meet the Intermediate Completion Deadline, until the date Contractor performs all work required to meet the Intermediate Completion Deadline. {Use as applicable}

(c)	$      per Day for Contractor’s failure to perform all work required to meet the Final Acceptance Deadline, until the date the Contractor achieves Final Acceptance.

(d)	$      per Day for Contractor’s failure to meet any specified completion or opening date proposed by the Contractor in the Contractor’s proposal, until the date Contractor performs all Work required to meet the such completion or opening date. {Use as applicable}

(e)	$      per Day for Contractor’s failure to meet any intermediate completion deadline proposed by the Contractor in the Contractor’s proposal, until the date Contractor performs all work required to meet those proposed Intermediate Completion Deadlines or restricted periods. {Use as applicable}

### 17.1.2	Reasonableness of Liquidated Damage Amounts

Contractor understands and agrees that any Liquidated Damages payable in accordance with this Section 17.1 are in the nature of liquidated damages and not a penalty and that such sums are reasonable under the circumstances existing as of the date of execution and delivery of the Contract. Contractor further acknowledges and agrees that Liquidated Damages may be owing even though no Event of Default has occurred.

## 17.2	Offset; Waiver

### 17.2.1	Offset

Mn/DOT shall have the right to deduct any amount owed by Contractor to Mn/DOT hereunder from any amounts owed by Mn/DOT to Contractor.

### 17.2.2	Waiver of Liquidated Damages

Mn/DOT may reduce or waive all or any portion of the Liquidated Damages, in its sole discretion, if the Project is in condition for safe and convenient use by the traveling public.

Permitting or requiring Contractor to continue and finish the Work or any part thereof after a Completion Deadline shall not act as a waiver of Mn/DOT’s right to receive Liquidated Damages hereunder or any rights or remedies otherwise available to Mn/DOT.  Neither by the act of taking over the Work nor by Termination or Default of the Contract shall Mn/DOT forfeit the right to recover Liquidated Damages from the Contractor or the Contractor’s Sureties.

## 17.3	Payment of Liquidated Damages

Liquidated Damages, to the extent not paid as provided in Section 17.2, shall be payable by Contractor to Mn/DOT within 10 Days after Contractor’s receipt of an invoice therefor from Mn/DOT.

# 18	INDEMNIFICATION

## 18.1	Indemnifications by Contractor

### 18.1.1	General Indemnities

Subject to Section 18.1.3, Contractor shall release, indemnify and hold harmless Mn/DOT and its agents, and their respective successors and assigns and their respective shareholders, officers, directors, agents and employees (collectively referred to as the “Indemnified Parties”) from and against any and all claims, causes of action, suits, judgments, investigations, legal or administrative proceedings, penalties, fines, damages, losses, liabilities, costs and expenses, including any injury to or death of persons or damage to or loss of property (including damage to utility facilities), and including attorneys’, accountants’ and expert witness fees and costs, arising out of, relating to or resulting from:

(a)	the breach or alleged breach of the Contract by any Contractor-Related Entity;

(b)	the failure or alleged failure by any Contractor-Related Entity to comply with any applicable Environmental Laws or other Governmental Rules (including Governmental Rules regarding handling, generation, treatment, storage, transportation and disposal of Contaminated Materials) or Governmental Approvals in performing the Work;

(c)	any alleged patent or copyright infringement or other allegedly improper appropriation or use of trade secrets, patents, proprietary information, know-how, copyright rights or inventions in performance of the Work, or arising out of any use in connection with the Project of methods, processes, designs, information or other items furnished or communicated to Mn/DOT or another Indemnified Party pursuant to the Contract; provided that this indemnity shall not apply to any infringement resulting from Mn/DOT’s failure to comply with specific written instructions regarding use provided to Mn/DOT by Contractor;

(d)	the alleged negligent act or omission or willful misconduct of any Contractor-Related Entity;

(e)	any and all claims by any governmental or taxing authority claiming taxes based on gross receipts, purchases or sales, or the use of any property or income of Contractor or any of its Subcontractors or any of their respective agents, officers or employees with respect to any payment for the Work made to or earned by any Contractor-Related Entity;

(f)	any and all stop notices and/or Liens filed in connection with the Work, including all expenses and attorneys’, accountants’ and expert witness fees and costs incurred in discharging any stop notice or Lien, provided that Mn/DOT is not in default in payments owing to Contractor with respect to such Work;

(g)	any spill or release or threatened spill or release of a Contaminated Material [i] attributable to the negligence, willful misconduct or breach of contract by any Contractor-Related Entity, or [ii] which was brought onto the Site by any Contractor-Related Entity; and/or

(h)	the claim or assertion by any contractor of inconvenience, disruption, delay or loss caused by interference by any Contractor-Related Entity with or hindering the progress or completion of work being performed by other contractors as described in Standard Specification 1505, or failure of any Contractor-Related Entity to cooperate reasonably with other contractors in accordance therewith.

### 18.1.2	Design Defects

Subject to Section 18.1.3, Contractor shall release, indemnify and hold harmless the Indemnified Parties from and against any and all claims, causes of action, suits, judgments, investigations, legal or administrative proceedings, penalties, fines, damages, losses, liabilities, costs and expenses, including any injury to or death of persons or damage to or loss of property (including damage to utility facilities), and including attorneys’, accountants’ and expert witness fees and costs, arising out of, relating to or resulting from Errors in the Design Documents, regardless of whether such Errors were also included in the Basic Configuration or RID. Contractor agrees that, because the Basic Configuration and RID are subject to review and modification by Contractor, it is appropriate for Contractor to assume liability for Errors in the completed Project even though they may be related to Errors in the Basic Configuration or RID.

### 18.1.3	Losses Due to Negligence of Indemnified Parties

Contractor’s indemnity obligation under Sections 18.1.1 and 18.1.2 shall not extend to any loss, damage or cost to the extent that such loss, damage or cost was caused by the negligence or willful misconduct of such Indemnified Party or its agents, servants or independent contractors who are directly responsible to such Indemnified Party (in other words, a comparative negligence standard shall apply).

### 18.1.4	Claims by Employees

In claims by an employee of Contractor, a Subcontractor, anyone directly or indirectly employed by them or anyone for whose acts they may be liable, the indemnification obligation under this Section 18.1 shall not be limited by any limitation on the amount or type of damages, compensation or benefits payable by or for Contractor or a Subcontractor under workers’ compensation, disability benefit or other employee benefits laws.

### 18.1.5	Reliance on Contractor’s Performance

Contractor hereby acknowledges and agrees that it is Contractor’s obligation to cause the Project to be designed and to construct the Project in accordance with the Contract Documents and that the Indemnified Parties are fully entitled to rely on Contractor’s performance of such obligation. Contractor further agrees that any review, acceptance and/or approval by Mn/DOT and/or others hereunder shall not relieve Contractor of any of its obligations under the Contract Documents or in any way diminish its liability for performance of such obligations or its obligations to provide indemnities hereunder.

## 18.2	Responsibility of Mn/DOT for Certain Contaminated Materials

### 18.2.1	Pre-Existing Site Contamination

It is recognized that Mn/DOT may assert that certain third persons or parties may rightfully bear the ultimate legal responsibility for any and all Contaminated Materials which may currently be present on the Site. It is further recognized that certain state and federal statutes provide that individuals and firms may be held liable for damages and claims related to Contaminated Materials under such doctrines as joint and several liability and/or strict liability. It is not the intention of the parties that Contractor be exposed to any such liability to the extent arising out of (a) pre-existing Site contamination, whether known or unknown, except as otherwise provided in Section 18.1.1(g), (b) the performance not attributable to the negligence, willful misconduct or breach of contract by any Contractor-Related Entity in the handling of such Contaminated Materials, and/or (c) the activities of any Persons not described in clause (b) above, including Mn/DOT.

The Contractor shall not be entitled to a Change Order for work dealing with Contaminated Materials for which the Contractor has agreed to be responsible as described in Section 18.1.1(g).

### 18.2.2	Generator Number for Hazardous Waste Materials

Except for Contaminated Materials for which Contractor is responsible as described in Section 18.1.1(g) and without contradiction of any assertion by Mn/DOT of third-party liability:

(a)	Contractor shall not be required to execute any hazardous waste manifests as a “generator”; and

(b)	Contaminated Materials encountered in the performance of the Work shall be disposed of, if at all, utilizing an EPA Identification Number or other appropriate legal device obtained by, and carried in the name of, Mn/DOT or another Person designated by Mn/DOT.

## 18.3	No Effect on Other Rights

The foregoing obligations shall not be construed to negate, abridge or reduce other rights or obligations which would otherwise exist in favor of a party indemnified hereunder.

## 18.4	CERCLA Agreement

Without limiting their generality, the indemnities set forth in Section 18.1.1(g) are intended to operate as agreements pursuant to Section 107(e) of the Comprehensive Environmental Response, Compensation and Liability Act, 42 U.S.C. Section 9607(e), to insure, protect, hold harmless and indemnify the Indemnified Parties.

## 18.5	Intent of Indemnity for Breach of Contract

The requirement to provide an indemnity for breach of contract set forth in Section 18.1.1(a) is intended to provide protection to Mn/DOT with respect to third party claims associated with such breach. It is not intended to provide Mn/DOT with an alternative cause of action for damages incurred directly by Mn/DOT with respect to such breach.

# 19	PARTNERING, CLAIMS FOR ADJUSTMENT AND DISPUTES

## 19.1	Partnering {Use if applicable}

The Contractor, Mn/DOT, and stakeholders shall enter into a procedure for Partnering as identified within this Section 19. The use of a third party facilitator is not required.

Within seven Days after NTP1, the Contractor shall arrange a Partnering meeting between the Contractor, Mn/DOT, and key stakeholders. This meeting will establish:

Communication procedures

A dispute resolution process, including the development of a dispute resolution ladder

A partnering checklist to be reviewed at project meetings (if applicable). The checklist should contain items such as quality, communication, issue resolution, team and work relationships, and schedule

The partnering process will continue as part of the regularly scheduled project meetings or at events that require additional partnering sessions. These meetings should include primarily Project-level personnel with frequent visits from both Mn/DOT and Contractor middle management. The meetings should review the partnering checklist and identify actions that need to be escalated up the dispute resolution ladder. All costs associated with partnering shall be incidental.

If the Contractor and Mn/DOT determine that a third party facilitator would enhance the Partnering process, the Contractor shall make all arrangements to hire a Partnering facilitator and provide a suitable meeting location for the workshops. The length of time devoted to the workshop, along with the content for the workshop, will be determined by a cooperative effort between the Contractor and Mn/DOT. Mn/DOT and the Contractor will mutually select the Partnering facilitator. All costs associated with the Partnering workshops using a Partnering facilitator will be shared equally between Mn/DOT and the Contractor. No additional allowance will be provided to the Contractor for the cost associated with paying these bills and submitting the bills to Mn/DOT for later partial reimbursement.

## 19.1	Partnering {Use if applicable}

Partnering will be required on this Contract. Tom Warne will be the Partnering Facilitator. The partnering process will include Mn/DOT, Contractor, its Subcontractors, FHWA and other stakeholders, where appropriate. The partnering relationship will be structured to draw on the strengths of each organization to identify and achieve reciprocal goals. The objectives include effective and efficient Project performance and completion on schedule, within budget and in accordance with the Contract Documents.

### 19.1.1	Partnering Participants

This Contract will require a full-time partnering effort involving Executive Management, Project Management, Project Task Force and others. Participation is required by the agencies involved. Partnering between Mn/DOT and Contractor has proven to improve the probability of meeting each party’s Project goals. The parties shall attempt to resolve disputes through partnering between appropriate representatives of Mn/DOT and Contractor (including, where appropriate, any Subcontractor) at the following levels:

(a)	Project Task Force Teams

1.	Mn/DOT chief inspectors and project engineers/supervisors

2.	Contractor’s and subcontractors’ project supervisors and technical area supervisors

3.	Utilities and other third parties

4.	Permitting and government agencies

(b)	Project Management Team

1.	Mn/DOT’s Project Manager, deputy project managers

2.	Project manager, deputy project managers and design manager

3.	Utilities and other third parties

4.	Permitting and government agencies

(c)	Executive Management Team

1.	Mn/DOT’s Project Manager, Assistant District Engineer, and other Mn/DOT staff as needed.

2.	Contractor and major subcontractor management

3.	FHWA Division Administration

Team members at each level will be established at the Initial Partnering Meeting. The levels listed above are meant to be broad descriptions of the required levels needed for effective issue resolution.  Additional levels or specific task force teams can be added, as appropriate.

To resolve issues in a timely and effective manner, representatives of the parties shall meet regularly and explore resolution for each issue at the lowest level possible (i.e., Project Task Force Team first, Project Management Team next, and Executive Management Team last). If both parties determine, in good faith, that effective resolution is not possible at the current level, then the issue will be elevated to the next level in the partnering process. If both parties make such a determination during partnering at the Executive Management Team level, then the dispute will be elevated in accordance with Section 19.2.

### 19.1.2	Partnering Workshops

#### 19.1.2.1  	Initial Partnering Meeting

The initial partnering meeting will occur within 30 Calendar Days of NTP1. This meeting will be facilitated by the Partnering Facilitator. At this session, all representatives from each party at each level shall attend. The participants will develop the teams at each level, develop the list of goals for the Project, establish a dispute resolution ladder and process, and develop project goals evaluation tools.

#### 19.1.2.2  	Project Goals Evaluation

The Project Goals determined at the initial partnering meeting will be evaluated on a monthly basis. This evaluation will be sent to participants at all levels in the Partnering Process. The evaluation will ask each participant to rate how effective the teams are in meeting each of the project goals. The rating system will be determined by the parties in conjunction with the Partnering Facilitator. Space will be provided on the evaluation form to allow participants to include additional written comments and details about the effectiveness of meeting the project goals. The evaluations will be submitted, compiled and the results distributed by the Partnering Facilitator. The participants will determine whether the evaluations will be anonymous at the initial partnering meeting.

#### 19.1.2.3  	Project Task Force Team Meetings

Informal partnering sessions without the facilitator will be required frequently during the duration of the Project at the Project Task Force level. These sessions will involve members of the Project Task Force teams and/or members of the Project Management teams. These sessions can be in the form of weekly Project update meetings or field reviews by team members. The goal of these meetings should not only provide an update on the Project, but include discussions on Quality, Communication, Issue Resolution, Team and Work Relationships, and Schedule. Each meeting should review outstanding issues discussed at previous partnering sessions.

#### 19.1.2.4  	Project Task Force Team Meetings

Informal partnering sessions without the facilitator will be required frequently during the duration of the Project at the Project Management level.  These sessions will involve members of the Project Management teams.  These sessions can be in the form of weekly Project update meetings or field reviews by team members.  The agenda of these meetings shall include discussion of issues that have been agreed to be raised from the Project Task Force Team level. These meetings should not only provide an update on the Project, but include discussions on Safety, Quality, Communication, Issue Resolution, Team and Work Relationships, and Schedule. Each meeting should review outstanding issues discussed at previous partnering sessions.

#### 19.1.2.5  	Executive Management Team Meetings

Formal partnering sessions at the Executive Management level without the facilitator will be held monthly during the duration of the Project. These sessions will involve members of the Executive Management teams. The Agenda for these will be agreed upon by both parties prior to each meeting.  The Agenda for each meeting shall include discussion of issues that have been agreed to be raised from the Project Management Team level. The goal of these meetings should not only provide an update on the Project, but include discussions on Safety, Quality, Communication, Issue Resolution, Team and Work Relationships, and Schedule. Each meeting will review outstanding issues discussed at previous partnering sessions.  Each meeting will also include a review and discussion of the monthly project goals evaluations.

#### 19.1.2.6  	Quarterly Partnering Workshops

Formal facilitated partnering workshops will be conducted at quarterly intervals throughout the Project and at the times of critical events (as agreed upon by each party). The workshops will include all Project Task Force, Project Management and Executive Management Teams. The partnering workshops will include the Partnering Facilitator to guide the partnering process.

Each partnering session will review the major topics related to the Project.  Topics should include: Quality, Communication, Issue Resolution, Team and Work Relationships, Schedule and any other topics that the teams feel are important to the success of the Project. Each meeting will also include a review and discussion of the monthly project goals evaluations. The Partnering Facilitator will prepare minutes of the meetings and circulate for comments, revisions, and/or approval of all parties.

Both Mn/DOT and the Contractor will submit agenda items to the facilitator in advance of each quarterly partnering workshop.   The agenda shall generally include the following:

(a)	Opening remarks by Mn/DOT, FHWA and Contractor Executive Management.

(b)	A description by Contractor of Work accomplished since the last meeting, current status of the current Monthly Progress Update, schedule for future Work, potential issues and status of past issues.

(c)	Discussion by Mn/DOT of the Work schedule as Mn/DOT views it, potential issues, and status of past issues.

(d)	Review of monthly project goals evaluations.

(e)	Discussion regarding the major topics on the Agenda or raised at the meeting.

(f)	Setting date for next meeting.

All issues discussed during the Partnering Workshop shall be documented in the minutes. Any issue not resolved at the Workshop shall have an agreed-upon issue resolution timeline. For each of these issues identified for resolution, the participants from each affected party required to resolve the issue and the schedule to resolve the issue will be determined and recorded to ensure the issue is resolved in an effective and timely manner. These participants will report on the issue resolution at the next quarterly partnering workshop.

## 19.2	Disputes

This Section 19 shall not preclude the Contractor from notifying Mn/DOT in writing, of issues or potential issues as those issues come up.

## 19.3	Costs

See Section 19.1.

## 19.4	Claims for Compensation Adjustment and Disputes

If issue resolution efforts through Partnering are not successful, disputes shall be resolved through DBS-1517 and Standard Specification 1517.

# 20	ACCEPTANCE OF PROJECT

## 20.1	Substantial Completion

### 20.1.1	Notice by Contractor

Contractor shall provide written notice to Mn/DOT when all of the following have occurred with respect to the Project:

(a)	Contractor has completed all Work (except for Punch List items and other items only included in the requirements for Final Acceptance);

(b)	Contractor has ensured that the Work has been performed in accordance with the requirements of the Contract Documents;

(c)	Contractor has received all applicable Governmental Approvals required for Project use;

(d)	Contractor has furnished to Mn/DOT certifications from Contractor’s Design Manager, in form and substance satisfactory to Mn/DOT, certifying conformity of the Design Documents with the requirements of the Contract Documents;

(e)	Contractor has furnished to Mn/DOT certifications from Contractor’s Project Manager, in form and substance satisfactory to Mn/DOT, certifying conformity of the construction with the Design Documents;

(f)	Contractor has furnished to Mn/DOT certifications from Contractor’s Construction Quality Manager, in form and substance satisfactory to Mn/DOT, certifying that there are no outstanding nonconformances other than those identified on the Punch List;

(g)	Contractor has ensured that the Project may be used without damage to the Project or any other property on or off the Site, and without injury to any Person;

(h)	Contractor has obtained all applicable third party approvals relating to the Work (including Utility Owners as required under any applicable utility agreements and Section 6 of Book 2), and all third parties have completed all work that involves obligations by Contractor (including Utility Owners under any utility agreements and Section 6 of Book 2);

(i)	Contractor has ensured that the Project is fully opened to traffic and that no further work is required which would involve any lane or shoulder closure except for the following:  Nighttime lane closures in accordance with Book 2, Section 18 may be allowed, at Mn/DOT’s sole discretion, for Punch List, bridge and retaining wall painting, maintenance, final cleanup and turf establishment items.  Shoulder closures may be allowed (except on weekdays from 6 a.m. to 9 a.m. and 3 p.m. to 6 p.m.), at Mn/DOT’s sole discretion, for Punch List, bridge and retaining wall painting, maintenance, final cleanup and turf establishment items; and

(j)	Quality Manager certifies Work is completed in accordance with the requirements.

### 20.1.2	Correction of Defects

Upon receipt of Contractor’s notice under Section 20.1.1, Mn/DOT will conduct such inspections, surveys and/or testing as Mn/DOT deems desirable. If such inspections, surveys and/or tests disclose that any Work does not meet the requirements of the Contract Documents, Mn/DOT will promptly advise Contractor as to Nonconforming Work (including incomplete Work) necessary to be corrected as a condition to Substantial Completion, Nonconforming Work (including incomplete Work) which may be corrected as Punch List items and/or whether Contractor shall reassess the accuracy and completeness of its notice. Upon correction of the Nonconforming Work (including incomplete Work) identified as a prerequisite to Substantial Completion, Contractor shall provide written notification to Mn/DOT and Mn/DOT will conduct additional inspections, surveys and/or tests as Mn/DOT deems desirable. This procedure shall be repeated until Mn/DOT finds that all prerequisites to Substantial Completion have been met.

### 20.1.3	Notice of Substantial Completion

Mn/DOT will issue a Notice of Substantial Completion at such time as:

(a)	Mn/DOT determines that all conditions set forth in Section 20.1.1 have been satisfied;

(b)	Mn/DOT determines that all Nonconforming Work (including incomplete Work) identified as prerequisites to Substantial Completion has been corrected; and

(c)	Contractor prepared and Mn/DOT Approved a Punch List.

## 20.2	Final Acceptance

### 20.2.1	Conditions to Final Acceptance

#### 20.2.1.1	Performance of Work after Substantial Completion

Promptly after Substantial Completion has occurred, Contractor shall perform all Work, if any, which was deferred for purposes of Substantial Completion, and shall satisfy all of its other obligations under the Contract Documents, including ensuring that the Project has been completed and all components have been properly adjusted and tested.

#### 20.2.1.2	Conditions to Affidavit of Final Completion

Contractor shall provide to Mn/DOT an executed sworn Affidavit of Final Completion in accordance with Section 20.2.1.3 when all of the following have occurred:

(a)	all requirements for Substantial Completion have been fully satisfied;

(b)	Mn/DOT has received all Released for Construction Documents, Design Documents, As-Built Documents, right-of-way record maps, surveys, material certifications, test data and other deliverables required under the Contract Documents;

(c)	all special tools, equipment, furnishings and supplies purchased by and/or used by Contractor as provided in the Contract Documents have been delivered to Mn/DOT and all replacement spare parts have been purchased and delivered to Mn/DOT free and clear of Liens;

(d)	all of Contractor’s and Subcontractors’ personnel, supplies, equipment, waste materials, rubbish and temporary facilities have been removed from the Site, Contractor has restored and repaired all damage or injury arising from such removal to the satisfaction of Mn/DOT and the Site is in good working order and condition;

(e)	Contractor has furnished to Mn/DOT certifications from Contractor’s Design Manager, in form and substance satisfactory to Mn/DOT, certifying conformity of the Design Documents with the requirements of the Contract Documents;

(f)	Contractor has furnished to Mn/DOT certifications from Contractor’s Project Manager, in form and substance satisfactory to Mn/DOT, certifying conformity of the construction with the Design Documents;

(g)	Contractor has furnished to Mn/DOT certifications from Contractor’s Construction Quality Manager, in form and substance satisfactory to Mn/DOT, certifying that there are no outstanding nonconformances;

(h)	Contractor has delivered to Mn/DOT a notice of completion for the Project in recordable form and meeting all statutory requirements;

(i)	the Punch List items have been completed to the satisfaction of Mn/DOT; and

(j)	all of Contractor’s other obligations under the Contract Documents (other than obligations which by their nature are required to be performed after Final Acceptance as determined by Mn/DOT) have been satisfied in full or waived in writing by Mn/DOT.

(k)	Contractor has identified a single point of contact to address the Warranty requirements of Section 21 throughout the duration of the Project Warrranty term.

#### 20.2.1.3	Requirements of Affidavit of Final Completion

The Affidavit of Final Completion referred to in Section 20.2.1.2 shall include the following statement:

To the best of Contractor’s knowledge and belief, the Work under the Contract has been completed in strict accordance with the Contract Documents, no lawful debts for labor or materials are outstanding and no federal excise tax has been included in the Contract Price; all requests for funds for undisputed work under the Contract, including changes in the Work, and under all billings of whatsoever nature are accurate, complete and final and no additional compensation over and above the final payment will be requested or is due under the Contract or under any adjustment issued thereunder for said undisputed work; there are no outstanding claims, Liens or stop notices relating to the Project, including claims by Utility Owners; there is no existing default by Contractor under any Utility Agreement, and no event has occurred which, with the passing of time or giving of notice or both, would lead to a claim relating to the Work or event of default under any Utility Agreement; and upon receipt of final payment, Contractor and Subcontractors acknowledge that Mn/DOT and any and all employees of Mn/DOT and their authorized representatives will thereby be released, discharged and acquitted from any and all claims or liability for additional sums on account of undisputed work performed under the Contract.

If Contractor is unable to provide the affidavit in the above form, the affidavit shall certify that all such outstanding matters are set forth in an attached list which shall describe the outstanding matters in such detail as may be requested by Mn/DOT. The affidavit shall include a representation of Contractor that it is diligently and in good faith contesting all such matters by appropriate legal proceedings and shall provide a status report regarding the same including an estimate of the maximum payable with respect to each such matter.

### 20.2.2	Inspection and Issuance of Notice of Final Acceptance

Upon Mn/DOT’s receipt of the Affidavit of Final Completion, Mn/DOT will make final inspection and Mn/DOT will either issue a Notice of Final Acceptance or notify Contractor regarding any Work remaining to be performed. If Mn/DOT fails to issue a Notice of Final Acceptance, Contractor shall promptly remedy the defective and/or uncompleted portions of the Work. Thereafter, Contractor shall provide to Mn/DOT a revised Affidavit of Final Completion with a new date based on when the defective and/or uncompleted portions of the Work were corrected. The foregoing procedure shall apply successively thereafter until Mn/DOT has issued a Notice of Final Acceptance.

### 20.2.3	Overpayments; No Relief from Continuing Obligations

Final Acceptance will not prevent Mn/DOT from correcting any measurement, estimate or certificate made before or after completion of the Work, or from recovering from Contractor, the Surety(ies) and/or any Guarantor, the amount of any overpayment sustained due to failure of Contractor to fulfill the obligations under the Contract. A waiver on the part of Mn/DOT of any breach by Contractor shall not be held to be a waiver of any other or subsequent breach. Final Acceptance shall not relieve Contractor from any of its continuing obligations hereunder, or constitute any assumption of liability by Mn/DOT.

## 20.3	Opening of Sections of Project to Traffic

### 20.3.1	Plan for Opening to Traffic

The Contract Schedule shall set forth Contractor’s plan for completing sections of the Project and opening them to traffic. Mn/DOT may request that Contractor expedite certain sections of the Project, and Contractor shall accommodate such requests to the extent that it can do so without significant disruption to its schedule or a significant increase in its costs. Notwithstanding the foregoing, if Mn/DOT orders Contractor to open portions of the Project which cannot be accommodated without significant disruption to Contractor’s schedule or a significant increase in Contractor’s costs, such direction shall be considered a Mn/DOT-Directed Change.

### 20.3.2	Direction to Open Following Contractor Failure to Perform

If Contractor is delinquent in completing shoulders, drainage structures or other features of the Work, Mn/DOT may, but is not obligated to, order all or a portion of the Project opened to traffic notwithstanding such incomplete elements. Contractor shall then conduct the remainder of the construction operations, minimizing obstruction to traffic. Except as provided in Section 20.3.1, Contractor shall not receive any added compensation due to the added costs attributable to the opening of the Project to traffic.

### 20.3.3	No Waiver

Opening of portions of the Project prior to Final Acceptance does not constitute Acceptance of the Work or a waiver of any provisions of the Contract Documents.

## 20.4	Assignment of Causes of Action

Contractor hereby offers and agrees to assign to Mn/DOT all rights, title and interest in and to all causes of action it may have under Section 4 of the Clayton Act (15 U.S.C. Section 15), arising from purchases of goods, services or materials pursuant to the Contract or any Subcontract. This assignment shall be made and become effective at the time Mn/DOT tenders final payment to Contractor, without further acknowledgment by the parties.

# 21	WARRANTIES

## 21.1	Warranties by Contractor

### 21.1.1	Project Warranties

Contractor warrants that:

(a)	all design Work furnished pursuant to the Contract Documents shall conform to all professional engineering principles generally accepted as standards of the industry in the State;

(b)	the Project shall be free of defects (including design defects except to the extent that such defects are inherent in prescriptive specifications included in the Contract Documents, unless (i) Contractor has actual or constructive knowledge of such defects and (ii) Contractor fails to request a change thereto by Mn/DOT);

(c)	materials and equipment furnished under the Contract Documents shall be of good quality and, when installed, shall be new;

(d)	the Work shall meet all of the requirements of the Contract Documents;

(e)	the specifications and/or drawings selected or prepared for use during construction are appropriate for their intended use; and

(f)	the Project shall be fit for use for the intended function.

### 21.1.2	Project Warranty Term

The Warranty term shall commence upon Substantial Completion or, if earlier, upon final acceptance of specific elements of the Project by a third party owner. Subject to extension under Section 21.2 and notwithstanding any shorter warranty term for specific Project elements that may be set forth elsewhere in the Contract Documents, the Warranty shall remain in effect until three years after Substantial Completion. If Mn/DOT determines that any of the Work has not met the standards set forth in this Section 21.1 at any time within the Warranty period, then Contractor shall correct such Work as specified below, even if the performance of such corrective work extends beyond the stated warranty period.

### 21.1.3	Additional Warranty Requirements

Additional Warranty requirements are set forth in Exhibit C.

### 21.1.4	Corrective Work

Mn/DOT and Contractor shall conduct a walkthrough of the Site together at least one time per year prior to the expiration of the Warranty period.  On each walkthrough, Mn/DOT will produce a punch list of items requiring Warranty Work. In addition, Mn/DOT reserves the right at any time during the Warranty period to identify Work that fails to meet the warranty.

Contractor may also monitor the Site using non-destructive testing for any Warranty Work required during the Warranty period. Contractor shall provide advance notification to Mn/DOT of all monitoring dates and times.

Mn/DOT will notify Contractor of any failure of any of the Work that is Contractor’s, or any Subcontractor’s, responsibility to correct under the terms of the Warranty. Contractor shall correct any areas which exceed the warranty threshold limits established for the Project. Mn/DOT may require corrective actions at any time within the Warranty period, or defer corrective action until the end of the initial Warranty period.

For all corrective actions required, Contractor shall provide a written proposal for performing Warranty Work within 10 Working Days from receiving notification from Mn/DOT that corrective work is required.  Contractor shall also provide a written proposal for performing the corrective Work if Contractor elects to perform this Work based on Contractor’s assessment of the Site.

The proposal shall include, as a minimum:

(a)	The proposed construction remedy

(b)	The proposed schedule for prosecution and completion of the Work

(c)	The proposed traffic management plan

Mn/DOT shall respond as to the adequacy and suitability of the proposal within 10 Working Days of the date of Contractor’s submittal.  Mn/DOT may agree to Accept Nonconforming Work in accordance with Section 5.7.2.

During the Warranty period, Contractor will not be held responsible for distresses caused by identifiable factors unrelated to materials and workmanship. Upon written request from Contractor and on a case-by-case basis, Mn/DOT will consider other factors that appear to be beyond the control of Contractor and may relieve Contractor from its Warranty obligations with respect thereto.

Contractor shall commence corrective action Work within 30 Calendar Days after notice by Mn/DOT of Acceptance of the written plan for warranty correction. If the Work cannot be started then because of seasonal limitations, Contractor must so notify Mn/DOT and submit (for Mn/DOT approval) a schedule for completion of the corrective action Work. If Contractor does not use its best efforts to proceed to effectuate that corrective action Work within the agreed time, or if Contractor and Mn/DOT fail to reach such an agreement, Mn/DOT, after notice to Contractor, shall have the right to perform or have performed by third parties the necessary remedy, and the costs thereof shall be borne by Contractor. The Contractor shall be responsible for the inspection and testing of the Warranty Work.

If Mn/DOT determines that emergency repairs are necessary for public safety, Mn/DOT may perform the corrective Work. Any such emergency repairs will be authorized by Mn/DOT’s Project Manager, or his/her representative. Prior to making the emergency repairs, Mn/DOT will document the basis for the emergency action, and will preserve evidence, such as photographs or videotapes, of the defective condition. Emergency repairs will be coordinated with Contractor when possible. All costs associated with the emergency repairs that are covered by the Warranty Work shall be borne by Contractor.

### 21.1.5	Costs of Correction of Work

All costs of correcting such rejected Work, including additional testing and inspections, shall be deemed included in the Contract Price. Contractor shall reimburse Mn/DOT and pay Mn/DOT’s expenses made necessary thereby within 10 Days after Contractor’s receipt of invoice therefor. Contractor shall be responsible for obtaining any required Governmental Approvals or other consents from any other Person in connection with the Warranty Work.

## 21.2	Warranty of Corrected Work

The Warranties shall apply to all Work redone, repaired, corrected or replaced pursuant to the terms of the Contract. The Warranties as to each redone, repaired, corrected or replaced element of the Work shall extend beyond the original warranty period if necessary to provide at least a one-year warranty period following Acceptance thereof by Mn/DOT or acceptance thereof by the appropriate Person who will own such element.

## 21.3	Subcontractor Warranties

### 21.3.1	Assignment

Without in any way derogating Contractor’s own representations and warranties (including the Warranties) and other obligations with respect to all of the Work, Contractor shall obtain from all Subcontractors and cause to be extended to Mn/DOT, appropriate representations, warranties, guarantees and obligations with respect to the design, materials, workmanship, equipment, tools and supplies furnished by such Subcontractors, including all such representations, warranties, guarantees and obligations required to be furnished by Subcontractors under Book 2. All representations, warranties, guarantees and obligations of Subcontractors (a) shall be written so as to survive all Mn/DOT and Contractor inspections, tests and approvals, and (b) shall run directly to and be enforceable by Contractor and/or Mn/DOT and their respective successors and assigns. Contractor hereby assigns to Mn/DOT all of Contractor’s rights and interest in all extended warranties for periods exceeding the applicable Warranty period which are received by Contractor from any of its Subcontractors.

### 21.3.2	Enforcement

Upon receipt from Mn/DOT of notice of a failure of any of the Work to satisfy any Subcontractor warranty, representation, guarantee, or obligation, Contractor shall enforce or perform any such representation, warranty, guarantee or obligation, in addition to Contractor’s other obligations hereunder. Mn/DOT’s rights under this Section 21.3.2 shall commence at the time such representation, warranty, guarantee or obligation is furnished, and shall continue until the expiration of Contractor’s relevant Warranty (including extensions thereof under Section 21.2). Until such expiration, Contractor shall be responsible for the cost of any equipment, material, labor (including re-engineering) or shipping, and Contractor shall be required to replace or repair defective equipment, material or workmanship furnished by any Subcontractor.

## 21.4	No Limitation of Liability

The foregoing warranties are in addition to all rights and remedies available under the Contract Documents or applicable law, and shall not limit Contractor’s liability or responsibility imposed by the Contract Documents or applicable law with respect to the Work, including liability for design defects, latent construction defects, strict liability, negligence or fraud; provided, however, that, upon expiration of the Warranties, Contractor shall have no further liability to Mn/DOT hereunder for patent construction defects.

## 21.5	Warranty Beneficiaries

In addition to benefiting Mn/DOT and its successors and assigns, the Warranties and Subcontractor warranties provided under this Section 21 shall inure to the benefit of, and shall be directly enforceable by, any local agencies and Utility Owners with respect to those portions of the Work owned or controlled by each such Person.

## 21.6	Remedies for Breach of Warranty

In addition to Mn/DOT’s other rights and remedies hereunder, at law or in equity, Contractor shall be liable for actual damages resulting from any breach of an express or implied warranty or any defect in the Work.

## 21.7	Disputes

Any disagreement between Mn/DOT and Contractor relating to this Section 21 shall be subject to the dispute resolution provisions contained in Section 19, provided that Contractor shall proceed as directed by Mn/DOT pending resolution of the dispute.

# 22	DOCUMENTS AND RECORDS

## 22.1	Escrowed Proposal Documents

Contractor shall submit the escrowed proposal documents (EPD) to Mn/DOT’s Central Office (395 John Ireland Boulevard, St. Paul, MN 55155) in a container suitable for sealing no later than 10 Calendar Days following Award of the Contract by Mn/DOT.

The container shall be clearly marked "Bid Documentation" and shall have entered on the face of the container, Contractor's name, the date of submittal, and the State Project Number. Failure to submit the EPD may result in cancellation of the Award, in which case Mn/DOT will retain the Proposal Bond.

Upon receipt of the EPD, authorized representatives of Mn/DOT and Contractor will review the EPD for accuracy and completeness. Should a discrepancy exist, Contractor shall furnish Mn/DOT with any other needed bid documentation within three Working Days. Mn/DOT, upon determining that the EPD appear to be complete, will immediately place the EPD and affidavit in the container in the presence of Contractor's representative, and seal it.

Mn/DOT will retain the EPD for placement in a safety deposit box, vault or other secure accommodation. The cost of accommodation will be borne by Mn/DOT. Payment for compilation of the data, container, cost of verification of the EPD or any other costs that may be incurred by Contractor in fulfilling these requirements shall be considered incidental to the Contract. The EPD will be returned to the Contractor following final acceptance by .

### 22.1.1	Review of EPD

The EPD shall be available during business hours for joint review by Contractor and Mn/DOT in connection with the resolution of Disputes, an audit under Section 22.3.5 (if the EPD are the subject of an audit) and as described in Section 22.1.6. Subject to Section 22.1.7, Mn/DOT shall be entitled to review all or any part of the EPD in order to satisfy itself regarding the applicability of the individual documents to the matter at issue and shall be entitled to make and retain copies of such documents as it deems appropriate in connection with any such matters. The foregoing shall in no way be deemed a limitation on Mn/DOT’s discovery rights with respect to such documents.

### 22.1.2	Property of Contractor

The EPD are, and shall always remain, the property of Contractor, and shall be considered to be in Contractor’s possession, subject to Mn/DOT’s right to review the EPD as provided herein. Mn/DOT acknowledges that Contractor considers that the EPD constitute trade secrets or proprietary information. This acknowledgment is based upon Mn/DOT’s understanding that the information contained in the EPD are not known outside Contractor’s business, is known only to a limited extent and by a limited number of employees of Contractor, is safeguarded while in Contractor’s possession, and may be valuable to Contractor’s business strategies, assumptions and intended means, methods and techniques. Mn/DOT further acknowledges that Contractor expended money in developing the information included in the EPD and further acknowledges that it would be difficult for a competitor to replicate the information contained therein. Mn/DOT acknowledges that the EPD and the information contained therein are being provided to Mn/DOT only because it is an express prerequisite to award of the Contract.

### 22.1.3	Representation and Warranty

Contractor represents and warrants that the EPD provided concurrently with the Proposal constitute all of the information used in the preparation of its Proposal and agrees that no other Proposal preparation information will be considered in resolving Disputes or Claims. Contractor also agrees that the EPD are not part of the Contract and that nothing in the EPD shall change or modify the Contract.

### 22.1.4	Contents of EPD

The EPD provided with the Proposal shall, at a minimum, clearly detail how the components of the Proposal Price were determined and shall be adequate to enable a complete understanding and interpretation of how Contractor arrived at the Proposal Price. The EPD provided in connection with quotations and Change Orders shall, at a minimum, clearly detail how the total price and individual components of that price were determined and shall be adequate to enable a complete understanding and interpretation of how Contractor arrives at its quotation and/or Change Order price. All Work shall be separated into subitems as required to present a complete and detailed estimate of all costs. Crews, equipment, quantities and rates of production shall be detailed. Estimates of costs shall be further divided into Contractor’s usual cost categories such as direct labor, repair labor, equipment ownership and operation, expendable materials, permanent materials and subcontract costs as appropriate. Plant and equipment and indirect costs shall also be detailed in Contractor’s usual format. Contractor’s allocation of plant and equipment, indirect costs, contingencies, mark-up and other items to each direct cost item shall be clearly identified. The EPD shall itemize the estimated costs of the Payment and Performance Bond and the insurance premiums for each coverage required to be provided by Contractor under Section 9. The EPD shall include all assumptions, quantity takeoffs, rates of production, Contractor internal equipment rental rates and progress calculations, quotes from Subcontractors (including Suppliers), memoranda, narratives and all other information used by Contractor to arrive at the Proposal Price or Change Order price, as applicable. For each item of Work, the EPD shall itemize any related amounts not included in the stated price for such item such as any amount allocated for contingency.

### 22.1.5	Format of EPD

Contractor shall submit the EPD in the format actually used by Contractor in preparing its Proposal. It is not intended that Contractor perform any significant extra work in the preparation of these documents. However, Contractor represents and warrants that the EPD related to the Proposal have been personally examined prior to delivery to Mn/DOT by an authorized officer of Contractor and that they meet the requirements of Section 22.1.4 and are adequate to enable a complete understanding and interpretation of how Contractor arrived at its Proposal Price. Contractor further represents, warrants and covenants that the EPD related to each Change Order will be personally examined prior to delivery to escrow by an authorized officer of Contractor and that they meet the requirements of Section 22.1.4 and will be adequate to enable a complete understanding and interpretation of how Contractor arrived at its Change Order price.

### 22.1.6	Review by Mn/DOT

Mn/DOT may, at any time, conduct a review of the EPD to determine whether it is complete. If Mn/DOT determines that the EPD are incomplete, Mn/DOT may request Contractor to supply data to make the EPD complete. Contractor shall provide all such data within three Working Days of the request, and at that time it will be date stamped, labeled to identify it as supplementary EPD information and added to the EPD. Contractor shall have no right to add documents to the EPD except upon Mn/DOT’s request. At Mn/DOT’s option, which may be exercised at any time, the EPD associated with any Change Order or contract amendment shall be reviewed, organized and indexed as described in ITP Section 6.1.

### 22.1.7	Confidentiality Agreement

At Contractor’s request, confidentiality agreements prepared by Mn/DOT in Mn/DOT’s sole discretion shall be executed and delivered to Contractor by Mn/DOT’s employees or agents who review or have access to the EPD.

## 22.2	Subcontractor Pricing Documents

Contractor shall require each Subcontractor of a Subcontract over $50,000 and each permanent pavement marking Subcontractor to submit to Contractor a copy of all documentary information used in determining its Subcontract price, immediately prior to executing the Subcontract or change orders or amendments thereto, to be held in the same manner as the EPD and which shall be accessible by Contractor, Mn/DOT, and other dispute resolvers, on terms substantially similar to those contained herein. Each such Subcontract shall include a representation and warranty from the Subcontractor stating that its EPD constitutes all the documentary information used in establishing its Subcontract price. Each Subcontract that is not subject to the foregoing requirement shall include a provision that requires the Subcontractor to preserve all documentary information used in establishing its Subcontract price and to provide such documentation to Contractor and/or Mn/DOT in connection with any claim made by such Subcontractor.

## 22.3	Project Records

### 22.3.1	Maintenance of Records

Contractor shall maintain at Contractor’s Project Manager's office in the State a complete set of all books, records and documents prepared or employed by Contractor with respect to the Project.

### 22.3.2	Audit and Inspection Rights

Contractor grants to Mn/DOT, FHWA, the U.S. Comptroller General and Utility Owners, and their respective authorized representatives, such audit and inspection rights and allows such Persons such access to and the right to copy such books and records (including all tax returns and supporting documentation filed with any Governmental Persons) as such Persons may request from time to time in connection with the issuance of Change Orders, the resolution of disputes, and such other matters as such Persons reasonably deems necessary for purposes of complying or verifying compliance with the Contract and Governmental Rules.

### 22.3.3	Audit of Time and Materials Work

Where the payment method for any Work is on a time and materials basis, such examination and audit rights shall include all books, records, documents and other evidence and accounting principles and practices sufficient to reflect properly all direct and indirect costs of whatever nature claimed to have been incurred and anticipated to be incurred for the performance of such Work. If an audit indicates Contractor has been overcredited under a previous progress report or progress payment, that overcredit will be credited against current progress reports or payments.

### 22.3.4	Change Order Pricing Data

For cost and pricing data submitted in connection with pricing Change Orders, unless such pricing is based on adequate price competition, established catalog or market prices of commercial items sold in substantial quantities to the public, or prices set by law or regulation, such Persons and their representatives have the right to examine all books, records, documents and other data of Contractor related to the negotiation of or performance of Work under such Change Orders for the purpose of evaluating the accuracy, completeness and currency of the cost or pricing data submitted. The right of examination shall extend to all documents deemed necessary by such Persons to permit adequate evaluation of the cost or pricing data submitted, along with the computations and projections used therein.

### 22.3.5	Claims Audits

All Claims filed against Mn/DOT shall be subject to audit at any time following the filing of the Claim. The audit may be performed by employees of Mn/DOT or by an auditor under contract with Mn/DOT. No notice is required before commencing any audit before 60 Days after Final Acceptance. Thereafter, Mn/DOT shall provide 20 Days notice to Contractor, any Subcontractors or their respective agents before commencing an audit. Contractor, Subcontractors or their agents shall provide adequate facilities, acceptable to Mn/DOT, for the audit during normal business hours. Contractor, Subcontractors and their agents shall cooperate with the auditors. Failure of Contractor, Subcontractors or their agents to maintain and retain sufficient records to allow the auditors to verify all or a portion of the Claim or to permit the auditors access to the books and records of Contractor, Subcontractors or their agents shall constitute a waiver of the claim and shall bar any recovery thereunder. At a minimum, the auditors shall have available to them the following documents:

(a)	Daily time sheets and supervisor’s daily reports;

(b)	Union agreements;

(c)	Insurance, welfare and benefits records;

(d)	Payroll registers;

(e)	Earnings records;

(f)	Payroll tax forms;

(g)	Material invoices and requisitions;

(h)	Material cost distribution worksheet;

(i)	Equipment records (list of company equipment, rates, etc.);

(j)	Subcontractors’ (including Suppliers) and agents’ invoices;

(k)	Subcontractors’ and agents’ payment certificates;

(l)	Canceled checks (payroll and Suppliers);

(m)	Job cost report;

(n)	Job payroll ledger;

(o)	General ledger;

(p)	Cash disbursements journal;

(q)	e-mail, letters and correspondence;

(r)	network servers, data storage devices, backup media;

(s)	All documents that relate to each and every Claim together with all documents that support the amount of damages as to each Claim; and

(t)	Work sheets used to prepare the Claim establishing the cost components for items of the Claim including labor, benefits and insurance, materials, equipment, Subcontractors, all documents that establish the time periods, individuals involved, the hours for the individuals and the rates for the individuals.

Full compliance by Contractor with the provisions of this Section 22.3.5 is a contractual condition precedent to Contractor’s right to seek relief under Section 19. Contractor represents and warrants the completeness and accuracy of all information it or its agents provides in connection with this Section 22.3.

## 22.4	Retention of Records

Contractor shall maintain indefinitely, unless otherwise notified by Mn/DOT, all records and documents relating to the Contract (including copies of all original documents delivered to Mn/DOT) . If Approved by Mn/DOT, photographs, microphotographs or other authentic reproductions may be maintained instead of original records and documents. Contractor shall notify Mn/DOT where such records and documents are kept.

Notwithstanding the foregoing, all records which relate to Claims being processed or actions brought under the dispute resolution provisions hereof shall be retained and made available until such actions and Claims have been finally resolved. Records to be retained include all books and other evidence bearing on Contractor’s costs and expenses under the Contract Documents. Contractor shall make these records and documents available for audit and inspection to Mn/DOT, at Contractor’s office, at all reasonable times, without charge, and shall allow such Persons to make copies of such documents (at no expense to Contractor).

## 22.5	Minnesota Government Data Practices Act

### 22.5.1	Applicability of Act

Contractor acknowledges and agrees that all records, documents, drawings, plans, specifications and other materials in Mn/DOT’s possession or those to which Mn/DOT is entitled to access, including materials submitted by Contractor, are subject to the provisions of the Minnesota Government Data Practices Act. Contractor shall be solely responsible for all determinations made by it under such act and for clearly and prominently marking each and every page or sheet of its materials with “trade secret” or “non-public” as it determines to be appropriate. Contractor is advised to contact legal counsel concerning such act and its application to Contractor.

### 22.5.2	Confidential Materials

If any of the materials submitted by Contractor to Mn/DOT are clearly and prominently labeled “trade secret” or “non-public” by Contractor, Mn/DOT will endeavor to advise Contractor of any request for the disclosure of such materials prior to making any such disclosure. Under no circumstances, however, will Mn/DOT be responsible or liable to Contractor or any other Person for the disclosure of any such labeled materials, whether the disclosure is required by law, by court order or occurs through inadvertence, mistake or negligence on the part of Mn/DOT, except for any disclosure of trade secrets or proprietary information in violation of the confidentiality agreement described in Section 22.1.7.

### 22.5.3	Contractor to Defend Against Disclosure Request

In the event of litigation concerning the disclosure of any material submitted by Contractor to Mn/DOT, Mn/DOT’s sole involvement will be as a stakeholder retaining the material until otherwise ordered by a court, and Contractor shall be fully responsible for otherwise prosecuting or defending any action concerning the materials at its sole cost and risk.

# 23	MISCELLANEOUS PROVISIONS

## 23.1	Amendments

The Contract may be amended only by a written instrument duly executed by the parties or their respective successors or assigns.

## 23.2	Waiver

### 23.2.1	No Waiver of Subsequent Rights

Either party’s waiver of any breach or failure to enforce any of the terms, covenants, conditions or other provisions of the Contract Documents at any time (including any agreement by Mn/DOT to Accept Nonconforming Work under Section 5.7.2) shall not in any way limit or waive that party’s right thereafter to enforce or compel strict compliance with every term, covenant, condition or other provision, any course of dealing or custom of the trade notwithstanding. Furthermore, if the parties make and implement any interpretation of the Contract Documents without documenting such interpretation by an instrument in writing signed by both parties, such interpretation and implementation thereof will not be binding in the event of any future Disputes. The consent by one party to any act by the other party requiring such consent shall not be deemed to render unnecessary the obtaining of consent to any subsequent act for which consent is required, regardless of whether similar to the act for which consent is given.

### 23.2.2	Custom Does not Constitute Waiver

No act, delay or omission done, suffered or permitted by one party or its agents shall be deemed to waive, exhaust or impair any right, remedy or power of such party under any Contract Document, or to relieve the other party from the full performance of its obligations under the Contract Documents. No custom or practice between the parties in the administration of the terms of the Contract Documents shall be construed to waive or lessen the right of a party to insist upon performance by the other party in strict compliance with the terms of the Contract Documents.

### 23.2.3	Waivers Must Be in Writing

No waiver of any term, covenant or condition of the Contract Documents shall be valid unless in writing and signed by the party providing the waiver.

## 23.3	Independent Contractor

Contractor is an independent contractor, and nothing contained in the Contract Documents shall be construed as constituting any relationship with Mn/DOT other than that of Project owner and independent contractor. In no event shall the relationship between Mn/DOT and Contractor be construed as creating any relationship whatsoever between Mn/DOT and any of Contractor’s employees. Neither Contractor nor any of its employees is or shall be deemed to be an employee of Mn/DOT. Except as otherwise specified in the Contract Documents, Contractor has sole authority and responsibility to employ, discharge and otherwise control its employees and has complete and sole responsibility as a principal for its agents, for all Subcontractors and for all other Persons that Contractor or any Subcontractor hires or engages to perform or assist in performing the Work.

## 23.4	Successors and Assigns

The Contract Documents shall be binding upon and inure to the benefit of Mn/DOT and Contractor and their permitted successors, assigns and legal representatives.

### 23.4.1	Assignment by Mn/DOT

Mn/DOT may assign all or part of its right, title and interest in and to the Contract, including rights with respect to the Payment and Performance Bond, any Guaranty and any other performance security provided, to any Person with the prior written approval of Contractor.

### 23.4.2	Assignment by Contractor

Contractor may collaterally assign its rights to receive payment under the Contract Documents and may subcontract Work in compliance with the requirements of the Contract Documents. Contractor shall not otherwise sublet, transfer, assign or dispose of any portion of the Contract, or delegate any of its duties hereunder, except with Mn/DOT’s prior Approval. Contractor’s assignment or delegation of any of its Work under the Contract Documents shall be ineffective to relieve Contractor of its responsibility for the Work assigned or delegated, unless Mn/DOT, in its sole discretion, has Approved such relief from responsibility. Any assignment of money shall be subject to all proper set-offs and withholdings in favor of Mn/DOT and to all deductions provided for in the Contract. No partner, joint venturer, member or shareholder of Contractor may assign, convey, transfer, pledge, mortgage or otherwise encumber its ownership interest in Contractor without the prior Approval of Mn/DOT, in Mn/DOT’s sole discretion.

## 23.5	Designation of and Cooperation with Representatives

### 23.5.1	Designation of Representatives

Mn/DOT and Contractor shall each designate an individual or individuals who shall be authorized to make decisions and bind the parties on matters relating to the Contract Documents. Such designations may be changed by a subsequent writing delivered to the other party in accordance with Section 23.10. The parties may also designate technical representatives who shall be authorized to investigate and report on matters relating to the construction of the Project and negotiate on behalf of each of the parties but who do not have authority to bind Mn/DOT or Contractor.

### 23.5.2	Cooperation

Contractor shall cooperate with Mn/DOT and all representatives of Mn/DOT designated as described above.

## 23.6	Officials not to Benefit

Without prior written consent of State, Contractor must not employ any professional or technical personnel to provide services under the Contract who are or have been at any time during the time period of the Contract in the employ of State, except retired State employees, without written consent from State.

Contractor warrants that it has not employed or retained any company or person, other than a bona fide employee working solely for Contractor, to solicit or secure the Contract, and that Contractor has not paid or agreed to pay any company or person, other than a bona fide employee working for Contractor, any fee, commissions, percentage, brokerage fee, gifts, or any other consideration, contingent upon or resulting from the award of making of the Contract.

The rights and remedies of Mn/DOT specified in this Section 23.6 are not exclusive and are in addition to any other rights and remedies allowed by law.

## 23.7	Survival

Contractor’s representations and warranties, the dispute resolution provisions contained in Section 19, and all other provisions which by their inherent character should survive termination of the Contract, shall survive the termination of the Contract.

## 23.8	Limitation on Third-Party Beneficiaries

It is not intended by any of the provisions of the Contract Documents to create any third-party beneficiary hereunder, or to authorize anyone not a party hereto to maintain a suit for personal injury or property damage pursuant to the terms or provisions hereof, except to the extent that specific provisions (such as the warranty and indemnity provisions) identify third parties (such as Utility Owners) and state that they are entitled to benefits hereunder. Except as otherwise provided in this Section 23.8, the duties, obligations and responsibilities of the parties to the Contract Documents with respect to third parties shall remain as imposed by law. The Contract Documents shall not be construed to create a contractual relationship of any kind between Mn/DOT and a Subcontractor or any other Person except Contractor.

## 23.9	No Personal Liability

Mn/DOT’s authorized representatives are acting solely as agents and representatives of Mn/DOT when carrying out the provisions of or exercising the power or authority granted to them under the Contract Documents. They shall not be liable either personally or as employees of Mn/DOT for actions in their ordinary course of employment. No agent, consultant, officer or employee of Mn/DOT shall be personally responsible for any liability arising under the Contract.

## 23.10	Notices and Communications

### 23.10.1	Delivery of Notices

Notices under the Contract Documents shall be in writing and (a) delivered personally, (b) sent by certified mail, return receipt requested, (c) sent by a recognized overnight mail or courier service, with delivery receipt requested, or (d) sent by via telephone communication followed by a hardcopy or with receipt confirmed by telephone, to the following addresses (or to such other address as may from time to time be specified in writing by such Person):

All correspondence with Contractor shall be sent to Contractor’s Project Manager or as otherwise directed by such Project Manager. The address for such communications shall be:

Attn.:

Telephone:

FAX:

In addition, copies of all notices to proceed and suspension, termination and default notices shall be delivered to the following persons:

____________________

____________________

Attn.: _______________

Telephone: __________

FAX: _______________

All communications to Mn/DOT shall be marked with Mn/DOT’s project identification number and shall be delivered to Mn/DOT’s Project Manager, with copies to such additional Persons as may be designated by Mn/DOT’s Project Manager, at the address set forth below:

Attn.:

Telephone:

FAX:

In addition, copies of all notices regarding disputes, termination and default notices shall be delivered to the following persons:

____________________

____________________

Attn.: _______________

Telephone: __________

FAX: _______________

### 23.10.2	Receipt of Notices

Notices shall be deemed received when actually received in the office of the addressee (or by the addressee if personally delivered) or when delivery is refused, as shown on the receipt of the U. S. Postal Service, private carrier or other Person making the delivery. Notwithstanding the foregoing, notices sent by telefacsimile after 4:00 p.m. Central Time and all other notices received after 5:00 p.m. Central Time shall be deemed received on the first Working Day following delivery (that is, in order for a fax to be deemed received on the same day, at least the first page of the fax must have been received before 4:00 p.m.).

### 23.10.3	Copies of Correspondence to Mn/DOT

Contractor shall copy Mn/DOT on all written correspondence pertaining to the Contract between Contractor and any Person other than Contractor’s Subcontractors, consultants and attorneys.

## 23.11	Further Assurances

Contractor shall promptly execute and deliver to Mn/DOT all such instruments and other documents and assurances as are reasonably requested by Mn/DOT to further evidence the obligations of Contractor hereunder, including assurances regarding assignments of Subcontractors contained herein.

## 23.12	Severability

If any clause, provision, section or part of the Contract is ruled invalid under Section 19 or otherwise by a court of competent jurisdiction, then the parties shall: (a) promptly meet and negotiate a substitute for such clause, provision, section or part, which shall, to the greatest extent legally permissible, effect the original intent of the parties, including an equitable adjustment to the Contract Price to account for any change in the Work resulting from such invalidated portion; and (b) if necessary or desirable, apply to the court or other decision maker (as applicable) which declared such invalidity for an interpretation of the invalidated portion to guide the negotiations. The invalidity or unenforceability of any such clause, provision, section or part shall not affect the validity or enforceability of the balance of the Contract, which shall be construed and enforced as if the Contract did not contain such invalid or unenforceable clause, provision, section or part.

## 23.13	Headings

The captions of the sections of the Contract Documents are for convenience only and shall not be deemed part of the Contract or considered in construing the Contract.

## 23.14	Governing Law

The Contract Documents shall be governed by and construed in accordance with the law of the State, without regard to conflict of law principles.

## 23.15	Limit of Liability

Notwithstanding anything to the contrary contained herein, the State’s liability for payment extends only to the amount actually appropriated for the purpose of the Project. The Project shall in no event create an obligation of Trunk Highway Funds.

## 23.16	Entire Agreement

The Contract Documents contain the entire understanding of the parties with respect to the subject matter hereof and supersede all prior agreements, understandings, statements, representations and negotiations between the parties with respect to its subject matter.

## 23.17	Counterparts

This instrument may be executed in two or more counterparts, each of which shall be deemed an original, but all of which together shall constitute one and the same instrument.

IN WITNESS WHEREOF, the parties have executed the Contract as of the last date set forth next to signatures of the parties, below.

STATE OF MINNESOTA

| COMMISSIONER OF TRANSPORTATION: Date: ___________________________, 20__ By: __________________________________ Authorized Signature | COMMISSIONER OF ADMINISTRATION: Date: ___________________________, 20__ By: __________________________________ Pursuant to Delegation of Authority |
| --- | --- |
| APPROVED AS TO FORM AND EXECUTION: Date: ___________________________, 20__ By: __________________________________ Nancy Boeve, Pre-Awards Unit | ENCUMBRANCE VERIFICATION SIGNATURE: Date: ___________________________, 20__ By: __________________________________ |

CONTRACTOR

| By: . |  |
| --- | --- |
| By: ___________________________ Name: _________________________ Title: __________________________ Date: _______________, 20__ | By: ___________________________ Name: _________________________ Title: __________________________ Date: _______________, 20__ |
| By: .: |  |
| By: ___________________________ Name: _________________________ Title: __________________________ Date: _______________, 20__ | By: ___________________________ Name: _________________________ Title: __________________________ Date: _______________, 20__ |