#### I-94 Reconstruction Design-Build Project

#### DRAFT Scoring Criteria

#### *These criteria are subject to change prior to the release of the Design-Build Request For Proposals, which is scheduled for the first week of March, 2014.*

- Maintenance (8 Points)

The Proposer shall provide a narrative, supported by exhibits in the Appendices, that describes the Proposer’s approach to designing and constructing a high quality product that minimizes the need for future maintenance.  The Proposer shall describe their plans for the future drainage system within the narrative.  The narrative may contain specific commitments to minimize future maintenance.  MnDOT will evaluate the following subfactors:

- Approach and commitments to minimize future drainage system maintenance.  (4 points)

- Approach and commitments to minimize future maintenance in other areas such as slopes, structures, materials, etc.  (4 points)

- Maintenance of Traffic (5 Points)

The Proposer shall provide a narrative, supported by exhibits in the Appendices, that describes the Contractor’s approach to construction staging and traffic management.  The narrative may contain specific commitments to increase the safety and traffic flow characteristics of the maintenance of traffic plans.  MnDOT will evaluate the following subfactors:

- Safety of the proposed staging plans.

- Approach and commitments to minimize traffic impacts on I-94 during the construction season.

- Approach and commitments to minimize traffic impacts on I-94 during winter conditions.

- Clarity, adequacy, and reliability of the proposed staging plans.

- Ramp Closures (4 Points)

The Proposer shall provide commitments regarding the maximum number of Calendar Days that the following three ramps will be closed during the Project.  Points will be awarded based on the following formula for each individual ramp:

Points Awarded = [(Maximum Time - Proposed Closure) / (Maximum Time)] * X

where:	Maximum Time		= 25 Days for the exit ramp from WB I-94 to TH 241

= 10 Days for the entrance ramp from TH 241 to EB I-94

= 10 Days for the entrance ramp from TH 101 to WB I-94

Proposed Closure = The maximum number of Days the Proposer will close the ramp

X	= 2 for the exit ramp from WB I-94 to TH 241

= 1 for the entrance ramp from TH 241 to EB I-94

= 1 for the entrance ramp from TH 101 to WB I-94

- Preliminary Schedule (3 Points)

The Proposer shall provide a short narrative, supported by exhibits in the Appendices, that describes the Proposer’s approach to completing the work planned for the project.  MnDOT will evaluate the following subfactors:

- Adequacy and reliability of the identified critical elements.

- Clarity, adequacy, and reliability of the schedule logic and task durations