## Final_1
Fugitive Dust BMPs Template
The Fugitive Dust BMPs Template has been developed to guide contractors in compliance adherence to Minnesota Rule 7011.0150 stated below.
No person shall cause or permit the handling, use, transporting, or storage of any material in a manner which allow avoidable amounts of particulate mater to become airborne. No person shall cause or permit a building or its appurtenances or a road, or a driveway, or an open area to be constructed, used, repaired, or demolished without applying all such reasonable measures as may be required to prevent particulate matter from becoming airborne. All persons shall take reasonable precautions to prevent the discharge of visible fugitive dust emissions beyond the lot line of the property on which the emissions matter from becoming airborne including, but not limited to, paving or frequent clearing of roads, driveways, and parking lots; application of dust free surfaces; application of dust-free surfaces; application of water; and the planting and maintenance of vegetative ground cover.
The contractor is required to complete this template or approved equal prior to the start of construction by developing a fugitive dust prevention program, an implementation plan, and further amending this plan as necessary for compliance to the MN Rule:
1. Identify all potential fugitive dust emission sources from examples listed in the spreadsheet. If not listed below, add as necessary.
2. Select and assign dust control Best Management Practices appropriate to each type of dust generating work (more than one may be required).
3. Ensure fugitive dust prevention plan BMPs are compliant to the requirements of the project SWPPP.
4. Assign points of contacts, method of notification and training of all operators.
5. Develop protocol for ceasing operations when fugitive dust emissions exceed the MN Rule, and corrective actions.
3. Determine frequency of application.
4. Record all dust control activities every day of operation.
5. Monitor dust control efforts.
Project Number:
MnDOT Project Manager:
Prime/Sub Contacts | Fugitive Dust Generating Activities | Best Management Practices (Least To Most Expensive) | Photo Reference and Guidance | Other Sources
| Haul roads, in-grade access roads, project exits | 1. Develop and follow the 1717 Site Management and Quality Control Plans | See photo Series 1 | http://www.bouldercounty.org/doc/publichealth/dustbestmgmtpract.pdf
|  | 2. Ensure vehicles stay on established routes |  | http://www.michigan.gov/documents/deq/Grand_Rapids_-_Fugitive_Dust_Control_Methods_451916_7.pdf
|  | 3. Stabilize project exists to minimized need for sweeping |  | http://www.dot.ca.gov/hq/construc/stormwater/CSBMPM_303_Final.pdf
4. Limit speed of vehicle to control dust (suggest < 10 mph)
5. Apply water often (and sweep when road is paved)
6. Apply dust suppression chemicals
7. Place wheel washers at exits that lead from unpaved to paved areas
| Pavement grinding for marking, striping, and rumble strips | 1. Use water sprays and mists during shallow pavement milling | See photo Series 2 | http://www.iowadot.gov/erl/archives/apr_2008/GS/content/2527.htm
2. Vacuum area prior to air blast cleaning
3. Grind with vacuum system capacity capable to allow settling of particulate matter in hopper
4. Grind/groove with properly sized and maintained High Efficiency Particulate Absolute (HEPA) on vacuum system
5. Grind/groove with hydraulic water blaster system with vacuum
6. Sweep with pickup style broom
7. Manage waste dust stockpile with plastic covers and ensure proper disposal
| Stockpiles, large exposed open areas, and grading operations | 1. Limit areas of exposed soils | See photo Series 3 | http://www.bouldercounty.org/doc/publichealth/dustbestmgmtpract.pdf
|  | 2. Limit height of stockpiles |  | http://www.wsdot.wa.gov/NR/rdonlyres/34D9BCF6-3417-4C8C-8B89-977AFABBE95F/0/FBL_FugitiveDust.pdf
|  | 3. Limit placement in confined areas |  | https://www.deq.idaho.gov/media/61833-dust_control_plan.pdf
|  | 4. Preserve vegetated buffers |  | http://www.dot.ca.gov/hq/construc/stormwater/CSBMPM_303_Final.pdf
|  | 5. Use wind fences in the area of construction to reduce soil disturbance* |  | http://water.epa.gov/polwaste/npdes/swbmp/Dust-Control.cfm
6. Till/form soil clods
7. Apply water at a sufficient frequency, quantity and depth, including pre-soaking. Hot, dry days may require several additional water applications throughout the day *
8. Apply dust suppression tackifiers and glues*
9. Apply hydraulic mulches*
10. Apply dust suppression chemicals*
11. Apply soil imprinting or surface roughing techniques
12. Install anchored tarps, plastic or other material to shield piles from wind
*Maintain installed BMPs
| Saw cutting of decks, pavements, and structures | 1. Develop and follow the 1717 Site Management and Quality Control Plans | See photo Series 4 | http://www.forconstructionpros.com/article/10116869/breathe-safe-when-concrete-cutting
|  | 2. Apply water to cutting area with controls of gutter sumps, trap sumps, shoulder sumps, and Sediment Control Log (SCL) Type Compost. Squeegee, shovel, sweep, or vacuum removals of collected slurries. |  | http://www.wsdot.wa.gov/NR/rdonlyres/34D9BCF6-3417-4C8C-8B89-977AFABBE95F/0/FBL_FugitiveDust.pdf
|  | 3. Prewetting of surfaces prior to dust/slurry collected material removals |  | https://www.youtube.com/watch?v=2zKxcTlL5xs
4. Washing area of cut/joint for cleaning into defined area
5. Use of wind and slurry shrouds including plywood, plastic and wind fencing
6. Washing area with containment control system such as inlet sump air bladder seal prior to next operation
7. Use a vacuum system that is equipped with a HEPA filter for collecting dust
| Surface/structure preparation for epoxies, stains, cleaning agents, sealants, concrete and bituminous overlays | 1. Develop and follow 1717 Site Management and Quality Control Plans | See photo Series 5
2. Utilized wind deflection and material capture shrouds
3. Water and slurry collection management controls
4. Provide vacuum system concurrent with the activity
5. When preparing for bridge deck low slump overlay, use shot-blasting along with vacuum recovery
6. Provide appropriate enclosures to contain dust
7. Use hydro-demolition delamination
| Surface preparation for failed railing and barrier coatings | 1. Following 1717 Site Management and Quality Control Plans | See photo Series 6 | http://www.pca.state.mn.us/index.php/view-document.html?gid=16409
2. Utilized wind deflection and material capture shrouds and ground covers
3. Directionally water-blast into controlled zone, not over water
4. Install gutter checks and seal inlets prior to blasting
5. Water and slurry collection management controls
6. Provide vacuum system concurrent with the activity
7. Provide appropriate enclosures to contain dust
8. Modified-wet blasting (adding only enough water to the air-based blasting stream to capture dust without causing the wetted dust to adhere to the surface being blasted)
9. Ensure barges are gap sealed prior to provide work on them
| Street sweeping and prevention of trackout | 1. Develop and follow Dust Prevention Program | See photo Series 7
2. Develop and follow the 1717 Site Management and Quality Control Plans
3. Clean pavements of previous operation prior to sweeping and direct debris to cut-off sump inlets, or SCL Type Compost Gutter sump checks, or unpaved/future shoulder area
4. Maintain project exits, update as necessary to keep in a functional condition
5. Sweep when trackout minor layer of sediment or debris
6. Use properly maintained pickup style sweeper appropriate to the task
7. Pre-wet the pavement and sediment prior to sweeping operation
8. Use HEPA filter modified street sweeper
9. Wash tires off prior to tracking onto pavement
| Demolition of buildings and bridges | 1. Develop and follow 1717 Site Management and Quality Control Plans | See photo Series 8 | http://www.panynj.gov/bridges-tunnels/pdf/gbr-environmental-commitments.pdf
2. Work during period of low wind velocities
3. Rapid start to finish speed of operation
4. Time of year
5. Stop demolition when wind speed exceeds 12 mph
6. Defend and protect inlets
7. Application of water by misters, spray rigs or spray nozzles
8. Wind diversions and shrouds
9. Develop debris management/capture program
10. Blast mat covers
| Rock blasting , material grinding and crushing | 1. Develop and follow Dust Prevention Program | See photo Series 9
2. Develop and follow 1717 Site Management and Quality Control Plans
3. Monitor wind speed and direction with identified stop work process
4. Apply water mists and sprays at all appropriate material process locations
5. Enclose operation
6. Use blast mats and pre-wetting when possible
|  | Series 10 is intentionally left blank | See photo Series 10
|  | Series 11 is intentionally left blank | See photo Series 11
| Concrete and Dowel bar drilling | 1. Develop and follow 1717 Site Management and Quality Control Plans | See photo Series 12
2. Perform work when wind velocity is low
3. If drill bits don't tolerate water, apply water mists at an angle that avoid contact with drill bits
4. Use drill bits that tolerate water and apply water mist when drilling
5. Use drilling machine with slurry vacuum system
6. Use drilling machine with dust vacuum system
7. Place plastic cover/shrouds over drill hammers
8. Material disposal in work area of slab
*Slurry management as per Pavement Saw Cutting Guidance
|  | Series 13 is intentionally left blank. | See photo Series 13
| Partial and full pavement removals | 1. Develop Dust Prevention Programab for work over water and on-land | See photo Series 14
2. Develop and follow 1717 Site Management and Quality Control Plans
3. Monitor wind speed and direction with identified stop work process
4. Apply water mists and sprays at all appropriate material removal operations
5. Deploy wind shrouds
6. Use pre-wetting and resonant pavement rubblization methods
7. Use power-vacuum systems
8. Use hydro-demolition and power vacuum system
a. Follow diamond grinding requirements
b. See also saw cutting guidance Series 4
|  | Series 15 is intentionally left blank. | See photo Series 15
| Mobile concrete and mortar batch mixing and plant operations | 1. Develop and follow 1717 Site Management Plan and Quality Control Plan Implementation* | See photo Series 16
2. Notification signage problem correction declaration
3. Equipment performance management, for example, use hopper door seals
4. Haul road trackout stabilization liquid and dust abstraction
5. Utilized wind deflection and material capture shrouds
6. Mange wash water appropriately
7. Apply appropriate amount of water when needed
8. Preform work in an enclosed environment
9. Use vacuum systems with HEPA filter for collecting dust
10. Aggregate water management with weight scale calibration
*Includes Spill Prevention Control and Countermeasure (SPCC) Program
| Epoxy chip seal | 1. Develop and follow Dust Prevention Program | See photo Series 17
2. Monitor wind speed and direction with identified stop work process
3. Apply aggregate chips in low wind velocity at times of day including night and early morning
4. Use rolling isolation shrouds
5. Require reduction in granite chip fine aggregate
Note: | (1) Additional Stormwater Pollution Prevention Plan (SWPPP) and strategies will be required to implement the above Fugitive Dust Generating Activities.
(2) Material Safety Data Sheet (MSDS) must be on file within project documents.
(3) Part of contractor submittal for the work.
(4) If all BMPs are exhausted, constractors are encourage to invent new means and methods of dust control.