## Slide 1: AUTHORITY

## Slide 2: Authority
As we travelled around the state talking to PMs and management, we heard over and over again that PMs need more authority or that they need to exercise the authority they have.

## Slide 3: What is Authority?
Each person at the table share a brief story about an issue with Authority
As a group answer the following questions:
  What do we mean by Authority?
  What are the common characteristics of issues surrounding Authority?
In about 30 minutes we’ll report out

## Slide 4: Some Thoughts on Addressing the Issue of Project Manager Authority

## Slide 5: Authority: Clear Lines
Line of Authority:
  Commissioner
  Deputy Commissioner
  Division Director
  District Engineer/Office Director
  Project Sponsor
  PM
  Project staff
Ultimate authority and accountability for project decisions must stay in this line

## Slide 6: Authority: Endowment
The Project Sponsor sets the authority of the Project Manager defining types of decisions that should be made by technical staff, by the PM, and those reserved for the Sponsor.
This will depend on the technical knowledge and people skills of the PM, the personality of the Sponsor, and the complexity and risk of the project.
Will require talking about it.
This is captured in the Project Charter so it is clearly communicated.

## Slide 7: Authority: Avoid Wielding It
Project Sponsor – select wise PMs with good people skills who respect the expertise of technical staff
Project Manager – builds a team, communicates effectively, strives for consensus among team members
Project Staff – work with team, break down silos

## Slide 8: Authority: Issue Escalation
Keep decisions on project whenever possible
Ideally we get to agreement on decisions
When there is disagreement, the Charter indicates who makes the call
The issue is elevated if:
  effect goes beyond project
  there is a dispute over a decision

## Slide 9: Authority: Issue Escalation Process
If a team member strongly disagrees with the decision, they inform the PM that they are disputing it
The PM arranges a discussion with the disputing individuals and the next highest step in the process
The PM sets timelines for the decision and stays engaged with the discussions
1st Step – Project Sponsor
2nd Step – District Engineer/Office Director
3rd Step – Division Director
Final decision rests with sponsoring division

## Slide 10: Authority: Issues with this Approach
At your table, discuss:
  The problems that may arise with this approach
  Any questions that remain unanswered
And then discuss:
  Solutions to those problems
  Answers to those questions
In 20-30 minutes we will report back

## Slide 11: If there is still time…Accountability
What are the conditions for accountability to occur?
What tools/organization changes would help with holding people accountable?