Processes for Coordinating PPMS and P6 Data

July 3, 2013

Now that all of the PPMS Schedules have been converted to P6 there are some new protocols to make sure project information is kept up to date in both systems until the retirement of PPMS.  PPMS will continue to be the authoritative source for the project data noted above until replaced. P6 is now the authoritative source for schedule data. Below are a few guidelines to help ensure that P6 project information is accurate.

Letting Date Changes:

For any let date changes, please add your Shared Service Center (SSC) contact to the list of cc:’s when submitting the change form to Val for approval.  Once Val has approved the change, the SSCs will be sent the approved spreadsheet.

PPMS Data Changes:

Please send an email to your SSC notifying them of any changes made to the following items in PPMS as they are now being held in P6.

Program				Bridge #

Fiscal Year				Bridge Work Type

Project Complexity			Construction Cost

Route #					Const. Res. Eng.

Letting Process				Beg. Ref. Pt.

Primary Work Type			Final Ref. Pt.

Project Status				PUMA Prime SP

Proj. Sponsor				PUMA SP

Project Tied/Untied			PUMA Element ID

If a formal amendment or modification is submitted that alters any of the information described above, please send an email specifying what was changed to your SSC.

PPMS Data Changes Received by the SSC:

If a project manager requests that the SSC make changes to any non-schedule data they will be redirected to the PPMS Coordinator. The information will then come from the PPMS Coordinator to the SSC.

Creating New Projects in PPMS and Schedules in P6:

Projects will continue to be created in PPMS for project data and funding purposes. New schedules should no longer be created in APV; they will be created in P6. The following process should be used for now, but expect updates in the future:

- Requests for new projects will go to the PPMS Coordinators as usual, with a completed attribute form, or using their current process for obtaining project information.

- PUMA Coordinators will create the Bundle & Element in PUMA, generate the SP# and request a job number from SWIFT

- PPMS Coordinators will create the project in PPMS with all header information

- PPMS Coordinator will forward the information to their SSC and copy the requestor.

- SSC staff will connect with the requestor on the next steps for building their schedule.

Updating Schedules:

As of July 10th Project Managers, Functional Group Supervisors and Functional Group Leads will have access to update schedules using P6 Team Member. Updates in APV or Task Status Manager are not reflected in P6. Please don’t make them there.

Reports

Any schedule related reports can now be found on the Project Management website, along with a report showing the PPMS Header information.  These are static reports that will be updated every two weeks after the data date is moved in P6.

http://ihub/projectmanagement/project-development/pmsu/proj-info.html

Any non-schedule reports can still be created using Crystal Reports on the PPMS website.

http://ihub/projectmanagement/project-development/pmsu/ppms/index.html

We are scoping out the effort to make P6 data available to Crystal Reports through the Enterprise Data Warehouse.

Thank you for your patience and cooperation during this transition to the new software.  As always, if you have any questions please feel free to contact your SSC.