- In late April-early May 2013, approximately 400 PPMS converted project schedules were role loaded.  That role loading process was documented in a memo dated May 13, 2013.

Throughout the summer of 2013, feedback was solicited from districts and central office groups to determine how the role loading process could be improved.  Most of the feedback focused on ways to improve the following elements:

  - Pre-construction cost (project)

  - Pre-construction labor hours (project)

  - Pre-construction labor hours (per activity)

  - Role titles that better reflect current district and central office roles

Additionally, during this timeframe, research was conducted to determine current pre-construction estimating practices being utilized by other state DOT’s.

The role loading process for PPMS converted schedules was refined during September - December 2013 to reflect the inputs listed above.  In December 2013 – January 2014, the role loading process was further refined to address projects with enhanced schedules.

This memo documents the revised process for role loading:

- PPMS converted schedules (“Role Loading 2.0”)

- Enhanced schedules (“Role Loading 2.1”)

- A master spreadsheet tool (the “tool”) was created specifically for role loading.  Inputting the element number automatically brings in the associated project information:

  - SP number

  - District

  - Project description

  - Primary work type (PWT)

  - Construction cost estimate

The tool calculates the project’s target labor hours by applying using one of the following formulas:

| Construction cost | Target labor hours |
| --- | --- |
| < $3 Million | = PCR factor * PWT factor * 0.0015 * (Construction cost estimate) + 150 |
| ≥ $3 Million and ≤ $10 Million | = PCR factor * PWT factor * 0.0007 * (Construction cost estimate) + 2640 |
| > $10 Million | = PCR factor * PWT factor * 0.00045 * (Construction cost estimate) + 5100 |

Project Complexity and Risk (PCR) factors:

  - Minor		1.00

  - Moderate	1.05

  - Major		1.10

  - Mega		1.20

PWT factors:

  - Appurtenances (APPU)					1.1

  - Bridge Rehabilitation (BRRH)				0.8

  - Bridge Replace or Construction (BRPC)		1.2

  - Grade and Surface (GRSU)				0.6

  - Grade, Surface, and Bridge (GSBR)			1.0

  - Intelligent Transportation System (ITS)		1.0

  - Planning (PLAN)					1.2

  - Preservation / Maintenance (PRMN)			0.4

  - Pavement Resurfacing and Rehab (PVTR)		0.6

  - Right of Way (ROW)					1.0

  - Traffic Control Devices (TRCD)			0.8

  - Transit (TRAN)						0.6

- The tool features:

  - an embedded database containing the range of durations and range of labor hours for all PPMS activities

  - an embedded database containing the range of durations and range of labor hours for all enhanced schedule activities

  - the ability to extract only those activities needed for a given project from the afore mentioned embedded databases

- The tool assigns target labor hours to each project activity.  For the PPMS schedules, this information was based upon duration and labor hour ranges found in the PPMS Network Generator Rules.   For the enhanced schedules, this information was based upon duration and labor hour ranges developed by OPMTS.

For each activity, the tool determines where the duration contained in the project schedule fits within the duration range, and then calculates the target labor hours for the activity by applying the same pro-rating to the labor hours.

It is important to note that the PPMS Rules are based on calendar days and the project schedule durations are measured in working days.  The tool converts the project schedule durations to calendar days to ensure that calculations are made using consistent units.

Durations in the enhanced schedule database are all in working days.

Example:

Activity 1003 – Project Scoping

Range of activity durations: 	45 – 180 calendar days (per Appendix)

Range of labor hours: 	120 – 880 hours (per Appendix)

Duration per project schedule: 	62 working days (= 87 calendar days)

Target labor hours = [[(87 – 45)/(180 – 45)] * [880 – 120]] + 120 = 356 hours

For durations less than the low end of the duration range, the target labor hours are set to be equal to the corresponding low end of the labor hour range.

For durations greater than the high end of the duration range, the target labor hours are set to be equal to the corresponding high end of the labor hour range.

- The tool adjusts the target labor hours for each activity until the sum of all hours equals the overall target labor hours for the project as calculated in Step 2.

- Using percentages in the embedded database, the tool calculates proposed labor hours for each role that will be involved in each activity.  All hours between 0 and 1 are rounded up to 1 hour.  Because of this roundup function, the sum of the hours assigned to each role title for a given activity will typically exceed the target labor hours for that activity.  These new hours are referred to as the normalized project hours.

- Miscellaneous notes re: role loading

  - When a given activity warrants involvement by numerous roles within a functional group (e.g. Lead, Engineer, Senior Technician, and Technician), a typical split is 11%-22%-33%-34%.

  - Overall PM hours for the project should be approximately 5%.  PM hours should be manually adjusted as necessary to achieve this percentage.

- APPENDIX – ROLE LOADING 2.0

| Ranges of Durations and Labor Hours for PPMS Activities (from PPMS Network Generator Rules) |
| --- |
| Activity ID | Activity Name | Duration (calendar days) | Labor Hours |
|  |  | Low | High | Low | High |
| 1001 | PROJECT INITIATION | 1 | 1 | 8 | 8 |
| 1003 | PROJECT SCOPING | 45 | 180 | 120 | 880 |
| 1011 | CONSULTANT ACQUISITION FOR MULTIPLE ACTIVITIES | 160 | 160 | 40 | 40 |
| 1012-1011 | CONSULTANT ACQUISITION FOR AERIAL IMAGERY | 33 | 33 | 8 | 8 |
| 1012 | AERIAL IMAGERY | 90 | 180 | 10 | 90 |
| 1015 | TRAFFIC FORECASTING | 20 | 90 | 8 | 16 |
| 1016 | ESAL CALCULATIONS | 20 | 40 | 8 | 16 |
| 1018 | PHOTOGRAMMETRIC BASE MAP | 250 | 400 | 185 | 1,580 |
| 1021 | PRELIMINARY DESIGN SURVEYS | 40 | 202 | 560 | 3,980 |
| 1030 | CONTROL SURVEYS | 20 | 40 | 55 | 160 |
| 1032 | DISTRICT LAND SURVEYS | 80 | 440 | 160 | 880 |
| 1040 | FINAL DESIGN SURVEYS | 15 | 220 | 254 | 1,460 |
| 1041 | BRIDGE SURVEYS | 30 | 120 | 200 | 2,200 |
| 1050 | EIS SCOPING DOCUMENT | 120 | 360 | 750 | 2,060 |
| 1051 | PUBLIC EIS SCOPING MEETING | 60 | 90 | 200 | 300 |
| 1052 | EIS SCOPING DECISION DOCUMENT | 60 | 120 | 200 | 400 |
| 1068 | VALUE ENGINEERING | 120 | 120 | 380 | 380 |
| 1070 | CATEX | 60 | 150 | 240 | 570 |
| 1075 | STRUCTURE RECOMMENDATIONS | 30 | 180 | 300 | 600 |
| 1080 | PRELIMINARY LAYOUTS | 30 | 360 | 225 | 645 |
| 1082 | WETLANDS | 10 | 45 | 80 | 280 |
| 1083 | WETLANDS JURISDICTIONAL DELINEATIONS | 10 | 90 | 160 | 760 |
| 1085 | CULTURAL RESOURCES UNIT DETERMINATION | 60 | 365 | 80 | 530 |
| 1086 | COST-EFFECTIVENESS ANALYSIS | 70 | 70 | 300 | 300 |
| 1093 | ASBESTOS/REGULATED MATERIALS & WASTE IN BLDGS/ BRGS | 180 | 270 | 600 | 800 |
| 1095 | CONTAMINATION INVESTIGATION - PHASE I | 90 | 180 | 200 | 560 |
| 1100 | DRAFT ENVIRONMENTAL IMPACT STATEMENT | 365 | 1095 | 5,000 | 15,000 |
| 1110 | PUBLIC HEARING ON A DRAFT ENVIRONMENTAL IMPACT STATEMENT | 60 | 120 | 200 | 200 |
| 1111 | PUBLIC HEARING ON AN ENVIRONMENTAL ASSESSMENT | 60 | 120 | 200 | 400 |
| 1113 | PUBLIC INFORMATION MEETING | 60 | 120 | 100 | 200 |
| 1120 | FINAL ENVIRONMENTAL IMPACT STATEMENT | 180 | 360 | 3,000 | 8,150 |
| 1121 | ADEQUACY DETERMINATION | 14 | 14 | 40 | 40 |
| 1122 | RECORD OF DECISION | 60 | 150 | 80 | 130 |
| 1129 | ENVIRONMENTAL ASSESSMENT | 180 | 360 | 1,750 | 3,350 |
| 1131 | EIS NEED DECISION | 60 | 100 | 30 | 50 |
| 1132 | FINDING OF NO SIGNIFICANT IMPACT | 30 | 30 | 40 | 40 |
| 1140 | FINAL GEOMETRIC LAYOUT | 60 | 150 | 150 | 2,130 |
| 1141 | PRELIM HYDRAULICS DESIGN | 30 | 120 | 20 | 880 |
| 1142 | MUNICIPAL APPROVAL OF FINAL LAYOUT | 90 | 90 | 16 | 16 |
| 1150 | PROJECT DESIGN MEMORANDUM | 60 | 60 | 80 | 80 |
| 1165 | INTERSECTION CONTROL EVALUATION (ICE) | 30 | 90 | 40 | 400 |
| 1170 | PAVEMENT TYPE SELECTION | 160 | 160 | 240 | 240 |
| 1180 | MATERIALS DESIGN RECOMMENDATION | 14 | 90 | 56 | 360 |
| 1181 | SOILS REVIEW AND APPROVAL | 30 | 100 | 60 | 200 |
| 1182 | MATERIALS SURVEY AND TESTING | 14 | 180 | 112 | 1,440 |
| 1190 | FOUNDATION RECOMMENDATION | 30 | 180 | 300 | 600 |
| 1191 | FOUNDATION RECOMMENDATION - BRIDGE | 14 | 360 | 140 | 1,214 |
| 1194 | UTILITY IDENTIFICATION | 60 | 315 | 100 | 300 |
| 1195 | UTILITY COORDINATION | 90 | 675 | 100 | 504 |
| 1196 | UTILITY VERIFICATION & RELOCATION PLANS | 90 | 90 | 40 | 40 |
| 1200 | CONSTRUCTION LIMITS | 30 | 360 | 240 | 2,880 |
| 1210 | TITLE ORDER | 40 | 84 | 32 | 132 |
| 1220 | RIGHT OF WAY PACKAGE | 60 | 160 | 100 | 624 |
| 1225 | PLATS AND PRELIMINARY DESCRIPTIONS | 90 | 180 | 48 | 840 |
| 1230 | RIGHT OF WAY PREACQUISITION | 100 | 180 | 48 | 960 |
| 1233 | CONTAMINATION INVESTIGATION - PHASE II DRILLING | 60 | 180 | 200 | 900 |
| 1235 | VALUATION | 90 | 180 | 180 | 952 |
| 1240 | REAL ESTATE PURCHASE | 240 | 300 | 110 | 800 |
| 1241 | EMINENT DOMAIN | 155 | 270 | 80 | 400 |
| 1249 | FINAL HYDRAULICS DESIGN | 70 | 140 | 60 | 330 |
| 1250 | ROAD PLANS | 90 | 720 | 720 | 5,760 |
| 1251 | SIGNAL PLANS | 30 | 180 | 120 | 1200 |
| 1252 | LIGHTING PLANS | 20 | 180 | 80 | 960 |
| 1253 | TIME AND TRAFFIC | 10 | 30 | 45 | 126 |
| 1254 | TRAFFIC CONTROL PLAN | 13 | 123 | 90 | 1,525 |
| 1255 | SIGNING PLANS | 30 | 180 | 56 | 560 |
| 1256 | TRAFFIC MANAGEMENT SYSTEM PLANS | 30 | 270 | 14 | 800 |
| 1257 | LANDSCAPE PLANS | 30 | 150 | 120 | 1,020 |
| 1258 | FLASHER PLANS | 30 | 180 | 60 | 240 |
| 1259 | HYDRAULICS LETTER | 28 | 105 | 300 | 450 |
| 1260 | PRELIMINARY BRIDGE PLANS | 120 | 180 | 80 | 800 |
| 1270 | FINAL STRUCTURE PLANS | 45 | 210 | 320 | 3,200 |
| 1273 | TRANSPORTATION MANAGEMENT PLAN | 60 | 180 | 120 | 480 |
| 1274 | PAVEMENT MARKING PLANS | 60 | 120 | 32 | 50 |
| 1275 | PROJECT TURN IN | 14 | 14 | 56 | 56 |
| 1280 | PERMITS | 120 | 210 | 80 | 140 |
| 1290 | AGREEMENTS - MUNICIPAL | 77 | 77 | 220 | 220 |
| 1291 | AGREEMENTS - RAILROADS | 60 | 120 | 150 | 300 |
| 1292 | AGREEMENTS - UTILITIES | 77 | 77 | 220 | 220 |
| 1293 | AGREEMENTS - OTHERS | 77 | 77 | 220 | 220 |
| 1294 | AGREEMENTS - SIGNAL | 77 | 77 | 220 | 220 |
| 1295 | AGREEMENTS - LIGHTING | 77 | 77 | 220 | 220 |
| 1296 | AGREEMENTS - DETOUR | 77 | 77 | 220 | 220 |
| 1300 | PLANS, SPECIAL PROVISIONS, AND ESTIMATES | 36 | 36 | 200 | 200 |
| 1301 | STRUCTURES PS&E | 14 | 14 | 80 | 80 |
| 1310 | LETTING | 28 | 28 | 24 | 24 |
| 1311 | APPROVAL OF CONSTRUCTION CONTRACT | 40 | 40 | 40 | 40 |

- APPENDIX – ROLE LOADING 2.1

| Ranges of Durations and Labor Hours for Enhanced Schedule Activities |
| --- |
| Activity ID | Activity Name | Duration (working days) | Labor Hours |
|  |  | Low | High | Low | High |
| A4300 | *** Need Activity Here *** | 2 | 10 | 10 | 80 |
| ADA1000 | Conduct ADA Field Walk | 5 | 40 | 10 | 40 |
| ADA1010 | Prepare Draft ADA Field Walk Recommendations | 2 | 20 | 10 | 40 |
| ADA1020 | Review ADA Field Walk Recommendations by District | 5 | 20 | 10 | 20 |
| ADA1030 | Finalize ADA Field Walk Recommendations | 5 | 20 | 10 | 20 |
| ADT1000 | Issue Adequecy Determination by MNDOT | 2 | 10 | 20 | 40 |
| AIR1010 | Procure Prequalified Air Quality Analysis Consultant | 40 | 80 | 30 | 50 |
| AIR1020 | Develop/Approve Receptor Sites - Air Quality | 2 | 20 | 20 | 40 |
| AIR1030 | Conduct Ambient Background Air Quality Monitoring | 20 | 60 | 40 | 120 |
| AIR1040 | Acquire Air Quality Analysis Modeling Input Data | 10 | 40 | 20 | 80 |
| AIR1110 | Prepare Draft Air Quality Report for Preferred Alternative | 2 | 10 | 20 | 80 |
| AIR1120 | Review Draft Air Quality Repor for Preferred Alternative | 5 | 25 | 20 | 80 |
| AIR1130 | Revise Draft Air Quality Report for Preferred Alternative | 5 | 25 | 20 | 80 |
| AIR1140 | Review Draft Air Quality Report for Preferred Alternative by EMTU | 5 | 25 | 20 | 80 |
| AIR1150 | Prepare Final Air Quality Report for Preferred Alternative | 5 | 25 | 10 | 40 |
| ATH1000 | Acquire Architectural History Consultant | 20 | 80 | 30 | 50 |
| ATH1010 | Conduct Architectural History (Phase 1) Investigation | 2 | 15 | 20 | 80 |
| ATH1020 | Architectural History (Phase 1) Review | 2 | 15 | 10 | 40 |
| ATH2000 | Conduct Architectural History (Phase 2) Investigation | 2 | 15 | 10 | 40 |
| ATH2010 | Architectural History (Phase 2) Review | 2 | 15 | 10 | 40 |
| ATH2020 | Provide Architectural History (Phase 2) Determination | 2 | 15 | 10 | 40 |
| ATH2030 | Architectural History (Phase 2) Complete (No Properties Effected) | 0 | 0 | 10 | 20 |
| ATH2040 | Obtain Architectural History (Phase 2) SHPO Concurrence | 2 | 15 | 10 | 40 |
| ATH2050 | Provide Architectural History (Phase 2) Findings | 2 | 15 | 10 | 40 |
| ATH2060 | Architectural History Findings Complete (No Adverse Effects Determined) | 0 | 0 | 10 | 20 |
| ATH2070 | Obtain Architectural History (Phase 2) SHPO Concurrence | 2 | 15 | 10 | 40 |
| ATH2080 | Prepare Documentation of Adverse Effect for Architectural History (Phase 2) | 2 | 15 | 10 | 40 |
| ATH2090 | Prepare MOA/PA for Architectural History (Phase 2) | 2 | 15 | 10 | 40 |
| ATH2100 | Implement Architectural History (Phase 2) Mitigation | 2 | 15 | 10 | 40 |
| CCA1000 | Discuss Cost Participation with LGU | 10 | 40 | 20 | 160 |
| CCA1010 | Prepare & Submit Cooperative Agreement Request | 3 | 20 | 20 | 80 |
| CCA1020 | Prepare Draft Cooperative Construction Agreement | 5 | 45 | 20 | 80 |
| CCA1030 | Negotiate Cooperatve Construction Agreement with LGU & Submit for Approval | 10 | 40 | 20 | 80 |
| CCA1040 | Obtain Resolution on Cooperative Construction Agreement from LGU | 15 | 45 | 20 | 80 |
| CCA1050 | Cooperative Construction Agreement Signed | 0 | 0 | 0 | 0 |
| CPS1000 | Review Information Obtained From Phase 1/Phase 2 | 2 | 15 | 20 | 80 |
| CPS1010 | Prepare Draft Provisions | 2 | 15 | 20 | 40 |
| CPS1020 | Review Draft Provisions | 2 | 15 | 10 | 20 |
| CPS1030 | Prepare Contaminated Properties Special Provisions | 2 | 15 | 20 | 40 |
| CRU1000 | Conduct Preliminary Cultural Resources Evaluation | 2 | 20 | 20 | 80 |
| CRU1010 | Submit SHPO Notification | 2 | 10 | 10 | 20 |
| CRU1020 | Conduct Tribal Consultation | 2 | 10 | 10 | 20 |
| CRU1025 | Prepare & Send CRU Findings Letter | 2 | 10 | 10 | 20 |
| CRU1030 | Obtain SHPO Response To Notification | 2 | 60 | 10 | 20 |
| CRU1040 | Public Consultation for CRU Investigation | 2 | 60 | 10 | 20 |
| CTX1000 | Prepare CATEX Document | 2 | 20 | 20 | 80 |
| CUD1000 | Determine Drainage Areas & Flows for Culverts | 5 | 60 | 40 | 200 |
| CUD1010 | Determine Culvert Size & Flow Lines | 5 | 60 | 40 | 200 |
| DEIS1000 | Prepare & Approve of EIS Project Coordination Plan | 30 | 60 | 120 | 240 |
| DEIS1010 | Prepare DEIS | 260 | 520 | 5000 | 10000 |
| DEIS1020 | Review DEIS by OES EAU | 20 | 40 | 120 | 240 |
| DEIS1030 | Revise DEIS Based on OES Comments | 10 | 20 | 120 | 240 |
| DEIS1040 | Review DEIS by FHWA | 30 | 60 | 10 | 20 |
| DEIS1050 | Revise DEIS Based on FHWA Comments | 10 | 20 | 120 | 240 |
| DEIS1060 | Review DEIS by DOI (Note: Only if there is a Full 4(f)) | 30 | 60 | 10 | 20 |
| DEIS1070 | Review DEIS by Cooperating Agencies | 20 | 40 | 10 | 20 |
| DEIS1080 | Revise DEIS Based on Cooperating Agencies Comments | 10 | 20 | 120 | 240 |
| DEIS1090 | Obtain District, OES, FHWA Signatures for DEIS | 5 | 20 | 10 | 20 |
| DEIS1100 | Submit Federal Register Notice for DEIS | 5 | 20 | 10 | 20 |
| DEIS1110 | Public Comment Period for DEIS | 40 | 50 | 10 | 20 |
| DME1000 | Prepare & Approve Design Memo in District | 2 | 15 | 10 | 40 |
| DME1010 | Approve Formal Design Exception by State Design Engineer | 5 | 30 | 10 | 20 |
| DTD1000 | Collect Drain Tile Maps | 5 | 60 | 10 | 60 |
| DTD1010 | Conduct Drain Tile Meetings with Farm Owners/Operators | 5 | 60 | 10 | 120 |
| DTD1020 | Determine Drain Tile Size & Flow Lines | 5 | 60 | 20 | 200 |
| EAW1000 | Prepare EA/EAW Statement of Purpose & Need | 5 | 15 | 20 | 80 |
| EAW1010 | Review EA/EAW Statement of Purpose & Need by OES & FHWA | 20 | 40 | 120 | 240 |
| EAW1020 | Prepare EA/EAW Document | 130 | 260 | 1650 | 3300 |
| EAW1030 | Review EA/EAW Document by OES EAU | 20 | 40 | 120 | 240 |
| EAW1040 | Revise EA/EAW Document | 10 | 20 | 80 | 160 |
| EAW1050 | Review EA/EAW Document by FHWA | 20 | 40 | 10 | 20 |
| EAW1055 | Review EA/EAW/4(f) by DOI (Note: Only if there is a Full 4(f)) | 30 | 60 | 10 | 20 |
| EAW1060 | Revise EA/EAW Document | 10 | 20 | 80 | 160 |
| EAW1070 | Obtain District, OES, FHWA Signatures for EA/EAW | 5 | 20 | 10 | 20 |
| EAW1080 | Public Comment Period for EA/EAW | 40 | 50 | 10 | 20 |
| EDD1000 | Prepare EDD 1 & Submit to CO EIU | 2 | 10 | 20 | 80 |
| EDD1010 | Review & Respond to EDD 1 by CO EIU | 50 | 70 | 40 | 80 |
| EDD2000 | Prepare EDD 2 & Submit to CO EIU | 2 | 10 | 10 | 80 |
| EDD2010 | Review & Respond to EDD 2 by CO EIU | 5 | 10 | 10 | 20 |
| EDD3000 | Prepare EDD 3 & Submit to CO EIU | 2 | 10 | 20 | 80 |
| EDD3010 | Prepare EDD 3 (CO EIU) & Route For Signatures | 30 | 50 | 10 | 20 |
| EDD3020 | Obtain EDD 3 Signatures | 10 | 30 | 20 | 40 |
| EDD3030 | Present EDD 3 to Deputy Commissioner | 10 | 30 | 40 | 80 |
| EDD3040 | Finalize EDD 3 with Deputy Commissioner Determination | 2 | 10 | 10 | 20 |
| EIS1000 | Prepare EIS Statement of Purpose & Need | 5 | 20 | 40 | 160 |
| EIS1010 | Review EIS Statement of Purpose & Need by OES & FHWA | 20 | 40 | 80 | 120 |
| EIS1020 | Develop Scoping Alternatives | 5 | 20 | 40 | 120 |
| EIS1030 | Prepare Preliminary SD/DSDD | 5 | 20 | 40 | 80 |
| EIS1040 | Review Preliminary SD/DSDD by OES | 20 | 40 | 80 | 160 |
| EIS1050 | Revise Preliminary SD/DSDD Based on Comments by OES | 5 | 10 | 20 | 40 |
| EIS1060 | Review Preliminary SD/DSDD by FHWA | 30 | 60 | 10 | 20 |
| EIS1070 | Revise Preliminary SD/DSDD Based on Comments by FHWA | 5 | 20 | 40 | 80 |
| EIS1080 | Review Preliminary SD/DSDD by Cooperating Agencies | 20 | 40 | 10 | 20 |
| EIS1090 | Revise Preliminary SD/DSDD Based on Comments by Cooperating Agencies | 5 | 20 | 40 | 80 |
| EIS1100 | Obtain District & OES Signatures for SD/DSDD | 20 | 40 | 20 | 40 |
| EIS1110 | Public Comment Hearing for SD/DSDD | 25 | 35 | 10 | 20 |
| ENM1000 | Prepare & Distribute ENM | 5 | 30 | 40 | 120 |
| ENM1005 | Review & Respond to ENM | 20 | 60 | 10 | 40 |
| ENM1010 | Review & Respond to ENM by CRU | 20 | 60 | 10 | 40 |
| ENM1020 | Respond to ENM by EIU | 2 | 60 | 8 | 40 |
| ENM1030 | Review & Respond to ENM for Regulated Waste | 20 | 60 | 10 | 40 |
| ENM1040 | Review & Respond to ENM by DNR | 20 | 60 | 10 | 20 |
| ENM1050 | Review & Respond to ENM by EMTU | 20 | 60 | 10 | 40 |
| ENM1060 | Review & Respond to ENM for T&ES | 20 | 60 | 10 | 40 |
| ENM1070 | Review & Respond to ENM for Vegetation | 20 | 60 | 10 | 40 |
| ENM1080 | Review & Respond to ENM for Bike/Ped | 20 | 60 | 10 | 40 |
| ENM1090 | Review & Respond to ENM for ADA | 20 | 60 | 10 | 40 |
| ENM1100 | Review & Respond to ENM by Aeronautics | 20 | 60 | 10 | 40 |
| ENM1110 | Review & Respond to ENM by Rail Office | 20 | 60 | 10 | 40 |
| ENM1120 | Review & Respond to ENM for Value Engineering | 20 | 60 | 10 | 40 |
| ESA1000 | Prepare Scope of Work & Obtain Cost Estimate to Hire Consultant - Phase I | 5 | 20 | 20 | 40 |
| ESA1010 | Execute ESA Phase I Contract | 20 | 40 | 10 | 20 |
| ESA1020 | Prepare Draft Phase I ESA | 40 | 80 | 80 | 160 |
| ESA1030 | Review Draft Phase I ESA | 5 | 20 | 10 | 20 |
| ESA1040 | Prepare Final Phase I ESA | 5 | 20 | 10 | 20 |
| ESA2000 | Prepare Scope of Work & Obtain Cost Estimate to Hire Consultant - Phase II | 5 | 20 | 20 | 40 |
| ESA2010 | Execute ESA Phase II Contract | 20 | 40 | 10 | 20 |
| ESA2020 | Develop Work Plan For Drilling (No Parcels to Acquire) | 2 | 10 | 10 | 20 |
| ESA2030 | Complete Drilling & Discuss Field Findings With Consultant | 5 | 20 | 40 | 80 |
| ESA2040 | Receive, Review, and Tabulate Analytical Results | 10 | 30 | 10 | 20 |
| ESA2050 | Receive Results & Determine if Liabilty Protections are Required | 5 | 20 | 10 | 20 |
| ESA2060 | Update EDD 2 and Send to PM/RW | 2 | 10 | 10 | 20 |
| ESA2070 | Prepare Draft Phase 2 Report | 20 | 60 | 40 | 80 |
| ESA2080 | Review Draft Phase II Report | 10 | 30 | 10 | 20 |
| ESA2090 | Prepare Final Phase 2 Report | 2 | 10 | 10 | 20 |
| EST1000 | Prepare Engineer's Estimate | 10 | 40 | 40 | 120 |
| EST1010 | Develop TGB/DBE Goals by EEO | 10 | 40 | 10 | 40 |
| EST1020 | Enter Project Into TRANS*PORT | 10 | 40 | 20 | 120 |
| FDB1000 | Request Scoping Input | 1 | 10 | 4 | 8 |
| FDB1010 | Identify Potential Scope Items by Project Manager | 20 | 60 | 20 | 40 |
| FDB1020 | Identify Potential Scope Items by Planning | 20 | 60 | 20 | 40 |
| FDB1030 | Identify Potential Scope Items by State Aid | 20 | 60 | 20 | 40 |
| FDB1040 | Identify Potential Scope Items by Land Management | 20 | 60 | 20 | 40 |
| FDB1050 | Identify Potential Scope Items by Surveys | 20 | 60 | 20 | 40 |
| FDB1060 | Identify Potential Scope Items by Environmental Coordinator | 20 | 60 | 20 | 40 |
| FDB1070 | Identify Potential Scope Items by Bridge | 20 | 60 | 40 | 80 |
| FDB1080 | Identify Potential Scope Items by Resident Office | 20 | 60 | 20 | 40 |
| FDB1090 | Identify Potential Scope Items by Design | 20 | 60 | 20 | 40 |
| FDB1100 | Identify Potential Scope Items by Hydraulics/Water Resources | 20 | 60 | 20 | 80 |
| FDB1110 | Identify Potential Scope Items by Maintenance | 20 | 60 | 20 | 40 |
| FDB1120 | Identify Potential Scope Items by Materials | 20 | 60 | 20 | 80 |
| FDB1130 | Identify Potential Scope Items by Traffic | 20 | 60 | 20 | 40 |
| FDB1140 | Identify Potential Scope Items by Others | 20 | 60 | 20 | 40 |
| FDB1150 | Determine & Document Final Baseline Scope | 1 | 60 | 4 | 100 |
| FDB1160 | Develop & Approve Final Baseline Estimate (TPCE) | 5 | 40 | 20 | 80 |
| FDB1170 | Develop Final Baseline Schedule | 5 | 30 | 20 | 160 |
| FDR1000 | Prepare & Submit Foundation Request by District | 1 | 5 | 4 | 16 |
| FDR1010 | Prepare Borings Plan | 2 | 5 | 8 | 40 |
| FDR1020 | Obtain Foundations Borings | 10 | 40 | 20 | 320 |
| FDR1030 | Survey Foundations Borings | 2 | 10 | 20 | 80 |
| FDR1040 | Test Foundations Borings | 5 | 20 | 20 | 320 |
| FDR1050 | Borings Logs Complete | 0 | 0 | 0 | 0 |
| FDR1060 | Design Foundations Recommendation | 5 | 20 | 20 | 160 |
| FDR1070 | Prepare Foundations Report & Submit to Bridge/PM | 2 | 20 | 20 | 40 |
| FDR1080 | Prepare Foundations Special Provisions | 2 | 10 | 20 | 40 |
| FEIS1000 | Respond to DEIS Public Comments | 5 | 10 | 10 | 20 |
| FEIS1010 | Refine Preferred Alternative, Mitigation & Other Analysis | 5 | 40 | 40 | 320 |
| FEIS1020 | Prepare Draft FEIS | 130 | 260 | 2500 | 5000 |
| FEIS1030 | Review Draft FEIS by OES | 20 | 40 | 120 | 240 |
| FEIS1040 | Revise Draft FEIS Based on OES Comments | 10 | 20 | 120 | 240 |
| FEIS1050 | Review Draft FEIS by FHWA | 30 | 60 | 10 | 20 |
| FEIS1060 | Revise Draft FEIS Based on FHWA Comments | 10 | 20 | 120 | 240 |
| FEIS1070 | Review FEIS by DOI (Note: Only if there is a Full 4(f)) | 30 | 60 | 10 | 20 |
| FEIS1080 | Review Draft FEIS by Cooperating Agencies | 20 | 40 | 10 | 20 |
| FEIS1090 | Revise Draft FEIS Based on Cooperating Agencies Comments | 10 | 20 | 120 | 240 |
| FEIS1100 | Conduct Legal Sufficiency by FHWA | 20 | 40 | 10 | 20 |
| FEIS1110 | Revise Draft FEIS Based on FHWA Legal Sufficiency Comments | 10 | 20 | 120 | 240 |
| FEIS1120 | Obtain District, OES, FHWA Signatures For FEIS | 5 | 20 | 10 | 20 |
| FEIS1130 | Submit Federal Register Notice for FEIS | 5 | 20 | 10 | 20 |
| FEIS1140 | Public Comment Period for FEIS | 25 | 35 | 10 | 20 |
| FFC1000 | Prepare Findings of Fact & Conclusions | 5 | 10 | 20 | 80 |
| FFC1010 | Review Findings of Fact & Conclusions by OES | 20 | 40 | 10 | 20 |
| FFC1020 | Revise Findings of Fact & Conclusions | 5 | 20 | 10 | 20 |
| FFC1030 | Review Findings of Fact & Conclusions by FHWA | 20 | 40 | 10 | 20 |
| FFC1040 | Review of Final 4(f) Legal Sufficiency (Note: Only if there is a Full 4(f)) | 20 | 40 | 10 | 20 |
| FON1000 | Request FONSI from FHWA | 2 | 10 | 10 | 20 |
| FON1010 | Issue FONSI by FHWA | 5 | 20 | 10 | 20 |
| FON1020 | Publish Public Notice of FONSI & Negative Declaration | 2 | 10 | 10 | 20 |
| GCS1000 | Request Geodetic Control Survey | 1 | 5 | 4 | 8 |
| GCS1010 | Build Project into DB | 1 | 5 | 4 | 20 |
| GCS1020 | Conduct Geodetic Control Survey Recon | 2 | 10 | 8 | 20 |
| GCS1030 | Perform Geodetic Control Survey Monumentation | 2 | 10 | 20 | 80 |
| GCS1040 | Conduct Geodetic Control Survey Field Observations | 10 | 20 | 40 | 120 |
| GCS1050 | Process Geodetic Control Survey Data | 2 | 10 | 20 | 80 |
| GCS1060 | Submit Geodetic Control Survey Report to District | 2 | 10 | 10 | 20 |
| GCS1070 | Input Geodetic Control Survey Data into DB | 1 | 5 | 4 | 20 |
| GEM1000 | Acquire Geomorphology Consultant | 2 | 10 | 20 | 40 |
| GEM1010 | Conduct Geomorphology (Phase 1) Investigation | 2 | 10 | 20 | 80 |
| GEM1020 | Geomorphology (Phase 1) Review | 2 | 10 | 10 | 20 |
| GEM2000 | Conduct Geomorphology (Phase 2) Investigation | 2 | 10 | 20 | 80 |
| GEM2010 | Geomorphology (Phase 2) Review | 2 | 10 | 10 | 20 |
| GEM2020 | Provide Geomorphology (Phase 2) Determination | 2 | 10 | 10 | 20 |
| GEM2030 | Geomorphology (Phase 2) Complete (No Properties Effected) | 0 | 0 | 10 | 20 |
| GEM2040 | Obtain Geomorphology (Phase 2) SHPO Concurrence | 2 | 10 | 10 | 20 |
| GEM2050 | Provide Geomorphology (Phase 2) Findings | 2 | 10 | 10 | 20 |
| GEM2060 | Geomorphology Findings Complete (No Adverse Effects Determined) | 0 | 0 | 10 | 20 |
| GEM2070 | Obtain Geomorphology (Phase 2) SHPO Concurrence | 2 | 10 | 10 | 20 |
| GEM2080 | Prepare Documentation of Adverse Effect for Geomorphology (Phase 2) | 2 | 10 | 10 | 20 |
| GEM2090 | Prepare MOA/PA for Geomorphology (Phase 2) | 2 | 10 | 10 | 20 |
| GEM2100 | Implement Geomorphology (Phase 2) Mitigation | 2 | 10 | 10 | 20 |
| HAG1000 | Acquire Historical Archeology Consultant | 2 | 10 | 20 | 40 |
| HAG1010 | Conduct Historical Archeology (Phase 1) Investigation | 2 | 10 | 20 | 80 |
| HAG1020 | Historical Archeology (Phase 1) Review | 2 | 10 | 10 | 20 |
| HAG2000 | Conduct Historical Archeology (Phase 2) Investigation | 2 | 10 | 20 | 80 |
| HAG2010 | Historical Archeology (Phase 2) Review | 2 | 10 | 10 | 20 |
| HAG2020 | Provide Historical Archeology (Phase 2) Determination | 2 | 10 | 10 | 20 |
| HAG2030 | Historical Archeology (Phase 2) Complete (No Properties Effected) | 0 | 0 | 10 | 20 |
| HAG2040 | Obtain Historical Archeology (Phase 2) SHPO Concurrence | 2 | 10 | 10 | 20 |
| HAG2050 | Provide Historical Archeology (Phase 2) Findings | 2 | 10 | 10 | 20 |
| HAG2060 | Historical Archeology Findings Complete (No Adverse Effects Determined) | 0 | 0 | 10 | 20 |
| HAG2070 | Obtain Historical Archeology (Phase 2) SHPO Concurrence | 2 | 10 | 10 | 20 |
| HAG2080 | Prepare Documentation of Adverse Effect for Historical Archeology (Phase 2) | 2 | 10 | 10 | 20 |
| HAG2090 | Prepare MOA/PA for Historical Archeology (Phase 2) | 2 | 10 | 10 | 20 |
| HAG2100 | Implement Historical Archeology (Phase 2) Mitigation | 2 | 10 | 10 | 20 |
| HYD1000 | Prepare Hydraulics Recommendations | 10 | 30 | 20 | 40 |
| IDB1000 | Request Scoping Input - Initial | 1 | 10 | 4 | 8 |
| IDB1010 | Identify Potential Scope Items by Project Manager - Initial | 20 | 60 | 20 | 40 |
| IDB1020 | Identify Potential Scope Items by Planning - Initial | 20 | 60 | 20 | 40 |
| IDB1030 | Identify Potential Scope Items by State Aid - Initial | 20 | 60 | 20 | 40 |
| IDB1040 | Identify Potential Scope Items by Land Management - Initial | 20 | 60 | 20 | 40 |
| IDB1050 | Identify Potential Scope Items by Surveys - Initial | 20 | 60 | 20 | 40 |
| IDB1060 | Identify Potential Scope Items by Environmental Coordinator - Initial | 20 | 60 | 20 | 40 |
| IDB1070 | Identify Potential Scope Items by Bridge - Initial | 20 | 60 | 40 | 80 |
| IDB1080 | Identify Potential Scope Items by Resident Office - Initial | 20 | 60 | 20 | 40 |
| IDB1090 | Identify Potential Scope Items by Design - Initial | 20 | 60 | 20 | 40 |
| IDB1100 | Identify Potential Scope Items by Hydraulics/Water Resources - Initial | 20 | 60 | 20 | 80 |
| IDB1110 | Identify Potential Scope Items by Maintenance - Initial | 20 | 60 | 20 | 40 |
| IDB1120 | Identify Potential Scope Items by Materials - Initial | 20 | 60 | 20 | 80 |
| IDB1130 | Identify Potential Scope Items by Traffic - Initial | 20 | 60 | 20 | 40 |
| IDB1140 | Identify Potential Scope Items by Others - Initial | 20 | 60 | 20 | 40 |
| IDB1150 | Determine & Document Initial Baseline Scope | 1 | 60 | 8 | 100 |
| IDB1160 | Develop & Approve Initial Baseline Estimate (TPCE) | 5 | 40 | 20 | 80 |
| IDB1170 | Develop Initial Baseline Schedule | 5 | 30 | 20 | 160 |
| LET1000 | Print Plan and Proposal | 1 | 10 | 10 | 40 |
| LET1005 | Conduct CO Plan Review & Revisions | 10 | 20 | 40 | 120 |
| LET1010 | FHWA Authorization | 1 | 10 | 10 | 20 |
| LET1020 | Advertise Project | 1 | 10 | 10 | 40 |
| LET1030 | Contractor Bidding Period | 15 | 45 | 10 | 20 |
| LPR1000 | Enter Regulatory Program | 2 | 5 | 10 | 20 |
| LPR1010 | Write NAD Request Per Each Parcel | 2 | 8 | 4 | 8 |
| LPR1020 | Regulatory Review Per Each Parcel | 25 | 35 | 10 | 20 |
| LPR1030 | Obtain Assurance From Regulators For Each Parcel | 2 | 5 | 4 | 8 |
| LPR1040 | Send EDD 2 Form to District & OLM | 2 | 10 | 4 | 8 |
| LPR1050 | Obtain No Further Action Letter for Each Parcel | 25 | 35 | 4 | 8 |
| MDR1000 | Conduct Borings | 2 | 40 | 40 | 400 |
| MDR1010 | Design Pavement Alternatives | 2 | 20 | 32 | 180 |
| MDR1020 | Prepare LCCA | 2 | 20 | 24 | 140 |
| MDR1030 | Review LCCA by Maplewood | 2 | 20 | 24 | 140 |
| MDR1040 | Review LCCA by Industry | 2 | 20 | 10 | 20 |
| MDR1050 | Revise Pavement Design | 2 | 20 | 16 | 80 |
| MDR1060 | Prepare MDR | 2 | 40 | 40 | 240 |
| MS_100 | Project Initiated | 0 | 0 | 0 | 0 |
| MS_110 | Initial Design Project Baselined | 0 | 0 | 0 | 0 |
| MS_120 | Layout Staff Approved | 0 | 0 | 0 | 0 |
| MS_130 | Construction Limits Completed | 0 | 0 | 0 | 0 |
| MS_140 | Municipal Consent Obtained | 0 | 0 | 0 | 0 |
| MS_150 | Environmental Document Approved | 0 | 0 | 0 | 0 |
| MS_160 | Preliminary Bridge Design Completed | 0 | 0 | 0 | 0 |
| MS_170 | Final Design Project Baselined | 0 | 0 | 0 | 0 |
| MS_180 | MDR Completed | 0 | 0 | 0 | 0 |
| MS_190 | Utility Notice and Orders Sent | 0 | 0 | 0 | 0 |
| MS_200 | Municipal Agreement Request Submitted | 0 | 0 | 0 | 0 |
| MS_210 | Roadway Plans Ready | 0 | 0 | 0 | 0 |
| MS_220 | Final Bridge Plans Ready | 0 | 0 | 0 | 0 |
| MS_230 | Project Turned In | 0 | 0 | 0 | 0 |
| MS_240 | Permits Acquired | 0 | 0 | 0 | 0 |
| MS_250 | RW Title and Possession Obtained | 0 | 0 | 0 | 0 |
| MS_260 | FHWA Authorization Received | 0 | 0 | 0 | 0 |
| MS_270 | Letting | 0 | 0 | 0 | 0 |
| NOI1010 | Procure Prequalified Noise Analysis Consultant | 40 | 80 | 20 | 40 |
| NOI1020 | Develop/Approve Receptor Sites - Noise | 2 | 10 | 4 | 20 |
| NOI1030 | Conduct Noise Monitoring | 5 | 20 | 40 | 100 |
| NOI1040 | Conduct Noise Modeling for Preferred Alternative | 2 | 10 | 20 | 40 |
| NOI1110 | Prepare Draft Noise Report for Preferred Alternative | 2 | 10 | 40 | 80 |
| NOI1120 | Review Draft Noise Report for Preferred Alternative | 5 | 20 | 10 | 20 |
| NOI1130 | Revise Draft Noise Report for Preferred Alternative | 10 | 20 | 10 | 20 |
| NOI1140 | Review Draft Noise Report for Preferred Alternative by EMTU | 10 | 20 | 10 | 20 |
| NOI1150 | Prepare Final Noise Report for Preferred Alternative | 10 | 20 | 10 | 20 |
| NPD1000 | Staff Approved Layout Review by MPCA | 10 | 60 | 10 | 20 |
| NPD1010 | 60% Plan Review & Approval Letter by MPCA | 10 | 60 | 10 | 20 |
| NPD1020 | Prepare NPDES Permit Application | 2 | 20 | 20 | 60 |
| OPM1000 | Perform Ongoing Project Management | 250 | 1500 | 250 | 1500 |
| PCA1000 | Acquire Pre-Contact Archeology Consultant | 2 | 10 | 20 | 40 |
| PCA1010 | Conduct Pre-Contact Archeology (Phase 1) Investigation | 2 | 10 | 20 | 80 |
| PCA1020 | Pre-Contact Archeology (Phase 1) Review | 2 | 10 | 10 | 20 |
| PCA2000 | Conduct Pre-Contact Archeology (Phase 2) Investigation | 2 | 10 | 20 | 80 |
| PCA2010 | Pre-Contact Archeology (Phase 2) Review | 2 | 10 | 10 | 20 |
| PCA2020 | Provide Pre-Contact Archeology (Phase 2) Determination | 2 | 10 | 10 | 20 |
| PCA2030 | Pre-Contact Archeology (Phase 2) Complete (No Properties Effected) | 0 | 0 | 10 | 20 |
| PCA2040 | Obtain Pre-Contact Archeology (Phase 2) SHPO Concurrence | 2 | 10 | 10 | 20 |
| PCA2050 | Provide Pre-Contact Archeology (Phase 2) Findings | 2 | 10 | 10 | 20 |
| PCA2060 | Pre-Contact Archeology Findings Complete (No Adverse Effects Determined) | 0 | 0 | 10 | 20 |
| PCA2070 | Obtain Pre-Contact Archeology (Phase 2) SHPO Concurrence | 2 | 10 | 10 | 20 |
| PCA2080 | Prepare Documentation of Adverse Effect for Pre-Contact Archeology (Phase 2) | 2 | 10 | 10 | 20 |
| PCA2090 | Prepare MOA/PA for Pre-Contact Archeology (Phase 2) | 2 | 10 | 10 | 20 |
| PCA2100 | Implement Pre-Contact Archeology (Phase 2) Mitigation | 2 | 10 | 10 | 20 |
| PCS1000 | Conduct Project Control Survey Recon | 2 | 10 | 8 | 20 |
| PCS1010 | Perform Project Control Survey Monumentation | 2 | 10 | 20 | 80 |
| PCS1020 | Conduct Project Control Survey Field Observations | 10 | 20 | 40 | 120 |
| PCS1030 | Process Project Control Survey Data | 2 | 10 | 20 | 80 |
| PCS1040 | Input Project Control Survey Data into DB | 1 | 5 | 4 | 20 |
| PLN1000 | Prepare Road Plans & Special Provisions | 60 | 260 | 480 | 4160 |
| PLN1040 | Prepare Moderate Preservation Special Provisions | 20 | 60 | 80 | 400 |
| PLN3010 | Prepare Title Page | 1 | 10 | 8 | 40 |
| PLN3020 | Prepare General Layout | 2 | 20 | 16 | 80 |
| PLN3030 | Prepare Typical Sections | 2 | 20 | 16 | 80 |
| PLN3040 | Prepare Inplace Topography Sheets | 2 | 20 | 16 | 80 |
| PLN3050 | Prepare Construction Plan Sheets | 2 | 60 | 16 | 800 |
| PLN3060 | Prepare Profile Sheets | 2 | 60 | 16 | 800 |
| PLN6010 | Prepare Earthwork Tab & Summary | 2 | 10 | 16 | 64 |
| PLN6020 | Prepare Soils & Construction Notes | 2 | 10 | 16 | 64 |
| PLN6030 | Prepare Tabulated Quantities | 2 | 40 | 16 | 240 |
| PLN6040 | Prepare Utility Tabs | 2 | 40 | 16 | 240 |
| PLN6050 | Prepare Special Environmental Plan | 2 | 40 | 16 | 240 |
| PLN6060 | Prepare Alignment Plan & Tabs | 2 | 20 | 16 | 120 |
| PLN6070 | Prepare Removal Plans | 2 | 20 | 16 | 120 |
| PLN6080 | Prepare Drainage Plans Profiles & Tabs | 2 | 40 | 16 | 280 |
| PLN6090 | Prepare Stormwater Pollution Prevention Plan (SWPPP) & Water Resources Notes | 2 | 40 | 16 | 280 |
| PLN6100 | Prepare Erosion Control Plan | 2 | 20 | 16 | 120 |
| PLN6110 | Prepare Traffic Barrier Plan | 2 | 20 | 16 | 120 |
| PLN6120 | Prepare Cross Sections & Cross Section Matchline Layout | 2 | 60 | 16 | 800 |
| PLN9010 | Prepare Statement of Estimated Quantities | 2 | 20 | 16 | 120 |
| PLN9020 | List Standard Plates | 2 | 10 | 16 | 80 |
| PLN9030 | Develop Details | 2 | 40 | 16 | 520 |
| PLN9040 | Incorporate Standard Plans | 2 | 10 | 16 | 80 |
| PLN9050 | Develop Intersection Details | 2 | 40 | 16 | 280 |
| PLN9060 | Develop Pedestrian Accommodation Details | 2 | 20 | 16 | 120 |
| PLN9070 | Prepare Concrete Paving Plan & Details | 2 | 40 | 16 | 520 |
| PLN9080 | Prepare Bituminous Paving Plan & Details | 2 | 40 | 16 | 520 |
| PLN9090 | Prepare Superelevation Plans | 2 | 20 | 16 | 120 |
| PLN9100 | Develop Drainage Details | 2 | 40 | 16 | 520 |
| PLN9110 | Prepare Turf Establishment Plans | 2 | 20 | 16 | 120 |
| PLN9120 | Prepare Impact Attenuator Plan & Details | 2 | 20 | 16 | 120 |
| PLN9130 | Develop Traffic Barrier Details | 2 | 20 | 16 | 120 |
| PLN9140 | Prepare Fencing Plans | 2 | 20 | 16 | 120 |
| PLN9150 | Prepare Temporary Pedestrian Access Route | 2 | 20 | 16 | 120 |
| PLN9160 | Prepare 90% Plans Special Provisions | 2 | 40 | 16 | 240 |
| PLN9170 | Assemble 90% Plan | 2 | 10 | 16 | 80 |
| PLR1340 | Prepare 95% Plans Special Provisions | 2 | 40 | 16 | 240 |
| POD1000 | Determine Pond Size & Location | 2 | 20 | 16 | 120 |
| POD1010 | Design Pond Contours, Drainage Structures, & Seeding | 2 | 40 | 16 | 280 |
| PSP1000 | Determine Permit Requirements by OLM | 10 | 40 | 20 | 60 |
| PSP1010 | Review Signing Special Provisions by OTST | 10 | 40 | 20 | 80 |
| PSP1020 | Review Lighting Special Provisions by OTST | 10 | 40 | 20 | 80 |
| PSP1030 | Review Signal Special Provisions by OTST | 10 | 40 | 20 | 80 |
| PSP1040 | Obtain Right of Way Authorization by OLM | 10 | 40 | 20 | 80 |
| PSP1050 | Review Bridge Plans & Special Provisions by Bridge Office | 10 | 40 | 40 | 160 |
| PSP1060 | Assemble Special Provisions & Prepare /Proposal | 10 | 40 | 20 | 80 |
| PSP1070 | Conduct CO Plan Review & Revisions | 10 | 40 | 20 | 80 |
| PSP1080 | Obtain Environmental Approvals by OES | 10 | 40 | 10 | 60 |
| PTI1000 | Review Final Plan by District | 10 | 40 | 40 | 180 |
| PTI1010 | Revise Final Plan | 5 | 40 | 40 | 320 |
| PTI1020 | Conduct 100% Quality Control Check Process by District | 5 | 40 | 40 | 200 |
| PTI1030 | Prepare Final Construction Cost Estimate by District | 5 | 40 | 20 | 80 |
| PTI1040 | Prepare Submittal Memo and Submit Plans & Specs | 5 | 40 | 20 | 64 |
| PUB1000 | Perform Resident Coordination | 250 | 1500 | 80 | 480 |
| PUB1010 | Perform Business Coordination | 250 | 1500 | 80 | 480 |
| PUB1020 | Perform Interest Group Coordination | 250 | 1500 | 80 | 480 |
| PUB1030 | Perform Airport Coordination | 250 | 1500 | 80 | 480 |
| PUB1040 | Perform Railroad Coordination | 250 | 1500 | 80 | 480 |
| PUB1050 | Perform Transit Coordination | 250 | 1500 | 80 | 480 |
| PUB1060 | Perform Emergency Services Coordination | 250 | 1500 | 80 | 480 |
| PUB1070 | Perform School Coordination | 250 | 1500 | 80 | 480 |
| PUB1080 | Perform City Coordination | 250 | 1500 | 80 | 480 |
| PUB1090 | Perform County Coordination | 250 | 1500 | 80 | 480 |
| PUB1100 | Perform DNR Coordination | 250 | 1500 | 80 | 480 |
| PUB1110 | Perform MPCA Coordination | 250 | 1500 | 80 | 480 |
| PUB1120 | Perform SHPO Coordination | 250 | 1500 | 80 | 480 |
| PUB1130 | Perform FHWA Coordination | 250 | 1500 | 80 | 480 |
| PUB1140 | Perform Tribal Coordination | 250 | 1500 | 80 | 480 |
| PUB1150 | Perform Major Projects Coordination | 250 | 1500 | 80 | 480 |
| RAP1000 | Prepare Response Action Plan | 20 | 40 | 20 | 80 |
| RAP1010 | Submit Response Action Plan to Regulator | 20 | 40 | 4 | 8 |
| RCD1000 | Good Faith Negotiation Period | 10 | 40 | 40 | 400 |
| RCD1010 | Call Back Memo | 1 | 5 | 4 | 8 |
| RCD1020 | Assemble Condemnation Package | 2 | 10 | 10 | 20 |
| RCD1030 | Supplement Condemnation Package | 2 | 10 | 4 | 8 |
| RCD1040 | Update Titles Opinion | 5 | 20 | 20 | 200 |
| RCD1050 | Identify Affected Commissioner's Orders | 1 | 5 | 4 | 8 |
| RCD1060 | Investigate/Update ACOT | 2 | 10 | 10 | 20 |
| RCD1070 | Draft Petition | 2 | 10 | 10 | 20 |
| RCD1080 | Request Condemnation Acton | 2 | 10 | 10 | 20 |
| RCD1090 | Obtain Hearing Date | 5 | 15 | 4 | 8 |
| RCD1100 | Prepare Condemnation Notice | 5 | 25 | 10 | 100 |
| RCD1110 | Serve Condemnation Notice | 10 | 40 | 4 | 40 |
| RCD1120 | 90 Day Quick Take Period | 65 | 65 | 20 | 200 |
| RCD1130 | Prehearing Meeting | 10 | 40 | 10 | 20 |
| RCD1140 | File Proof of Service | 1 | 5 | 4 | 8 |
| RCD1150 | Hearing on Petition | 5 | 20 | 10 | 40 |
| RCD1160 | 35 Day Waiting Period for Title and Possession | 25 | 25 | 10 | 20 |
| RCD1170 | Judge Signs Court Order | 2 | 10 | 10 | 20 |
| RCD1180 | AG Request Quick Take Payment | 2 | 10 | 10 | 20 |
| RCD1190 | Process & Make Payment | 2 | 10 | 10 | 40 |
| RCD1200 | Quick Take Notice Period | 5 | 5 | 10 | 20 |
| RCD1210 | Title & Possession | 0 | 0 | 10 | 20 |
| RCL1000 | Prepare Preliminary Cross Sections | 2 | 10 | 20 | 80 |
| RCL1010 | Review & Revise Preliminary Cross Sections | 5 | 15 | 5 | 20 |
| RCL1020 | Prepare & Submit Construction Limits | 2 | 10 | 10 | 20 |
| RDP1000 | Direct Purchase Offer | 5 | 20 | 20 | 80 |
| RDP1010 | Direct Purchase Negotiation | 10 | 40 | 20 | 200 |
| RDP1020 | Admiinistrative Settlement | 2 | 10 | 10 | 20 |
| RDP1030 | Purchase | 2 | 10 | 10 | 20 |
| RDP1040 | State Acceptance Date | 10 | 40 | 10 | 20 |
| RDP1050 | Closing Package | 5 | 20 | 20 | 40 |
| RDP1060 | Direct Purchase Final Payment | 2 | 10 | 10 | 20 |
| RFR1000 | Identify Known Contaminated Sites on Regulatory Website Review | 2 | 10 | 10 | 40 |
| RFR1010 | Request Files From Regulator | 20 | 30 | 10 | 20 |
| RFR1020 | Review Regulator Files | 5 | 20 | 20 | 40 |
| RFR1030 | Summarize Regulatory File Findings | 2 | 10 | 10 | 20 |
| ROD1000 | Develop Record of Decision | 2 | 10 | 20 | 60 |
| ROD1010 | Review Record of Decision by OES | 2 | 10 | 10 | 20 |
| ROD1020 | Revise Record of Decision Based on OES Comments | 20 | 40 | 10 | 20 |
| ROD1030 | Review Record of Decision by FHWA | 5 | 10 | 10 | 20 |
| ROD1040 | Revise Record of Decision Based on FHWA Comments | 20 | 40 | 10 | 20 |
| ROD1050 | Issue Record of Decision by FHWA | 5 | 10 | 10 | 20 |
| RPA1000 | Right of Way Receive and Distribute | 1 | 5 | 5 | 20 |
| RPA1010 | Review and Approve Legal Descriptions | 2 | 10 | 10 | 100 |
| RPA1020 | Review and Approve Plats | 10 | 40 | 20 | 200 |
| RPA1030 | File Plats | 1 | 5 | 5 | 10 |
| RPA1040 | Attorney's Condition of Title | 2 | 10 | 5 | 10 |
| RPA1050 | Conveyance Documents | 5 | 20 | 5 | 10 |
| RPA1060 | Commissioner's Orders | 2 | 10 | 5 | 10 |
| RPA1070 | Encumber Funds | 1 | 5 | 5 | 10 |
| RPA1080 | Direct Purchase Documents | 1 | 5 | 5 | 10 |
| RTO1000 | Title Map | 1 | 5 | 10 | 20 |
| RTO1010 | Prepare Title Opinions | 10 | 40 | 10 | 100 |
| RTO1020 | Unrecorded Utilities Easements | 10 | 40 | 10 | 40 |
| RVL1000 | Procure Valuation Consultant | 20 | 40 | 20 | 40 |
| RVL1010 | Complete Valuations | 40 | 80 | 20 | 200 |
| RVL1020 | Review & Certify Valuations | 10 | 20 | 10 | 40 |
| RVW3000 | Conduct 30% Plan Functional Group Review | 5 | 20 | 8 | 160 |
| RVW6000 | Conduct 60% Plan Functional Group Review | 5 | 20 | 8 | 160 |
| RWP1000 | Authorization Map | 10 | 40 | 20 | 40 |
| RWP1010 | Work Map | 20 | 60 | 40 | 80 |
| RWP1020 | Prepare Plats | 20 | 80 | 40 | 640 |
| RWP1030 | Market Data | 2 | 10 | 20 | 60 |
| RWP1040 | Parcel Sketches | 10 | 40 | 10 | 100 |
| RWP1050 | Field Titles | 10 | 40 | 10 | 100 |
| RWP1060 | Write Legal Descriptions | 5 | 40 | 10 | 200 |
| RWP1070 | Prepare Right of Way Packages | 2 | 10 | 10 | 80 |
| SAL1000 | Develop Alternative Concepts | 10 | 40 | 20 | 200 |
| SAL1010 | Develop Preliminary Layouts | 10 | 80 | 40 | 400 |
| SAL1020 | Conduct Layout Review & Coordination | 20 | 100 | 20 | 200 |
| SAL1030 | Select Preferred Alternative | 10 | 40 | 10 | 40 |
| SAL1040 | Prepare Final Geometric Layout & Profile | 10 | 40 | 40 | 800 |
| SAL1050 | Review Geometric Layout by Distict | 5 | 20 | 10 | 100 |
| SAL1060 | Review Geometric Layout by GDSU | 20 | 40 | 10 | 100 |
| SAL1070 | Revise, Sign, & Distribute Geometric Layout | 10 | 40 | 20 | 120 |
| SDD1000 | Prepare Draft Final SDD | 5 | 10 | 20 | 40 |
| SDD1010 | Review Draft Final SDD by FHWA & OES | 20 | 40 | 10 | 20 |
| SDD1020 | Revise & Issue Draft Final SDD by OES | 5 | 10 | 10 | 20 |
| SSD1000 | Determine Drainage Areas & Flows for Storm Sewers | 5 | 60 | 40 | 200 |
| SSD1010 | Determine Storm Sewer Size & Flow Lines | 5 | 60 | 40 | 200 |
| SUR1000 | Submit Preliminary Survey Request | 2 | 20 | 4 | 20 |
| SUR1005 | Submit Final Survey Request | 2 | 20 | 4 | 20 |
| SUR1010 | Perform Existing Alignment Office Research | 5 | 30 | 10 | 40 |
| SUR1020 | Conduct Existing Alignment Field Work | 20 | 120 | 80 | 480 |
| SUR1030 | Construct Existing Alignment Survey File | 5 | 30 | 10 | 40 |
| SUR1040 | Conduct Topography Survey Field Work | 20 | 120 | 80 | 480 |
| SUR1045 | Conduct Topography/DTM Survey | 10 | 30 | 40 | 240 |
| SUR1050 | Construct Topography Survey File | 5 | 30 | 10 | 40 |
| SUR1060 | Conduct Drainage Survey Field Work | 20 | 120 | 80 | 480 |
| SUR1065 | Conduct Drainage Survey | 10 | 30 | 40 | 240 |
| SUR1070 | Construct Drainage Survey File | 5 | 30 | 10 | 40 |
| SUR1080 | Conduct Utilities Survey Field Work | 20 | 120 | 40 | 480 |
| SUR1085 | Conduct Utilities Survey | 10 | 30 | 20 | 240 |
| SUR1090 | Construct Utilities Survey File | 5 | 30 | 10 | 40 |
| TMP1000 | Prepare Transportation Management Plan (TMP) | 5 | 30 | 80 | 320 |
| TRC1000 | Develop Traffic Counting Plan | 2 | 8 | 16 | 40 |
| TRC1010 | Conduct Traffic Counts & Process Data | 2 | 20 | 16 | 160 |
| TRC1020 | Prepare Traffic Count Report | 2 | 20 | 40 | 160 |
| TRF1000 | Prepare Traffic Forecasts | 5 | 20 | 10 | 20 |
| TRF1010 | Calculate ESALs | 5 | 20 | 10 | 20 |
| UTA1000 | Prepare & Submit Draft Utility Agreement | 1 | 10 | 20 | 80 |
| UTA1010 | Negotiate Utility Agreement & Submit for Approval | 10 | 40 | 80 | 240 |
| UTA1020 | Obtain Approval of Utility Agreement | 20 | 60 | 10 | 40 |
| UTI1000 | Send Plan Information & Conduct Utility Information Meetings | 10 | 40 | 32 | 120 |
| UTI1005 | Prepare & Send Utility Information Only Letters | 2 | 10 | 10 | 20 |
| UTI1010 | Conduct Utility Design Meeting | 5 | 40 | 20 | 60 |
| UTI1020 | Obtain & Review Utility Relocation Plans | 10 | 40 | 32 | 160 |
| UTI1030 | Prepare & Send Utility Verification Letters | 2 | 5 | 10 | 20 |
| UTI1040 | Utility Permit Application Prepared by Utility Company | 5 | 60 | 10 | 20 |
| UTI1050 | Review Utility Permit Application by District | 5 | 20 | 10 | 40 |
| UTI1060 | Prepare & Approve Utility Permit by CO Utilities Unit | 5 | 20 | 10 | 40 |
| UTI1070 | Prepare & Send Utility Notice & Orders | 1 | 5 | 10 | 20 |
| WDP1000 | Prepare Watershed District Permit | 20 | 40 | 20 | 40 |
| X | Prepare 95% Plans Special Provisions | 2 | 40 | 16 | 240 |
| X | Prepare 95% Design Special Provisions | 2 | 40 | 16 | 240 |
| X | Prepare Moderate Preservation Special Provisions | 2 | 40 | 16 | 240 |
| X | Prepare Scope of Work/Obtain Cost Estimate to Hire Consultant - Phase II (High Risk) | 5 | 20 | 20 | 40 |
| X | Prepare Scope of Work/Obtain Cost Estimate to Hire Consultant for Phase I/II | 5 | 20 | 20 | 40 |
| X | Prepare Scope of Work/Obtain Cost Estimate to Hire Consultant | 5 | 20 | 20 | 40 |