WORKSHEET

for

Defining the Role of

MnDOT Project Managers

Contents

Introduction and Instructions

- What Is This Worksheet?

- Worksheet Usage Notes

The Worksheet

- General PM Role

- Project Concept Definition Role

- Project Scoping and Baselining

- Project Pre-Design

- Project Design Role

- Project Post-Letting Role

- Functional Group Resource Management Role

- Project Execution, Monitoring and Control Role

- Risk Management Role

- Project Team on-Going Communications Role

- Consultant Management Role

- PM Interface with MnDOT Leadership

- Role in Working with External Stakeholders

- Project Team Leadership Role

- Project Closure Role

- PM Role in Understanding / Applying MnDOT Infrastructure

- Role in Advancing the Discipline of Project Management in MnDOT

Introduction and Instructions

What Is This Worksheet?

This worksheet is a tool to develop a definition of the role and accountabilities for project managers managing MnDOT construction projects. This worksheet provides the following:

- A framework of topics that define the areas of a PM role and accountabilities

- A background summary for each topic to establish a common understanding of what each role is

- Draft PM role draft wording to provide a starting point for customized role definitions

- Alternative role variations for selected roles where variations are common

Worksheet Usage Notes

PM Role Definition Working Teams - Multiple Team Approach

- The PM role definition effort will involve several teams of PMs and Functional Group individuals working to capture ideas on what the PM role should be with each team working independently with facilitators

- Differences of opinion will be noted with rationale

- As each team is interviewed, the facilitators might update the worksheet with new role categories or role clarifications for use by subsequent teams; in any case and at completion, all teams will have an opportunity to review and comment on the final draft role definition prior to a review with leadership for leadership input

- Leadership from all districts and the central office will be involved in the leadership review

- For areas of work for which the role may vary widely from project to project and would be based on the circumstances for a given project, that role might not be included in the final role definition or might be included with application notes

Purpose of Team Meetings

- To capture attendees views and ideas on the PM role and authorities

- To identify areas of role agreement

- To identify areas of role non-agreement including rationale for different views

- It is not intended that the team meetings to complete the worksheet would result in consensus on every role topic

Meeting Process for Each Team

- Several meetings will typically be needed for each team

- For a given meeting, the team members will be notified of a subset of the worksheet role definitions that will be addressed in a given meeting

- Team members will collect their thoughts on those worksheet sections allocated to a given meeting prior to a given meeting and will be prepared to provide their inputs verbally at the meeting

- The meeting facilitators will capture all views and comments

- Where extensive re-writes are generated by any given team member, those would be discussed in the meeting and then emailed to the facilitators after the meeting

- The first team meeting is planned to be a face to face in St. Paul with all subsequent meetings intended to be virtual

- As each meeting is conducted, the facilitators will collect all views, clarify team member inputs, identify areas of agreement and areas of disagreement with rationale

- After each meeting, the facilitators will provide an updated worksheet that includes team comments

Role Definition Ground Rules

- A concise, but substantive and definitive, role definition is needed

- The resulting PM role definition is….

  - Is NOT how the role is accomplished today

  - Is NOT what role is viewed to be politically acceptable

  - Is NOT what role is best for the biggest projects

  - Is the best definition of the PM’s role on all construction projects to support project and MnDOT success

Worksheet and Meetings Level of Detail vs. Final Published PM Role Definition

- The worksheet and the meetings that will be used to capture ideas on the PM role will typically involve more detailed and more complex discussions than what the final published role definition will be

- The detail is needed to ensure the eventual role definition has considered the many variables associated with defining the PM role

- The final MnDOT PM Role Definition is intended to be a small number of pages, with a goal of 3 to 5 pages

- During meeting discussions, the level of detail will be managed by the facilitators as sufficient detail is needed to ensure a sound definition results while too much detail can generate a threat of stalling progress

Guidelines for the Level of Detail

- The final role definition will embody role definitions that are

  - Sufficiently substantive and definitive…..

    - To provide a sound definition of what the PM does and does not do

    - To avoid role confusion

    - To support project and MnDOT success

  - Sufficiently general and broad….

    - To apply to all  projects

    - To be easily understood, accepted and implemented

- It will be the shared responsibility of the meeting facilitators and the team to support the attainment of the above guidelines

Team Meeting Instructions and Agenda

- Preparation - Meeting attendees are expected to have reviewed the PM role topics allocated to a given meeting and to be prepared to offer comments in the meeting on each role topic as it is discussed.

- Review of Past Work - Where a meeting is an extension to a previous meeting, the facilitator will review what was done at the prior meeting.

- Topic Introduction – For each role topic in the worksheet, the meeting facilitators will introduce a given PM role topic by discussing what the topic is, why it is important and any background information that is pertinent.

- Questions on Topic Scope or Intent - The facilitators will ask the entire group if there are any questions about the scope of the role topic before comments are solicited to ensure all have a common understanding of what the role topic is and is not.

- Potential Wording Introduction - The facilitators will review the “potential wording” included in the worksheet, where such exists, and may include any rationale for the potential wording where that applies.

- Each Attendee Offers Comments - Each meeting attendee will be asked, in turn, to offer their thoughts on what this role should be. This might be agreement on the draft content, disagreement, new role information to be included or information to be deleted. Each attendee will indicate if any part, or all, of the potential wording is a “Show Stopper” meaning that the respective wording is completely unacceptable. Each attendee, in turn, would offer comments or proposed wording changes. The facilitator will capture the comments from each attendee and will repeat those back to each attendee to ensure accuracy. Clarifications or questions by the group may be a part of the response from a given attendee.

- Off Topic but Important Comments Put in “Parking Lot” – Where any ideas or comments or recommendations surface in a meeting that are adjacent to the core purpose of the meeting, those topics can be put in a “parking lot” list for potential consideration later or for review to some other individual or organization.

- Show Stopper Disagreements Identified – Should significant disagreements exist for a given role topic such that any one or more meeting attendees could not live with a given role wording, the facilitators will identify those disagreements as “Show Stoppers.” It is not the intent of these team meetings to resolve such differences but if a short discussion might provide resolution, the facilitators might allow such discussion.

- Differences of Opinion - Where different views on the role definition for a given role topic exist, the facilitator will capture those disagreements with rationale for each position taken. Resolution of disagreements will be addressed in each meeting as is possible. Where differences of views are not resolvable in a given meeting, resolution will happen after all teams are interviewed and the remaining differences are presented to leadership.

- Final Comments or Questions and Topic Closure - As all attendees have responded to a given role topic, the facilitator will ask the group if there are any additional thoughts to be captured for that topic. The facilitator will review what thoughts have been captured for that topic and verify accuracy with the group before moving to the next role topic.

- Meeting Record After the Meeting – After the meeting, the facilitator will update the worksheet and forward to all with a request to identify any discrepancies.

<<  Return to Contents >>

The Worksheet

Potential Role Definition Wording and Your Input

1)-General PM Role

- The project manager’s role is to lead and manage a project to meet all project goals, requirements and within the constraints defined for each project.

- The PM is accountable for the project overall.

- The PM is responsible to initiate, plan, perform, control and complete the project successfully. The project manager acts as a facilitator of project work and as a single point of contact for all stakeholders involved in the project.

- The PM is proactive in supporting project success and seeks out issues to resolve vs. waiting for issues to become real problems.

- The PM is responsible for ensuring the project work and team comply with all pertinent organization processes and policies and all regulatory and legal constraints that apply to a given project.

- The PM acts in an ethical manner and leads the team to do the same.

- The PM seeks to build an understanding of the organization, its processes, systems, roles and culture in the team to best support the successful projects.

- The PM builds and maintains an awareness of true customer priorities and needs.

- The PM considers each project a “business on to itself” and manages the project with a clear “business sense.”

===========================================================

Your Working Area

Prepare your role definition here.

1)-General PM Role

Select one of the options below and then add information as needed.

☐ No Showstoppers – Nothing in the potential wording is totally unacceptable

☐ Showstoppers Exist – The potential wording is unacceptable

Select one of the options below.

☐ Use potential wording “as is”

☐ Modify the potential wording as follows: (insert your comments below)

☐ Replace all potential wording with the following new wording: (insert your new wording below)

Your Comments:

- Xx

- Xx

- xx

<<  Return to Contents >>

=================================================================================

=================================================================================

=================================================================================

2)-Project Concept Definition Role

Background – MnDOT currently has a centralized process for programming projects using State Preservation Program (SPP) funds for pavements and bridges and Highway Safety Improvement Program (HSIP) funds.  The role of the project manager has not been clearly defined in the selection of the projects or the establishment of project parameters.

District functional groups select projects using the District Risk Management Funding.  The role of the project manager has not been clearly defined in the selection of projects or development of project parameters.

District planning staff may initiate planning or corridor studies that result in anticipated projects.  However, a project manager may not have been involved to help develop the project concepts and parameters resulting in discontinuity.

The role for the project manager related to “Project Concept Definition” phase efforts applies to the following project types.

- State Preservation Program (SPP) and (HSIP)

- District Risk Management Program (DRMP)

- Planning and Corridor Studies – District

The PM shall:

- Maintain an awareness of new projects and the parameters established when the projects were programmed.

- Take action to insert themselves into the project programming efforts to ensure their involvement can sufficiently support subsequent scoping and baselining efforts

- Participate in planning studies, at appropriate times, to guide the outcomes such that resulting project recommendations result in projects that can be developed within a defined scope, schedule, and budget.

===========================================================

Your Working Area

Prepare your role definition here.

2)-Project Concept Definition Role

Select one of the options below and then add information as needed.

☐ No Showstoppers – Nothing in the potential wording is totally unacceptable

☐ Showstoppers Exist – The potential wording is unacceptable

Select one of the options below.

☐ Use potential wording “as is”

☐ Modify the potential wording as follows: (insert your comments below)

☐ Replace all potential wording with the following new wording: (insert your new wording below)

Your Comments:

- Xx

- Xx

- xx

<<  Return to Contents >>

=================================================================================

=================================================================================

=================================================================================

3)-Project Scoping and Baselining

Background – MnDOT project managers are expected to lead projects through the scoping and baselining phase to ensure that project parameters are well established.  Well scoped projects are less likely to experience delay, scope creep, or budget overruns.

- a) General Project Startup Role

  - Project Requirements and Definition - Ensures the project requirements and the definition of the project is sufficiently complete and accurate to support adequate project scoping and baselining

  - Project Constraints - Ensures that known project constraints including budgets, schedules and requirements and design constraints are defined.

  - Functional Group Identification to Support Scoping – Identifies the set of MnDOT functional groups that will be needed to support the project.

  - Project Startup Information Communication - Ensures that project start up information (such as the above information) is communicated to, and understood by, all appropriate stakeholders

  - External Stakeholders - Identifies external stakeholders and their project involvement.

  - Management Approach - Establishes how the project will be managed and how the project team will communicate.

- b) Scope Finalization

  - Solicits and receives scoping input from affected functional and specialty offices

  - Facilitates resolution of scoping comments

  - Ensures scoping issues identified conform to project constraints

  - Validates final scope definition baseline

- c) Work Definition (WBS) and Schedule Development Role

  - Conducts work package concurrence meetings with affected functional and specialty offices

  - Validates completeness and accuracy of work package definitions to fully align with needed project work

  - Initiates development of schedule with Shared Service Center scheduling staff

  - Obtains schedule concurrence from affected functional and specialty offices

- d) Budget Development Role

  - Works with functional and specialty offices, Shared Service Center staff, and programming staff to establish project budget

  - Works with staff to identify budget risks

  - Ensures budgets exist for all project work

- e) Role for Ensuring Scope, Budget and Schedule are Mutually Compatible

  - Ensures project scope, budget, and schedule are mutually compatible can be delivered prior to programming

Your Working Area

Prepare your role definition here.

3)-Project Scoping and Baselining

Select one of the options below and then add information as needed.

☐ No Showstoppers – Nothing in the potential wording is totally unacceptable

☐ Showstoppers Exist – The potential wording is unacceptable

Select one of the options below.

☐ Use potential wording “as is”

☐ Modify the potential wording as follows: (insert your comments below)

☐ Replace all potential wording with the following new wording: (insert your new wording below)

Your Comments:

- Xx

- Xx

- xx

<<  Return to Contents >>

===========================================================

===========================================================

===========================================================

4)-Project Pre-Design – Concept, Layout Development and Environmental Role

Background – The development of a project concept, layout, and environmental review can involve resolving many conflicting points of view.  A project’s success relies on these issues being identified and resolved.

It is the role of the project manager in the Pre-Design phase to:

- Project Management Functions, Pre-Design

  - Public engagement – Ensures that an appropriate public engagement program is established for the project and that all affected parties are identified and included in the project development process.  Draws upon resources and techniques as appropriate to ensure success. Leads the public engagement effort.

  - Coordination with Environmental Agencies and Development of Environmental Strategies – Works with specialty office staff and environmental review agencies to ensure environmental issues are addressed. Prepares, or ensures the preparation of, needed environmental coordination document.

  - Consistent Baselines - Ensures that scope, schedule, and budget are maintained during the project development

- Technical Functions, Pre-Design

  - Selection of design standards – Works with specialty offices and communities to gather input on appropriate design standards for the project and program constraints and the context of the project.  Selects appropriate design standards.

  - Technical Data Development - Works with functional groups and specialty offices to ensure that technical data is developed and used in the concept development, i.e. traffic counts

  - Coordination and development of concepts – Oversees the development of the concepts and layout to ensure that the project objectives are met within the project constraints and selected design standards.

- Project Consultant Agreements – Identifies work to be performed by project consultants and initiates actions to select and establish agreements with needed external businesses.

===========================================================

Your Working Area

Prepare your role definition here.

4)-Project Pre-Design – Concept, Layout Development

and Environmental Role

Select one of the options below and then add information as needed.

☐ No Showstoppers – Nothing in the potential wording is totally unacceptable

☐ Showstoppers Exist – The potential wording is unacceptable

Select one of the options below.

☐ Use potential wording “as is”

☐ Modify the potential wording as follows: (insert your comments below)

☐ Replace all potential wording with the following new wording: (insert your new wording below)

Your Comments:

- Xx

- Xx

- xx

<<  Return to Contents >>

===========================================================

===========================================================

===========================================================

5)-Project Design Role

Background – During final design, a final design squad leader may perform some of the roles of a project coordinator, helping coordinate the deliverables and decisions necessary to keep a project design on schedule.  The project manager maintains a role in resolving issues that rise above the level of design coordination and ensuring that the design conforms to the established scope, budget, and schedule.

- Project Management Functions, Design Phase

  - Allows final design squad leader to coordinate deliverables and design decisions with functional groups and specialty offices as necessary to keep the project design on schedule and within scope and budget

  - Allows final design squad leader to coordinate deliverables and design decisions with utilities and local governments as necessary to keep the project design on schedule and within scope and budget.  Project manager remains responsible for overall management of project and resolution of issues with utilities and local governments.

  - Escalates issues when agreement on issues cannot be reached,

  - Ensures project construction plans are delivered in compliance with scope, budget and schedule

- Technical Functions, Design Phase

  - Ensures that design decisions developed during the pre-design phase are incorporated in the final design

===========================================================

Your Working Area

Prepare your role definition here.

5)-Project Design Role

Select one of the options below and then add information as needed.

☐ No Showstoppers – Nothing in the potential wording is totally unacceptable

☐ Showstoppers Exist – The potential wording is unacceptable

Select one of the options below.

☐ Use potential wording “as is”

☐ Modify the potential wording as follows: (insert your comments below)

☐ Replace all potential wording with the following new wording: (insert your new wording below)

Your Comments:

- Xx

- Xx

- xx

<<  Return to Contents >>

===========================================================

===========================================================

===========================================================

6)-Project Post Letting Role

Background – During construction, the resident engineer and staff serve as MnDOT’s authority in dealing with the construction contractor.  However, the project manager still has a role to play in managing the project, public engagement, and project commitments.

- Project Management Functions, Post-Letting

  - Project Changes –Facilitates decisions on project changes that affect scope, budget, or schedule.  Routine field changes are addressed by the construction project supervisor.

  - Public Engagement – Continues to serve as the project manager for issues dealing with project commitments or on issues that are elevated above routine day to day questions.  Delegates most day to day communication to the construction project supervisor since the project supervisor is best equipped to answer routine questions.

  - Project Commitments – Ensures that commitments made during project development and design are addressed during construction.

- Technical Functions, Post-Letting

  - Contract Administration – Delegates contract administration and inspection tasks to the resident office.

===========================================================

Your Working Area

Prepare your role definition here.

6)-Project Post Letting Role

Select one of the options below and then add information as needed.

☒ No Showstoppers – Nothing in the potential wording is totally unacceptable

☐ Showstoppers Exist – The potential wording is unacceptable

Select one of the options below.

☐ Use potential wording “as is”

☐ Modify the potential wording as follows: (insert your comments below)

☐ Replace all potential wording with the following new wording: (insert your new wording below)

Your Comments:

- Xx

- Xx

- xx

<<  Return to Contents >>

===========================================================

===========================================================

===========================================================

7)-Functional Group Resource Management Role

Background – Functional groups are responsible to ensure that their tasks are completed on time and within scope and budget.  Functional groups may need to augment their staff in order to meet their commitments.

- Selection of internal resources – Functional group leaders are responsible for optimizing their staff resources in order to deliver their tasks on time.  They are also responsible to develop their staff.  Therefore, the functional group leader is best suited to select staff to work on assigned project tasks.

- Selection of consultant resources – Functional groups are responsible for optimizing their staff resources.  If they are not able to complete the assigned project tasks, they are responsible for acquiring the required external resources to complete their assigned project tasks on time.

- Priority of resources – Once projects are baselined, all functional groups are committed to deliver their tasks on time.  MnDOT has incorporated an enterprise-wide project scheduling system to establish timeframes for work task completion.  A project manager may request a functional group to reprioritize their work.  If a functional group does not agree to reprioritize, the project manager needs to resolve the situation and may elevate the request to establish district or statewide priority for the project.

===========================================================

Your Working Area

Prepare your role definition here.

7)-Functional Group Resource Management Role

Select one of the options below and then add information as needed.

☐ No Showstoppers – Nothing in the potential wording is totally unacceptable

☐ Showstoppers Exist – The potential wording is unacceptable

Select one of the options below.

☐ Use potential wording “as is”

☐ Modify the potential wording as follows: (insert your comments below)

☐ Replace all potential wording with the following new wording: (insert your new wording below)

Your Comments:

- Xx

- Xx

- xx

<<  Return to Contents >>

===========================================================

===========================================================

===========================================================

8)-Project Execution, Monitoring and Control Role

Background – All projects need to manage requirements, changes, schedule and budget and the PM is the individual accountable to ensure that these core project management functions are accomplished.

  - Scope Change Management Role

    - The PM manages the scope of the project

    - When scope changes are identified, the PM develops, or ensures the development of, resources, budget and schedule impacts

    - The PM validates that all necessary approvals are in place before officially accepting a scope change

    - The PM notifies all affected team members and stakeholders of the change

    - The PM ensures that the project plan is modified to reflect the scope change

  - Requirements Management Role

    - The PM ensures all team members understand the project requirements as is needed for individual team members

    - The PM reviews the project requirements compliance periodically during  the project

    - The PM works with the project team to determine if project requirements compliance is adequate or if corrective actions are needed

    - Where corrective actions are needed, the PM works with the project team to determine what actions are needed and who should implement each action

    - The PM tracks corrective actions related to requirements compliance

  - Schedule Management Role

    - The PM ensures all team members update the project schedule on a periodic basis

    - The PM reviews the project schedule periodically during  the project

    - The PM works with the project team to determine if project schedule performance is adequate or if corrective actions are needed

    - Where corrective actions are needed, the PM works with the project team to determine what actions are needed and who should implement each action

    - The PM tracks the progress of schedule corrective actions

    - The PM works with the project team to identify “Barriers to Schedule Success” and takes action to avoid those barriers as is possible

  - Budget Management Role

    - The PM reviews the project budget status periodically during  the project

    - The PM works determines if project budget performance is adequate or if corrective actions are needed

    - Where corrective actions are needed, the PM works with the project team to determine what actions are needed and who should implement each action

    - The PM tracks the progress of budget corrective actions

    - The PM works with the project team to identify “Barriers to Success in Meeting the Budget” and takes action to avoid those barriers as is possible

===========================================================

Your Working Area

Prepare your role definition here.

8)-Project Execution, Monitoring and Control Role

Select one of the options below and then add information as needed.

☐ No Showstoppers – Nothing in the potential wording is totally unacceptable

☐ Showstoppers Exist – The potential wording is unacceptable

Select one of the options below.

☐ Use potential wording “as is”

☐ Modify the potential wording as follows: (insert your comments below)

☐ Replace all potential wording with the following new wording: (insert your new wording below)

Your Comments:

- Xx

- Xx

- xx

<<  Return to Contents >>

===========================================================

===========================================================

===========================================================

9)-Risk Management Role – Potential Wording

Background – All projects have threats to success and a core function of the project manager is to work to control these threats. Classic project risk management actions need to be inherent in every project and the project manager needs to lead the team in this necessary effort.

It is the role of the project manager to:

- Understand the basics of project risk management

- Have a risk management mindset that proactively looks for and controls risks to project success

- Instill a “risk management” mindset in the project team to form a team approach to managing threats to the project

- Work with the project team to identify technical risks and risks to the project’s schedule and budget baselines

- Work to assess and prioritize risks to determine the most important risks to control

- Work with the project team to identify risk controls that will avoid the risk and/or control the impacts of the risk if it materializes as a problem

- Ensure identified risk controls are implemented

- Track the progress and effectiveness of risk controls and makes changes to those controls to best benefit the project

- Report significant risks to MnDOT leadership including probability and impact assessment and risk control information

===========================================================

Your Working Area

Prepare your role definition here.

9)-Risk Management Role

Select one of the options below and then add information as needed.

☐ No Showstoppers – Nothing in the potential wording is totally unacceptable

☐ Showstoppers Exist – The potential wording is unacceptable

Select one of the options below.

☐ Use potential wording “as is”

☐ Modify the potential wording as follows: (insert your comments below)

☐ Replace all potential wording with the following new wording: (insert your new wording below)

Your Comments:

- Xx

- Xx

- xx

<<  Return to Contents >>

===========================================================

===========================================================

===========================================================

10)-Project Team on-Going Communications Role

Background – (TBD)

- General Team Communications

    - It is the role of the PM to establish an open and effective communications environment on the project.

    - It is the role of the PM to ensure sufficient team communications exist to support project success and to establish sound teamwork and productive working relationships.

    - It is the role of the project manager to establish periodic, consistent and substantive team communications or meetings to review project technical work, schedule progress, risks, issues and corrective actions and other project information pertinent to performing and managing the project.

- Requirements and Design Related Communications

    - It is the role of the project manager to ensure that all project requirement and design level decisions are properly documented and communicated to all project team members

- Technical Issues and Corrective Actions Communications

    - (Insert MnDOT procedures, forms, systems or reports as appropriate)

- Project Schedule and Budget Status, Problems and Corrective Actions Communications

    - It is the role of the project manager to communicate changes to scope, schedule, and budget to project team members and other affected stakeholders within and outside of MnDOT and gain consensus to proceed with the change

===========================================================

Your Working Area

Prepare your role definition here.

10)- Project Team on-Going Communications Role

Select one of the options below and then add information as needed.

☐ No Showstoppers – Nothing in the potential wording is totally unacceptable

☐ Showstoppers Exist – The potential wording is unacceptable

Select one of the options below.

☐ Use potential wording “as is”

☐ Modify the potential wording as follows: (insert your comments below)

☐ Replace all potential wording with the following new wording: (insert your new wording below)

Your Comments:

- Xx

- Xx

- xx

<<  Return to Contents >>

===========================================================

===========================================================

===========================================================

11)-Consultant Acquisition and Management Role

Background – Consultant resources may be hired to support project level activities such as the entire pre-design process or to support specific tasks such as prepare construction plans or perform a traffic analysis.

- Project Level Consultants

Note: This section address management of consultants hired to support the project overall and that are managed by the project manager. Consultants hired to perform work for a given functional group are managed by the respective functional group.

It is the role of the project manager to:

- Identify project work that can be done either internally or externally to MnDOT

- Complete a “Make or Buy” decision for work that can be done within MnDOT or by an external consultant

- Complete a “Source Selection” decision for work where multiple consultants are available so that the best consultant is selected for the project using multiple criteria such as past experience with MnDOT, schedule, cost, technical expertise and the ability of the PM to integrate the consultant’s work with all other project work

- Form the requirements for the consultant’s work scope

- Work with all needed MnDOT organizations to form an agreement with the consultant that includes a statement of work, requirements and other necessary terms and conditions

- Work with all needed MnDOT organizations to negotiate and finalize the consultant agreement

- Ensures the consultant work scope, schedule and budget are integrated into the overall project plan

- Determines how the project will  interface with the consultant during the project and how the consultant’s work will be managed

- Establishes a sound and productive working relationship with the consultant to best support project success

- During the project, ensures adequate communication with the consultant for both technical and status information

- Ensure the consultant is notified of any changes on the project that affects the consultant’s work scope

- Include the consultant in the project’s risk management activities to the extent necessary to support project success and where the consultant’s work generates risk and/or where the consultants work can be a part of risk controls

- Resource Level Consultants

Note: This section address management of consultants hired to support a functional group in delivering a specific functional task.

It is the role of the project manager to:

- Support the functional group in the acquisition of the consultant resources and incorporate the work of the consultant into the project

It is the role of the functional group to:

- Identify project work that can be done either internally or externally to MnDOT

- Complete a “Make or Buy” decision for work that can be done within MnDOT or by an external consultant

- Complete a “Source Selection” decision for work where multiple consultants are available so that the best consultant is selected for the project using multiple criteria such as past experience with MnDOT, schedule, cost, technical expertise and the ability of the functional group to integrate the consultant’s work with all other project work

- Form the requirements for the consultant’s work scope

- Work with all needed MnDOT organizations to form an agreement with the consultant that includes a statement of work, requirements and other necessary terms and conditions

- Work with all needed MnDOT organizations to negotiate and finalize the consultant agreement

- Determines how the project will  interface with the consultant during the project and how the consultant’s work will be managed

- Establishes a sound and productive working relationship with the consultant to best support project success

- During the project, ensures adequate communication with the consultant for both technical and status information

- Ensure the consultant is notified of any changes on the project that affects the consultant’s work scope

- Include the consultant in the project’s risk management activities to the extent necessary to support project success and where the consultant’s work generates risk and/or where the consultants work can be a part of risk controls

===========================================================

Your Working Area

Prepare your role definition here.

11)-Consultant Acquisition and Management Role

Select one of the options below and then add information as needed.

☐ No Showstoppers – Nothing in the potential wording is totally unacceptable

☐ Showstoppers Exist – The potential wording is unacceptable

Select one of the options below.

☐ Use potential wording “as is”

☐ Modify the potential wording as follows: (insert your comments below)

☐ Replace all potential wording with the following new wording: (insert your new wording below)

Your Comments:

- Xx

- Xx

- xx

<<  Return to Contents >>

===========================================================

===========================================================

===========================================================

12)-PM Interface with MnDOT Leadership

Background – (N/A)

- Significant Project Issues – It is the role of the project manager to inform management of issues seriously jeopardizing project technical, schedule or budget success. This communication would include the background of the issue, what specifically the issue is, what actions the project is taking or will take and what, if any, support from leadership is requested. The probability of success for current actions in resolving the issue is an important part of this problem communication. The PM has a responsibility to inform management of serious issues in a timely fashion such that advice or support for issue resolution can be provided to best support project success.

- Periodic Project Status – It is the role of the project manager to periodically report overall project status information , including issues and corrective actions to management.

- Project Changes - Where significant changes to the project’ requirements, design, technical work issues, schedule or budget happen, the project manager has the responsibility to ensure leadership is made aware of the change and what impacts the change generates.

- Contact with Important External Stakeholders – Where the project manager has contact with important external stakeholders, these communications would be identified to leadership. Examples include communications with the legislature and federal and state regulatory agencies.

- Other Leadership Communications – (TBD)

===========================================================

Your Working Area

Prepare your role definition here.

12)-PM Interface with MnDOT Leadership

Select one of the options below and then add information as needed.

☐ No Showstoppers – Nothing in the potential wording is totally unacceptable

☐ Showstoppers Exist – The potential wording is unacceptable

Select one of the options below.

☐ Use potential wording “as is”

☐ Modify the potential wording as follows: (insert your comments below)

☐ Replace all potential wording with the following new wording: (insert your new wording below)

Your Comments:

- Xx

- Xx

- xx

<<  Return to Contents >>

===========================================================

===========================================================

===========================================================

13)-PM Role in Working with External Stakeholders (Municipalities, MPCA, Corp of Engineers, etc.)

Background – Working relationships and communications with external stakeholders can be a critical aspect of managing a project and support success. The project manager is the focal point and is accountable for this important project managing function.

- The PM is the focal point for establishing and maintaining working relationships with external stakeholders.

- The PM is the focal point for communications with external stakeholders.

- The PM takes a proactive approach by identifying all external stakeholders related to a given project and then to identify the nature or function of each one of those stakeholder interfaces.

- The PM communicates the set of stakeholders and their roles to the project team

- The PM maintains a sufficient awareness of external stakeholder views, needs and actions.

- The PM takes a proactive approach by identifying and addressing issues related to external stakeholders and their involvement in the project.

- The PM is accountable for ensuring the interfaces with external stakeholders are handled in a professional and constructive manner to both support project success and to develop and maintain effective on-going working relationships.

- The PM obtains internal and external resources as needed to successfully work with external stakeholders

===========================================================

Your Working Area

Prepare your role definition here.

13)- PM Role in Working with External Stakeholders

(Municipalities, MPCA, Corp of Engineers, etc.)

Select one of the options below and then add information as needed.

☐ No Showstoppers – Nothing in the potential wording is totally unacceptable

☐ Showstoppers Exist – The potential wording is unacceptable

Select one of the options below.

☐ Use potential wording “as is”

☐ Modify the potential wording as follows: (insert your comments below)

☐ Replace all potential wording with the following new wording: (insert your new wording below)

Your Comments:

- Xx

- Xx

- xx

<<  Return to Contents >>

===========================================================

===========================================================

===========================================================

14)-Project Team Leadership

Background – The project manager has many roles. In addition to being an effective manager of project details, the PM is a “Leader” of the project. Leadership is distinctly different from managing the technical details and schedules on a project and is a key attribute all productive PMs should exhibit.

Note: The approach here will be to identify 12 top leadership attributes for inclusion in the final PM role definition from this list or from your own experience.

It is the role of the project manager to:

- Exhibit sound leadership behaviors to the project team and stakeholders at all times

- Take responsibility for the project and its issues and risks

- Lead the team in a fashion that is aligned with sound leadership practices including the following:

- General

  - Leads by earning the respect of others

  - Garners respect from others by his/her actions, not from words

  - Leads by instilling the belief that what needs to be done is the right thing to do

  - Is a model of leadership for others to follow

  - Leads by example

  - Takes responsibility for own actions

  - Considers themselves as a part of the team, not the dictator of the team

  - Considers themselves to be the servant of the team to foster an environment to make the team’s efforts successful

- Vision / Strategic Thinking / Planning

  - Has a clear vision of what needs to be done, why it is important and is able to cause others to believe in it

  - Has a strategic thinking mindset

  - Identifies the goal and then identifies the tactical means to reach that goal

  - Able to productively identify segments of work needed to complete the effort

  - Uses business case analysis techniques to select the best path to a goal

- Empowerment / Delegation / Accountability / Direction / Resources

  - Is able to inspire others

  - Instills accountability in the team as a whole and in individual team members

  - Knows the team’s strengths and leverages them, knows the team weaknesses accommodates and works to resolve them

  - Able to productively delegate that work to individuals that can do the work

  - Provides clear and unambiguous direction

  - Empowers team members with clearly defined work scopes, roles and decision authorities

  - Ensures the team has the right resources to complete the effort

  - Makes team members accountable for their respective work scopes

  - Works to elicit improvement ideas from the team and takes action when ideas are feasible and are the best action for the project as a whole

  - Is accountable for the project overall, takes responsibility for project decisions, does not blame others

  - Is able to  “trust the team” and step back and let the team do it after sound requirements have been provided, does not micro-manage

- Drives Results / A Focus on “Barriers to Success” / Bold / Not a Bully

  - Is results oriented, always looking for what progress can be made today

  - Drives results on the project in a professional and productive manner, is not arrogant

  - Is proactive in own work and instills that behavior in the team

  - Maintains a focus on the destination but includes a focus on the journey

  - Works with a sense of “urgency” and instills a productive level of urgency in the team while maintaining a sustainable work load

  - Is engaged on the project, has a focus on making the project successful

  - Maintains an awareness of what “Barriers to Success” exist for the project and focuses actions on removing those barriers

  - Is bold in a productive and positive manner, but is not a bully

  - Able to confront others on important issues in a positive, constructive and professional manner

  - Works hard, takes on undesirable tasks, has a focus on the end result

  - Understands what drives individual team members and uses that to energize and motivate them

  - Learns to follow one’s instincts vs following others

  - Exhibits patience while driving results

- Handles Difficult Situations / Manages Uncertainty and Risks

  - Does not shy away from messy and difficult situations, addresses them head on

  - Carefully considers alternative solutions and picks the best solution by considering all impacts

  - Handles difficulties with professionalism and grace

  - Identifies areas of uncertainty and takes actions when appropriate

  - Identifies risks to effort success and takes action to avoid or to lessen impacts

- Communications / Social Skills

  - Has the social skills necessary to support communication

  - Able to construct messages that are organized, clear and understandable to many different learning styles

  - Explains the “why” of important messages

  - Is able to “teach” others

  - Clearly communicates the need and priorities of the project to the team and why it is important to customers

  - Is a great communicator and instills the need for transparent, complete and accurate communications on the project

  - Understands the need to be sensitive to the timing and environment for important messages

  - Is open to feedback, shows interest in receiving feedback

  - Maintains an open and transparent communications environment

  - Is a good listener, listens to others regardless of what they have to say

  - Listens before speaking, asks questions to fully understand the thoughts of others

  - Is open minded about changes, improvements and solutions provided by others

  - Matches communication style with the receiver

  - Able to make presentations in public with confidence, that are organized, logical and able to send clear messages

  - Able to conduct effective, concise and productive meetings to best support team efforts

- Stakeholder Management

  - Sets stakeholder expectations at effort start, maintains realistic expectations during the effort

  - Garners necessary stakeholder support, sets the rules of engagement for each stakeholder

  - Manages stakeholder conflict to best benefit the effort

  - Buffers the team from stakeholder intrusion

- Continuous Learner / New Experiences / Curiosity

  - Takes actions to cause continuous learning for one self

  - Seeks advice of others

  - Involves oneself in new experiences

  - Spends time reading

  - Being curious and seeking out new knowledge

  - Works to increase their level of competence in important areas related to their responsibilities and their interests

  - Keeps up to date on information and skills related to their responsibilities

  - Keeps a focus on the journey (the process) aside from a focus on the destination to learn from the journey

- Improver / Innovator / Independent Thinker

  - Has a continuous improvement mindset, does not accept the status quo as all that is needed

  - Seeks out things to improve and takes action

  - Supports and empowers the team to be innovative and to make improvements

  - Is an example to others in making improvements

  - Is an independent thinker but works with others to make improvements

- Ethics / Standards / Personal Values / Value to Others

  - Performs the PM role in a fully ethical manner

  - Instills the need for ethical practices in the team and requires that behavior of all associated with the project

  - Is honest, tells the truth, requires others to do the same

  - Exhibits information transparency and supports others in doing the same

  - Acts in a manner that one would be proud of if it was on the news

  - Exhibits standards of behavior consistent with ethical, organization and lawful practices

  - Conducts themselves in alignment with their own personal values

  - Conducts themselves in a manner that benefits society, their community, their customers and organization

- Teamwork / Motivation / Energizing / Difficult Issues / Support / Growth

  - Motivates the team

  - Accurately sets team expectations on what will and will not be done and how hard it might be

  - Understands what drives individual team members and uses that to energize and motivate them

  - Is able to get the team to do the right work because the team believes it is the right thing to do

  - Works to builds a trusting team environment that fosters open communication and solid working relationships

  - Identifies both strong and weak team member performance and takes actions to resolve any team performance issues and appropriately rewards and corrects team and individual performance

  - Able and willing to address difficult issues even though it might be painful and/or no clear resolution is apparent

  - Gives credit where credit is due

  - Looks for ways to support individual team members in their professional and personal lives

  - Rewards accomplishments

  - Addresses weaknesses

  - Works to advance the skills and knowledge of the team members

  - Works to understand the growth needs of the team and to take action to support valuable growth

  - Is a coach, knows  how to coach, knows who to coach and knows what to coach

  - Advises the team in a mature manner where the PM has appropriate experience, listens to the advice of others in a constructive manner

  - Buffers the team from destructive internal or external politics or stakeholder intrusions

  - Maintains a realistic positive and constructive and customer oriented attitude and instills that behavior in the team through actions not words

  - Builds constructive working relationships with the team and stakeholders

- Decision Making / Negotiator / Calculated Risk Taker / Street Smart

  - Effectively directs team problem solving and decision making to best support the project and customers overall

  - Involves team members in important decisions where that is possible

  - Able to make decisions in a timely manner, but ensures adequate and relevant information is reviewed before making decisions

  - Mature enough to seek the advice of others in decisions

  - Able to apply “business case analysis” concepts to key decisions and able to explain to others the need for same

  - Is consistent and fair and reasonable in decision making

  - Thinks strategically, makes decision that support both the strategic and tactical not just the tactical

  - Makes decisions to best support the project and customers vs personal gain

  - Explains the why or why not of decisions

  - Able to negotiate agreements to the acceptance of all parties, is a fair and firm negotiator

  - Knows when to make a decision and when to wait

  - Makes decisions when needed, explains the “why” to others

  - Has the courage to make decisions and take calculated risks to support project success

  - Is “Street Smart” and makes decisions based on a clear understanding of the situation and consideration of alternatives and their impacts

  - Knows when one is competent to make a given decision and when one is not

- Managing Conflict / Personalities / Differences

  - Manages team conflict

  - Able to constructively work with all types of personalities

  - Able to lead different personalities and make them function as a productive team, leverages the energy and ideas of the “out-spoken” and elicits thoughts from the “quiet”

  - Is respectful of others and their opinions

  - Allows all ideas to be voiced in a professional and constructive manner

- Other Behaviors

  - Is insightful and offers insights to others

  - Is consistent, is predictable

  - Is organized, is a logical thinker

  - Knows and leverages their own strengths

  - Is resourceful, applies needed resources but is careful to conserve resources

  - Is flexible but maintains a focus on the end result and impacts on all stakeholders

  - Is open minded, is open to the ideas of others

  - Adaptable, able to make productive changes in the effort and team as the environment changes

  - Follows through on promises

  - Is self-motivated

  - Works to be creative and fosters creativity in the team, allows all ideas to be voiced in a professional and constructive manner

  - Can put oneself in the shoes of others to understand their perspective

  - Is humble, does not put oneself above others

  - Is disciplined in their actions, following their own standards of behavior

  - Hides emotions where those feelings would be of dis-benefit to the project or team

  - Is present for others to see and for communication

  - Able to put any situation into a proper perspective or context such that it is fully understood and prioritized

  - Acts in a self-confident manner but is not arrogant

  - Thinks strategically and identifies and implements tactical actions to attain strategic goals

  - Is persistent and consistent in solving issues and making improvements

  - Is assertive in a professional manner

  - Exhibits an energetic attitude

  - Works to be “personable” to support teamwork, trust, open communication and an overall productive team environment

  - Manages their time and energy on the most important actions to support project success

  - Is fair and reasonable

  - Is empathetic to the situations of others, has compassion for others

  - Is calm and constructive in the face of serious difficulties, maintains their composure to maintain the team’s energy

- Commitment

  - Is committed to the organization’s mission, vision, values and goals

  - Demonstrates commitment to the project through their actions

  - Works to instill team commitment in the project and the organization

===========================================================

Your Working Area

Prepare your role definition here.

14)-Project Team Leadership

Leadership can be defined in many ways and all of the preceding leadership attributes probably could apply to most any project.

The list is too long.

Scan the list for the 12 most important leadership attributes you see as key to MnDOT project success or write your own.

It is the role of the project manager to exhibit leadership qualities in the following ways:

- xx

- xx

- xx

- xx

- xx

- xx

- xx

- xx

- xx

- xx

- xx

- xx

<<  Return to Contents >>

===========================================================

===========================================================

===========================================================

15)-Project Closeout Role

Background – Once a project is completed, the project will need to be closed out.  While the resident office is responsible for closing out the construction contract, there are other issues that may need to be closed out.

- Environmental Closure – Ensures that all environmental commitments have been met or that those that have not been met have a plan for completion.

- Work Scope Complete - Validation that all stakeholders agree that the project work scope has been successfully completed

===========================================================

Your Working Area

Prepare your role definition here.

15)-Project Closure Role

Select one of the options below and then add information as needed.

☐ No Showstoppers – Nothing in the potential wording is totally unacceptable

☐ Showstoppers Exist – The potential wording is unacceptable

Select one of the options below.

☐ Use potential wording “as is”

☐ Modify the potential wording as follows: (insert your comments below)

☐ Replace all potential wording with the following new wording: (insert your new wording below)

Your Comments:

- Xx

- Xx

- xx

<<  Return to Contents >>

===========================================================

===========================================================

===========================================================

16)- PM Role in Understanding / Applying MnDOT Policies, Processes, Systems and Standards

Background – Project managers are not expected to be technical experts on all policies, processes, or standards. However, they must have a working knowledge of policies and standards in order to successfully manage projects.

It is the role of the project manager to perform the following.

- MnDOT Policy / Procedures / Guides – It is the role of the project manager to understand and apply MnDOT organization policies as they apply to project development.

- MnDOT Standards - It is the role of the project manager to understand and utilize MnDOT standards as they apply to project development.

===========================================================

Your Working Area

Prepare your role definition here.

16)- PM Role in Understanding / Applying MnDOT Policies, Processes, Standards and Systems

Select one of the options below and then add information as needed.

☐ No Showstoppers – Nothing in the potential wording is totally unacceptable

☐ Showstoppers Exist – The potential wording is unacceptable

Select one of the options below.

☐ Use potential wording “as is”

☐ Modify the potential wording as follows: (insert your comments below)

☐ Replace all potential wording with the following new wording: (insert your new wording below)

Your Comments:

- Xx

- Xx

- xx

<<  Return to Contents >>

===========================================================

===========================================================

===========================================================

17)- Role in Advancing the Discipline of Project Management in MnDOT

Background – Organizations that perform projects need a wide range of infrastructure elements to support project success. Project management policies, processes, tools, systems, roles, training and other guidance. These elements of infrastructure often take many years to develop and refine before a mature infrastructure can be considered to be in place. Additionally, as the environment the organization exists within changes, the project management infrastructure needs to change as well. Project managers are a key part of the development and maintenance of a PM infrastructure set in that PMs provide the need and requirements, try out new infrastructure elements and provide lessons learned and best practices to continuous improvements.

It is the role of the project manager to:

- Provide ideas for project management infrastructure developments and updates

- Collect and provide lessons learned and best practices related to the management of projects from projects they manage

- Work to support the implementation of project management infrastructure elements on projects

===========================================================

Your Working Area

Prepare your role definition here.

17)-Role in Advancing the Discipline of Project Management in MnDOT

Select one of the options below and then add information as needed.

☐ No Showstoppers – Nothing in the potential wording is totally unacceptable

☐ Showstoppers Exist – The potential wording is unacceptable

Select one of the options below.

☐ Use potential wording “as is”

☐ Modify the potential wording as follows: (insert your comments below)

☐ Replace all potential wording with the following new wording: (insert your new wording below)

Your Comments:

- Xx

- Xx

- xx

<<  Return to Contents >>

===========================================================

===========================================================

===========================================================