DEVELOPING A FUNCTIONAL GROUP WORK PACKAGE 
IN P6

Purpose:  How to develop a work package to be integrated into a schedule efficiently.  The work package will include the functional group activities and will easily identify what the standard relationships are. The sample below is a simplified version of the MDR work package.

Work package Structure- The work package will include the following activities parts:

- Work with the functional group to identify all Activities under the WBS(s) with inter-work package logic. Use Activity names with 3-character smart prefix based on the WBS Name. - Create a temporary WBS to contain temporary relationship activities representing the logic between the work package and schedule. Name the temporary WBS “Dissolvable Milestone (Dissolve after relationship Linked & remove node from WBS)”. Create Temporary Activities to hold the relationships between the Work package and the final schedule. These temporary activities will be a mirror of the activities the work package is typically linked to in the final schedule. Temporary Activities will use the following naming convention: - Temporary Activity ID’s will start with “ZZZ” followed by the actual Activity ID including smart prefix. - Temporary Activity Name should match actual activity name in the template/schedule to aid in connecting the relationships. Indicate either pred/succ and include relationship type and template/work package in which the activity resides in. - a. Link relationships between temporary activities and Work package activities. b. Each temporary activity will have an open end that will get linked to the permanent activity. - You may need to duplicate a temporary activity if it is both a predecessor and successor to different activities in the work package; this is indicated with ‘Pred’ or ‘Succ’. *All activities in work package will have a predecessor and successor (excluding dissolvable milestones). 00 3 4 5b 5a 6 Succ: Prepare Submittal Memo and Submit Plans & Specs (FS) (Project Template) Pred: Prepare 90% Plans (FS) (Project Template) Pred: Revise Final Plan (FS) (Project Template) Succ: Revise Final Plan (FS) (Project Template)