## General Info
Work Package
Dictionary
Updated Date 3/20/2015
Purpose:
This document contains information to assist the Shared Service Center and project managers in the creation of Primavera P6 schedules using functional group work packages. Note that the information given in this document is generalized. For more detailed information contact the MNDOT functional group listed for each work package.

## WBS
Updated Date 3/20/2015
| WBS Code | WBS Name (click hyperlink for work package guidance) | Work Package ID
0
3 | WBS | Standalone templates
9 | Multi level | Scoping Template | TEMPSCOP
9 | Multi level | Project Template | TEMPMODA
9 | Multi level | Minor Project Template (Signing, Signal, Lighting) | TEMPMINA
9 | Multi level | Landscaping Plan | TEMPLAND
| Multi level | Cable Median Barrier Project Plan | TEMPCMBP
| Multi level | Maintenance Plan | TEMPMAIN
9 | Multi level | CMGC Template | TEMPCMGC
0
5 | WBS_S | Scoping Schedule
7 | WBS_S.1 | Milestones (Scoping) | TEMP4000
7 | WBS_S.2 | Scoping
9 | WBS_S.2.1 | Scoping Document
9 | WBS_S.2.2 | Project Baseline
0
5 | WBS_D | Design Schedule
7 | WBS_D.1 | Milestones (Design) | TMPL3000
7 | WBS_D.2 | Project Management | TMPL3002
9 | WBS_D.2.1 | Ongoing Project Management
9 | WBS_D.2.2 | Public Involvement
7 | WBS_D.3 | Environmental
9 | WBS_D.3.1 | Early Notification Memo | TMPL3006
9 | WBS_D.3.2 | Environmental Studies
11 | WBS_D.3.2.1 | Cultural Resources - Work Package 1 Full Section 106 Review- All Federal Agencies | TMPL1302
11 | WBS_D.3.2.2 | Cultural Resources - Work Package 2 FHWA Funds | TMPL1304
11 | WBS_D.3.2.3 | Cultural Resources - Work Package 3 State Level Review (State Funds Only) | TMPL1302C
11 | WBS_D.3.2.4 | Regulatory File Review | TMPL 1305
11 | WBS_D.3.2.5 | Environmental Due Diligence 1 | TMPL 1306
11 | WBS_D.3.2.6 | Environmental Due Diligence 2 | TMPL 1308
11 | WBS_D.3.2.7 | Environmental Due Diligence 3 | TMPL 1310
11 | WBS_D.3.2.8 | Environmental Site Assessment (Phase I & II) No Acquisition | TMPL 1312
w | WBS_D.3.2.8.1 | Consultant Acquisition
| WBS_D.3.2.8.2 | Phase I
| WBS_D.3.2.8.3 | Phase II
11 | WBS_D.3.2.9 | Environmental Site Assessment (Phase I & II) Early Acquisition | TMPL 1313
| WBS_D.3.2.9.1 | Consultant Acquisition
| WBS_D.3.2.9.2 | Phase I
| WBS_D.3.2.9.3 | Phase II
12 | WBS_D.3.2.10 | Environmental Site Assessment (Phase I & II) Acquisition | TMPL 1314
| WBS_D.3.2.10.1 | Consultant Acquisition
| WBS_D.3.2.10.2 | Phase I
| WBS_D.3.2.10.3 | Phase II
12 | WBS_D.3.2.11 | Phase I Update | TMPL 1315
12 | WBS_D.3.2.12 | Phase II Update | TMPL 1316
12 | WBS_D.3.2.13 | No Association Determination | TMPL 1314
12 | WBS_D.3.2.14 | Response Action Plans | TMPL 1316
12 | WBS_D.3.2.15 | Contaminated Materials Management Special Provisions | TMPL 1318
12 | WBS_D.3.2.16 | Regulated Materials-Building | TMPL 1326
12 | WBS_D.3.2.17 | Regulated Materials Assessment-Building
12 | WBS_D.3.2.18 | Regulated Materials Abatement-Building
12 | WBS_D.3.2.17 | Regulated Materials-Bridge | TMPL 1327
14 | WBS_D.3.2.17.1 | Regulated Materials Assessment-Bridge
12 | WBS_D.3.2.18 | Noise Analysis | TMPL 1328
12 | WBS_D.3.2.19 | Air Quality Analysis | TMPL 1330
12 | WBS_D.3.2.20 | Section 7 Determination [Threatened & Endangered Species]
14 | WBS_D.3.2.20.1 | Mussel Survey | TMPL 1349
| WBS_D.3.2.20.2 | Section 7 Determination [Threatened & Endangered Species]- No Effect | TMPL 1370
| WBS_D.3.2.20.3 | Section 7 Determination [Threatened & Endangered Species]- May Affect | TMPL 1701
| WBS_D.3.2.20.4 | Section 7 Determination [Threatened & Endangered Species]- Formal Consultation | TMPL 1702
12 | WBS_D.3.2.21 | Vegetation Review | TMPL 1368
12 | WBS_D.3.2.22 | Wetland Delineations | TMPL 1348 or TEMP3008
12 | WBS_D.3.2.23 | Floodplain Assessment
12 | WBS_D.3.2.24 | Wild & Scenic River Coordination
12 | WBS_D.3.2.25 | Groundwater Impact Study
12 | WBS_D.3.2.26 | Section 6(f) Coordination | TMPL1420
12 | WBS_D.3.2.27 | Environmental Justice Analysis
12 | WBS_D.3.2.28 | Visual Impact Assessment | TMPL 1409
12 | WBS_D.3.2.29 | Earthborn Vibrations Study
12 | WBS_D.3.2.30 | Geotechnical Study
12 | WBS_D.3.2.31 | Farmland Conversion Impact Rating (Form AD 1006)
12 | WBS_D.3.2.32 | Energy Analysis
12 | WBS_D.3.2.33 | Other Environmental Study
12 | WBS_D.3.2.34 | Section 4(f) Coordination | TMPL1419
12 | WBS_D.3.2.35 | LOMAR/CLOMAR
9 | WBS_D.3.3 | Environmental Documents
11 | WBS_D.3.3.1 | Environmental Document Exemption
11 | WBS_D.3.3.2 | Categorical Exclusion - Non Programmatic | TMPL 1334
11 | WBS_D.3.3.3 | Categorical Exclusion - Programmatic | TMPL 1336
11 | WBS_D.3.3.4 | Environmental Assessment/Environmental Assessment Worksheet | TMPL 1338
11 | WBS_D.3.3.5 | Environmental Assessment Worksheet (EAW) State | TMPL1332
11 | WBS_D.3.3.6 | Environmental Impact Statement (EIS) | TMPL 1340
11 | WBS_D.3.3.7 | EIS Re-evaluation
11 | WBS_D.3.3.8 | Supplemental EIS
9 | WBS_D.3.4 | Permits
11 | WBS_D.3.4.1 | NPDES Stormwater Discharge Permit | TMPL 1346
11 | WBS_D.3.4.2 | Wetland/WCA & Aquatic Resources (404/401/Section 10) | TMPL 1355
11 | WBS_D.3.4.3 | DNR Public Waters Permit | TMPL 1350
11 | WBS_D.3.4.4 | Watershed District Permit | TMPL 1352
11 | WBS_D.3.4.5 | Section 9 (Coast Guard) Permit
7 | WBS_D.4 | Road Design
9 | WBS_D.4.1 | Surveys | TMPL3010
11 | WBS_D.4.1.1 | Control Surveys
13 | WBS_D.4.1.1.1 | Geodetic Control Surveys | TMPL 1400
13 | WBS_D.4.1.1.2 | Project Control Surveys | TMPL 1401
11 | WBS_D.4.1.2 | District Land Surveys | TMPL3012
11 | WBS_D.4.1.3 | Design Surveys | TMPL3014
11 | WBS_D.4.1.4 | Photogrammetric Basemap | TMPL 1402
9 | WBS_D.4.2 | Traffic Studies
11 | WBS_D.4.2.1 | Traffic Counts | TMPL1375
11 | WBS_D.4.2.2 | Traffic Forecasts | TMPL3016
11 | WBS_D.4.2.3 | Traffic Modeling
11 | WBS_D.4.2.4 | Crash Analysis
11 | WBS_D.4.2.5 | Intersection Control Evaluation | TMPL3018
11 | WBS_D.4.2.6 | Transportation Management Plan
11 | WBS_D.4.2.7 | Interstate Access Request | TMPL3022
9 | WBS_D.4.3 | Preliminary Design
11 | WBS_D.4.3.1 | Staff Approved Layout | TMPL3024
11 | WBS_D.4.3.2 | Design Memo/Design Exception | TMPL3026
11 | WBS_D.4.3.3 | RW Construction Limit | TMPL3028
11 | WBS_D.4.3.4 | Value Engineering | TMPL 1407
11 | WBS_D.4.3.5 | Municipal Consent | TMPL3030
11 | WBS_D.4.3.6 | Municipal Consent (Appeal Process) | TMPL3032
9 | WBS_D.4.4 | Recommendations
11 | WBS_D.4.4.1 | Foundation Recommendations | TMPL1414
11 | WBS_D.4.4.2 | Material Design Recommendations (MDR) | TMPL3034
11 | WBS_D.4.4.3 | Traffic Recommendations
13 | WBS_D.4.4.3.1 | Detour
13 | WBS_D.4.4.3.2 | Traffic Control
13 | WBS_D.4.4.3.3 | Staging
11 | WBS_D.4.4.4 | Hydraulics Design Recommendations
13 | WBS_D.4.4.4.1 | Stormwater Treatment Design | TMPL3036
13 | WBS_D.4.4.4.2 | Hydraulics Design | TMPL3038
13 | WBS_D.4.4.4.3 | Drain Tile Design
11 | WBS_D.4.4.5 | ADA Recommendations | TMPL 1416
11 | WBS_D.4.4.6 | Bike/Pedestrian Recommendations
11 | WBS_D.4.4.7 | Visual Quality Management Plan | TMPL1408
9 | WBS_D.4.5 | Final Design
11 | WBS_D.4.5.1 | Plan Set
13 | WBS_D.4.5.1.1 | Road Plans | TMPL3040
13 | WBS_D.4.5.1.2 | Hydraulics/WRE Plans | TMPL3042
13 | WBS_D.4.5.1.3 | Traffic Plans
15 | WBS_D.4.5.1.3.1 | Traffic Control/Staging Plan | TMPL3044
15 | WBS_D.4.5.1.3.2 | Pavement Marking Plan | TMPL3046
15 | WBS_D.4.5.1.3.3 | Signing Plan
15 | WBS_D.4.5.1.3.4 | Signal Plan
15 | WBS_D.4.5.1.3.5 | Lighting Plan
15 | WBS_D.4.5.1.3.6 | TMS Plan | TMPL3048
15 | WBS_D.4.5.1.3.7 | Time and Traffic | TMPL3050
11 | WBS_D.4.5.2 | Project Turn In | TMPL3054
11 | WBS_D.4.5.3 | Special Provisions | TMPL3052
11 | WBS_D.4.5.4 | Blowing and Drifting Snow Control | TMPL1417
9 | WBS_D.4.6 | Utilities
11 | WBS_D.4.6.1 | Subsurface Utility Engineering | TMPL1379
11 | WBS_D.4.6.2 | Utility Coordination | TMPL1425
7 | WBS_D.7 | Agreements
9 | WBS_D.7.1 | Informal Agreement
9 | WBS_D.7.2 | Lighting Agreement | TMPL1376
9 | WBS_D.7.3 | Signal Agreement | TMPL1377
9 | WBS_D.7.4 | Utility Agreement | TMPL1424
9 | WBS_D.7.5 | Cooperative Construction Agreement | TMPL3056
9 | WBS_D.7.6 | Railroad Agreement
11 | WBS_D.7.6.1 | Railroad Flagging Agreement | TMPL1422
11 | WBS_D.7.6.2 | Railroad Bridge Agreement | TMPL1421
11 | WBS_D.7.6.3 | Railroad Track Relocation Agreement | TMPL1423
9 | WBS_D.7.7 | Detour Agreement | TMPL3058
9 | WBS_D.7.8 | Turnback Agreement
9 | WBS_D.7.9 | Joint Powers Agreement
7 | WBS_D.8 | Letting
9 | WBS_D.8.1 | Process A | TMPL 2000
11 | WBS_D.8.1.2 | Administration
11 | WBS_D.8.1.3 | Civil Rights
11 | WBS_D.8.1.4 | Estimating
11 | WBS_D.8.1.5 | Special Provisions
11 | WBS_D.8.1.6 | Plan Review
9 | WBS_D.8.2 | Process B | TMPL 2001
11 | WBS_D.8.2.1 | Administration
11 | WBS_D.8.2.2 | Civil Rights
11 | WBS_D.8.2.3 | Land Management / Utilities
11 | WBS_D.8.2.4 | Land Management / RW
11 | WBS_D.8.2.5 | Estimating
11 | WBS_D.8.2.6 | Special Provisions
11 | WBS_D.8.2.7 | Plan Review / Signatures
9 | WBS_D.8.3 | Process B Complex | TMPL 2002
11 | WBS_D.8.3.1 | Administration
11 | WBS_D.8.3.2 | Civil Rights
11 | WBS_D.8.3.3 | Land Management / Utilities
11 | WBS_D.8.3.4 | Land Management / RW
11 | WBS_D.8.3.5 | Estimating
11 | WBS_D.8.3.6 | Special Provisions
11 | WBS_D.8.3.7 | Plan Review / Signatures
| WBS_D.8.4 | Process B PODI | TMPL2004
| WBS_D.8.4.1 | Administration
| WBS_D.8.4.2 | Civil Rights
| WBS_D.8.4.3 | Land Management / Utilities
| WBS_D.8.4.4 | Land Management / RW
| WBS_D.8.4.6 | Estimating
| WBS_D.8.4.7 | Special Provisions
| WBS_D.8.4.8 | Plan Review / Signatures
9 | WBS_D.8.5 | Prequalification (Tech Proposal) | TMPL 2003
11 | WBS_D.8.5.1 | Administration
11 | WBS_D.8.5.2 | Civil Rights
11 | WBS_D.8.5.3 | Land Management / Utilities
11 | WBS_D.8.5.4 | Land Management / RW
11 | WBS_D.8.5.5 | Estimating
11 | WBS_D.8.5.6 | Special Provisions
11 | WBS_D.8.5.7 | Plan Review / Signatures
9 | WBS_D.8.6 | Negotiated Contracts
9 | WBS_D.8.7 | Design-Build | TEMP2005
9 | WBS_D.8.8 | CMGC | TMPL2010
9 | WBS_D.8.9 | Letting by Others
0
5 | WBS_B | Bridge Schedule
7 | WBS_B.5 | Bridge Design
9 | WBS_B.5.1 | New Bridge | TMPL1500
11 | WBS_B.5.1.1 | Bridge Scoping & Structure Determination
11 | WBS_B.5.1.2 | Bridge Hydraulics Letter
11 | WBS_B.5.1.3 | Bridge Foundations Recommendations
11 | WBS_B.5.1.4 | Preliminary Bridge Design
11 | WBS_B.5.1.5 | Final Bridge Design
9 | WBS_B.5.2 | Culvert | TMPL1520
11 | WBS_B.5.2.1 | Culvert Scoping & Structure Determination
11 | WBS_B.5.2.2 | Hydraulics Letter
11 | WBS_B.5.2.3 | Final Culvert Design
9 | WBS_B.5.3 | Bridge Preservation | TMPL1511
11 | WBS_B.5.3.1 | Rehab Recommendations
11 | WBS_B.5.3.2 | Final Bridge Repair Plans
9 | WBS_B.5.4 | Bridge Redeck | TMPL1512
11 | WBS_B.5.4.1 | Rehab Recommendations
11 | WBS_B.5.4.2 | Final Bridge Repair Plans
9 | WBS_B.5.5 | Consultant Bridge Design (Prelim & Final Consultant) | TMPL1501
11 | WBS_B.5.5.1 | Bridge Scoping & Structure Determination
11 | WBS_B.5.5.2 | Hydraulics Letter
11 | WBS_B.5.5.3 | Foundations Recommendations-Bridge
11 | WBS_B.5.5.4 | Preliminary Bridge Design
11 | WBS_B.5.5.5 | Final Bridge Design
9 | WBS_B.5.6 | Consultant Bridge Design (Final Only Consultant) | TMPL1502
11 | WBS_B.5.6.1 | Bridge Scoping & Structure Determination
11 | WBS_B.5.6.2 | Hydraulics Letter
11 | WBS_B.5.6.3 | Foundations Recommendations-Bridge
11 | WBS_B.5.6.4 | Preliminary Bridge Design
11 | WBS_B.5.6.5 | Final Bridge Design
9 | WBS_B.5.7 | Bridge Substructure Widening | TMPL1508
9 | WBS_B.5.8 | Historic Bridge Study | TMPL1509
0
5 | WBS_R | Right of Way Schedule
7 | WBS_R.5 | Milestones (Right of Way)
7 | WBS_R.6 | Right of Way
9 | WBS_R.6.1 | Fee Acquisition | TMPL1600
11 | WBS_R.6.1.1 | Title Opinion
11 | WBS_R.6.1.2 | Right of Way Package
11 | WBS_R.6.1.3 | Valuations
11 | WBS_R.6.1.4 | Right of Way Pre-acquisition
11 | WBS_R.6.1.5 | Direct Purchase
11 | WBS_R.6.1.6 | Condemnation
11 | WBS_R.6.1.7 | Relocation | TMPL 1650
9 | WBS_R.6.2 | Temporary Right to Construct | TMPL1630
11 | WBS_R.6.2.1 | Title Opinion
11 | WBS_R.6.2.2 | Right of Way Package
11 | WBS_R.6.2.3 | Valuations
11 | WBS_R.6.2.4 | Right of Way Pre-acquisition
11 | WBS_R.6.2.5 | Direct Purchase
11 | WBS_R.6.2.6 | Condemnation
11 | WBS_R.6.2.7 | Relocation | TMPL 1650
9 | WBS_R.6.3 | Commissioner's Orders | TMPL1640
11 | WBS_R.6.3.1 | Title Opinion
11 | WBS_R.6.3.2 | Right of Way Package
11 | WBS_R.6.3.3 | Valuations
11 | WBS_R.6.3.4 | Right of Way Pre-acquisition
11 | WBS_R.6.3.5 | Direct Purchase
11 | WBS_R.6.3.6 | Condemnation
11 | WBS_R.6.3.7 | Relocation | TMPL 1650
9 | WBS_R.6.4 | Property Conveyance
| WBS_R.6.4.1 | Title Opinion
| WBS_R.6.4.2 | Right of Way Package
| WBS_R.6.4.3 | Valuations
| WBS_R.6.4.4 | Right of Way Pre-acquisition
| WBS_R.6.4.5 | Direct Purchase
| WBS_R.6.4.6 | Condemnation
| WBS_R.6.4.7 | Relocation | TMPL 1650
| WBS_R.6.5 | Acquisition (Metro) | TMPL1610

## WBS Definitions (hidden)
WBS Code | Project ID | WBS Name/Project Name | Description
WBS.1 | TMPLTMS | Milestones | The activities in this section of the WBS represent the Key Production Indicator (KPI) milestones for the project. They provide a high level view of the health of the project for a project manager or upper level management. These KPI milestones are REQUIRED in all Preconstruction Control Schedules. In the event that an individual KPI milestone is not applicable to a specific project (e.g. Preliminary Bridge Design Completed for a project that does not contain a bridge), it may be removed from the schedule.
WBS.2 | TMPLTPM | Project Management | Consists of the deliverables and activities needed to plan, organize, coordinate, and manage the constraints of a project.
WBS.2.1 | PTEM 5000 | Initial Design Project Baseline | When a project has a scope that consists of a multiple alternatives and the criteria for selection, a cost range that takes into consideration the possible alternatives, and a preliminary schedule; typically used for projects with complex environmental documentation.
WBS.2.2 | PTEM 5100 | Final Design Project Baseline | When a project has a scope with a defined alternative selected, a schedule for delivery of that scope, and a cost estimate consisting of a point cost that includes contingencies.
WBS.2.3 | TMPL 1220 | Ongoing Project Management | A deliverable that encompasses miscellaneous management activities, such as schedule maintenance, informal meetings, etc.
WBS.2.4 | TMPL 1230 | Transportation Management Plan | A deliverable where the project team determines, at the beginning of the project, how traffic will be handled and managed during construction.
WBS.2.5 | TMPL 1240 | Public Involvement | Involves project coordination with external stakeholders that may be affected by the project.
WBS.3 | TMPLTEN | Environmental | Consists of the deliverables and activities needed to assess the potential impacts a project may have to the surrounding environment and stakeholders, as well as the steps taken to avoid and/or mitigate those impacts.
WBS.3.1 | TMPL 1300 | Early Notification Memo | A document, sent to various groups in the MnDOT Office of Environmental Stewardship, that outlines the basic scope and location of a project and serves as a request for an assessment of the potential impacts that the project may have.
WBS.3.2 |  | Environmental Studies | Consists of various studies and assessments, by groups identified on the Early Notification Memo, performed to identify the potential environmental impacts that may be involved with a project.
WBS.3.2.1 |  | Cultural Resources | The tasks involved in determining the effects a project will have on cultural resources. Projects that exceed certain thresholds require SHPO Concurrence on and Tribal Review of Mn/DOT-FHWA Determination of Effect.
WBS.3.2.2 |  | Environmental Site Assessment
WBS.3.2.2.1 | TMPL 1306 | Environmental Due Diligence 1
WBS.3.2.2.2 | TMPL 1308 | Environmental Due Diligence 2
WBS.3.2.2.3 | TMPL 1310 | Environmental Due Diligence 3
WBS.3.2.2.4 | TMPL 1312 | Environmental Site Assessment (Phase I & II)
WBS.3.2.2.5 | TMPL 1314 | No Association Determined
WBS.3.2.2.6 | TMPL 1316 | Response Action Plans
WBS.3.2.2.7 | TMPL 1318 | Contaminated Materials Management Special Provisions
WBS.3.2.2.8 | TMPL 1324 | No Further Action Determined
WBS.3.2.3 |  | Regulated Waste | Consists of the activities needed for the assessment and removal of asbestos and other regulated materials in buildings or bridges
WBS.3.2.3.1 |  | Regulated Waste Assessment
WBS.3.2.3.2 |  | Regulated Waste Abatement
WBS.3.2.4 | TMPL 1328 | Noise Analysis | Consists of the activities needed to determine the noise impacts and abatement of a project.
WBS.3.2.5 | TMPL 1330 | Air Quality Analysis | Consists of the activities needed to determine the air quality impacts and abatement of a project.
WBS.3.2.6 |  | Threatened & Endangered Species
WBS.3.2.7 | TMPL 1368 | Vegetation Review
WBS.3.2.8 |  | Wetland Delineations
WBS.3.2.9 |  | Floodplain Assessment
WBS.3.2.10 |  | Wild & Scenic River Coordination
WBS.3.2.11 |  | Groundwater Impact Study
WBS.3.2.12 |  | Section 6(f) Coordination
WBS.3.2.13 |  | Environmental Justice Analysis
WBS.3.2.14 | TMPL 1409 | Visual Impact Assessment
WBS.3.2.15 |  | Earthborn Vibrations Study
WBS.3.2.16 |  | Geotechnical Study
WBS.3.2.17 |  | Farmland Conversion Impact Rating (Form AD 1006)
WBS.3.2.18 |  | Energy Analysis
WBS.3.2.19 |  | Other Environmental Study
WBS.3.3 |  | Environmental Documents | Documents that summarize the potential environmental impacts, provides avoidance and mitigation measures, and estimates the cost of a project.
WBS.3.3.1 |  | Environmental Document Exemption
WBS.3.3.2 | TMPL 1334 | Categorical Exclusion - Non Programmatic
WBS.3.3.3 | TMPL 1336 | Categorical Exclusion - Programmatic | Consists of the work necessary to complete the Categorical Exclusion Determination (CATEX). The Categorical Exclusion Determination is used for Class II Actions (Categorical Exclusions) in order to obtain Mn/DOT and FHWA environmental clearances.
WBS.3.3.4 | TMPL 1338 | Environmental Assessment/Environmental Assessment Worksheet
WBS.3.3.5 | TMPL 1340 | Environmental Impact Statement (EIS) | The process necessary to draft, review, and finalize an Environmental Impact Statement, which is a document that discusses the environmental impacts of a proposed Class I Action. It discusses all reasonable alternatives to the proposed action and summarizes the studies, reviews, consultations, and coordination required by law.
WBS.3.3.6 |  | EIS Re-evaluation
WBS.3.3.7 |  | Supplemental EIS
WBS.3.3.8 |  | Section 4(f)
WBS.3.4 |  | Permits | The work required to obtain the necessary permits from regulatory agencies that are needed in response to a potential impact of a project.
WBS.3.4.1 | TMPL 1346 | NPDES Stormwater Discharge Permit
WBS.3.4.2 |  | Wetland Permits
WBS.3.4.2.1 |  | 404 Corp Permit
WBS.3.4.2.2 |  | 401 MPCA Certification
WBS.3.4.2.3 |  | WCA Permit
WBS.3.4.3 | TMPL 1350 | DNR Public Waters Permit
WBS.3.4.4 | TMPL 1352 | Watershed District Permit
WBS.3.4.5 | TMPL 1354 | Section 9 (Coast Guard) Permit
WBS.3.4.6 |  | Section 10 (Navigable Waters) Permit
WBS.3.4.7 |  | Water Appropriation Permit
WBS.3.4.8 | TMPL 1360 | Industrial Discharge Permit
WBS.3.4.9 |  | Well Installation Permit
WBS.3.4.10 | TMPL 1364 | State Depredation Permit
WBS.3.4.11 | TMPL 1366 | Federal Depredation Permit
WBS.4 |  | Road Design | The deliverables and activities needed to produce the documents that comprise a roadway project contract to be bid on by a contractor.
WBS.4.1 |  | Surveys | The field work and technical work needed to provide complete and accurate data of the existing conditions of the project area to other functional groups.
WBS.4.1.1 |  | Control Surveys
WBS.4.1.1.1 | TMPL 1400 | Geodetic Control Surveys
WBS.4.1.1.2 | TMPL 1401 | Project Control Surveys
WBS.4.1.1.3 | TMPL 1402 | Photogrammetric Basemap
WBS.4.1.2 | TMPL 1403 | District Land Surveys
WBS.4.1.3 | TMPL 1404 | Design Surveys
WBS.4.2 |  | Preliminary Design | The work required to create the geometric design of a roadway, including design calculations, the illustrative layout of the design, and the documentation of and justification for design items that do not comply with standard design practices.
WBS.4.2.1 | TMPL 1405 | Staff Approved Layout
WBS.4.2.2 | TMPL 1406 | Design Memo/Design Exception
WBS.4.2.3 | TMPL 1412 | RW Construction Limit
WBS.4.2.4 | TMPL 1407 | Value Engineering on Geometric Layout
WBS.4.3 |  | Recommendations | Deliverables provided by various functional groups that identify recommended project items to be considered for incorporation into the final plans.
WBS.4.3.1 |  | Foundations Recommendations - Roadway
WBS.4.3.2 |  | Material Design Recommendations (MDR)
WBS.4.3.3 |  | Traffic Recommendations
WBS.4.3.3.1 |  | Detour
WBS.4.3.3.2 |  | Traffic Control
WBS.4.3.3.3 |  | Staging
WBS.4.3.4 |  | Hydraulics Design Recommendations
WBS.4.3.4.1 |  | Stormwater Treatment Design
WBS.4.3.4.2 |  | Culvert Design
WBS.4.3.4.3 |  | Storm Sewer Design
WBS.4.3.4.4 |  | Drain Tile Design
WBS.4.3.5 | TMPL 1416 | ADA Recommendations
WBS.4.3.6 |  | Bike/Pedestrian Recommendations
WBS.4.4 |  | Final Design | The detailed construction plans, special provisions, and final design estimate, as well as the turn-in process for those documents
WBS.4.4.1 |  | Plan Set
WBS.4.4.1.1 |  | Road Plans
WBS.4.4.1.1.1 |  | 30% Plans
WBS.4.4.1.1.2 |  | 60% Plans
WBS.4.4.1.1.3 |  | 90% Plans
WBS.4.4.2 |  | Project Turn In
WBS.4.5 |  | Utilities | A process where a Project Manager identifies conflicts and coordinates the proposed work on the project with utility companies involved.
WBS.4.5.1 |  | Subsurface Utility Engineering
WBS.4.5.2 | UTILITY | Utility Coordination
WBS.4.6 |  | Traffic Studies
WBS.4.6.1 |  | Traffic Counts
WBS.4.6.2 | Traffic | Traffic Forecasts
WBS.4.6.3 |  | Traffic Modeling
WBS.4.6.4 |  | Crash Analysis
WBS.4.6.5 |  | Intersection Control Evaluation
WBS.5 |  | Bridge Design | Consists of the deliverables and activities needed to produce the documents that comprise a bridge project contract to be bid on by a contractor.
WBS.5.1 |  | Bridge Scoping | Consists of the activities needed to determine the scope and preliminary cost estimate of bridge work on the project.
WBS.5.2 |  | Bridge Surveys | Consists of survey and drafting activities needed to provide the Bridge Office with the existing topography and proposed alignment of the project.
WBS.5.3 |  | Bridge Hydraulics Letter | Consists of the activities needed to analyze the body of water that a proposed bridge is spanning and establish recommendations for bridge design; analysis includes normal- and high-water levels, 50- and 100-year flood data, etc.
WBS.5.4 |  | Bridge Type Study | Consists of the activities needed to determine the feasible bridge types that can be utilized on a project.
WBS.5.5 |  | Foundations Recommendations - Structures | Consists of the field and laboratory work needed to determine the foundational requirements that will be needed for the bridge.
WBS.5.6 |  | Preliminary Bridge Design | Consists of the deliverables and activities needed to determine the design criteria of the bridge substructure and superstructure.
WBS.5.7 |  | Final Bridge Design | Consists of the deliverables and activities needed to produce the documents that comprise a bridge project contract to be bid on by a contractor.
WBS.6 |  | Right of Way | A process that is utilized to acquire property owned by others for temporary or permanent use.
WBS.6.1 |  | Title Opinion | A process that consists of identifying the names of the title holders for each parcel of property that is impacted by the project.
WBS.6.2 |  | Right of Way Package | A deliverable that consists of the title information (parcel number, landowner, etc.) for all parcels on a project, a map depicting the impacts to and acreages of the parcels, and the authorization of the construction limits on the project.
WBS.6.3 |  | Valuations | An appraisal the value of the individual property parcels to be acquired for the project.
WBS.6.4 |  | Right of Way Pre-acquisition | The initial meetings with individual landowners of parcels that will be impacted by the project to introduce the project, discuss impacts to each landowner, and possible mitigation techniques.
WBS.6.5 |  | Direct Purchase | An agreement between the State and a separate entity on the acquisition of a property that is achieved through negotiation.
WBS.6.6 |  | Condemnation | A process where the terms and conditions of the acquisition of property by the State from a separate entity is determined within the confines of a court of law.
WBS.6.7 | TMPL 1650 | Relocation | A process where the State agrees to acquire a parcel in full from a landowner and assume all costs required to move the landowner to a parcel and dwelling of equal value.
WBS.6.8 |  | Public Interest Finding | A process where the State must justify the value of the project to the public due to the fact that it is unable to secure the rights needed to access to one or multiple parcels impacted by the project prior to the letting date.
WBS.7 | TMPLTAG | Agreements | A process that is utilized to obtain agreements on various aspects of a project with other entities that are impacted or involved.
WBS.7.1 |  | Informal Agreement
WBS.7.2 |  | Lighting Agreement | The activities required to obtain an agreement with a different public agency in determining financial and operational responsibility for a lighting system.
WBS.7.3 |  | Signal Agreement | The activities required to obtain an agreement with a different public agency in determining financial and operational responsibility for a signal system.
WBS.7.4 | UTIL | Utility Agreement | The activities required to obtain an agreement with utility companies that determines compensation for the relocation of their facilities.
WBS.7.5 |  | Cooperative Construction Agreement | The activities required to obtain an agreement with another public agency that determines financial responsibility for construction and operational responsibility for the facility.
WBS.7.6 |  | Railroad Agreement | The activities required to acquire an agreement with a railroad company that is impacted by a project.
WBS.7.6.1 | RR FA | Railroad Flagging Agreement
WBS.7.6.2 | RR B | Railroad Bridge Agreement
WBS.7.6.3 | RR TR | Railroad Track Relocation Agreement
WBS.7.7 |  | Detour Agreement | The activities required to obtain an agreement with other public agencies to utilize their roadways as part of a detour for the project.
WBS.7.8 |  | Turnback Agreement | The activities required to release jurisdiction of a state-owned facility to another public agency.
WBS.7.9 |  | Joint Powers Agreement
WBS.8 | TMPLTLT | Letting | The process of authorizing a project and releasing it for bidding by contractors; refer to xxxxx for more information.
WBS.8.1 | TMPL 2000 | Process A | A letting process for small projects with minor scope.
WBS.8.1.1 |  | Plans & Special Provisions
WBS.8.1.2 |  | Estimating
WBS.8.1.3 |  | Letting
WBS.8.2 | TMPL 2001 | Typical Process B | A letting process that applies to most MnDOT projects; requires Central Office approval and involves a turn-in date at least 7 weeks prior to letting.
WBS.8.2.1 |  | Plans & Special Provisions
WBS.8.2.2 |  | Estimating
WBS.8.2.3 |  | Letting
WBS.8.3 | TMPL 2002 | Complex Process B | A letting process that applies to complex projects > $10 million.
WBS.8.3.1 |  | Plans & Special Provisions
WBS.8.3.2 |  | Estimating
WBS.8.3.3 |  | Letting
WBS.8.4 |  | Full Federal Oversight | A letting process that requires monitoring and oversight from the Federal Highway Administration.
WBS.8.5 |  | Negotiated Contracts
WBS.8.6 |  | Agreement | A letting process that includes an agreement with a county or municipality.
WBS.8.7 |  | DesignBuild | A letting process where the contractor is required to complete both design and construction of a project.
WBS.8.8 |  | CMGC | A letting process that contractually allows for a contractor to be involved with the design of a project and provides an opportunity for that contractor to bid on the project prior to it being released for bids.
WBS.8.9 |  | Letting by Others | A letting process whereby a local agency is able to let a state-funded project.
WBS.9 |  | Construction

## Activity Owner Guidance (hidden)
Ownership for Functional Groups
Americans With Disabilities Act (ADA)
Assign all ADA activities to Tara Olds.
Cultural Resources Unit
Cultural Resource assigns owners in house based on work load.
Likely owners are:
· Andrea Pizza
· Craig Johnson
· Elizabeth Abel
· Kristen Zschomler
· Teresa Martin
Environmental Assessment Unit
Mussel Survey
Assign all activities to Jason Alcott
Section 7 Determination [Threatened & Endangered Species]
Assign all activities to Jason Alcott
Environmental Investigation Unit
Regulated Materials
District | Owner
District 1, 2, 3, 4, Metro North and Metro East | Mark Vogel
District 6, 7, 8, Metro South and Metro West | Jackie Klein
Environmental Modeling and Testing Unit
Noise Analysis Template
All Activities are currently assigned to the correct owners for outstate. For Metro reassign all activities with Marilyn Jordahl-Larson to Peter Wasko.
Air Quality Analysis Template
All Activities are currently assigned to the correct owners for outstate. For Metro reassign all activities with Marilyn Jordahl-Larson to Peter Wasko.
Contaminated Materials
District | Owner
D1, D2, D3 and Metro North | Carolyn Boben
D4, Metro West and Metro East | Keri Aufdencamp
D6, D7, D8 and Metro South | Sarah Jarman
Transit Focused projects | Jim DeLuca
Geometric Design Support
Assign all projects to Darwin Yasis. Geometric Design Support will reassign the activity in house when the activity is started.
Office of Freight and Commercial Vehicle Operations – Rail Administration Section
District | Owner
District1 & 4 | Paul Delarosa
District 2 & 3 | Rick VanWagner
Metro | Jim Weatherhead
District 6, 7 & 8 | Dennis Williams
Roadside Vegetation Management Unit
Assign all projects to Tina Markeson. The Roadside Vegetation Management Unit will reassign the activity in house when the activity is started.
Temporary Right to Construct Activity Ownerships
All Projects- Only outstate Districts
District | Direct Offer | Closing
Duluth | John Hinzmann | Tom Weber
Bemidji | Denise Watkins | Tom Weber
Baxter | Brett Stark | Tom Weber
Detroit Lakes | Jeremy Flatau | Tom Weber
Rochester | Mark T-I | Tom Weber
Mankato | Tim Hoehn | Tom Weber
Willmar | Mike Lownsbury | Tom Weber
Title Services Activity
All Projects- Only outstate Districts
District | Prepare Title Opinions | Utility Easements | Title Map
D1 | John Hinzmann | John Hinzmann | John Hinzmann
D2 | Denise Watkins | Denise Watkins | Design Project Manager
D3 | Brett Stark | Brett Stark | Brett Stark
D4 | Brian Bausman | Brian Bausman | Brian Bausman
D6 | Mark T-I | Mark T-I | Jordan Kurth
D7 | TJ Thill | TJ Thill | Undetermined – needs further discussion in D7
D8 | Mike Lownsbury | Mike Lownsbury | Nathan Peterson, Design Project Manager
R/W Package Activity Ownerships
All Projects- Only outstate Districts | All Outstate Districts | Default Schedule Updates
District | Autho Map (1000) | Plats (1020) | Plat Desc. (1070) | Package (1080)
Duluth | John Hinzmann | John Hinzmann | John Hinzmann | John Hinzmann
Bemidji | Denise Watkins | Dan Domeier | Dan Domeier | Denis Watkins
Baxter | Brett Stark | Kevin Metz | Kevin Metz | Brett Stark
Detroit Lakes | Jeremy Flatau | Tom Harper | Tom Harper | Jeremy Flatau
Rochester | Mark T-I | Keith Kallin | Keith Kallin | Mark T-I
Mankato | Tim Hoehn | TJ Thill | TJ Thill | Tim Hoehn
Willmar | Mike Lownsbury | Adam Aarndt | Adam Aarndt | Mike Lownsbury
R/W Valuation Activity Ownerships
Large Projects- Only outstate Districts | All Outstate Districts | Default Schedule Updates
District | Contract Procurement | Complete Valuation | Certification
Duluth | Roberta Dwyer | Skip Pitzen | Skip Pitzen
Bemidji | Skip Pitzen | Skip Pitzen | Skip Pitzen
Baxter | Greg Thompson | Skip Pitzen | Skip Pitzen
Detroit Lakes | Skip Pitzen | Skip Pitzen | Skip Pitzen
Rochester | Ron Lambert | Ron Lambert | Ron Lambert
Mankato | Tim Hoehn | Tim Hoehn | Ron Lambert
Wilmar | Ron Lambert | Ron Lambert | Ron Lambert
Small Projects – ADA or other minor acquisitions
District | Contract Procurement | Complete Valuation | Certification
Duluth | Roberta Dwyer | Skip Pitzen | Skip Pitzen
Bemidji | Skip Pitzen | Skip Pitzen | Skip Pitzen
Baxter | Greg Thompson | Kevin Schmidt | Skip Pitzen
Detroit Lakes | Skip Pitzen | Skip Pitzen | Skip Pitzen
Rochester | Mark T-I | Ron Lambert | Mark T-I
Mankato | Tim Hoehn | Tim Hoehn | Tim Hoehn
Wilmar | Mike Lownsbury | Ron Lambert | Mike Lownsbury
Pre-acquisition Activity Ownerships
All Projects- Only outstate Districts | All Outstate Districts | Default Schedule Updates
District | Autho. Map(1000) | Orders (1090) | Encumber (1100) | Docs (1070)
Duluth | Julie Groetsch | Paul Hendrickson | Julie Groetsch | Don Goedken
Bemidji | Julie Groetsch | Paul Hendrickson | Julie Groetsch | Don Goedken
Baxter | Julie Groetsch | Paul Hendrickson | Julie Groetsch | Don Goedken
Detroit Lakes | Julie Groetsch | Paul Hendrickson | Julie Groetsch | Don Goedken
Rochester | Julie Groetsch | Paul Hendrickson | Julie Groetsch | Don Goedken
Mankato | Julie Groetsch | Paul Hendrickson | Julie Groetsch | Don Goedken
Willmar | Julie Groetsch | Paul Hendrickson | Julie Groetsch | Don Goedken
District | Plat Review (1040) | Plats (1050 & 1060) | Descriptions (1020 1030)
Duluth | Elliott Ruhland | John Hinzmann | Larry Sodergren
Bemidji | Elliott Ruhland | Dan Domeier | Larry Sodergren
Baxter | Elliott Ruhland | Brett Stark | Larry Sodergren
Detroit Lakes | Elliott Ruhland | Tom Harper | Larry Sodergren
Rochester | Elliott Ruhland | Keith Kallin | Larry Sodergren
Mankato | Elliott Ruhland | TJ Thill | Larry Sodergren
Willmar | Elliott Ruhland | Adam Aarndt | Larry Sodergren
Documents include – 1070, 1080 &1110
Utility Agreement and Utility Coordination Template
Ann Driver the Permit Coordinator will be the CO owner
Owners are assigned on a first come first serve basis.
This will also have district owners
Geodetic Unit---OLM--Office of Land Management
John Barke is the CO owner
District | Surveys
D1 | J. Hinzmann
D2 | D. Domeier
D3 | K. Metz
D4 | T.Harper
D6 | K. Kallin
D7 | T. Shorter
D8 | A. Ahrndt
Metro | D. Torfin

## Work Package Index
Work Packages
Acquisition (Metro)
ADA Recommendations
Air Quality Analysis
Blowing and Drifting Snow Control
Bridge Preservation
Bridge Redeck
Bridge Substructure Widening
Cable Median Barrier Project Plan
Categorical Exclusion - Non Programmatic
Categorical Exclusion - Programmatic
CMGC Template
Commissioner's Orders
Consultant Bridge Design (Final Only Consultant)
Consultant Bridge Design (Prelim & Final Consultant)
Contaminated Materials Management Special Provisions
Cooperative Construction Agreement
Cultural Resources - Work Package 1 Full Section 106 Review- All Federal Agencies
Cultural Resources - Work Package 2 FHWA Funds
Cultural Resources - Work Package 3 State Level Review (State Funds Only)
Culvert
Design Build
Design Memo/Design Exception
Design Surveys
Detour Agreement
District Land Surveys
DNR Public Waters Permit
Early Notification Memo
Environmental Assessment Worksheet (EAW) State
Environmental Assessment/Environmental Assessment Worksheet
Environmental Due Diligence 1
Environmental Due Diligence 2
Environmental Due Diligence 3
Environmental Impact Statement (EIS)
Environmental Site Assessment (Phase I & II) Acquisition
Environmental Site Assessment (Phase I & II) Early Acquisition
Environmental Site Assessment (Phase I & II) No Acquisition
Fee Acquisition
Foundation Recommendations
Geodetic Control Surveys
Historic Bridge Study
Hydraulics Design
Hydraulics/WRE Plans
Intersection Control Evaluation
Interstate Access Request
Landscaping Plan
Lighting Agreement
Lighting Plan
Maintenance Plan
Material Design Recommendations (MDR)
Milestones (Design)
Milestones (Scoping)
Minor Project Template (Signing, Signal, Lighting)
Municipal Consent
Municipal Consent (Appeal Process)
Mussel Survey
New Bridge
No Association Determination
Noise Analysis
NPDES Stormwater Discharge Permit
Ongoing Project Management
Pavement Marking Plan
Phase I Update
Phase II Update
Photogrammetric Basemap
Prequalification (Tech Proposal)
Process A
Process B
Process B Complex
Process B PODI
Project Baseline
Project Control Surveys
Project Management
Project Template
Project Turn In
Railroad Bridge Agreement
Railroad Flagging Agreement
Railroad Track Relocation Agreement
Regulated Materials-Bridge
Regulated Materials-Building
Regulatory File Review
Relocation
Response Action Plans
Road Plans
RW Construction Limit
Scoping Document
Scoping Template
Scoping Template
Section 4(f) Coordination
Section 6(f) Coordination
Section 7 Determination [Threatened & Endangered Species]- Formal Consultation
Section 7 Determination [Threatened & Endangered Species]- May Affect
Section 7 Determination [Threatened & Endangered Species]- No Effect
Section 9 (Coast Guard) Permit
Signal Agreement
Signal Plan
Signing Plan
Special Provisions
Staff Approved Layout
Stormwater Treatment Design
Subsurface Utility Engineering
Surveys
Temporary Right to Construct
Time and Traffic
TMS Plan
Traffic Control/Staging Plan
Traffic Counts
Traffic Forecasts
Transportation Management Plan
Utility Agreement
Utility Coordination
Value Engineering
Vegetation Review
Visual Impact Assessment
Visual Quality Management Plan
Watershed District Permit
Wetland Delineations
Wetland/WCA & Aquatic Resources (404/401/Section 10)

## Activity Owners
Work package Activity Ownership | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
ADA Requirements
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
ADA Unit | Chng2Dic | Chng2Dic | Chng2Dic | Chng2Dic | Chng2Dic | Chng2Dic | Chng2Dic | Chng2Dic
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Air Quality Analysis
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental modeling & Testing Unit | Marilyn Jordahl-Larson | Marilyn Jordahl-Larson | Marilyn Jordahl-Larson | Marilyn Jordahl-Larson | Peter Wasko | Marilyn Jordahl-Larson | Marilyn Jordahl-Larson | Marilyn Jordahl-Larson
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Blowing and Drifting Snow Control
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Road Veg. Mgmt | Dan Gullickson | Dan Gullickson | Dan Gullickson | Dan Gullickson | Dan Gullickson | Dan Gullickson | Dan Gullickson | Dan Gullickson
Project Delivery. Special Provisions | Paul Merchlewicz | Paul Merchlewicz | Paul Merchlewicz | Paul Merchlewicz | Paul Merchlewicz | Paul Merchlewicz | Paul Merchlewicz | Paul Merchlewicz
Bridge Preservation
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
RHB0900 Finalize Bridge Aesthetic Recommendation | Mellissa Schultz | Mellissa Schultz | Mellissa Schultz | Mellissa Schultz | Mellissa Schultz | Mellissa Schultz | Mellissa Schultz | Mellissa Schultz
RHB1000 Prepare Draft Repair Recommendation | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
RHB1010 Send Draft Repair Recommendation to District for Concurrence | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
RHB1020 District Provide Concurrence on Draft Repair Recommendation | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District
RHB1030 Receive Draft Repair Recommendation Concurrence from District | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
RHB1040 Prepare Final Repair Recommendation | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
RHB1050 Send Final Repair Recommendation to District for Signature | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
RHB1060 District Signs Final Repair Recommendations | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District
RHB1080 Prepare Bridge Rehab Preliminary Estimate | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward
FRP0900 Receive Signed Final Bridge Repair Recommendations | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FRP1000 Geometry | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FRP1010 General Coordination | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FRP1020 GP&E, Workpoints | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FRP1040 Repair Design and Coordination | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FRP1050 Repair Drafting | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FRP1060 Specs | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FRP1070 Plan Review by Regional Construction Bridge Engineer | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
FRP1080 Obtain State Bridge Engineer's Signature | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FRP1090 Final Estimate | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward
Bridge Redeck
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
RHB0900 Finalize Bridge Aesthetic Recommendation | Mellissa Schultz | Mellissa Schultz | Mellissa Schultz | Mellissa Schultz | Mellissa Schultz | Mellissa Schultz | Mellissa Schultz | Mellissa Schultz
RHB0980 Perform Bridge Load Rating Analysis | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
RHB0990 Perform Structural Analysis | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
RHB1000 Prepare Draft Repair Recommendation | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
RHB1010 Send Draft Repair Recommendation to District for Concurrence | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
RHB1020 District Provide Concurrence on Draft Repair Recommendation | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District
RHB1030 Receive Draft Repair Recommendation Concurrence from District | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
RHB1040 Prepare Final Repair Recommendation | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
RHB1050 Send Final Repair Recommendation to District for Signature | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
RHB1060 District Signs Final Repair Recommendations | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District
RHB1080 Prepare Bridge Rehab Preliminary Estimate | Sout1Jef | Sout1Jef | Sout1Jef | Sout1Jef | Sout1Jef | Sout1Jef | Sout1Jef | Sout1Jef
FRP0900 Receive Signed Final Bridge Repair Recommendations | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FRP1000 Geometry | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FRP1010 General Coordination | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FRP1020 GP&E, Workpoints | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FRP1040 Repair Design and Coordination | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FRP1050 Repair Drafting | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FRP1060 Specs | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FRP1070 Plan Review by Regional Construction Bridge Engineer | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
FRP1080 Obtain State Bridge Engineer's Signature | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FRP1090 Final Estimate | Sout1Jef | Sout1Jef | Sout1Jef | Sout1Jef | Sout1Jef | Sout1Jef | Sout1Jef | Sout1Jef
Bridge Substructure Widening
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
RHB0980 Perform Bridge Load Rating Analysis | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
RHB0990 Perform Bridge Structural Analysis | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
RHB1000 Prepare Bridge Draft Repair Recommendation | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
RHB1010 Send Draft Bridge Repair Recommendation to District for Concurrence | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
RHB1020 District Provide Concurrence on Draft Bridge Repair Recommendation | Ed Lutgen | Ed Lutgen | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District
RHB1030 Receive Draft Bridge Repair Recommendation Concurrence from District | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
RHB1040 Prepare Final Bridge Repair Recommendation | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
RHB1050 Send Final Bridge Repair Recommendation to District for Signature | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
RHB1060 District Signs Final Bridge Repair Recommendations | District PM | District PM | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District
BFR1000 Prepare and Submit Foundations Request by District | District PM | District PM | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District | District PM or Individual from District
BFR1010 Receive Substructures Locations for Geotechnical Investigation | Pers1Gar | Pers1Gar | Pers1Gar | Pers1Gar | Pers1Gar | Pers1Gar | Pers1Gar | Pers1Gar
BFR1020 Develop Geotechnical Investigation Plan | Pers1Gar | Pers1Gar | Pers1Gar | Pers1Gar | Pers1Gar | Pers1Gar | Pers1Gar | Pers1Gar
BFR1030 Perform Geotechnical Investigation | Brad1Dea | Brad1Dea | Brad1Dea | Brad1Dea | Brad1Dea | Brad1Dea | Brad1Dea | Brad1Dea
BFR1040 Perform Geotechnical Lab Analysis | Radj1Ras | Radj1Ras | Radj1Ras | Radj1Ras | Radj1Ras | Radj1Ras | Radj1Ras | Radj1Ras
BFR1050 Prepare Geotechnical Recommendation/Report | Pers1Gar | Pers1Gar | Pers1Gar | Pers1Gar | Pers1Gar | Pers1Gar | Pers1Gar | Pers1Gar
PBP1000 Receive Bridge Survey Files | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt
PBP1010 Receive Roadway Design Files | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt
PBP1020 Finalize Bridge Aesthetic Recommendation | Melissa Schultz | Melissa Schultz | Melissa Schultz | Melissa Schultz | Melissa Schultz | Melissa Schultz | Melissa Schultz | Melissa Schultz
PBP1030 Draft Preliminary Bridge Plan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan
PBP1040 Receive & Plot Borings | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan
PBP1050 Check Preliminary Bridge Plan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan
PBP1060 Distribute Bridge Plan, Borings, Foundation Report to Regional Const. Engineer | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt
PBP1070 Prepare Bridge Foundation Recommendation | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
PBP1080 Finalize Preliminary Bridge Plans with Foundation Recommendations | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan
PBP1090 Receive Bridge Foundation Recommendation | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan
PBP1100 Obtain State Bridge Engineer's Signature - Preliminary | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan
PBP1110 Distribute Signed Preliminary Bridge Plan | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt
PBP1120 Preliminary Bridge Estimate & District Letter | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan
PBP1130 FHWA Approval (if necessary) | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan
FBP0900 Receive Signed Final Bridge Repair Recommendations | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1000 Receive Signed Preliminary Bridge Plan | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1005 General Coordination | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FBP1031 Prepare 30% Final Bridge Plans | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1061 Prepare 60% Final Bridge Plans | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1091 Prepare 95% Final Bridge Plans | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1100 Bridge Specs | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1110 Bridge Plan Review by Construction & Estimating | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
FBP1120 Obtain State Bridge Engineer's Signature - Final | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1130 Bridge Final Estimate | Sout1Jef | Sout1Jef | Sout1Jef | Sout1Jef | Sout1Jef | Sout1Jef | Sout1Jef | Sout1Jef
Cable Median Barrier (Barrier Design)
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Design | District Design Engineer | District Design Engineer | District Design Engineer | District Design Engineer | District Design Engineer | District Design Engineer | District Design Engineer | District Design Engineer
Categorical Exclusion - Non Programmatic
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental Assessment Unit | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan
District Project Management | PM | PM | PM | PM | Writer: In general, Writer assignments are made by work-type Ahlm1deb - Traffic, Safety, RTMS (Program = SC, SH, TM) Bund1deb - Bridge Projects, Resurfacing (Program = BR, RS) Clay1can - EA projects, Resurfacing (Program = MC, RD, RC, RS) Gomb1bri - EA projects, Resurfacing (Program = MC, RD, RC, RS,) Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
Categorical Exclusion - Programmatic
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Project Management | PM | PM | PM | PM | Writer: In general, Writer assignments are made by work-type Ahlm1deb - Traffic, Safety, RTMS (Program = SC, SH, TM) Bund1deb - Bridge Projects, Resurfacing (Program = BR, RS) Clay1can - EA projects, Resurfacing (Program = MC, RD, RC, RS) Gomb1bri - EA projects, Resurfacing (Program = MC, RD, RC, RS,) Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
Commissioner's Orders
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
RPR 1000 Right of Way Receive and Distribute | Julie Groetsch | Julie Groetsch | Julie Groetsch | Julie Groetsch | Julie Groetsch | Julie Groetsch | Julie Groetsch | Julie Groetsch
RPR 1080 Commissioner's Orders | Paul Hendrickson | Paul Hendrickson | Paul Hendrickson | Paul Hendrickson | Paul Hendrickson | Paul Hendrickson | Paul Hendrickson | Paul Hendrickson
Consultant Bridge Design (Final Only Consultant)
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
STR1000 Receive Scoping Estimate Request (Form A) | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward
STR1010 Identify Structures & Determine Bridge Work Type | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
STR1020 Conduct Site Visit | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
STR1030 Conduct Hydraulics Scoping | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
STR1040 Prepare Program/Scoping Estimate (Form B) | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward
STR1050 Evaluate Feasible Alternatives, Identify Preferred Alternative & Propose Structure Type | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
STR1060 Review Project Information/Stakeholder Discussion | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
STR1080 Receive Structure Concurrence from District & Hydraulics | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
BHL1000 Receive Bridge Survey Data | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1010 Research & Field Review | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1020 Hydraulic Modeling | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1030 Risk Assessment | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1040 Write Hydraulic Letter | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1050 Review & Finalize Hydraulic Letter | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1060 Deck Drain Study | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1070 Scour Confirmation Letter | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
PBP1000 Receive Survey Files | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt
PBP1010 Receive Roadway Design Files | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt
PBP1020 Finalize Aesthetic Recommendation | Melissa Schultz | Melissa Schultz | Melissa Schultz | Melissa Schultz | Melissa Schultz | Melissa Schultz | Melissa Schultz | Melissa Schultz
PBP1030 Draft Preliminary Plan | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1040 Receive & Plot Borings | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1050 Check Preliminary Plan | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1060 Distribute Plan, Borings, Foundation Report to Regional Const. Engineer | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt
PBP1070 Prepare Bridge Foundation Recommendation | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
PBP1080 Finalize Preliminary Plans with Foundation Recommendations | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1090 Receive Bridge Foundation Recommendation | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1100 Obtain State Bridge Engineer's Signature - Preliminary | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1110 Distribute Signed Preliminary Bridge Plan | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt
PBP1120 Preliminary Estimate & District Letter | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1130 FHWA Approval (if necessary) | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
BFR1000 Prepare and Submit Foundations Request by District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District
BFR1010 Receive Substructures Locations for Geotechnical Investigation | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person
BFR1020 Develop Geotechnical Investigation Plan | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person
BFR1030 Perform Geotechnical Investigation | Brad1Dea | Brad1Dea | Brad1Dea | Brad1Dea | Brad1Dea | Brad1Dea | Brad1Dea | Brad1Dea
BFR1040 Perform Geotechnical Lab Analysis | Rassaki Radji | Rassaki Radji | Rassaki Radji | Rassaki Radji | Rassaki Radji | Rassaki Radji | Rassaki Radji | Rassaki Radji
BFR1050 Prepare Geotechnical Recommendation/Report | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person
FBP1000 Receive Signed Preliminary Bridge Plan | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1005 General Coordination | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FBP1031 Prepare 30% Final Bridge Plans - By Consultant | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1036 Perform 30% Final Bridge Plan Review - By MnDOT | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1061 Prepare 60% Final Bridge Plans - By Consultant | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1066 Perform 60% Final Bridge Plan Review - By MnDOT | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1091 Prepare 95% Final Bridge Plans - By Consultant | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1096 Perform 95% Plan Review - By MnDOT | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1100 Bridge Specs - By Consultant | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1110 Bridge Plan Review by Construction & Estimating - By MnDOT | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
FBP1120 Obtain State Bridge Engineer's Signature - Final - By Consultan | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1130 Final Estimate - By MnDOT | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward
Consultant Bridge Design (Prelim & Final Consultant)
Owner
| D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Activity ID/ Functional Group
STR1000 Receive Scoping Estimate Request (Form A) - By Consultant | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward
STR1010 Identify Structures & Determine Bridge Work Type - By Consultant | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
STR1020 Conduct Site Visit - By Consultant | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
STR1030 Conduct Hydraulics Scoping - By Consultant | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
STR1040 Prepare Program/Scoping Estimate (Form B) - By Consultant | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward
STR1050 Evaluate Feasible Alternatives, Identify Preferred Alternative & Propose Structure Type - By Consultant | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
STR1060 Review Project Information/Stakeholder Discussion - By Consultant | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
STR1080 Receive Structure Concurrence from District & Hydraulics - By Consultant | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
BHL1000 Receive Bridge Survey Data - By MnDOT | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1010 Research & Field Review- By MnDOT | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1020 Hydraulic Modeling- By MnDOT | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1030 Risk Assessment- By MnDOT | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1040 Write Hydraulic Letter- By MnDOT | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1050 Review & Finalize Hydraulic Letter- By MnDOT | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1060 Deck Drain Study- By MnDOT | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1070 Scour Confirmation Letter- By MnDOT | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
PBP1000 Receive Survey Files - By Consultant | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt
PBP1010 Receive Roadway Design Files - By Consultant | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt
PBP1025 Draft 30% Preliminary Plan - By Consultant | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1035 Review 30% Preliminary Plan - By MnDOT | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1040 Receive & Plot Borings - By Consultant | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1050 Check Final Preliminary Plan - By Consultant | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1055 Review Final Preliminary Plans - By MnDOT | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1060 Distribute Plan, Borings, Foundation Report to Regional Const. Engineer - By Consultant | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt
PBP1070 Prepare Bridge Foundation Recommendation - By Consultant | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
PBP1080 Finalize Preliminary Plans with Foundation Recommendations - By Consultant | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1090 Receive Bridge Foundation Recommendation - By Consultant | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1100 Obtain State Bridge Engineer's Signature - Preliminary - By Consultant | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1110 Distribute Signed Preliminary Bridge Plan - By Consultant | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt
PBP1120 Preliminary Estimate & District Letter - By Consultant | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1130 FHWA Approval (if necessary) - By Consultant | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
BFR1000 Prepare and Submit Foundations Request by District - By MnDOT | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District | District PM or Individual in the District
BFR1010 Receive Substructures Locations for Geotechnical Investigation - By MnDOT | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person
BFR1020 Develop Geotechnical Investigation Plan - By MnDOT | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person
BFR1030 Perform Geotechnical Investigation - By MnDOT | Brad1Dea | Brad1Dea | Brad1Dea | Brad1Dea | Brad1Dea | Brad1Dea | Brad1Dea | Brad1Dea
BFR1040 Perform Geotechnical Lab Analysis - By MnDOT | Rassaki Radji | Rassaki Radji | Rassaki Radji | Rassaki Radji | Rassaki Radji | Rassaki Radji | Rassaki Radji | Rassaki Radji
BFR1050 Prepare Geotechnical Recommendation/Report - By MnDOT | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person
FBP1000 Receive Signed Preliminary Bridge Plan - By Consultant | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1005 General Coordination | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FBP1031 Prepare 30% Final Bridge Plans - By Consultant | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1036 Perform 30% Final Bridge Plan Review - By MnDOT | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1061 Prepare 60% Final Bridge Plans - By Consultant | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1066 Perform 60% Final Bridge Plan Review - By MnDOT | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1091 Prepare 95% Final Bridge Plans - By Consultant | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1096 Perform 95% Final Bridge Plan Review - By MnDOT | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1100 Bridge Specs - By Consultant | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1110 Bridge Plan Review by Construction & Estimating - By MnDOT | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
FBP1120 Obtain State Bridge Engineer's Signature - Final - By Consultant | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1130 Bridge Final Estimate - By MnDOT | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward
Contaminated Materials Management Special Provisions
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental Investigations Unit (Jim DeLuca on Transit Focused Projects) | Carolyn Boben | Carolyn Boben | Carolyn Boben | Keri Aufdencamp | Carolyn Boben (N) Keri Aufdencamp (W/E) Sarah Jarman (S) | Sarah Jarman | Sarah Jarman | Sarah Jarman
District Construction |  |  |  |  | RE
Cooperative Construction Agreement
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
ACC1000 Discuss Cost Participation with LGU [District] | PM | PM | PM | PM | PM | Rhonda Prestegard | PM | PM
ACC1010 Prepare & Submit Cooperative Agreement Request [District] | PM | PM | Bob Nibbe |  | PM | Rhonda Prestegard | PM | PM
ACC1020 Agreement Turn In Complete [OPMTS] | Rob Rucker | Rob Rucker | Rob Rucker | Rob Rucker | Rob Rucker | Rob Rucker | Rob Rucker | Rob Rucker
ACC1030 Write Agreement [OPMTS] | Rob Rucker | Rob Rucker | Rob Rucker | Rob Rucker | Rob Rucker | Rob Rucker | Rob Rucker | Rob Rucker
ACC1035 Send/Obtain Signatures [District] | PM | PM | PM | PM | PM | Rhonda Prestegard | PM | PM
ACC1040 Execute Agreement [OPMTS] | Rob Rucker | Rob Rucker | Rob Rucker | Rob Rucker | Rob Rucker | Rob Rucker | Rob Rucker | Rob Rucker
Cultural Resources - Work Package 1 Full Section 106 Review- All Federal Agencies
Activity Owner will be reassigned by Kristen Zschomler after ENM Review | Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Cultural Resources | Kristen Zschomler | Kristen Zschomler | Kristen Zschomler | Kristen Zschomler | Kristen Zschomler | Kristen Zschomler | Kristen Zschomler | Kristen Zschomler
Cultural Resources - Work Package 2 FHWA Funds
Activity Owner will be reassigned by Kristen Zschomler after ENM Review | Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Cultural Resources | Kristen Zschomler | Kristen Zschomler | Kristen Zschomler | Kristen Zschomler | Kristen Zschomler | Kristen Zschomler | Kristen Zschomler | Kristen Zschomler
Cultural Resources - Work Package 3 State Level Review (State Funds Only)
Activity Owner will be reassigned by Kristen Zschomler after ENM Review | Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Cultural Resources | Kristen Zschomler | Kristen Zschomler | Kristen Zschomler | Kristen Zschomler | Kristen Zschomler | Kristen Zschomler | Kristen Zschomler | Kristen Zschomler
Culvert
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
STR1030 Conduct Hydraulics Scoping | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
STR1050 Identify Alternatives - Structure Type Study | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
STR1070 Propose Structure Type | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
STR1080 Receive District Concurrence from District and Hydraulics | District PM or Individual in District | District PM or Individual in District | District PM or Individual in District | District PM or Individual in District | District PM or Individual in District | District PM or Individual in District | District PM or Individual in District | District PM or Individual in District
BHL1000 Receive Bridge Survey Data | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1010 Research & Field Review | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1020 Hydraulic Modeling | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1030 Risk Assessment | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1040 Write Hydraulic Letter | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1050 Review & Finalize Hydraulic Letter | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
FCP1000 Receive Culvert Request Form from District | Jessica Duncan | Jessica Duncan | Jessica Duncan | Jessica Duncan | Paul Kettleson | Angel Staples | Angel Staples | Angel Staples
FCP1010 Culvert Design/Drafting | Jessica Duncan | Jessica Duncan | Jessica Duncan | Jessica Duncan | Paul Kettleson | Angel Staples | Angel Staples | Angel Staples
FCP1020 District Review of Culvert Design | District PM or Individual in District | District PM or Individual in District | District PM or Individual in District | District PM or Individual in District | District PM or Individual in District | District PM or Individual in District | District PM or Individual in District | District PM or Individual in District
FCP1030 Obtain State Bridge Engineer's Signature - Culvert | Jessica Duncan | Jessica Duncan | Jessica Duncan | Jessica Duncan | Paul Kettleson | Angel Staples | Angel Staples | Angel Staples
Detour Agreements
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Project Management | PM | Bill Pirkl | Darren Nelson |  | PM | Rhonda Prestegard | PM | PM
Design-Build
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Design-Build | Peter Davich | Peter Davich | Peter Davich | Peter Davich | Peter Davich | Peter Davich | Peter Davich | Peter Davich
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Engineering Cost Data & Estimating Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Letting Coordination Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Utility Agreements/Permits | Mollie Zauner | Ed Barrett | Sam Muench | Sam Muench | East Metro Mollie Zauner & West Metro Ed Barrett | Sam Muench | Mollie Zauner | Ed Barrett
Direct Purchase & Relocation Assistance Unit | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan
Design Memo/ Design Exception
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Project Management | PM | PM | PM |  | PM | PM | PM | PM
Surveys | Darwin Yasis | Darwin Yasis | Darwin Yasis |  | Darwin Yasis | Darwin Yasis | Darwin Yasis | Darwin Yasis
Design Surveys
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Surveys | Dave Huray | Dan Domeier | Kevin Metz |  | Dave Torfin | Keith Kallin | Travis Shorter | Adam Ahrndt
DNR Public Waters Permit
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Hydraulics/WRE |  |  |  |  | Use this Link |  | Chuck Slama | Nathan Pederson
Early Notification Memo
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
ENM1000 Prepare & Distribute ENM | District Environmental Coordinator or PM | District Environmental Coordinator or PM | District Environmental Coordinator or PM | District Environmental Coordinator or PM | Writer: In general, Writer assignments are made by work-type Ahlm1deb - Traffic, Safety, RTMS (Program = SC, SH, TM) Bund1deb - Bridge Projects, Resurfacing (Program = BR, RS) Clay1can - EA projects, Resurfacing (Program = MC, RD, RC, RS) Gomb1bri - EA projects, Resurfacing (Program = MC, RD, RC, RS) | District Environmental Coordinator or PM | District Environmental Coordinator or PM | District Environmental Coordinator or PM
ENM1020 Review & Respond to ENM by CMMT | Carolyn Boben | Carolyn Boben | Carolyn Boben | Keri Aufdencamp | If SP number begins with the numbers below, the Activity owner is the person in CMMT indicated: - 27, 13, 82 (corresponding to Metro West and East Areas) - Aufd1Ker - 02, 62 - (corresponding to Metro North Area) – Bobe1Car - 10, 19, 70 - (corresponding to Metro South Area) - Jarm1Sar For example, if the SP is 1981-124, the Activity owner is Sarah Jarman. | Sarah Jarman | Sarah Jarman | Sarah Jarman
ENM1030 Review & Respond to ENM by Regulated Materials | Mark Vogel | Mark Vogel | Mark Vogel | Mark Vogel | If SP number begins with the numbers below, the Activity owner is the person in CMMT indicated: - 02, 62, 13, 82 (corresponding to Metro North and East Areas) - Voge1Mar - 27, 10, 19, 70 (corresponding to Metro South and West Areas) - Klei1Jac | Mark Vogel | Mark Vogel | Mark Vogel
ENM1040 Review & Respond to ENM by DNR | District Environmental Coordinator | District Environmental Coordinator | District Environmental Coordinator | District Environmental Coordinator | Writer: Same Owner as ENM1000 Prepare & Distribute ENM | District Environmental Coordinator | District Environmental Coordinator | District Environmental Coordinator
ENM1050 Review & Respond to ENM by EMTU | Marilyn Jordahl-Larson | Marilyn Jordahl-Larson | Marilyn Jordahl-Larson | Marilyn Jordahl-Larson | Wask1Pet | Marilyn Jordahl-Larson | Marilyn Jordahl-Larson | Marilyn Jordahl-Larson
ENM1060 Review & Respond to ENM by T&ES | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott
ENM1070 Review & Respond to ENM by Vegetation | Tina Markeson | Tina Markeson | Tina Markeson | Tina Markeson | Tina Markeson | Tina Markeson | Tina Markeson | Tina Markeson
ENM1080 Review & Respond to ENM by Bike/Ped | Tim Mitchell | Tim Mitchell | Tim Mitchell | Tim Mitchell | Mitt1Gin | Tim Mitchell | Tim Mitchell | Tim Mitchell
ENM1100 Review & Respond to ENM by Aeronautics | PM | PM | PM | PM | Sore1deb | PM | PM | PM
ENM1110 Review & Respond to ENM by Rail Office | Paul Delarosa | Rick VanWagner | Rick VanWagner | Paul Delarosa | Jim Weatherhead | Dennis Williams | Dennis Williams | Dennis Williams
ENM1120 Review & Respond to ENM by Value Engineering | Minnie Milkert | Minnie Milkert | Minnie Milkert | Minnie Milkert | Minnie Milkert | Minnie Milkert | Minnie Milkert | Minnie Milkert
ENM1130 Review & Respond to ENM by COE | District Environmental Coordinator | District Environmental Coordinator | District Environmental Coordinator | District Environmental Coordinator | Metro does not send an ENM to COE See notebook topic | District Environmental Coordinator | District Environmental Coordinator | District Environmental Coordinator
ENM2000 ENM Review Complete | District Environmental Coordinator or PM | District Environmental Coordinator or PM | District Environmental Coordinator or PM | District Environmental Coordinator or PM | Metro does not need this activity see notebook topic | District Environmental Coordinator or PM | District Environmental Coordinator or PM | District Environmental Coordinator or PM
Environmental Assessment (EA)/Environmental Assessment Worksheet (EAW)
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental Assessment Unit | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan
EAW0900 Consultant Acquisition | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
EAW1000 Prepare EA/EAW Statement of Purpose & Need | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
EAW1010 Review EA/EAW Statement of Purpose & Need by OES & FHWA | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
EAW1020 Prepare EA/EAW Document | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
EAW1030 Review EA/EAW Document by OES | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
EAW1040 Revise EA/EAW Document Based Off Of OES Comments | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
EAW1050 Review EA/EAW Document by FHWA | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
EAW1060 Review EA/EAW 4(f) by DOI (Note: Only if there is a Full 4(f)) | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
EAW1070 Revise EA/EAW Document Based Off Of FHWA Comments | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
EAW1080 Obtain District, OES, FHWA Signatures for EA/EAW | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
EAW1090 Public Comment Period for EA/EAW | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
EAW1095 Revise EA/EAW Based Off Of Public Comments | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
EAW1100 Prepare Findings of Fact & Conclusions | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
EAW1110 Review Findings of Fact & Conclusions by OES | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
EAW1120 Revise Findings of Fact & Conclusions based off of OES Comments | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
EAW1130 Review Findings of Fact & Conclusions by FHWA | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
EAW1140 Review of Final 4(f) Legal Sufficiency (Note: Only if there is a Full 4(f)) | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
EAW1145 Revise Findings of Fact & Conclusions Based Off Of FHWA Comments | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
Environmental Assessment Worksheet (EAW) State
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental Assessment Unit | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan
SAW1000 Prepare EAW Statement of Purpose & Need | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
SAW1010 Review EAW Statement of Purpose & Need by OES | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
SAW1020 Prepare EAW Document | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
SAW1030 Review EAW Document by OES | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
SAW1040 Revise EAW Document Based Off Of OES Comments | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
SAW1050 Obtain, OES, Signatures for EAW & Publish Environmental Quality Board Monitor | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
SAW1060 Public Comment Period for EAW | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
SAW1070 Prepare Findings of Fact & Conclusions | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
SAW1080 Review Findings of Fact & Conclusions by OES | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
SAW1090 Revise Findings of Fact & Conclusions Based Off Of OES Comments | PM | PM | PM | PM | Dalt1Ric, Also change the MNDOT Functional Group code to District Project Management Unit | PM | PM | PM
Environmental Due Diligence 1
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental Investigations Unit (Jim DeLuca on Transit Focused Projects) | Carolyn Boben | Carolyn Boben | Carolyn Boben | Keri Aufdencamp | If SP number begins with the numbers below, the Activity owner is the person in CMMT indicated: - 27, 13, 82 (corresponding to Metro West and East Areas) - Aufd1Ker - 02, 62 - (corresponding to Metro North Area) – Bobe1Car - 10, 19, 70 - (corresponding to Metro South Area) - Jarm1Sar For example, if the SP is 1981-124, the Activity owner is Sarah Jarman. | Sarah Jarman | Sarah Jarman | Sarah Jarman
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Environmental Due Diligence 2
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental Investigations Unit (Jim DeLuca on Transit Focused Projects) | Carolyn Boben | Carolyn Boben | Carolyn Boben | Keri Aufdencamp | If SP number begins with the numbers below, the Activity owner is the person in CMMT indicated: - 27, 13, 82 (corresponding to Metro West and East Areas) - Aufd1Ker - 02, 62 - (corresponding to Metro North Area) – Bobe1Car - 10, 19, 70 - (corresponding to Metro South Area) - Jarm1Sar For example, if the SP is 1981-124, the Activity owner is Sarah Jarman. | Sarah Jarman | Sarah Jarman | Sarah Jarman
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Environmental Due Diligence 3
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental Investigations Unit (Jim DeLuca on Transit Focused Projects) | Carolyn Boben | Carolyn Boben | Carolyn Boben | Keri Aufdencamp | If SP number begins with the numbers below, the Activity owner is the person in CMMT indicated: - 27, 13, 82 (corresponding to Metro West and East Areas) - Aufd1Ker - 02, 62 - (corresponding to Metro North Area) – Bobe1Car - 10, 19, 70 - (corresponding to Metro South Area) - Jarm1Sar For example, if the SP is 1981-124, the Activity owner is Sarah Jarman. | Sarah Jarman | Sarah Jarman | Sarah Jarman
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Environmental Impact Statement (EIS)
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental Assessment Unit | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan | Debra Moynihan
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Environmental Site Assessment (Phase I & II) Acquisition
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental Investigations Unit (Jim DeLuca on Transit Focused Projects) | Carolyn Boben | Carolyn Boben | Carolyn Boben | Keri Aufdencamp | If SP number begins with the numbers below, the Activity owner is the person in CMMT indicated: - 27, 13, 82 (corresponding to Metro West and East Areas) - Aufd1Ker - 02, 62 - (corresponding to Metro North Area) – Bobe1Car - 10, 19, 70 - (corresponding to Metro South Area) - Jarm1Sar For example, if the SP is 1981-124, the Activity owner is Sarah Jarman. | Sarah Jarman | Sarah Jarman | Sarah Jarman
District Right of Way | [6 empty] | Tim Hoehn | Adam Ahrndt
Environmental Site Assessment (Phase I & II) Early Acquisition
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental Investigations Unit (Jim DeLuca on Transit Focused Projects) | Carolyn Boben | Carolyn Boben | Carolyn Boben | Keri Aufdencamp | If SP number begins with the numbers below, the Activity owner is the person in CMMT indicated: - 27, 13, 82 (corresponding to Metro West and East Areas) - Aufd1Ker - 02, 62 - (corresponding to Metro North Area) – Bobe1Car - 10, 19, 70 - (corresponding to Metro South Area) - Jarm1Sar For example, if the SP is 1981-124, the Activity owner is Sarah Jarman. | Sarah Jarman | Sarah Jarman | Sarah Jarman
District Right of Way | [6 empty] | Tim Hoehn | Adam Ahrndt
Environmental Site Assessment (Phase I & II) No Acquisition
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental Investigations Unit (Jim DeLuca on Transit Focused Projects) | Carolyn Boben | Carolyn Boben | Carolyn Boben | Keri Aufdencamp | If SP number begins with the numbers below, the Activity owner is the person in CMMT indicated: - 27, 13, 82 (corresponding to Metro West and East Areas) - Aufd1Ker - 02, 62 - (corresponding to Metro North Area) – Bobe1Car - 10, 19, 70 - (corresponding to Metro South Area) - Jarm1Sar For example, if the SP is 1981-124, the Activity owner is Sarah Jarman. | Sarah Jarman | Sarah Jarman | Sarah Jarman
Fee Acquisition
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
RTT0090 Consultant Acquisition for Title Opinion (District) | John Hinzmann | Denise Watkins | Brett Stark | Jermy Flatau | Debra Anderson | Mark T-I | TJ Thill | Adam Ahrndt
RTT1000 Prepare Title Map (District) | John Hinzmann | Denise Watkins | Brett Stark | Jermy Flatau | Debra Anderson | Mark T-I | Tim Hoehn | Adam Ahrndt
RTT1010 Confirm Title Opinions on Completion (District) | John Hinzmann | Denise Watkins | Brett Stark | Jermy Flatau | Debra Anderson | Mark T-I | Tim Hoehn | Adam Ahrndt
RTT1020 Determine Unrecorded Utilities Easement (District) | John Hinzmann | Denise Watkins | Brett Stark | Jermy Flatau | Debra Anderson | Keith Kallin | Tim Hoehn | Adam Ahrndt
RWP1000 Prepare Authorization & Work Map (District) | John Hinzmann | Denise Watkins | Brett Stark | Jermy Flatau | Debra Anderson | Mark T-I | TJ Thill | Adam Ahrndt
RWP1020 Prepare Plats/Certification of Location (District) | John Hinzmann | Dan Domeier | Kevin Metz | Tom Harper | Debra Anderson | Keith Kallin | TJ Thill | Adam Ahrndt
RWP1070 Write Plat Descriptions (District) | John Hinzmann | Dan Domeier | Kevin Metz | Tom Harper | Debra Anderson | Keith Kallin | TJ Thill | Adam Ahrndt
RWP1080 Prepare Right of Way Packages (District) | John Hinzmann | Denise Watkins | Brett Stark | Jermy Flatau | Debra Anderson | Mark T-I | Tim Hoehn | Adam Ahrndt
RVL1000 Procure Valuation Consultant [OLM] | Kirk Corson | Kirk Corson | Greg Thompson | Kirk Corson | Debra Anderson | Ron Lambert | Tim Hoehn | Ron Lambert
RVL1010 Complete Valuations/Minimum Comp [OLM] | Kirk Corson | Kirk Corson | Kirk Corson | Kirk Corson | Debra Anderson | Ron Lambert | Tim Hoehn | Ron Lambert
RVL1020 Review & Certify Valuations [OLM] | Kirk Corson | Kirk Corson | Kirk Corson | Kirk Corson | Debra Anderson | Ron Lambert | Ron Lambert | Ron Lambert
RPR1000 Receive and Distribute Right of Way Package [OLM] | Julie Groetsch | Julie Groetsch | Julie Groetsch | Julie Groetsch | Julie Groetsch | Julie Groetsch | Julie Groetsch | Julie Groetsch
RPR1020 Review and Approve Plat Descriptions [OLM] Platting Unit 5 | Dawna Butcher | Dawna Butcher | Dawna Butcher | Dawna Butcher | Dawna Butcher | Dawna Butcher | Dawna Butcher | Dawna Butcher
RPR1030 Write Narrative Description [OLM] Legal Desc & Comm. 20 | Dawna Butcher | Dawna Butcher | Dawna Butcher | Dawna Butcher | Dawna Butcher | Dawna Butcher | Dawna Butcher | Dawna Butcher
RPR1040 Review and Approve Plats [OLM] Platting Unit 20 | Elliott Ruhland | Elliott Ruhland | Elliott Ruhland | Elliott Ruhland | Elliott Ruhland | Elliott Ruhland | Elliott Ruhland | Elliott Ruhland
RPR1050 Perform Platting Monumentation [District] Surveys 5 | John Hinzmann | Dan Domeier | Kevin Metz | Tom Harper | Debra Anderson | Keith Kallin | Travis Shorter | Adam Ahrndt
RPR1060 File Plats [District] Surveys 2 | John Hinzmann | Dan Domeier | Kevin Metz | Tom Harper | Debra Anderson | Keith Kallin | TJ Thill | Adam Ahrndt
RPR1070 Prepare Attorney's Condition of Title [OLM] R.E. & Policy Dev. 5 | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema
RPR1080 Prepare Conveyance Documents [OLM] Legal Desc & Comm. 10 | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema
RPR1090 Prepare Commissioner's Orders [OLM] R.E. & Policy Dev. 5 | Paul Hendrickson | Paul Hendrickson | Paul Hendrickson | Paul Hendrickson | Paul Hendrickson | Paul Hendrickson | Paul Hendrickson | Paul Hendrickson
RPR1100 Encumber Funds [OLM] R.E. & Policy Dev..Purch 3 | Lanette Zaiger | Lanette Zaiger | Lanette Zaiger | Lanette Zaiger | Lanette Zaiger | Lanette Zaiger | Lanette Zaiger | Lanette Zaiger
RPR1110 Prepare Direct Purchase Package [OLM] | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber
RDP1000 Make Direct Purchase Offer & Negotiate [District] Right of Way 60 | John Hinzmann | Denise Watkins | Brett Stark | Jermy Flatau | Debra Anderson | Mark T-I | Tim Hoehn | Adam Ahrndt
RDP1010 30-Day Minimum Consideration Period [District] Right of Way 22 | John Hinzmann | Denise Watkins | Brett Stark | Jermy Flatau | Debra Anderson | Mark T-I | Tim Hoehn | Adam Ahrndt
RDP1030 Complete Purchase-Sign Document Files [District] Right of Way 10 | John Hinzmann | Denise Watkins | Brett Stark | Jermy Flatau | Debra Anderson | Mark T-I | Tim Hoehn | Adam Ahrndt
RDP1040 State Acceptance Date [OLM] R.E. & Policy Dev. Purch 0 | PM | PM | PM | PM | PM | PM | PM | PM
RDP1050 Prepare Closing Package [OLM] R.E. & Policy Dev. Purch 10 | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber
RDP1060 Make Direct Purchase Final Payment [OLM] | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber
RED1010 Start Condemnation/AG Obtains Hearing on Petition Date [OLM] | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema
RED1020 Send Notice of Hearing on Petition Date/Title & Possession [OLM] | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema | Connie Bultema
RED1210 Title & Possession [OLM] R.E. & Policy Dev. | PM | PM | PM | PM | PM | PM | PM | PM
Foundation Recommendations
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
FDR1010 Develop Geotechnical Investigation Plan | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person
FDR1020 Perform Geotechnical Investigation | Dean Brady | Dean Brady | Dean Brady | Dean Brady | Dean Brady | Dean Brady | Dean Brady | Dean Brady
FDR1030 Perform Geotechnical Lab Analysis & Logging | Radji Rassaki | Radji Rassaki | Radji Rassaki | Radji Rassaki | Radji Rassaki | Radji Rassaki | Radji Rassaki | Radji Rassaki
FDR1040 Prepare Geotechnical Recommendation/Report | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Geodetic Control Surveys
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Geodetic Unit | John Barke | John Barke | John Barke | John Barke | John Barke | John Barke | John Barke | John Barke
District Surveys | J. Hinzmann | D. Domeier | K. Metz | T.Harper | D. Torfin | K. Kallin | T. Shorter | A. Ahrndt
Historic Bridge Study
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
HBS1000 Collaboration Coordination | Level o f Effort | Level o f Effort | Level o f Effort | Level o f Effort | Level o f Effort | Level o f Effort | Level o f Effort | Level o f Effort
HBS1010 Received ENM | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari
HBS1020 Assemble/Review Data & Conduct Site Visit - By Engineering Consultant | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari
HBS1030 Assemble/Review Data & Conduct Site Visit - By Historic Consultant | Zsch1Kri | Zsch1Kri | Zsch1Kri | Zsch1Kri | Zsch1Kri | Zsch1Kri | Zsch1Kri | Zsch1Kri
HBS1040 Determine Capacity of Existing Bridge (Structural Analysis & Load Rating) - By Engineering Consultant | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari
HBS1050 Develop Evaluation Criteria & Rehab Alternatives - By Engineering Consultant | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari
HBS1060 Develop Evaluation Criteria & Rehab Alternatives - By Historic Consultant | Zsch1Kri | Zsch1Kri | Zsch1Kri | Zsch1Kri | Zsch1Kri | Zsch1Kri | Zsch1Kri | Zsch1Kri
HBS1070 Estimate Rehab Costs - By Engineering Consultant | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari
HBS1080 Write Draft Rehab Report - By Engineering Consultant | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari
HBS1090 Write Draft Rehab Report - By Historic Consultant | Zsch1Kri | Zsch1Kri | Zsch1Kri | Zsch1Kri | Zsch1Kri | Zsch1Kri | Zsch1Kri | Zsch1Kri
HBS1100 Review Rehab Study Report by MnDOT | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari
HBS1110 Review Rehab Study Report by FHWA | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari
HBS1120 Finalize Rehab Study Report - By Engineering Consultant | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari
HBS1130 Prepare Final Rehab Study Report - By Engineering Consultant | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari
HBS1130 Prepare Final Rehab Study Report - By Engineering Consultant | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari
HBS1130 Prepare Final Rehab Study Report - By Engineering Consultant | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari | Ehrl1Ari
Hydraulics Design
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Hydraulics/WRE | Dave Mohar | John Wingard | Bob Nibbe |  | Use this Link | Kris Langlie | Chuck Slama | Nathan A. Pederson
Hydraulics/WRE Plans
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Hydraulics/WRE | Dave Mohar | John Wingard | Bob Nibbe |  | Beth Neuendorf | Kris Langlie | Chuck Slama | Nathan A. Pederson
Intersection Control Evaluation
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Traffic | Jim Miles | Bill Pirkl | Tom Dumont |  | Lars Impola | Adam Wellner | Scott Thomas | Ryan Barney
Interstate Access Request
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Traffic |  | N/A | PM |  | Lars Impola | Adam Wellner | PM | Ryan Barney
Lighting Agreement
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Lighting Plan
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Lighting | James Miles | William Pirkl | Robin Delage | Les Bjerkvedt | Michael Gerbensky | Adam Wellner | Scott Thompson | Ryan Barney
Material Design Recommendations (MDR)
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
MDR1000 Conduct Roadway Borings/Field Work |  | Kristi Olson | Darren Nelson |  | Tim Clyne | Chris Dullian | Caleb Fenske | Lowell Flaten
MDR1010 Prepare Pavement Alternatives/PDM/LCCA |  | Kristi Olson | Darren Nelson |  | Tim Clyne | Chris Dullian | Kyle Vogt | Lowell Flaten
MDR1030 Review of LCCA by Maplewood/Industry |  |  |  |  | Tim Clyne | Chris Dullian | MDR Manager | Lowell Flaten
MDR1050 Prepare Pavement Recommendation |  | Kristi Olson | Darren Nelson |  | Tim Clyne | Chris Dullian | MDR Manager | Lowell Flaten
MDR1060 Prepare MDR |  | Kristi Olson | Darren Nelson |  | Tim Clyne | Chris Dullian | MDR Manager | Lowell Flaten
Municipal Consent
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Municipal Consent (Appeal Process)
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Mussel Survey
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental Assessment Unit | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott
New Bridge
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
STR1000 Receive Scoping Estimate Request (Form A) | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward
STR1010 Identify Structures & Determine Bridge Work Type | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
STR1020 Conduct Site Visit | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
STR1030 Conduct Hydraulics Scoping | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
STR1040 Prepare Program/Scoping Estimate (Form B) | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward
STR1050 Evaluate Feasible Alternatives, Identify Preferred Alternative & Propose Structure Type | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
STR1060 Review Project Information/Stakeholder Discussion | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
STR1080 Receive Structure Concurrence from District & Hydraulics | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
BHL1000 Receive Bridge Survey Data | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1010 Research & Field Review | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1020 Hydraulic Modeling | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1030 Risk Assessment | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1040 Write Hydraulic Letter | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1050 Review & Finalize Hydraulic Letter | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1060 Deck Drain Study | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
BHL1070 Scour Confirmation Letter | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall | Petra DeWall
PBP1000 Receive Survey Files | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt
PBP1010 Receive Roadway Design Files | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt
PBP1020 Finalize Aesthetic Recommendation | Melissa Schultz | Melissa Schultz | Melissa Schultz | Melissa Schultz | Melissa Schultz | Melissa Schultz | Melissa Schultz | Melissa Schultz
PBP1030 Draft Preliminary Plan | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1040 Receive & Plot Borings | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1050 Check Preliminary Plan | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1060 Distribute Plan, Borings, Foundation Report to Regional Const. Engineer | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt
PBP1070 Prepare Bridge Foundation Recommendation | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
PBP1080 Finalize Preliminary Plans with Foundation Recommendations | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1090 Receive Bridge Foundation Recommendation | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1100 Obtain State Bridge Engineer's Signature - Preliminary | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather | Dan Prather
PBP1110 Distribute Signed Preliminary Bridge Plan | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt | Larry Aamodt
PBP1120 Preliminary Estimate & District Letter | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward
PBP1130 FHWA Approval (if necessary) | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward
BFR1010 Receive Substructures Locations for Geotechnical Investigation | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person
BFR1020 Develop Geotechnical Investigation Plan | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person
BFR1030 Perform Geotechnical Investigation | Dean Brady | Dean Brady | Dean Brady | Dean Brady | Dean Brady | Dean Brady | Dean Brady | Dean Brady
BFR1040 Perform Geotechnical Lab Analysis | Rassaki Radji | Rassaki Radji | Rassaki Radji | Rassaki Radji | Rassaki Radji | Rassaki Radji | Rassaki Radji | Rassaki Radji
BFR1050 Prepare Geotechnical Recommendation/Report | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person | Gary Person
FBP1000 Receive Signed Preliminary Bridge Plan | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1005 General Coordination | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FBP1031 Prepare 30% Final Bridge Plans | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1061 Prepare 60% Final Bridge Plans | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1091Prepare 95% Final Bridge Plans | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1100 Bridge Specs | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1110 Bridge Plan Review by Construction & Estimating | Ed Lutgen | Ed Lutgen | Ed Lutgen | Ed Lutgen | Paul Pilarski | Dustin Thomas | Dustin Thomas | Dustin Thomas
FBP1120 Obtain State Bridge Engineer's Signature - Final | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date. | Assign to Arielle Ehrlich and she will reassign the activity at a later date.
FBP1130 Final Estimate | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward | Jeff Southward
Milestones (Design)
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Milestones (Scoping)
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Noise Analysis
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental modeling & Testing Unit | Marilyn Jordahl-Larson | Marilyn Jordahl-Larson | Marilyn Jordahl-Larson | Marilyn Jordahl-Larson | Peter Wasko | Marilyn Jordahl-Larson | Marilyn Jordahl-Larson | Marilyn Jordahl-Larson
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
NPDES Stormwater Permit
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Hydraulics/WRE |  |  |  |  | Use this Link |  | Chuck Slama | Nathan Pederson
Overhead Sign Structure
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Signing | James Miles | William Pirkl | Tom Dumont | Les Bjerkvedt | Josephine Tayse | Adam Wellner | Scott Thompson | Ryan Barney
District Design | District Designer | District Designer | District Designer | District Designer | District Designer | District Designer | District Designer | District Designer
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Pavement Marking Plan
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
TPM1000/District Traffic | James Miles | Bill Pirkl | Tom Dumont |  | Tiffany Dagon |  | PM | Ryan Barney
Photogrammetric Basemap
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Photogrammetric Unit | Peter Jenkins | Peter Jenkins | Peter Jenkins | Peter Jenkins | Peter Jenkins | Peter Jenkins | Peter Jenkins | Peter Jenkins
Prequalification (Tech Proposal)
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Design Services Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Engineering Cost Data & Estimating Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Letting Coordination Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Special Provisions Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Utility Agreements/Permits | Mollie Zauner | Ed Barrett | Sam Muench | Sam Muench | Mollie Zauner | Sam Muench | Mollie Zauner | Ed Barrett
Direct Purchase & Relocation Assistance Unit | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan
Process A
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Design Services Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Engineering Cost Data & Estimating Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Letting Coordination Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Utility Agreements/Permits | Mollie Zauner | Ed Barrett | Sam Muench | Sam Muench | Mollie Zauner | Sam Muench | Mollie Zauner | Ed Barrett
Special Provisions Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Direct Purchase & Relocation Assistance Unit | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan
Process B
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Design Services Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Engineering Cost Data & Estimating Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Letting Coordination Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Utility Agreements/Permits | Mollie Zauner | Ed Barrett | Sam Muench | Sam Muench | Mollie Zauner | Sam Muench | Mollie Zauner | Ed Barrett
Special Provisions Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Direct Purchase & Relocation Assistance Unit | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan
Process B Complex
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Design Services Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Engineering Cost Data & Estimating Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Letting Coordination Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Utility Agreements/Permits | Mollie Zauner | Ed Barrett | Sam Muench | Sam Muench | Mollie Zauner | Sam Muench | Mollie Zauner | Ed Barrett
Special Provisions Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Direct Purchase & Relocation Assistance Unit | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan
Process B PODI
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Design Services Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Engineering Cost Data & Estimating Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Letting Coordination Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Special Provisions Unit | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau | Merc1Pau
Utility Agreements/Permits | Mollie Zauner | Ed Barrett | Sam Muench | Sam Muench | Mollie Zauner | Sam Muench | Mollie Zauner | Ed Barrett
Direct Purchase & Relocation Assistance Unit | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan | Laig1Lan
Project Control Surveys
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Surveys | John Hinzman | Dan Domeier | Kevin Metz | Tom Harper | As Assigned by district | Keith Kallin | TJ Thill | Adam Arhndt
Project Turn In
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Design |  |  | Bob Nibbe |  | Rodney Koehn |  | Plans Manager | Nathan A. Pederson
Railroad Bridge Agreement
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Freight and Commercial Vehicle Operations | Paul Delarosa | Rick VanWagner | Rick VanWagner | Paul Delarosa | Jim Weatherhead | Dennis Williams | Dennis Williams | Dennis Williams
Railroad Flagging Agreement
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Freight and Commercial Vehicle Operations | Paul Delarosa | Rick VanWagner | Rick VanWagner | Paul Delarosa | Jim Weatherhead | Dennis Williams | Dennis Williams | Dennis Williams
Railroad Track Relocation Agreement
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Freight and Commercial Vehicle Operations | Paul Delarosa | Rick VanWagner | Rick VanWagner | Paul Delarosa | Jim Weatherhead | Dennis Williams | Dennis Williams | Dennis Williams
Regulated Materials-Building
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Regulated Materials | Mark Vogel | Mark Vogel | Mark Vogel | Mark Vogel | Mark Vogel(N,E)/Jackie Klein(S/W) | Jackie Klein | Jackie Klein | Jackie Klein
Regulated Materials-Bridge
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Regulated Materials | Mark Vogel | Mark Vogel | Mark Vogel | Mark Vogel | Mark Vogel(N,E)/Jackie Klein(S/W) | Jackie Klein | Jackie Klein | Jackie Klein
Regulatory File Review
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental Investigations Unit (Jim DeLuca on Transit Focused Projects) | Carolyn Boben | Carolyn Boben | Carolyn Boben | Keri Aufdencamp | If SP number begins with the numbers below, the Activity owner is the person in CMMT indicated: - 27, 13, 82 (corresponding to Metro West and East Areas) - Aufd1Ker - 02, 62 - (corresponding to Metro North Area) – Bobe1Car - 10, 19, 70 - (corresponding to Metro South Area) - Jarm1Sar For example, if the SP is 1981-124, the Activity owner is Sarah Jarman. | Sarah Jarman | Sarah Jarman | Sarah Jarman
Relocation
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
RRL1000 Advisory Services up to Title & Possession | John Hinzmann | Denise Watkins | Brett Stark | Brian Bausman | Debra Anderson | Mark T-I | TJ Thill | Ahrn1Ada
RRL1010 Detailed Relocation Study | John Hinzmann | Denise Watkins | Brett Stark | Brian Bausman | Debra Anderson | Mark T-I | TJ Thill | Ahrn1Ada
RRL1020 Replacement Housing Study | John Hinzmann | Denise Watkins | Brett Stark | Brian Bausman | Debra Anderson | Mark T-I | TJ Thill | Ahrn1Ada
RRL1030 Prepare & Issue Eligibility Notices | John Hinzmann | Denise Watkins | Brett Stark | Brian Bausman | Debra Anderson | Mark T-I | TJ Thill | Ahrn1Ada
RRL1040 Issue Vacate Notice and 90/120 Day Vacate Notice | John Hinzmann | Denise Watkins | Brett Stark | Brian Bausman | Debra Anderson | Mark T-I | TJ Thill | Ahrn1Ada
Response Action Plans
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental Investigations Unit (Jim DeLuca on Transit Focused Projects) | Carolyn Boben | Carolyn Boben | Carolyn Boben | Keri Aufdencamp | If SP number begins with the numbers below, the Activity owner is the person in CMMT indicated: - 27, 13, 82 (corresponding to Metro West and East Areas) - Aufd1Ker - 02, 62 - (corresponding to Metro North Area) – Bobe1Car - 10, 19, 70 - (corresponding to Metro South Area) - Jarm1Sar For example, if the SP is 1981-124, the Activity owner is Sarah Jarman. | Sarah Jarman | Sarah Jarman | Sarah Jarman
Road Plans
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Design |  |  | Bob Nibbe |  | Design Engineer | PM | Plans Manager | Nathan A. Pederson
RW Construction Limits
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Design |  |  | Bob Nibbe |  | Design Engineer | PM | Plans Manager | Nathan A. Pederson
Section 4(f) Coordination
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Section 6(f) Coordination
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Section 7 Determination [Threatened & Endangered Species] - No Effect
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental Assessment Unit | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott
Section 7 Determination [Threatened & Endangered Species] - May Affect
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental Assessment Unit | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott
Section 7 Determination [Threatened & Endangered Species] - Formal Consultation
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental Assessment Unit | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott | Jason Alcott
Section 9 (Coast Guard) Permit
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Preliminary Bridge | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan | Prat1Dan
Right of Way | District RW | District RW | District RW | District RW | District RW | District RW | District RW | District RW
Signal Agreement
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Signal Plan
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Traffic Management | N/A | N/A | N/A | N/A | Geoffrey Prelgo | N/A | N/A | N/A
District Signals | James Miles | William Pirkl | Robin Delage | Les Bjerkvedt | Michael Gerbensky | Adam Wellner | Tod Becker | Ryan Barney
District Signing | James Miles | William Pirkl | Tom Dumont | Les Bjerkvedt | Josephine Tayse | Adam Wellner | Ken Wenkel | Ryan Barney
Signing Plan
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Signing | James Miles | William Pirkl | Tom Dumont | Les Bjerkvedt | Josephine Tayse | Adam Wellner | Ken Wenkel | Ryan Barney
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Special Provisions
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Project Management | PM | 2A: Todd Vonasek 2B: Shawn Groven | Bob Nibbe |  | PM | PM | PM | PM
Staff Approved Layout
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
LAY1040 Prepare Preliminary Geometric Layout & Profile |  | Jeremy Hadrava | PM |  | PM | PM | Plans Manger | Nathan A. Pederson
LAY1050 Prepare Final Geometric Layout & Profile | PM | Jeremy Hadrava | PM |  | PM | PM | PM | PM
LAY1060 GDSU Review of Geometric Layout | Darwin Yasis | Darwin Yasis | Darwin Yasis | Darwin Yasis | Darwin Yasis | Darwin Yasis | Darwin Yasis | Darwin Yasis
LAY1070 Revise, Sign, & Distribute Geometric Layout | PM | Jeremy Hadrava | PM |  | PM | PM | Plans Manger | Nathan A. Pederson
Stormwater Treatment Design
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Hydraulics/WRE | Dave Mohar | John Wingard | Bob Nibbe |  | Use this Link | Kris Langlie | Chuck Slama | Nathan A. Pederson
Subsurface Engineering
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Utilities | PM | PM | PM | PM | PM | PM | PM | PM
Temporary Right to Construct
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
RDP1020 State Acceptance Date [OLM] | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber
RDP1030 Prepare Closing Package [OLM] | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber
RDP1040 Make Direct Purchase Final Payment [OLM] | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber | Tom Weber
RDP1000 Make Direct Purchase Offer & Negotiate [District] | Don Goedken | Don Goedken | Don Goedken | Don Goedken | Don Goedken | Don Goedken | Don Goedken | Don Goedken
RDP1010 Complete Purchase-Sign Document Files [District] | Don Goedken | Don Goedken | Don Goedken | Don Goedken | Don Goedken | Don Goedken | Don Goedken | Don Goedken
RPR1010 Commissioner's Orders [OLM] | Paul Hendrickson | Paul Hendrickson | Paul Hendrickson | Paul Hendrickson | Paul Hendrickson | Paul Hendrickson | Paul Hendrickson | Paul Hendrickson
RPR1030 Encumber Funds [OLM] | Lanette Zaiger | Lanette Zaiger | Lanette Zaiger | Lanette Zaiger | Lanette Zaiger | Lanette Zaiger | Lanette Zaiger | Lanette Zaiger
RVL1000 Procure Valuation Consultant (District) | Roberta Dwyer | Kirk Corson | Greg Thompson | Kirk Corson | Debra Anderson | Ron Lambert | Tim Hoehn | Ron Lambert
RVL1010 Complete Valuations (District) | Kirk Corson | Kirk Corson | Kirk Corson | Kirk Corson | Debra Anderson | Ron Lambert | Tim Hoehn | Ron Lambert
RVL1020 Review & Certify Valuations (District) | Kirk Corson | Kirk Corson | Kirk Corson | Kirk Corson | Debra Anderson | Ron Lambert | Ron Lambert | Ron Lambert
RPR1050 Direct Purchase Documents [District] | Don Goedken | Don Goedken | Don Goedken | Don Goedken | Don Goedken | Don Goedken | Don Goedken | Don Goedken
RTT1000 Consultant Acquisition for Title Opinion (District) | John Hinzmann | Denise Watkins | Brett Stark | Brian Bausman | Debra Anderson | Mark T-I | TJ Thill | Ahrn1Ada
RTT1010 Prepare Title Map (District) | John Hinzmann | Denise Watkins | Brett Stark | Brian Bausman | Debra Anderson | Jordan Kurth | PM | Ahrn1Ada
RTT1020 Confirm Title Opinions on Completion (District) | John Hinzmann | Denise Watkins | Brett Stark | Brian Bausman | Debra Anderson | Mark T-I | TJ Thill | Ahrn1Ada
RWP1000 Prepare Authorization Map (District) | John Hinzmann | Denise Watkins | Brett Stark | Jermy Flatau | Debra Anderson | Mark T-I | Tim Hoehn | Ahrn1Ada
RWP1050 Parcel Sketches (District) | John Hinzmann | Dan Domeier | Kevin Metz | Tom Harper | Debra Anderson | Keith Kallin | TJ Thill | Adam Aarndt
RWP1060 Field Titles (District) | John Hinzmann | Denise Watkins | Brett Stark | Brian Bausman | Debra Anderson | Mark T-I | TJ Thill | Ahrn1Ada
Time and Traffic
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Construction |  | 2A: Todd Vonasek 2B: Shawn Groven | Bob Nibbe |  | Resident Engineer | PM | Resident Engineer | Ryan J. Barney
TMS Plan
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Traffic Management |  | Bill Pirkl | Bob Nibbe |  | Geoff Prelgo | Adam Wellner | Scott Thomas | Ryan J. Barney
Traffic Counts
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Traffic Control/ Detour/ Staging Plan
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Traffic Control | Jim Miles | Bill Pirkl | Tom Dumont | Les Bjerketvedt | Tiffany Dagon | Adam Wellner | Brad Bruegger | Ryan Barney
Traffic Forecasts
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
TRF 1000 Prepare Traffic Forecasts and ESALs |  | Kristi Olson | Darren Nelson |  | Jim Henricksen | Tracy Schnell | PM | Ryan J. Barney
Transportation Management Plan (TMP)
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Project Management | PM | PM | Tom Dumont |  | PM | PM | PM | PM
Utility Agreement
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Utility Agreements/Permits | Mollie Zauner | Ed Barrett | Sam Muench | Sam Muench | Mollie Zauner | Sam Muench | Mollie Zauner | Ed Barrett
Utility Coordination
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
UTI1060 Prepare & Approve Utility Permit by CO Utilities Unit | Ann Driver | Ann Driver | Ann Driver | Ann Driver | Ann Driver | Ann Driver | Ann Driver | Ann Driver
UTI1070 Prepare & Send Utility Notice & Orders | Mollie Zauner | Ed Barrett | Sam Muench | Sam Muench | Mollie Zauner | Sam Muench | Mollie Zauner | Ed Barrett
District Utilities | PM | PM | PM | PM | Dale Nikkola | PM | PM | PM
Value Engineering
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Project Management | PM | PM | PM | PM | PM | PM | PM | PM
Value Engineering Unit | Minnie Milkert | Minnie Milkert | Minnie Milkert | Minnie Milkert | Minnie Milkert | Minnie Milkert | Minnie Milkert | Minnie Milkert
Vegetation Review
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Roadside Vegetation Unit | Tina Markeson | Tina Markeson | Tina Markeson | Tina Markeson | Tina Markeson | Tina Markeson | Tina Markeson | Tina Markeson
Visual Impact Assessment
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Environmental Planning & Design Unit | David Larson | David Larson | David Larson | David Larson | David Larson | David Larson | David Larson | David Larson
Visual Quality Management Plan
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Envt Planning & Design Unit | David Larson | David Larson | David Larson | David Larson | David Larson | David Larson | David Larson | David Larson
Watershed District Permit
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Hydraulics/WRE |  |  |  |  | Use this Link |  | Chuck Slama | Nathan Pederson
Wetland Delineation
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
Districts.Environmental | Michele Micke | Staci Cann | John Mackner | Paul Munsterteiger | This work package is not to be used on Metro projects | Nathan Gregor | Shanna Kent | Susann Karnowski
Wetland Delineation (Metro)
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Hydraulics/WRE | This work package is not to be used on outstate projects | This work package is not to be used on outstate projects | This work package is not to be used on outstate projects | This work package is not to be used on outstate projects | Katherine Heinz | This work package is not to be used on outstate projects | This work package is not to be used on outstate projects | This work package is not to be used on outstate projects
WTL2030 | This work package is not to be used on outstate projects | This work package is not to be used on outstate projects | This work package is not to be used on outstate projects | This work package is not to be used on outstate projects | Design Engineer | This work package is not to be used on outstate projects | This work package is not to be used on outstate projects | This work package is not to be used on outstate projects
District Project Management | This work package is not to be used on outstate projects | This work package is not to be used on outstate projects | This work package is not to be used on outstate projects | This work package is not to be used on outstate projects | PM | This work package is not to be used on outstate projects | This work package is not to be used on outstate projects | This work package is not to be used on outstate projects
Wetland/WCA & Aquatic Resources (404/401/Section 10)
Owner
Activity ID/ Functional Group | D1 | D2 | D3 | D4 | DM | D6 | D7 | D8
District Hydraulics/WRE |  |  |  |  | Use this Link |  | Chuck Slama | Nathan Pederson
Environmental Assessment Unit | Sarma Straumanis | Sarma Straumanis | Sarma Straumanis | Sarma Straumanis | Sarma Straumanis | Sarma Straumanis | Sarma Straumanis | Sarma Straumanis

## Milestones (Scoping) (hidden)
WBS | Project Name | Project ID | Threshold Criteria | Deliverable | Organization | Functional Group

## Scoping (hidden)
WBS | WBS Name | Work Package ID | Threshold Criteria | Deliverable | Organization | Functional Group
WBS_S.2.1 | Scoping Document
WBS_S.2.2 | Project Baseline

## Milestones (Design) (hidden)
WBS | Project Name | Project ID | Threshold Criteria | Deliverable | Organization | Functional Group

## Templates
Template Name | Template ID (click for Gantt chart) | Threshold Criteria
Scoping Template | TEMPSCOP | Used for scheduling the scoping process for all projects.
Project Template | TEMPMODA | Used for all design projects, unless directed to use one of the other templates.
Minor Project Template | TEMPMINA | Used as a standalone project template for lighting, signal, and signing projects.
Landscaping Plan | TEMPLAND | Used as a standalone project template for preparing and submitting a landscaping plan set for landscaping recently constructed roadway projects. A scoping template is also required for these projects.
Cable Median Barrier Plan | TEMPCMBP | Used as a standalone project template for Cable Median Barrier Construction Projects with no other roadway improvements. A scoping template is also required for these projects.
Maintenance Plan | TEMPMAIN | Used as a standalone project template for Maintenance Construction Projects with no other roadway improvements. A scoping activity is required for these projects.
CMGC Template | TEMPCMGC | Used for all CMGC design projects.
Signing Standalone Template | TEMPMINA-SG | Used for projects when you are putting up new signs or replacing existing signs. A scoping template is also required for these projects.
Signal Standalone Template | TEMPMINA-SL | Used for projects replacing or installing new signals. A scoping template is also required for these projects.
Lighting Standalone Template | TEMPMINA-LG | Used for projects replacing or installing new lighting. A scoping template is also required for these projects.

## Project Management (hidden)
WBS | WBS Name | Work Package ID | Threshold Criteria | Deliverable | Organization | Functional Group
WBS_D.2.1 | Ongoing Project Management | TMPL 1220

## Environmental
WBS | WBS Name (click for Gantt chart) The purpose of the Gantt chart pdfs is to show activity durations and logic. The Gantt charts do not necessarily reflect how the work package will look once it is placed in a schedule. | Work Package ID | Threshold Criteria | Deliverable | Organization | Functional Group | Notes
WBS_D.3.1 | Early Notification Memo | TMPL3006 | To be used on all projects | Early Notification Memo and responses from CRU, CMMT, Regulated Materials, DNR, EMTU, T&ES, Vegetation, Bike/Ped, Aeronautics, Rail Office, Value Engineering, COE | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES)
WBS_D.3.2 | Environmental Studies
WBS_D.3.2.1 | Cultural Resources - Work Package 1 Full Section 106 Review- All Federal Agencies | TMPL1302 | Project is receiving Federal Funds, Permits, or License. This is used with all Federal Agencies. If any of the following are required: · Tribal investigations · Architectural history investigations · Historical archeology investigations · Geomorphology investigation · Historical properties Please Note the durations are Highly Variable | Written SHPO Concurrence (and Memorandum of Agreement, if applicable) is obtained; and if applicable, when Tribal concerns have been addressed | Office of Environmental Stewardship (OES) | CRU Supervisor
WBS_D.3.2.2 | Cultural Resources - Work Package 2 FHWA Funds | TMPL1304 | Project is Receiving ONLY FHWA Funds and is a Minor/Moderate Project. | Written SHPO Concurrence (and Memorandum of Agreement, if applicable) is obtained; and if applicable, when Tribal concerns have been addressed | Office of Environmental Stewardship (OES) | CRU Supervisor
WBS_D.3.2.3 | Cultural Resources - Work Package 3 State Level Review (State Funds Only) | TMPL1302C | Project is receiving State Funds Only. | Written SHPO Concurrence (and Memorandum of Agreement, if applicable) is obtained; and if applicable, when Tribal concerns have been addressed | Office of Environmental Stewardship (OES) | CRU Supervisor
WBS_D.3.2.4 | Regulatory File Review | TMPL1305 | Required on all projects. | A summary of the findings of the file review and excerpts from the file reviews. The CMMT may use the regulatory file review to update the ENM response. Additional deliverables resulting from the file review include project Special Provisions | Office of Environmental Stewardship (OES) |  | For additional guidance use this hyperlink
WBS_D.3.2.5 | Environmental Due Diligence 1 | TMPL1306 | EDD-1 is needed for all MnDOT and cooperative projects that include MnDOT property transaction(s). Examples include: acquisitions, conveyances, turnbacks, leases/permits, transfers of custodial control, state aid actions, shared facilities, excess acquisition, commissioners orders and railbank | EDD-1 form | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES) | For additional guidance use this hyperlink
WBS_D.3.2.6 | Environmental Due Diligence 2 | TMPL1308 | EDD-2 is needed as determined through the EDD-1 review. The CMMT makes the determination if EDD-2 is needed. | EDD-2 form | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES) | For additional guidance use this hyperlink
WBS_D.3.2.7 | Environmental Due Diligence 3 | TMPL1310 | EDD-3 is needed when the EDD-1 and/or EDD-2 indicate that the EDD-3 is needed. The CMMT determines if EDD-3 is needed. The form should be initiated approximately 24 months before the project let date or parcel acquisition (whichever happens first). Sites that require the EDD-3 meet at least of the following criteria; cleanup costs would exceed $500,000 or 10% of total capital project costs, on-going cleanup is required or there are other regulatory obligations, land uses are high risk (e.g., uncontrolled dumps, Federal Superfund Sites, large-scale manufacturing, etc.). | EDD-3 form | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES) | For additional guidance use this hyperlink
WBS_D.3.2.8 | Environmental Site Assessment (Phase I & II) No Acquisition | TMPL1314 | The work package is needed if the ENM Response or EDD forms indicate that a Phase I ESA is needed and no property acquisition is required for the project. The CMMT determines when the work package is needed. | Report summarizing an environmental review completed to determine recognized environmental conditions (RECs) for the project. | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES) | For additional guidance use this hyperlink
WBS_D.3.2.8.1 | Consultant Acquisitions | [5 empty] | For additional guidance use this hyperlink
WBS_D.3.2.8.2 | Phase I | [5 empty] | For additional guidance use this hyperlink
WBS_D.3.2.8.3 | Phase II | [5 empty] | For additional guidance use this hyperlink
WBS_D.3.2.9 | Environmental Site Assessment (Phase I & II) Early Acquisition | TMPL1313 | The work package is needed if the ENM Response or EDD forms indicate that a Phase I ESA is needed and early property acquisition is required for the project. The CMMT determines when the work package is needed. | Report summarizing an environmental review completed to determine recognized environmental conditions (RECs) for the project. | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES) | For additional guidance use this hyperlink
WBS_D.3.2.9.1 | Consultant Acquisitions | [5 empty] | For additional guidance use this hyperlink
WBS_D.3.2.9.2 | Phase I |  | A Phase I Environmental Site Assessment (ESA) is an environmental review completed to determine recognized environmental conditions (RECs) for the project. A Phase I ESA consists of the following general tasks; a records review of state and federal registered hazardous waste storage/generator and release sites, a review of historical documents, a site reconnaissance, and interviews. All identified RECs within 500 feet of the construction limits are ranked as "high," "medium," or "low" potential for contamination. The Phase I ESA also includes a summary of known releases and previous investigations documented at the Minnesota Pollution Control Agency (MPCA), Minnesota Department of Agriculture (MDA), and United States Environmental Protection Agency (EPA). |  |  |  | For additional guidance use this hyperlink
WBS_D.3.2.9.3 | Phase II |  | The Phase II ESA consists of collection of soil, water, soil vapor, sediment, and/or waste samples and laboratory analysis of these samples in order to determine whether or not contamination is present. Commonly the Phase II investigation includes advancing soil borings or test pits to collect soil and groundwater samples. Potential areas of concern for contamination are determined through a Phase I ESA or similar environmental review. The Contaminated Materials Management Team (CMMT) in conjunction with an environmental consultant reviews the findings of the Phase I ESA, the construction plans, and parcel acquisitions to determine sampling locations, depths, and chemical parameters for the Phase II investigation. |  |  |  | For additional guidance use this hyperlink
WBS_D.3.2.10 | Environmental Site Assessment (Phase I & II) Acquisition | TMPL1312 | The work package is needed if the ENM Response or EDD forms indicate that a Phase I ESA is needed and property acquisition is required for the project. The CMMT determines when the work package is needed. | Report summarizing an environmental review completed to determine recognized environmental conditions (RECs) for the project. | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES) | For additional guidance use this hyperlink
WBS_D.3.2.11 | Consultant Acquisitions | [5 empty] | For additional guidance use this hyperlink
WBS_D.3.2.12 | Phase I |  | A Phase I Environmental Site Assessment (ESA) is an environmental review completed to determine recognized environmental conditions (RECs) for the project. A Phase I ESA consists of the following general tasks; a records review of state and federal registered hazardous waste storage/generator and release sites, a review of historical documents, a site reconnaissance, and interviews. All identified RECs within 500 feet of the construction limits are ranked as "high," "medium," or "low" potential for contamination. The Phase I ESA also includes a summary of known releases and previous investigations documented at the Minnesota Pollution Control Agency (MPCA), Minnesota Department of Agriculture (MDA), and United States Environmental Protection Agency (EPA). |  |  |  | For additional guidance use this hyperlink
WBS_D.3.2.13 | Phase II |  | The Phase II ESA consists of collection of soil, water, soil vapor, sediment, and/or waste samples and laboratory analysis of these samples in order to determine whether or not contamination is present. Commonly the Phase II investigation includes advancing soil borings or test pits to collect soil and groundwater samples. Potential areas of concern for contamination are determined through a Phase I ESA or similar environmental review. The Contaminated Materials Management Team (CMMT) in conjunction with an environmental consultant reviews the findings of the Phase I ESA, the construction plans, and parcel acquisitions to determine sampling locations, depths, and chemical parameters for the Phase II investigation. |  |  |  | For additional guidance use this hyperlink
WBS_D.3.2.11 | Phase I Update | TMPL1315 | A ESA Phase I Update is needed if a Phase I ESA was previously completed and an update is necessary for potential regulatory involvement. | Updated report summarizing an environmental review completed to determine recognized environmental conditions (RECs) for the project. | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES) | For additional guidance use this hyperlink
WBS_D.3.2.12 | Phase II Update | TMPL1316 | A ESA Phase II Update is needed to satisfy changing project needs (e.g. a new parcel will be acquired or construction plans change) or to obtain data for liability assurances. | Updated report prepared by a consultant, submitted to the CMMTUpdate Report summarizing an environmental review completed to determine recognized environmental conditions (RECs) for the project. | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES) | For additional guidance use this hyperlink
WBS_D.3.2.13 | No Association Determined | TMPL1317 | When liability protection is required for acquisition of a site contaminated with a hazardous substance, pollutant or contaminant. | Letter of determination from the Minnesota Pollution Control Agency (MPCA) or Minnesota Department of Agriculture (MDA) that the specific actions proposed by MnDOT (or LGA) will not associate MnDOT with the identified contamination. | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES) | For additional guidance use this hyperlink
WBS_D.3.2.14 | Response Action Plans | TMPL1318 | A Response Action Plan (RAP) is required if contamination exists and MnDOT seeks liability protection or seeks approval for reuse of soil that does not qualify as unregulated fill. | CMMT submits a RAP report to the MPCA/MDA and receives an approval letter from the MPCA/MDA for the RAP | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES) | For additional guidance use this hyperlink
WBS_D.3.2.15 | Contaminated Materials Management Special Provisions | TMPL1319 | Use when special provisions are required to address contaminated materials during construction. | Contaminated materials management special provisions | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES) | For additional guidance use this hyperlink
WBS_D.3.2.16 | Regulated Materials-Building | TMPL1326 | Used when there is a reason to assess the presence of asbestos and other regulated materials that are within a building. | Certified as clean for demolition
WBS_D.3.2.17 | Regulated Materials-Bridge | TMPL1327 | Used when there is a reason to assess the presence of asbestos and other regulated materials that are within a bridge. | Certified as clean for demolition
WBS_D.3.2.18 | Noise Analysis | TMPL1328 | Level of analysis is dependent upon the project funding type, and if the project meets the definition of a Type I project for noise analysis as per 43 CFR 772.5, (also defined in MnDOT’s Noise Policy located on the OES website.) http://www.dot.state.mn.us/environment/noise/index.html | Noise Report and Results of Noise Solicitation | Office of Environmental Stewardship (OES) | Outstate: Environmental Modeling & Testing Unit Metro: Staff in the Office of Project Documentation
WBS_D.3.2.19 | Air Quality Analysis | TMPL1330 | Air Quality Analysis is dependent upon project geographic, location and level of required environmental documentation. (See HPDP) | Air Quality Report | Office of Environmental Stewardship (OES) | Outstate: Environmental Modeling & Testing Unit Metro: Staff in the Office of Project Documentation
WBS_D.3.2.20.1 | Mussel Survey | TMPL1349 | This work package should be incorporated into the project schedule only upon the request of the OES Ecologist or the as the result of comments received from the MNDNR after the review of the ENM has been completed. | Mussel Survey Report | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES)
| Section 7 Determination [Threatened & Endangered Species] - No Effect | TMPL 1370 | This work package should be incorporated into the project schedule if the following criteria apply: 1) The project will be constructed using FHWA funding or if FHWA approval or oversight is required. 2) The project activities will be contained within the shoulder P.I.’s. | Determination of Effect Letter | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES)
| Section 7 Determination [Threatened & Endangered Species] - May Affect | TMPL 1701 | This work package should be incorporated into the project schedule if the following criteria apply: 1) The project will be constructed using FHWA funding or if FHWA approval or oversight is required. 2) The project activities will extend beyond the shoulder P.I.’s. | Determination of Effect Letter | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES)
| Section 7 Determination [Threatened & Endangered Species] - Formal Consultation | TMPL 1702 | This work package should be incorporated into the project schedule if the following criteria apply: 1) The project will be constructed using FHWA funding or if FHWA approval or oversight is required. 2) This work package should be incorporated into the project schedule only upon the request of the OES Ecologist after the review of the ENM has been completed, until that time or unless instructed otherwise, please follow the criteria for TES 1000 or TES 2000/2010/2020. | Determination of Effect Letter | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES)
WBS_D.3.2.21 | Vegetation Review | TMPL1368 | Used when the project includes clearing and grubbing, soil disturbance beyond the in slope, disruption of soil under any tree canopy, or when known specimen tree are included in or near the project area. | Special Provisions Document, Plan Review and/or Vegetation Memo | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES)
WBS_D.3.2.22 | Wetland Delineations | TMPL1348 Or TEMP3008 | To be used on all schedules | Wetland delineation line work Wetland Delineation Report | Office of Environmental Stewardship (OES) | Hydraulics/WRE | There are two work packages for Wetland Declinations. One for metro and one for outstate
WBS_D.3.2.23 | Floodplain Assessment
WBS_D.3.2.24 | Wild & Scenic River Coordination
WBS_D.3.2.25 | Groundwater Impact Study
WBS_D.3.2.26 | Section 6(f) Coordination | TMPL1420 | If project impacts outdoor recreation lands where Land and Water Conservation (LAWCON) funds were used for the planning, acquisition, or development of the property. | Approval letter from DNR and National Perk Service | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES)
WBS_D.3.2.27 | Environmental Justice Analysis |  | See HPDP
WBS_D.3.2.28 | Visual Impact Assessment | TMPL1409 | Used when there may be Visual Quality/Aesthetic impacts. | Visual impact section of the environmental document. | Office of Environmental Stewardship (OES) | EPDU Supervisor
WBS_D.3.2.29 | Earthborn Vibrations Study
WBS_D.3.2.30 | Geotechnical Study
WBS_D.3.2.31 | Farmland Conversion Impact Rating (Form AD 1006)
WBS_D.3.2.32 | Energy Analysis
WBS_D.3.2.33 | Other Environmental Study
WBS_D.3.2.34 | Section 4(f) Coordination | TMPL1419 | Use if the project impacts publicly owned parks, recreation areas, wildlife and/or waterfowl refuges, or any publicly or privately owned historic sites listed or eligible for listing on the National Register of Historic Places from conversion to a transportation use. This is only required if funding, permits or approval is need by FHWA. | 4(f) Evaluation Report and FHWA Approval Letter | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES)
WBS_D.3.2.37 | LOMAR/CLOMAR | TEMLCM
WBS_D.3.3 | Environmental Documents
WBS_D.3.3.1 | Environmental Document Exemption |  |  |  | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES)
WBS_D.3.3.2 | Categorical Exclusion - Non Programmatic | TMPL1334 | • For federally funded actions that do not individually or cumulatively have a significant effect on the environment. • Project-type listed in 23 CFR 771.177(c) or (d) and exceeds a threshold in Attachment B of the Programmatic Agreement between MnDOT and FHWA. See the HPDP for Class II Actions. • Document requires review and signature by OES and FHWA. | signed CATEX Document | Office of Environmental Stewardship (OES) | ENVT Assessment Unit
WBS_D.3.3.3 | Categorical Exclusion - Programmatic | TMPL1336 | • For federally funded actions that do not individually or cumulatively have a significant effect on the environment. • Project-type listed in 23 CFR 771.177(c) or (d) and does not exceed any threshold in Attachment B of the Programmatic Agreement between MnDOT and FHWA. See the HPDP for Class II Actions. • Document signed by the Project Manager (PM) and the District Engineer (DE). | signed CATEX Document | Office of Environmental Stewardship (OES) | ENVT Assessment Unit
WBS_D.3.3.4 | Environmental Assessment/Environmental Assessment Worksheet | TMPL1338 | • A federally funded project that has the potential to significantly affect the environment, or it is unclear if environmental impacts are significant. See the HPDP for Class III Actions. • The project action exceeds thresholds in Attachment B of the Programmatic Agreement between MnDOT and FHWA. • The project exceeds a mandatory threshold under Minn. Rules 4410.4300. • Document requires review and signature by OES and FHWA. | Environmental Assessment (EA), Environmental Assessment Worksheet Document (EAW), FONSI and Negative Declaration | Office of Environmental Stewardship (OES) | ENVT Assessment Unit
WBS_D.3.3.5 | Environmental Assessment Worksheet (EAW) State | TMPL1332 | • A state funded project that has the potential to significantly affect the environment, or it is unclear if environmental impacts are significant. • The project exceeds a mandatory threshold under Minn. Rules 4410.4300. • Document requires review and signature by OES. | Environmental Assessment Worksheet (EAW) and Negative Declaration | Office of Environmental Stewardship (OES) | ENVT Assessment Unit
WBS_D.3.3.6 | Environmental Impact Statement (EIS) | TMPL1340 | • A federally funded project that will significantly affect the environment and is similar to examples of actions listed in 23 CFR 771.115. See the HPDP for Class I Actions. • A state funded project that exceeds a mandatory threshold under Minn. Rules 4410.4400. • Document requires review and signature by OES and FHWA. | SDD, Draft EIS, Final EIS, ROD, Adequacy Determination, and Legal Sufficiency | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES)
WBS_D.3.3.7 | EIS Re-evaluation |  |  |  | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES)
WBS_D.3.3.8 | Supplemental EIS |  |  |  | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES)
WBS_D.3.4 | Permits
WBS_D.3.4.1 | NPDES Stormwater Discharge Permit | TMPL1346 | On all projects that have 1 or more acres of land disturbance. NPDES Permit is required on all Design Build projects. | NPDES Prepared Application | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES)
WBS_D.3.4.2 | Wetland/WCA & Aquatic Resources (404/401/Section 10) | TMPL1355 | On all projects. | Letter for Section 10, 404 Permit, 401 certification and WCA notification. | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES) | The COE has stated that it is taking longer for permit application reviews. The timeframes are based on permit type and amount of wetland impact and are as follows: GP (wetland impact < 0.5 acre) 85 days LOP (wetland impact > 0.5 acre but < 5 acres) 4 – 8 months (we are going with average of 180 days, 6 months, due to new COE/MnDOT Liaison) SIP (wetland impacts > 5 acres) 360 days, may be able to lessen this based on project type
WBS_D.3.4.3 | DNR Public Waters Permit | TMPL1350 | On all projects. | DNR Public Waters Permit | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES)
WBS_D.3.4.4 | Watershed District Permit | TMPL1352 | On all projects. | Watershed Permit | Office of Environmental Stewardship (OES) | Office of Environmental Stewardship (OES)
WBS_D.3.4.5 | Section 9 (Coast Guard) Permit | TMPL1354 | The work associated with this work package is for the coordination, development, and receipt of the permit from the United States Coast Guard (USCG) for major bridges over water (e.g.: TH 63 over Mississippi River in Red Wing). Use this work package when a bridge over water is required to obtain a permit from the USCG. Any bridges required to obtain a USCG permit that are not major bridges should discuss the project with the Bridge Office when developing a project schedule. | Signed Coast Guard Permit | Bridge Office | Bridge Office

## Road Design
WBS | WBS Name (click for Gantt chart) The purpose of the Gantt chart pdfs is to show activity durations and logic. The Gantt charts do not necessarily reflect how the work package will look once it is placed in a schedule. | Work Package ID | Threshold Criteria | Deliverable | Organization | Functional Group | Notes
WBS_D.4.1 | Surveys | TMPL3010 | To be used on all projects | Survey Request | District Project Management | District Project Management | This work package only exists in the Project Template. Owners are give in the Activity Owners tab.
WBS_D.4.1.1 | Control Surveys
WBS_D.4.1.1.1 | Geodetic Control Surveys | TMPL1400 | When there needs to be field observations for precise surveying and mapping. This will also provide support for Geographic Information Systems and Land Information System. | Documentation in a survey report and control list is delivered to the Project Manager (District Land Surveyor in Metro). | Office of Land management (OLM) | Geodetic Unit
WBS_D.4.1.1.2 | Project Control Surveys | TMPL1401 | When a project survey needs to be flown (Photogrammetric Surveys) or when control points are deemed necessary by a District Land Surveyor. | A file for surveys on which to base district land surveys and design surveys | District Surveys | District Surveys
WBS_D.4.1.2 | District Land Surveys | TMPL1403 | To be add to all projects. Can be removed with the approval of District Land Survey. | Existing Right of Way survey, AS-Built Alignment survey and Existing Properties survey. | District
WBS_D.4.1.3 | Design Surveys | TMPL3014 | To be used on all projects | Existing alignments, right-of-way, topography, bridge geometrics, utility and drainage information in the Survey Base Mapping and DTM files | District Surveys | District Surveys
WBS_D.4.1.4 | Photogrammetric Basemap | TMPL1402 | Used to generate base map for the creation of: ROW base map, survey base map, roadway base map. | Photogrammetric Base Map file and Orthomosaic Map. | Office of Land management (OLM) | OLM
WBS_D.4.2 | Traffic Studies
WBS_D.4.2.1 | Traffic Counts | TMPL1375 | Use when field traffic counts are required. | Intersection or roadway traffic count volumes. | District Traffic | District Traffic
WBS_D.4.2.2 | Traffic Forecasts | TMPL3016 | To be used on all projects | Traffic forecasts and ESALs | District Traffic | District Traffic
WBS_D.4.2.3 | Traffic Modeling |  | To be used on all projects |  | District Traffic | District Traffic | This work package only exists in the Project Template. Owners are give in the Activity Owners tab.
WBS_D.4.2.4 | Crash Analysis |  | To be used on all projects |  | District Traffic | District Traffic | This work package only exists in the Project Template. Owners are give in the Activity Owners tab.
WBS_D.4.2.5 | Intersection Control Evaluation | TMPL3018 | When considering a signal, flashing beacon, roundabout for installation or modification. When additional traffic control is desired at a specific location(s) due to a planning study, a safety concern or improvement project on other documented studies. | Intersection Control Evaluation Report | District Traffic | District Traffic
WBS_D.4.2.6 | Transportation Management Plan | TMPL3020 | To be used on all projects | Transportation Management Plan | Office of Environmental Stewardship (OES) | OES
WBS_D.4.2.7 | Interstate Access Request | TMPL3022 | When considering adding, removing or modifying an interstate access | Interstate Access Report and Federal Access Approval Letter | District Traffic | District Traffic
WBS_D.4.3 | Preliminary Design
WBS_D.4.3.1 | Staff Approved Layout | TMPL3024 | Projects meeting Level 1 or 2 layout process criteria -or- Level 3 criteria ( require Municipal Consent, or need a layout for project development, or need a layout for the public involvement process | Signed Geometric Layout | District Project Management | District Project Management
WBS_D.4.3.2 | Design Memo/Design Exception | TMPL3026 | To be used on all projects | Documentation of design standards and approval of design exceptions by State Design Engineer. | Geometric Design Support | Geometric Design Support | This work package only exists in the Project Template. Owners are give in the Activity Owners tab.
WBS_D.4.3.3 | RW Construction Limit | TMPL3028 | To be used on all projects | Construction Limits used for determining right-of-way | District Design | District Design
WBS_D.4.3.4 | Value Engineering | TMPL1407 | Required on all projects with a Total Project Cost Estimate (TPCE) of $20 million or more, regardless of funding source or the roadway status on the NHS. See TM 11-07-TS-01 for more details | VE Report | Office of Project Management & Technical Support | Design support
WBS_D.4.3.5 | Municipal Consent | TMPL3030 | Projects requiring Municipal approval of final geometric layout | Council/Board resolution approving Final Geometric Layout | District Project Management | District Project Management
WBS_D.4.3.6 | Municipal Consent (Appeal Process) | TMPL3032 | Projects that require municipal consent but did not receive municipal approval | Appeal Board recommendation | District Project Management | District Project Management
WBS_D.4.4 | Recommendations
WBS_D.4.4.1 | Foundation Recommendations | TMPL1414 | Included in schedules for projects that include any or all of the following structures: -Retaining Walls -Noise Walls -Cable Median Guardrail -High Mast Light Towers -New Overhead Sign Structures -Embankments on Poor Soils | Geotechnical Recommendation Report | Office of Materials & Road Research | Office of Materials & Road Research
WBS_D.4.4.2 | Material Design Recommendations (MDR) | TMPL3034 | To be used on all projects | Borings, Material Design Recommendations Report | Material Engineering Services | Material Engineering Services
WBS_D.4.4.3 | Traffic Recommendations
WBS_D.4.4.3.1 | Detour
WBS_D.4.4.3.2 | Traffic Control
WBS_D.4.4.3.3 | Staging
WBS_D.4.4.4 | Hydraulics Design Recommendations
WBS_D.4.4.4.1 | Stormwater Treatment Design | TMPL3036 | To be used on all projects | Preliminary storm water treatment design recommendation and soil boring/piezometer request | District Hydraulics/WRE | District Hydraulics/WRE
WBS_D.4.4.4.2 | Hydraulics Design | TMPL3038 | To be used on all projects | Preliminary and Final Hydraulic design recommendation, staged construction hydraulic design, SWPPP and Erosion Control Plans, special provisions and estimate | District Hydraulics/WRE | District Hydraulics/WRE
WBS_D.4.4.4.3 | Drain Tile Design
WBS_D.4.4.5 | ADA Recommendations | TMPL1416 | ADA should be included on all projects that involve construction with pavement resurfacing, pavement rehabilitation, signals, trails, sidewalks, rest areas, intersection modifications (roundabouts, turn lanes, reduced conflict intersections, curbed channelization, etc.), bridges with walks, and/or all urban bridges. | Draft and Final ADA Recommendations Letter, ADA comments on 30% and 60% Plans | ADA | ADA
WBS_D.4.4.6 | Bike/Pedestrian Recommendations
WBS_D.4.4.7 | Visual Quality Management Plan | TMPL1408 | Used when Visual Quality Manual is required for a project or corridor. | Visual Quality Manual | Office of Environmental Stewardship (OES) | EPDU Supervisor
WBS_D.4.5 | Final Design
WBS_D.4.5.1 | Plan Set
WBS_D.4.5.1.1 | Road Plans | TMPL3040 | To be used on all projects | 30% Plans, 60% Plans and 90% Plans, and Construction Cost Estimates | District Design | District Design
WBS_D.4.5.1.2 | Hydraulics/WRE Plans | TMPL3042 | To be used on all projects requiring culvert or storm sewer plans | Culvert and Storm Sewer Plans, Specifications and estimate | District Hydraulics/WRE | District Hydraulics/WRE
WBS_D.4.5.1.3 | Traffic Plans
WBS_D.4.5.1.3.1 | Traffic Control/Staging Plan | TMPL3044 | To be used on all projects | Traffic control, detour and staging plans, special provisions and estimate | District Traffic Control | District Traffic Control
WBS_D.4.5.1.3.2 | Pavement Marking Plan | TMPL3046 | To be used on all projects | Pavement marking plans, special provisions, and estimate | District Traffic Control | District Traffic Control
WBS_D.4.5.1.3.3 | Signing Plan | TMPL1339 | Used when putting up new signs or replacing existing signs. | Signing plans, special provisions and estimate | District Signing | District Signing | Can be used with either the Project Template or the Minor Template
WBS_D.4.5.1.3.4 | Signal Plan | TMPL1341 | Used when replacing or installing new signals. | Signal plans, special provisions and estimate | District Signal | District Signal | Can be used with either the Project Template or the Minor Template
WBS_D.4.5.1.3.5 | Lighting Plan | TMPL1335 | Used when replacing or installing new lighting. | Lighting plans, special provisions and estimate | District Lighting | District Lighting | Can be used with either the Project Template or the Minor Template
WBS_D.4.5.1.3.6 | TMS Plan | TMPL3048 | Projects that require Traffic Management System Plans | TMS Plans, Special Provisions and construction cost estimates | District Traffic Management | District Traffic Management | This work package only exists in the Project Template. Owners are give in the Activity Owners tab.
WBS_D.4.5.1.3.7 | Time and Traffic | TMPL3050 | To be used on all projects | Contract Time and Traffic Provisions, both of which are include in the Special Provisions | District Construction | District Construction
WBS_D.4.5.2 | Project Turn In | TMPL3054 | To be used on all projects | Submittal memo and construction plans, special provisions and estimate | District Project Management | District Project Management
WBS_D.4.5.3 | Special Provisions | TMPL3052 | To be used on all projects | Special Provisions Document | District Project Management | District Project Management
WBS_D.4.5.4 | Blowing and Drifting Snow Control | TMPL1417 | Required for the following projects types or if the project has an unsheltered fetch distance greater than 1,000 feet. New Highway Interchange Construction New Roundabout Construction projects Grading projects within an inventoried snow trap problem area. Grade Separation projects. New Highway Alignments adjacent to lakes. Highway expansion from 2 to 4 lanes. | Under Blowing Snow Trap Analysis- • Estimated snow transport report from University of Minnesota and State Climatology website. • Benefit Cost Report on the Return on Investment for Implementing a Blowing Snow Control Practice. • In some cases, a GEOPAK snow drift prediction report. Under Foundations- • Soils report to determine structural snow fence footings. Under PIF-will only be used for Structural Snow Fencing until multiple vendors become available • PIF Letter of Support to allow a sole source manufacturer Under Record Blowing and Drifting Snow Correction Results • Update Snow Trap Inventory with action taken or not taken to correct the problem. | District Project Management | District Project Management | The following link is to the Blowing and Drifting Snow Trap inventory. To open this link you must have access to MnDOTs public files and have Google Earth on your computer. \\Ad\co\Public\Environmental\SnowControl\SnowTrapInventory\SnowTrapsAug2014.kmz
WBS_D.4.6 | Utilities |  |  |  | District Traffic |  | This work package only exists in the Project Template. Owners are give in the Activity Owners tab.
WBS_D.4.6.1 | Subsurface Utility Engineering | TMPL1379 | Use on all Design-Build Projects. | Subsurface Utility Exploration (SUE) files containing utility locate information (often dgn). May also include the preparation of Utility Identification Sheets (UIS). | District Surveys | District Surveys
WBS_D.4.6.2 | Utility Coordination | TMPL1425 | Required when a utility meeting is conducted and utility relocation plans will be generated by the utilities. | Utility Relocation Plans from utility owners | Office of Land management (OLM) | OLM
|  | TEMP3012 | To be used on all projects

## Agreements
WBS | WBS Name (click for Gantt chart) The purpose of the Gantt chart pdfs is to show activity durations and logic. The Gantt charts do not necessarily reflect how the work package will look once it is placed in a schedule. | Work Package ID | Threshold Criteria | Deliverable | Organization | Functional Group | Notes
WBS_D.7.1 | Informal Agreement
WBS_D.7.2 | Lighting Agreement | TMPL1376 | Used to supplement the Road Project Template. This is not required if the PM and district want to track this under Cooperative Construction Agreement activities. | Lighting Agreement between MnDOT and another jurisdiction | District Traffic | District Traffic
WBS_D.7.3 | Signal Agreement | TMPL1377 | Used to supplement the Road Project Template. This is not required if the PM and district want to track this under Cooperative Construction Agreement activities. | Lighting Agreement between MnDOT and another jurisdiction | District Traffic | District Traffic
WBS_D.7.4 | Utility Agreement | TMPL1424 | Required to generate or modify utility agreements for utilities within MnDOT ROW. | Agreement with utilities within MnDOT ROW | Office of Land management (OLM) | OLM
WBS_D.7.5 | Cooperative Construction Agreement | TMPL3056 | Projects that include construction agreements with a city, county, township or other governmental agency. | Executed Agreement | Co-op Agreements | Co-op Agreements
WBS_D.7.6 | Railroad Agreement
WBS_D.7.6.1 | Railroad Flagging Agreement | TMPL1422 | When construction activities impact railroad right-of-way or when it is possible for construction equipment to fall across railroad tracks. Before adding this work package contact the office of Freight & Commercial Vehicle operations. | Agreement with the railroad company for flagging | Office of Freight and Commercial Vehicle Operations | Rail Administration Section
WBS_D.7.6.2 | Railroad Bridge Agreement | TMPL1421 | When project impacts a railroad bridge or a non-railroad roadway bridge that intersect with railroad track or right-of-way. Note that Rehab project will likely only need the Railroad Flagging Agreement Template, there for on rehab projects start with the Railroad Flagging Agreement Template.Before adding this work package contact the office of Freight & Commercial Vehicle operations. | Agreement with the railroad company for work involving a bridge | Office of Freight and Commercial Vehicle Operations | Rail Administration Section
WBS_D.7.6.3 | Railroad Track Relocation Agreement | TMPL1423 | When commercial freight railroad track needs to be relocated.Before adding this work package contact the office of Freight & Commercial Vehicle operations. | Agreement with the railroad company for work involving track relocation. | Office of Freight and Commercial Vehicle Operations | Rail Administration Section
WBS_D.7.7 | Detour Agreement | TMPL3058 | Projects that use other agency routes for the project detour | Executed Detour Agreement | District Traffic | District Traffic
WBS_D.7.8 | Turnback Agreement
WBS_D.7.9 | Joint Powers Agreement

## Letting
WBS | WBS Name (click for Gantt chart) The purpose of the Gantt chart pdfs is to show activity durations and logic. The Gantt charts do not necessarily reflect how the work package will look once it is placed in a schedule. | Work Package ID | Threshold Criteria | Deliverable | Organization | Functional Group | Notes
WBS_D.8.1 | Process A | TMPL2000 | Small projects, which are minor in scope. These projects contain no more than 50 plan sheets and comprise less than 20 pay items. | Proposal Package | Office of Project Management & Technical Support (OPMTS) | Pre- Letting Unit
WBS_D.8.1.2 | Administration
WBS_D.8.1.3 | Civil Rights
WBS_D.8.1.4 | Estimating
WBS_D.8.1.5 | Special Provisions
WBS_D.8.1.6 | Plan Review
WBS_D.8.2 | Process B | TMPL2001 | Plans and Special Provisions that need Central Office approval. | Proposal Package | Office of Project Management & Technical Support (OPMTS) | Pre- Letting Unit
WBS_D.8.2.1 | Administration |  |  |  |  | Pre- Letting Unit
WBS_D.8.2.2 | Civil Rights |  |  |  |  | Pre- Letting Unit
WBS_D.8.2.3 | Land Management / Utilities |  |  |  |  | Pre- Letting Unit
WBS_D.8.2.4 | Land Management / RW |  |  |  |  | Pre- Letting Unit
WBS_D.8.2.5 | Estimating |  |  |  |  | Pre- Letting Unit
WBS_D.8.2.6 | Special Provisions |  |  |  |  | Pre- Letting Unit
WBS_D.8.2.7 | Plan Review / Signatures |  |  |  |  | Pre- Letting Unit
WBS_D.8.3 | Process B Complex | TMPL2002 | Plans and Special Provisions that need Central Office approval and require more Central Office coordination, federal review, district involvement, and agreements. The complex process B projects may in some cases require special letting dates to accommodate their complexity. | Proposal Package | Office of Project Management & Technical Support (OPMTS) | Pre- Letting Unit
WBS_D.8.3.1 | Administration |  |  |  |  | Pre- Letting Unit
WBS_D.8.3.2 | Civil Rights |  |  |  |  | Pre- Letting Unit
WBS_D.8.3.3 | Land Management / Utilities |  |  |  |  | Pre- Letting Unit
WBS_D.8.3.4 | Land Management / RW |  |  |  |  | Pre- Letting Unit
WBS_D.8.3.5 | Estimating |  |  |  |  | Pre- Letting Unit
WBS_D.8.3.6 | Special Provisions |  |  |  |  | Pre- Letting Unit
WBS_D.8.3.7 | Plan Review / Signatures |  |  |  |  | Pre- Letting Unit
WBS_D.8.4 | Process B PODI | TMPL2004 | Plans and Special Provisions that need Central Office approval and require more Central Office coordination, full federal review, district involvement, and agreements. | Proposal Package | Office of Project Management & Technical Support (OPMTS) | Pre- Letting Unit
WBS_D.8.5.1 | Administration |  |  |  |  | Pre- Letting Unit
WBS_D.8.5.2 | Civil Rights |  |  |  |  | Pre- Letting Unit
WBS_D.8.5.3 | Land Management / Utilities |  |  |  |  | Pre- Letting Unit
WBS_D.8.5.4 | Land Management / RW |  |  |  |  | Pre- Letting Unit
WBS_D.8.5.6 | Estimating |  |  |  |  | Pre- Letting Unit
WBS_D.8.5.7 | Special Provisions |  |  |  |  | Pre- Letting Unit
WBS_D.8.5.8 | Plan Review / Signatures |  |  |  |  | Pre- Letting Unit
WBS_D.8.5 | Prequalification (Tech Proposal) | TMPL 2003 | The typical Prequal project consists of plans that follow the standard Typical Process B format, but have additional time allotted for a 2-step advertisement period to determine which Contractors are eligible to bid on the price proposal and the evaluation of the price proposals to determine the Apparent Low Bidder. | Proposal Package | Office of Project Management & Technical Support (OPMTS) | Pre- Letting Unit
WBS_D.8.4.1 | Administration |  |  |  | Office of Project Management & Technical Support (OPMTS)
WBS_D.8.4.2 | Civil Rights |  |  |  | Office of Project Management & Technical Support (OPMTS)
WBS_D.8.4.3 | Land Management / Utilities |  |  |  | Office of Project Management & Technical Support (OPMTS)
WBS_D.8.4.4 | Land Management / RW |  |  |  | Office of Project Management & Technical Support (OPMTS)
WBS_D.8.4.5 | Estimating |  |  |  | Office of Project Management & Technical Support (OPMTS)
WBS_D.8.4.6 | Special Provisions |  |  |  | Office of Project Management & Technical Support (OPMTS)
WBS_D.8.4.7 | Plan Review / Signatures |  |  |  | Office of Project Management & Technical Support (OPMTS)
WBS_D.8.6 | Negotiated Contracts |  |  |  | Office of Project Management & Technical Support (OPMTS)
WBS_D.8.7 | Design Build | TEMP2005 | When the Project is designated as Design Build | Proposal Package | Office of Project Management & Technical Support (OPMTS) | Design Build | Input from the Design Build Project Manager is needed to create a design build schedule. After adding the work package contact the Design Build Project Managers for their input.
WBS_D.8.8 | CMGC | TMPL2010
WBS_D.8.9 | Letting by Others

## Bridge Design
WBS | WBS Name (click for Gantt chart) The purpose of the Gantt chart pdfs is to show activity durations and logic. The Gantt charts do not necessarily reflect how the work package will look once it is placed in a schedule. | Work Package ID | Threshold Criteria | Deliverable | Organization | Functional Group | Notes
WBS_B.5.1 | New Bridge | TMPL1500 | When the design will be done by the Bridge Office for new/replacement bridges. | Bridge Plan Set, Construction Cost Estimate and Bridge Specifications | Bridge Office | Bridge Office
WBS_B.5.1.1 | Bridge Scoping & Structure Determination |  |  |  |  | Bridge Office
WBS_B.5.1.2 | Bridge Hydraulics Letter |  |  |  |  | Bridge Office
WBS_B.5.1.3 | Bridge Foundations Recommendations |  |  |  |  | Bridge Office
WBS_B.5.1.4 | Preliminary Bridge Design |  |  |  |  | Bridge Office
WBS_B.5.1.5 | Final Bridge Design |  |  |  |  | Bridge Office
WBS_B.5.2 | Culvert | TMPL1520 | When a bridge culvert construction plan is needed on a project. | Culvert Plan Set, Construction Cost Estimate and Bridge Specifications | Bridge Office | Bridge Office
WBS_B.5.2.1 | Culvert Scoping & Structure Determination |  |  |  |  | Bridge Office
WBS_B.5.2.2 | Hydraulics Letter |  |  |  |  | Bridge Office
WBS_B.5.2.3 | Final Culvert Design |  |  |  |  | Bridge Office
WBS_B.5.3 | Bridge Preservation | TMPL1503 | When simple bridge preservation construction plans are needed for a project. | Bridge Preservation Recommendations & Bridge Preservation Plan Set, Construction Cost Estimate and Bridge Specifications | Bridge Office | Bridge Office
WBS_B.5.3.1 | Rehab Recommendations |  |  |  |  | Bridge Office
WBS_B.5.3.2 | Final Bridge Repair Plans |  |  |  |  | Bridge Office
WBS_B.5.4 | Bridge Redeck | TMPL1504 | The work associated with this work package is for the scoping, design, and drafting of bridge redeck projects for typical 2-span highway structures. Use whenever bridge redeck construction plans are needed. Also use when there is a risk of bridge preservation projects changing scope to redeck projects. Use also when minor deck widening is included in the scope. Any bridge redeck projects on any other type of bridge should talk with the Bridge Office when developing a project schedule. . | Bridge Redeck Recommendations & Bridge Redeck Plan Set, Construction Cost Estimate and Bridge Specifications | Bridge Office | Bridge Office
WBS_B.5.4.1 | Rehab Recommendations |  |  |  |  | Bridge Office
WBS_B.5.4.2 | Final Bridge Repair Plans |  |  |  |  | Bridge Office
WBS_B.5.5 | Consultant Bridge Design (Prelim & Final Consultant) | TMPL1501 | When a consultant will be hired for the preliminary and final bridge design | Consultant Preliminary & Final Bridge Plan Sets, Construction Cost Estimate and Bridge Specifications | Bridge Office | Bridge Office
WBS_B.5.5.1 | Bridge Scoping & Structure Determination |  |  |  | Bridge Office | Bridge Office
WBS_B.5.5.2 | Hydraulics Letter |  |  |  | Bridge Office | Bridge Office
WBS_B.5.5.3 | Foundations Recommendations-Bridge |  |  |  | Bridge Office | Bridge Office
WBS_B.5.5.4 | Preliminary Bridge Design |  |  |  | Bridge Office | Bridge Office
WBS_B.5.5.5 | Final Bridge Design |  |  |  | Bridge Office | Bridge Office
WBS_B.5.6 | Consultant Bridge Design (Final Only Consultant) | TMPL1502 | When a consultant will be hired only for the final bridge design. | MnDOT Delivered Preliminary Plan Set &Consultant Delivered Final Bridge Plan Set, Construction Cost Estimate and Bridge Specifications | Bridge Office | Bridge Office
WBS_B.5.6.1 | Bridge Scoping & Structure Determination |  |  |  | Bridge Office | Bridge Office
WBS_B.5.6.2 | Hydraulics Letter |  |  |  | Bridge Office | Bridge Office
WBS_B.5.6.3 | Foundations Recommendations-Bridge |  |  |  | Bridge Office | Bridge Office
WBS_B.5.6.4 | Preliminary Bridge Design |  |  |  | Bridge Office | Bridge Office
WBS_B.5.6.5 | Final Bridge Design |  |  |  | Bridge Office | Bridge Office
WBS_B.5.8 | Bridge Substructure Widening | TMPL1508 | The work associated with this work package is for the scoping, design, and drafting of a bridge substructure widening project for typical 2-span highway structures. Use this work package when the bridge deck and substructures need to be widened. A preliminary bridge plan is included in this work package as they are typically required for these types of widenings. Any substructure and deck widenings on any other type of bridge should talk with the Bridge Office when developing a project schedule. | Bridge Substructure Widening Plan Set, Construction Cost Estimate and Bridge Specifications | Bridge Office | Bridge Office
WBS_B.5.9 | Historic Bridge Study | TMPL1509 | The work associated with this work package is for the coordination, analysis, and development of a historic bridge rehab study for bridges that are eligible for or on the National Register of Historic Places. Use this work package for any historic bridges to determine if rehabilitation is a viable option. Coordination with the Bridge Office and CRU is highly recommended for these types of bridge projects when developing a project schedule. | Historic bridge rehab study | Bridge Office | Bridge Office

## Milestones (Right of Way) (hidden)
WBS | WBS Name | Work Package ID | Threshold Criteria | Deliverable | Organization | Functional Group

## Right of Way
WBS | WBS Name (click for Gantt chart) The purpose of the Gantt chart pdfs is to show activity durations and logic. The Gantt charts do not necessarily reflect how the work package will look once it is placed in a schedule. | Work Package ID | Threshold Criteria | Deliverable | Organization | Functional Group | Notes
WBS_R.6.1 | Fee Acquisition | TMPL1600 | Used when MnDOT is acquiring parcels for construction. | Parcel ownership documents | Office of Land Management (OLM) | OLM
WBS_R.6.1.1 | Title Opinion
WBS_R.6.1.2 | Right of Way Package
WBS_R.6.1.3 | Valuations
WBS_R.6.1.4 | Right of Way Pre-acquisition
WBS_R.6.1.5 | Direct Purchase
WBS_R.6.1.6 | Condemnation
WBS_R.6.1.7/ WBS_R.6.2.7/ WBS_R.6.3.7 | Relocation | TMPL 1650 | Used when MnDOT needs to relocate a property owner/occupant for construction. | Relocation of Property Owner/Occupant | Office of Land Management (OLM) | OLM
WBS_R.6.2 | Temporary Right to Construct | TMPL1630 | Used when the property owner is willing to negotiate temporary land access for construction. A shorter version of the ROW Template. Generally used on pedestrian ramp and culvert projects. | Signed Temporary Right to Construct Document | Office of Land Management (OLM) | OLM
WBS_R.6.2.1 | Title Opinion
WBS_R.6.2.2 | Right of Way Package
WBS_R.6.2.3 | Valuations
WBS_R.6.2.4 | Right of Way Pre-acquisition
WBS_R.6.2.5 | Direct Purchase
WBS_R.6.2.6 | Condemnation
WBS_R.6.2.7 | Relocation | TMPL 1650
WBS_R.6.3 | Commissioner's Orders | TMPL1640 | Acquire property for highway purposes from a local government unit. | Certified copies of Commissioner’s Orders as required for condemnation and other legal purposes | Office of Land management (OLM) | Staff in Right of Way (ROW) | Used when new right of way is acquired for highway purposes. Official Commissioner Order identifies the limits of the right of way required for highway purposes as designated by the Commissioner of Transportation. Orders may be in the form of a map or plat showing the lands and interests in land required for highway purposes.
WBS_R.6.3.1 | Title Opinion
WBS_R.6.3.2 | Right of Way Package
WBS_R.6.3.3 | Valuations
WBS_R.6.3.4 | Right of Way Pre-acquisition
WBS_R.6.3.5 | Direct Purchase
WBS_R.6.3.6 | Condemnation
WBS_R.6.3.7 | Relocation | TMPL 1650
WBS_R.6.4 | Property Conveyance | TMPL1620 |  |  | Office of Land management (OLM) | OLM
WBS_R.6.4.1 | Title Opinion
WBS_R.6.4.2 | Right of Way Package
WBS_R.6.4.3 | Valuations
WBS_R.6.4.4 | Right of Way Pre-acquisition
WBS_R.6.4.5 | Direct Purchase
WBS_R.6.4.6 | Condemnation
WBS_R.6.4.7 | Relocation | TMPL 1650
WBS_R.6.5 | Acquisition (metro) | TMPL1610 | For use in Metro right of way acquisition. | Parcel ownership documents | Office of Land Management (OLM) | Metro District Right of Way | Used for all forms of right of way. (Fee Acquisition, Temporary Right to Construct and Commissioner's Orders)

## Scoping Schedule
WBS | WBS Name (click for Gantt chart) The purpose of the Gantt chart pdfs is to show activity durations and logic. The Gantt charts do not necessarily reflect how the work package will look once it is placed in a schedule. | Work Package ID | Threshold Criteria | Deliverable | Organization | Functional Group | Notes
WBS_S.1 | Milestones (Scoping) | TEMP4000 | To be used on all Scoping Schedules |  | Template Group | Template Group
WBS_S.2.1 | Scoping Document | TEMP4002 | To be used on all Scoping Schedules | Scoping Document, Project Management Plan and Total Project Cost Estimate | Template Group | Template Group
WBS_S.2.2 | Project Baseline | TEMP4001 | To be used on all Scoping Schedules | Preliminary Schedule | Template Group | Template Group

## Design Schedule
WBS | WBS Name (click for Gantt chart) The purpose of the Gantt chart pdfs is to show activity durations and logic. The Gantt charts do not necessarily reflect how the work package will look once it is placed in a schedule. | Work Package ID | Threshold Criteria | Deliverable | Organization | Functional Group | Notes
WBS_D.1 | Design Milestones | TEMP3000 | To be used on all Design Schedules | None | Template Group | Template Group
WBS_D.2 | Project Management | TEMP3002 | To be used on all Design Schedules | None | Template Group | Template Group