## Sheet1
Pay Item Guidance for Projects with ADA Curb Ramps
Standalone Signal Projects/ADA Retrofits
1) Remove Curb and Gutter - Indicate sawcuts are incidental with a note in the SEQ. (2104.501 Remove Curb and Gutter - LIN FT)
2) Remove Concrete Walk - Indicate sawcuts are incidental with a note in the SEQ. (2104.503 Remove Concrete Walk - SQ FT)
3) Mill and Patch Bituminous Pavement - Use for bituminous pavements in good condition (2232.603 Mill and Patch Bituminous Pavement - LIN FT)
4) Remove and Replace Bituminous Pavement - Use for bituminous pavements in poor condition (2104.603 Remove and Replace Bituminous Pavement- LIN FT)
5) Concrete Curb and Gutter (2531.603 Concrete Curb & Gutter - LIN FT)
6) Concrete Walk (2521.618 Concrete Walk - SQ FT) - Walk thickness is indicated in curb ramp standard plans.
7) Truncated Domes (2531.618 Truncated Domes - SQ FT)
8) Concrete Curb Design V (2531.603 Concrete Curb Design V - LIN FT)
9) Turf Est. and Grading (2575.602 Site Restoration - EACH)
Designer should provide grading quantities for all borrow material expected to be over 8 CY (CV) at a quadrant
If borrow quantity is measured in the field to be greater than 8 CY (CV) at any particular quadrant and that quantity is not specifically provided for in the plan,
then the contractor will receive fixed price for all borrow in that quadrant
Use 2106 spec and pay items when paying for grading on curb ramp projects.
Excavation/Borrow quantities that are expected to be less than 8 CY (CV)at a quadrant are incidental unless specifically provided for in the plan
Mill & Overlay with Curb Ramps
1) Remove Curb and Gutter - Indicate sawcuts are incidental with a note in the plan. (2104.501 Remove Curb and Gutter - LIN FT)
2) Remove Concrete Walk - Indicate sawcuts are incidental with a note in the plan. (2104.503 Remove Concrete Walk - SQ FT)
3) Concrete Curb and Gutter (2531.603 Concrete Curb & Gutter - LIN FT)
4) Concrete Walk (2521.618 Concrete Walk - SQ FT)
5) Truncated Domes (2531.618 Truncated Domes - SQ FT)
6) Concrete Curb Design V (2531.603 Concrete Curb Design V - LIN FT)
7) Turf Est. and Grading (2575.602 Site Restoration - EACH)
Large Grading/Regrading Project and/or Projects with Large Quantities of Sidewalk
1) Use Specific Curb and Gutter types B624, etc…..ADA Standard Plan sheets will be included in all plans.
2) Truncated Domes
3) 4" Concrete Walk for the sidewalks and 6" Concrete Walk in curb ramp areas
4) Concrete Curb Design V (2531.603 Concrete Curb Design V - LIN FT)