Public-Private Partnership Project Screening and Assessment

Prepared for the Minnesota Department of Transportation

Final Report

Prepared by Parsons Brinckerhoff

December 3, 2010

Contents

Executive Summary	5

1.	Introduction	11

1.1	Background and Objectives	11

1.2	Screening Process Overview	12

1.3	Public Private Partnership Delivery Models	13

1.3.1	Spectrum of P3 Options	13

1.3.2	Delivery Model without Private Financing	15

1.3.3	Delivery Model with Private Financing	16

1.3.4	Delivery Options Considered for this Study	18

1.3.5	Revenue and Payment Options	18

1.3.6	Procurement Phasing Options	21

2.	Level I Screening	23

2.1	Methodology	23

2.2	Screening Criteria	25

2.3	Level I Screening Results	29

2.3.1	Projects Proceeding to Level II Analysis	30

2.3.2	Projects with P3 Potential in the Long-Term	33

2.3.3	Projects Withheld from Level II Analysis	34

3.	Level II Assessment	36

3.1	Cost Recovery Analysis for Revenue-Generating Projects	36

3.1.1	Assumptions	36

3.1.2	Cost Recovery Analysis Results	42

3.2	Review of Potential P3 Delivery Options and Efficiencies	45

3.2.1	Pavement Preservation Program	45

3.2.2	Chapter 152 Bridge Program	54

3.2.3	Managed Lanes Program	57

3.2.4	Interstate Truck Havens & Commercialized Rest Areas	59

3.2.5	St. Croix River Crossing and Lowry Hill Tunnel	61

4.	Strategic Guidance for Mn/DOT P3 Program	63

4.1	Legislative Strategy	64

4.2	Organizational and Institutional Capabilities	65

4.3	Public Outreach Program	68

4.4	Value-for-Money Analysis	69

4.5	Performance Standards	71

5.	Conclusions	72

Appendix 1 - Level I Project Screening Documentation	75

Acknowledgements and Contact Information	115

Figures

Figure 1: P3 Screening Process Overview Flow Chart	13

Figure 2: P3 Project Delivery & Financing Methods	14

Figure 3: Level I Screening Process Flow Chart	24

Figure 4: Map of Revenue-Generating Projects Advanced as P3 Candidates	33

Figure 5: Percentage Estimate of Capital Cost Covered by Toll Revenue Bonds (Order-of-Magnitude)	44

Figure 6: P3 Procurement Process Overview	63

Tables

Table 1: Short-Term and Medium-Term P3 Project Candidates Summary (Individual Projects)	31

Table 2: Project Groups Advanced as P3 Project Candidates	32

Table 3: Long-Term Potential P3 Project Candidates	34

Table 4: Projects Withheld from Level II Analysis	35

Table 5: Assumptions Used for the MnPass Projects	38

Table 6: TH 36 St Croix River Crossing Cash Flow Analysis Assumptions	40

Table 7: Lowry Hill Tunnel Cash Flow Analysis Assumptions	41

Table 8: Level 2 Cost Recovery Analysis Summary (Order-of-Magnitude, 2010$)	43

# Executive Summary

Under the aegis of the Innovative Finance Program, the Minnesota Department of Transportation (Mn/DOT or the Department) conducted a screening of planned surface transportation projects in the State to identify those projects that are most likely to generate greater value through the use of public-private partnership (P3) delivery methods.  While there is a wide range of P3 procurement strategies allowing for different levels of control, risk and responsibility allocation, and funding and financing options, Mn/DOT’s Innovative Finance Program focused this study on P3s that involve private-sector financing.  Projects were therefore primarily assessed for their potential to be delivered under Design-Build-Finance-Operate-Maintain (DBFOM) procurements (or variants such as DBFO or DBFM).

Mn/DOT developed a list of 38 transportation projects from among its statewide priority investments and retained Parsons Brinckerhoff (“the PB Team”) to screen these projects and identify the best candidates for P3 delivery and develop recommendations to analyze further and implement these projects.  The goal of the screening was not to identify all potential P3 projects, but only the most promising.  To that end, the PB Team developed a two-step screening process.

The first level of screening (Level I) involved a fatal flaw and opportunity-based scan of project data, relying primarily upon existing documentation and interviews with Mn/DOT staff.  The Level I screening was intended to identify projects that exhibit the general attributes of good P3 project candidates and align most closely with the specific goals of the Department.  Projects meeting the Level I criteria as described below were advanced to the second step of the assessment (Level II):

- Project size and complexity: Highway, rail or transit improvements above $400 million and bridge improvements above $250 million were considered along with some smaller projects with opportunities to benefit from P3 approaches stemming from complexity in implementation or operations for which the Department may have limited internal capabilities.  Some projects were grouped to make up large enough projects when such grouping made sense from transportation and commercial perspectives.

- Criticality: The criticality criterion reflects a prioritization of the projects that best align the P3 project candidates with the Department’s priorities and encompasses safety, legislative obligations, system preservation, mobility, and network completion.  Projects meeting size and criticality criteria were advanced to Level II assessment.

- Revenue potential: Revenue projects that satisfied the size and complexity criteria (independently of criticality) as well as the implementation timeline and environmental clearance criteria were advanced for Level II assessment.

- Implementation timeframe and environmental clearance: Projects that could be implemented in the short (two to three year) to medium (four to eleven year) term were advanced to Level II assessment if they met the criticality and/or revenue potential criteria and were in the environmental approval process or could reasonably be expected to be implemented within the medium-term.  Longer-term, critical projects were flagged for future consideration as potential P3 candidates but were not assessed in Level II.

Seven projects, made up of ten individual projects that conformed to the Level I screening criteria, were advanced into a Level II assessment, which involved two separate analyses (

First, revenue-generating projects were evaluated for their bonding capacity using benchmarking and planning level, order-of-magnitude estimates of capital, operation and maintenance (O&M), and rehabilitation and renewal (R&R) costs over a twenty to forty year horizon.  The Level II assessment then provides an overview discussion of the type of P3 contracting methods that could be used for these projects and the sources of efficiencies that could be realized, based on the industry knowledge of the PB Team, interviews with industry participants from the private and public sectors, and research conducted by the PB Team.

As a first order-of-magnitude, two out of the four revenue projects could cover up to 40% of their initial capital cost net of O&M and R&R expenses, while the two remaining projects barely breakeven.  Therefore, for the project reviewed in the Level II assessment, any P3 delivery model involving private financing would necessarily require an availability payment (or a shadow toll) payment mechanism potentially combined with a direct subsidy in the form of construction payments.  Mn/DOT is likely to retain most of if not all the revenue risk.

The final set of projects recommended for further analysis as potential P3 candidates, along with a starting point for the type of contract structures that may be possible, is presented below.

In The Near Term

- The Saint Croix River Crossing is a P3 candidate as a toll bridge and Mn/DOT has started a more detailed analysis of revenue and costs and potential delivery under a DBFOM model as legislatively directed.  The order-of-magnitude analysis of bonding capacity revealed that project toll revenue could cover up to 40% of its capital costs after O&M and R&R expenses.

- Two near-term groups of MnPass Managed Lane Projects including the Northwest Metro Corridor (I-94 and I-494 MnPass Lanes and TH610) and North Minneapolis-Central MnPass Lanes (I-35W/I-94) could be implemented under a DBFOM model.  As a first order estimate, the Northwest Metro Corridor does not quite generate sufficient revenue to cover its capital costs through revenue bonds after O&M and R&R, while the North Minneapolis-Central MnPass Lanes covers only a small portion of capital costs (although network synergies may improve revenue).  Several payment mechanisms exist that could be used to implement such managed lane P3 projects and allow the State to retain control on toll rates if this is a policy objective.

- Parts of the statewide Pavement Preservation Program could be delivered under a DBFOM structure with an initial investment in pavement rehabilitation addressing the critical sections of pavement followed by a long-term (20 to 30 years) maintenance program for these sections and other sections that are likely to reach lower performance levels over the course of the contract.  The concession would require an availability payment structure, although ancillary revenue (e.g. utility rights) could lower the costs to the State.  To be delivered under a P3, the scope of the rehabilitation work (including geographic distribution and network continuity) and the allocation of O&M responsibilities between Mn/DOT and a potential partner would require careful definition.  The program would also have to be based on a comprehensive set of metrics for pavement performance.  Mn/DOT’s experience with such metrics provides a solid basis to build from.  Such programs have been implemented under the Private Finance Initiative in the U.K.  Highway maintenance and pavement preservation P3 contracts have also been used in the U.S. providing Mn/DOT with domestic public-sector counterparts to share existing experience and demonstrating private-sector interest for such approaches.

- Truck Havens could also be delivered under a DBFOM structure.  The State currently has no commercial rest areas.  To improve safety, Mn/DOT is investigating the feasibility of developing a partnership project serving truckers on sections of the State highway system where truck volumes are too low to support the private development of private truck stop operations.  To enable development, the State could partner with the private sector and participate in the development cost of the facility and/or supporting infrastructure.  Rest areas procurements have been successfully implemented in the U.S. under P3 models despite the federal limitations on the use of right of way on the Interstate Highway system.  With the nature of such developments more akin to land development than traditional highway projects, the potential private partners for such concessions are more likely to be specialized developers and private hospitality companies running commercial concessions that provide food, beverage and retail services.

In The Medium- Term

- The Lowry Hill Tunnel meets the criticality criteria in the long-term for system preservation and in the medium-term for mobility.  Although at a preliminary planning stage, the project is likely to be very large (over $1 billion) and require innovative urban tunneling techniques.  In the medium term, the project could be considered for a Pre-Development Agreement, in which the private partner participates in the preliminary design of the project during the environmental review process either at a reduced or deferred cost, in exchange for the right of first refusal to develop the project on a DBFOM basis.  Tunnel projects of this type and magnitudes are likely to attract strong domestic and international completion for a P3.  The preliminary bond capacity analysis shows that, if the project were tolled, revenue could cover approximately 13% of its capital costs with a $1 toll rate or up to 40% with $2 toll rate after O&M and R&R. Further detailed studies are required to assess alignment, scope, costs and revenues.

- Future Bridge Program similar to the Chapter 152 Program could be considered for P3 procurement.  An analysis of the Chapter 152 Program was initially developed but quickly arrived at the conclusion that the program was too far advanced to change the current procurement method.  For future bridge programs, the bundling of multiple bridge repair projects in a single, large private rehabilitation project can generate efficiencies in terms of schedule acceleration and cost reduction stemming from standardization in addition to other, more common risk transfers available under P3.  There may be greater programmatic benefits from including smaller, more standard bridges in a P3 rehabilitation program when compared to larger more complex bridges, which are usually better procured on a standalone basis.  Given the long life expectancy of bridges and the ability to specify performance over time, the use of a P3 approach with a bridge program provides opportunities to capture lifecycle costs efficiencies.  The same recommendations as to scope definition, responsibility allocation, and performance metrics apply to the Bridge Program as they do for the Pavement Preservation Program.

Longer-term projects beyond eleven years were not evaluated.  However, some of these projects should continue to be considered for P3 delivery as the projects are further developed, including the two high-speed rail projects in the State (Twin Cities to Chicago and Twin Cities to Rochester), the I-35 / I-535 "Can of Worms" Project, the I-535 Blatnik Bridge, the I-494 Bloomington MnPass Lane, and the TH-41 Bridge at Chaska.

Next Steps Towards a P3 Program

In order for the identified projects to move along to implementation using a P3 delivery method, a series of activities related to the framework of the Department’s P3 program must be completed.

First, the legal framework for P3s (including contracting authority, procurement development and evaluation and award process, among others) must be defined before any project enters the procurement phase.  From a legislative standpoint, to begin this effort, it is advisable to identify one project to spearhead a broader program to follow.  Framing the discussion of public versus private pros and cons in light of one project’s costs, risks and timeline can far better illustrate the benefits of the P3 approach, and can serve to educate all involved about the types of P3s and their appropriate uses.  This strategy is likely to move projects faster into implementation and also limits the initial legislative risks associated with broader authority.  In addition, having a real project to talk about will assure that the national and international players in the P3 market will pay attention to the legislative debate and provide input as appropriate.

At the same time, in order to develop a P3 program, the institutional capacity of the State must be built through a combination of in-house expertise and specialized consultants and be supported by political leadership (i.e.  the program needs a political “champion”) to (1) ensure that the State is effectively represented through procurement and negotiation stages, (2) ensure that the public interest is protected, (3) provide a long-term source of information and advocacy for the program, (4) communicate to the private sector that the State is committed to the program, and (5) provide the appropriate level of oversight.

Delivering P3 projects represent a paradigm shift for a Department of Transportation (DOT) from designing and constructing projects to setting value and performance standards and managing and overseeing contracts.  Such a change in the traditional delivery functions of a DOT requires building up new capabilities and reorganizing existing capabilities to focus on delivering services as opposed to building projects.  The skills required can be broadly divided by project phases including, project scope definition and development, procurement preparation, running the competitive procurement process, and contract management and oversight.  From an organizational perspective, a fundamental decision will be that of centralization or distribution of these resources at the District level and how best to ensure that the Districts consider P3 delivery systematically as they move projects through the development cycle.

If the P3 structure being selected for a particular project includes O&M services, then the procurement documents must define the mandatory performance requirements over the life of the contract.  O&M requirements (and to a great extent Design-Build requirements) should be stated as measurable service goals and performance metrics to be achieved and leave the choice of means and methods to the private partner.  Developing such performance standards in support of a P3 program would require a significant investment from the Department, in addition to the paradigm shift necessary for their implementation.  The Department’s established experience with Design-Build contracting and performance metrics is solid first steps towards building in-house competencies for a P3 program.

When asked about the primary reasons for success or failure of a P3 project, government and private sector executives almost unanimously cite public outreach as the number one factor.  Whether the public was informed and understood the pros and cons of private-sector participation, had the opportunity to participate in the debate, and was given assurance that the public interest was protected are all key success factors.  The outreach needs to be focused on key constituencies who have an interest in transportation improvements including policy makers, local governments, design and construction industry, unions, environmental groups, as well as the general public.

Before any project is moved forward using a P3 delivery method, a sound business case must be built for the project to ensure that the public sponsor maximizes its risk-adjusted return on investment.  This business case, referred to as Value-for-Money (VfM) analysis, compares the net present value of the life-cycle, risk-adjusted, public-sector procurement cost if the project were to be funded, financed, built, operated, and maintained by the public sponsor (referred to as “Public Sector Comparator” or PSC) with the net present value of the likely private bid under the P3 option (referred to as “shadow bid”).  Such analysis must extend 20 to 40 years into the future in order to capture representative lifecycle costs and compare sometime widely different investment strategies.

The VfM allows the public sponsor to test various procurement models, risk allocation strategies, and to select those risks that can be most efficiently transferred to the private sector.   For the PSC (and the VfM) to be realistic, it needs to represent the actual experience of the public sponsor in delivering similar projects, including the risks of cost overruns and schedule delays.  The shadow bid in turn must be derived from the analyst’s knowledge of private sector delivery, risk pricing, and capital market.  All P3 projects must undergo VfM before moving into the procurement phase, which must be confirmed prior to award with actual bids received though transparent, competitive procurement.  The value of the P3 project to the State must be confirmed prior to award with actual bids received.

# Introduction

# Background and Objectives

The 2008 and 2009 Sessions of the Minnesota State Legislature accomplished much in trying to restore the eroding purchasing power of traditional sources of funds for surface transportation in Minnesota, including passing a five-cent increase in the fuel tax and a 3.5 cent fuel surcharge, increases in tab fees and dedication of the motor vehicle sales tax, authorization for Counties to levy sales tax for transportation, and over $2 billion in bonding authorization over the next 10 years.

Despite these proactive legislative steps, the need to address safety, system preservation, and mobility in Minnesota (and across the Nation) continues to grow faster than revenue: Statewide unfunded highway investment needs total $50 billion over the next 20 years, with a majority of those investments required to improve mobility.  With uncertainty surrounding the future of federal funding and the State nearing its Trunk Highway bonding capacity, the Minnesota Department of Transportation (Mn/DOT or the Department) created a new Innovative Finance Program to explore new revenue streams, financing techniques and partnering approaches to help deliver transportation improvements more quickly and cost-effectively.

In this context, Mn/DOT conducted the screening study presented in this report. The study identifies the planned transportation projects in the State that could benefit from public-private partnerships (P3) procurement strategies. The goals of this study are to:

- Identify a list of the best short-term (two to three years) and  medium-term (four to eleven years) projects that are most likely to generate greater value resulting from risk transfers and cost and schedule efficiencies through the use of P3 delivery and financing methods, and

- Develop recommendations to analyze further and implement these projects using P3 delivery.

In order to accomplish these goals, Mn/DOT developed a list of 38 transportation projects from among its statewide priority investments (see Appendix 1) and retained Parsons Brinckerhoff (PB or the PB Team) to screen these projects and identify the best candidates for P3 delivery.  This report presents the two-step methodology developed by the PB Team to conduct the screening and the results of our analysis.

It is important to note that that this screening study was conducted without regard to existing legal authority for any given procurement model, as it is the Department’s intent to seek special authority should a project justify the use of a P3 delivery and financing method.

# Screening Process Overview

The screening process used for this study is geared toward supporting the success of a statewide transportation P3 program and therefore is focused on identifying the most promising P3 project candidates from among the State’s priority surface transportation projects.  The goal is not to identify all P3 candidate projects, but only the most promising.  To that end, and in order to provide for an efficient and effective review of project suitability for P3 considerations for such a large pool of project candidates, the PB Team developed a two-step screening process.

The first level of screening (referred to as Level I) involved a fatal flaw and opportunity-based scan of project data, relying primarily upon existing documentation and interviews with District staff.  Project information collected by PB and used for the Level I screening is summarized in Appendix 1.  The intent of the Level I screening process was to identify a small number of basic parameters that make projects strong candidates for P3 development and align the projects with Mn/DOT’s goals for using P3 delivery.  In other words, the criteria used for the Level I screening need to reflect simultaneously the general attributes of good P3 project candidates and the specific goals of the Department.  For that purpose, the Level I screening started with a half-day workshop session held at Mn/DOT’s headquarters in Saint Paul on Thursday, June 17, 2010, where the Department’s goals were clarified and the Level I criteria were initially developed and tested against a number of project candidates.  Projects that did not meet these criteria were eliminated from further consideration, although some projects, which are at a very early planning stage, may be considered viable for potential P3 development in the long-term.  The detailed criteria used for Level I screening and the results of this analysis are presented in Section 2.2.

Projects that conformed to those criteria were advanced into a Level II assessment where a quantitative assessment of financing capacity was performed (where data was available) and potential allocation of responsibilities between public and private sector partners were reviewed in more detail.  The analysis conducted for Level II assessment is presented in Section 3.

This two-step approach is summarized in the flow chart in Figure 1 and is based on the methodology provided in PB’s technical proposal for the P3 Screening and Assessment Study, together with the input and direction received from Mn/DOT.  The more detailed steps involved in Level I screening are further described in Section 2.1 and Figure 3.

Figure 1: P3 Screening Process Overview Flow Chart

# Public Private Partnership Delivery Models

# Spectrum of P3 Options

There is a wide range of P3 delivery and financing methods allowing for different levels of control, risk and responsibility allocation, and funding and financing strategies.  Identifying an appropriate procurement strategy from the range of P3 options for a given project requires matching the public goals for the project with the unique attributes of the project and the environment in which it will be built.

A P3 delivery method must address on the one hand the degree of private sector risk participation in the physical delivery of the project/service, and the degree to which the public sponsor (i.e.  Mn/DOT) assumes the direct financial risk for delivering the project/service.  Figure 2 summarizes these two primary dimensions of the procurement strategy and provides a general framework and terminology used in this report when describing P3 delivery options.  Although it is useful to look at these two dimensions separately, ultimately, they should be considered simultaneously when analyzing risks.

Figure 2: P3 Project Delivery & Financing Methods

Private sector participation in the physical delivery of the project ranges from a traditional, fully segmented approach such as the traditional Design-Bid-Build (DBB) to a fully integrated method requiring a true partnership with the private sector and combining infrastructure and services such as Design-Build-Operate-Maintain (DBOM) (see horizontal axis in Figure 2).  Options for assuming financial risk range from direct public funding using pay-as-you-go mechanisms or public financing to full private debt and equity financing (see vertical axis in Figure 2).  Any financing strategy relying on private sector participation must also be elaborated in parallel with a careful analysis of the revenue streams that may need to be leveraged to deliver the project (see Section 1.3.5).

Therefore, identifying suitable project candidates for P3 procurement involves assessing options along a continuum of structures for the physical provision of the infrastructure and associated services and a parallel range of funding and financing options.  All of these variables must be considered simultaneously to determine which combination will ultimately best meet Mn/DOT’s objectives to deliver projects faster and more cost-effectively.

The following provides further information on the project delivery options identified in Figure 2.

# Delivery Model without Private Financing

Design-Build (DB)

Design-Build (DB) is a project delivery method that combines two, usually separate services into a single contract.  With DB procurements, owners execute a single, fixed- fee contract for both architectural/engineering services and construction.  The DB entity may be a single firm, a consortium, joint venture or other organization assembled for a particular project.  The design-builder assumes responsibility for the majority of the design work and all construction activities, together with the risks associated with providing these services for a fixed fee.  When using DB delivery, the public sponsor usually retains responsibility for financing, operating and maintaining the project.  While DB procurement has been prevalent in private sector work and outside the U.S., it is also gaining acceptance among many public sector transportation infrastructure owners.  Because it features fixed prices identified at the proposal stage, design-build delivery is often used with projects that involve debt financing – either by the public or private sector.

The State of Minnesota, along with Arizona, Utah, and Florida, has been a leader in the use of DB contracting.  Mn/DOT started using DB in 1996 as a pilot delivery method.  While the first DB projects were awarded on a low bid basis, legislation was passed in the early 2000s allowing Mn/DOT to use DB on a best value basis.  Since then, Mn/DOT has built up an in-house team of DB experts and uses DB contracts routinely.

Operations and Maintenance Agreements

Public agencies utilize operations and maintenance (O&M) procurements to transfer a wide range of O&M responsibilities to the private sector.  These comprehensive agreements involve both service and management aspects and can be useful in encouraging enhanced efficiencies and technological sophistication.  Contractors can be paid either on a fixed fee basis or based on performance where contractors may receive premiums for meeting specified service levels or performance targets or be charged penalties for not achieving such targets.

O&M contracts that are based on performance specifications may be used as a means to transfer risks and responsibilities to the private sector for on- going operation activities (e.g. landscaping, tolling operations) as well as routine maintenance (e.g. guardrail  and pavement crack repairs) and major repairs (e.g. pavement replacement).  Standalone O&M contracts are usually short term ranging from three to seven years.

When in the purview of the public sector, maintenance decisions can be affected by budget availability.  Transferring that responsibility to the private sector through the use of performance-based contracts may allow owners to generate efficiencies by transferring performance risks and promoting innovation through the implementation of best practices in asset management as well as increase funding stability of O&M activity.  Such O&M arrangements incentivize the private partner to utilize asset management strategies that emphasize system preservation and evaluate the trade-offs among maintenance alternatives to identify cost-effective investment decisions.

Longer contract terms that encompass major repairs allow taking better advantage of life-cycle cost efficiencies; such contracts generally fall under the category of Design-Build-Operate-Maintain or Design-Build-Finance-Operate-Maintain as described hereafter.

Design-Build-Operate-Maintain

The Design-Build-Operate-Maintain (DBOM) model is an integrated delivery method that combines the design and construction responsibilities of DB procurements with performance-based O&M contracting for a specified period of time (usually 15 to 30 years), thereby transferring risks in design, construction and operation and incentivizing the private partner to implement best practices in asset management over the duration of the contract.  The DBOM model is often used with transit projects where the private partner often regroups rolling stock and systems manufacturers and operates the system, thereby limiting interface risks.  The public sponsor is responsible for securing financing for DBOM projects and retains revenue risk once the project is operational.

# Delivery Model with Private Financing

Design-Build-Finance

Design-Build-Finance (DBF) is a P3 technique that allows for private capital to kick-start project development and construction in advance of when public funds would be available.  In simple terms, the winning contractor agrees to provide all or some of the construction financing and to be paid back either through milestone or completion payments made from public funds.  These arrangements are typically short-term in nature, repaid at construction completion or extending only a few years later.  DBFs only transfer some of the design and construction risk and do not involve any transfer of operating or maintenance risks to the private partner and therefore produce limited efficiencies beyond those that can be achieved in a DB procurement.  In essence, a DBF arrangement is a DB procurement with short-term gap financing.  For the private parties to be willing to put their own money into the project, they must be assured that repayment will be forthcoming on the schedule and in the amounts anticipated.  As such, these arrangements are most often used when there is a full funding grant agreement in place with funds flowing into the project later than construction needs require, or in cases where the contractor will be repaid in one lump sum upon full completion, or in case of emergency on the part of the public sponsor.

Design-Build-Finance-Operate-Maintain

The Design-Build-Finance-Operate-Maintain (DBFOM)  model (and variants like DBFO and  DBFM)  offer an integrated delivery method that combines the design and construction responsibilities of DB procurements with performance-based O&M contracting, and private-sector financing for a fixed period of time (usually 25 to 40 years, up to 75 and 99 years in some cases).  In exchange the private partner has the right to collect the revenue from the project and/or is compensated through a payment for services based on performance specifications for the duration of the contract.  As with DBOM procurements, the responsibility for performance of O&M activities in the long-term is transferred to the private partner creating incentives to optimize life-cycle costs.

There is a great deal of variety in DBFOM arrangements and especially in the degree to which financial risks are actually transferred to the private sector.  Contracting and financing for a project delivered under a DBFOM generally requires the incorporation of a new concession company created for the sole purpose of the project called a special-purpose vehicle (SPV).  The SPV is the recipient of project revenues whether they are user fees (e.g. tolls) or public funds (e.g. availability payments), which are leveraged to issue bonds or other debt on a non-recourse basis and pay for project development costs. Depending on the revenue sources and the risk allocation, private partners may or may not be exposed to revenue risks.

In all cases, private partners are required to make direct equity investments into the SPV with leverage generally varying from 70% to 90% depending on the project risks and liquidity in the debt capital market.  Equity from different sources can be invested at various stages of the project with equity investments first required during the construction period.  Early investors are usually replaced at the end of the construction period (or soon after) by investors with longer investment horizons and risks profiles more closely aligned with the revenue risks of the concession company.  Other types of equity investors take an active role from early development into the operation period and remain invested throughout the life of the concession.

Equity investors hold a junior claim on project revenue and generate a return only if the concession can cover its O&M costs, debt service, capital investment obligations, and reserve requirements.  As such, equity is the most risky and most expensive form of capital and requires a return on the order of 12% to 20% with early investors requiring higher return for a higher degree of risk than later-stage investors.

In nearly all cases, the public agency sponsoring the project retains full ownership over the project assets throughout the concession period, although tax ownership can be (and usually is) transferred to allow for tax depreciation.   Debt and equity providers in DBFOM concessions impose strict discipline on the design-build and O&M contractors working for the SPV through contractual structures that include enforceable liquidated damages, security packages, and warranty provisions forcing the concessionaire to manage risk proactively.

Privatization

Under a privatization scheme (also known as Build-Own-Operate model), a private company is granted or sold the right to develop, finance, design, build, own, operate, and maintain a transportation project.  The private sector partner owns the project outright and retains the operating revenue risk and all of the surplus operating revenue in perpetuity, corresponding to a full privatization.  While this approach is more common in the water and telecommunication sectors, it has also been used historically to develop transportation infrastructure (e.g. freight railroad).

# Delivery Options Considered for this Study

Mn/DOT’s Innovative Finance Program is currently focusing on P3 procurement strategies that involve private-sector financing.  Therefore, this study focused primarily on concession structures like DBFOM (and variants DBFM or DBFO) and the term concession is used generically to refer to these types of delivery methods.

# Revenue and Payment Options

There are three basic types of revenues sources for surface transportation DBFOM concessions: user-fee revenues, public-sector payments, and ancillary revenues. Public-sector payments can take the form of progress payments during or after construction, long-term availability payments, or shadow tolls. Hence, from the concessionaire’s perspective, revenue could include a combination of the revenue types presented below:

### User Fees

The user-fee approach involves collecting tolls from motorists using a highway or crossing project or fares from passengers on transit and rail system (and oftentimes third party, ancillary revenue such as station retail and advertising).  The primary risk is that user fee revenue will not meet expectations or forecasts, particularly with greenfield projects.  When user-fee revenue are not sufficient to cover the complete cost of financing, building and operating the improvement, a public sponsor may opt to provide a subsidy to the concession in order to make the project financeable, particularly if the public sponsor believes that a P3 procurement with private financing would result in additional cost and schedule efficiencies.

### Construction Payments

Direct public subsidies can take the form of a lump-sum payment for a portion of the project cost made at the end of the construction period or a series of progress payments corresponding to project milestones.  Construction payments can be used in conjunction with user-fee revenue (to make the project financeable) or as a way to reduce a long-term availability payment.  The amount of such payments is usually determined, among other considerations, by the project capital needs, the public sponsor’s ability to use capital or operating funds to pay for the concession, the concession financing structure, the credit quality of the project, and risk appetite (the greater the construction payment, the fewer design and construction risks effectively transferred to the private sector).

### Availability Payments

Availability payments (APs) are a means of compensating a private partner for the provision of a transportation service achieving a specified level of performance.  These payments are made by the public sponsor and are contracted under the concession contract based on the availability and overall performance of the facility.  The availability and performance standards are set forth in the concession contract, such as incident management, maintenance-related lane closures, etc.  When these pre-determined availability and performance conditions are met, the system is said to be “available,” and the corresponding APs are made.  When the performance conditions are not fully met, the APs are reduced based on rules defined in the concession contract and on the actual level of performance achieved.  APs are used in DBOM and DBFOM contracts and the agreement generally allows for rate escalation to account for inflation.

APs can be used on revenue facilities, either to supplement insufficient user revenue or to isolate the private partner from the underlying revenue risk (if for example the public sponsor wants to retain complete control over toll rates for policy reasons).  APs are usually indexed, at least partially, on inflation.

While there is a cap on their upward revenue generation potential, APs can be attractive to private investors as they are far less risky than user-fee concessions that must achieve certain levels of traffic and revenue in order to be profitable and are subject to demand risk.  Instead, the concessionaire receives a predictable, set of fixed payments over the life of the agreement.  From the concessionaire’s perspective, the credit quality of the project is directly linked to the source of funds and appropriation procedure used by the sponsor and not to the achievement of predicted market demand.

It should be emphasized that the public sponsor must pay these availability payments with funds coming out of its annual budget for the duration of the concession.  APs are therefore a liability much akin to debt and are considered as part of debt capacity in some jurisdictions.  In addition, because AP projects create a long-term liability on the sponsor’s  budget, choosing to deliver a project using a concession with an availability payment mechanism is equivalent to prioritizing  funds for that particular project over others that may be equally important, and should be evaluated in that light.  From a public policy perspective, public sponsors should only consider using availability payment P3 arrangements on priority projects (see “criticality” screening criteria in Section 2.2).

### Shadow Tolls

Shadow tolling strategies are a means of compensating a private partner for the provision of transportation services exclusively in the road sector.  Under such a strategy, roadway users do not pay tolls for the use of the asset; rather, the public sponsor makes periodic payments to the concessionaire based on traffic volume.  Though variations exist, the public-sector payments are typically based on vehicle miles traveled (VMT) or on the number of vehicles using the facility.  The payment structure may also take into account the traffic mix and incorporate higher rates for heavy vehicles.  Usually the payment structure incorporates a guaranteed minimum payment (floor) plus additional payments based on decreasing rates (per VMT or per vehicle) as traffic volume increases.  Above a specified traffic volume the rate drops to zero, capping the maximum annual payment from the public sponsor at a predetermined ceiling.  The agreement may also allow for rate escalation to account for inflation.

As such, shadow tolling is not a funding source but a financing mechanism that allows the public sponsor to pay for the project over time and transfer risks associated with project delivery and operation and maintenance, as well as traffic risk from the public sponsor to the concessionaire. The strategy has been primarily used in the U.K. but is also allowed in the State of Texas under its Pass-Through Financing Program.

### Ancillary Revenues

A series of other sources of revenue can be added to supplement user fees and public-sector payments including transit station retail, advertising, development rights (including land rights and air rights), utility rights (e.g. cell phone towers, fiber optic cables, pipelines), and sponsorship.  In some cases, ancillary revenues can account for a large part of project revenue, particularly when real estate development rights are granted as part of the concession.

# Procurement Phasing Options

Public sponsors may make the decision to advance a transportation improvement as a P3 procurement at different phases in the project development cycle.  The most common approach is to let P3 procurements for projects that have cleared all necessary environmental approvals.  However, in certain cases P3 procurements can be awarded prior to the completion of the environmental review process.  When this is done, the private partner plays an active role in the definition of the alternatives assessed in the environmental approval process.  These two approaches are further discussed hereafter.

### P3 Procurements for Projects with Environmental Approvals

One of the greatest unknowns in implementing transportation improvements is the timeframe for gaining the required environmental approvals. Over the course of the environmental process, the scope of the project inevitably changes and delayed approvals oftentimes result in cost escalations.  In order to avoid these risks, potential private-sector bidders are likely to avoid pursuing P3 projects that have not received environmental approvals, as they are not in a position to manage this risk as effectively as the public sector.

Public sector project sponsors obtaining environmental approvals for P3 projects must be sure that the preferred alternatives emerging from the process include all the attributes and operational requirements (including tolling) that would be needed to implement the project on a P3 basis.  The definition of the project should also include estimates of the costs for implementing and operating the facility.  This information is also helpful to public sector sponsors as it enables them to make direct comparisons of the costs and terms of the different P3 proposals it receives.  It also enables the sponsor to compare both the cost and schedule implications of a P3 delivery to those of a traditional public sector-led procurement (see Section 4.4).

### Pre-Development Agreement P3 Procurements

One of the reasons to seek private partners is to be able to tap into their capacity to develop and implement innovative solutions in a cost effective manner.  However, if a private partner is brought into a project too far into the development process, many of the opportunities to modify the design or scope of a project may be limited, particularly if it has already received environmental clearances. Following the Record of Decision (ROD), opportunities to solicit P3 developer alternatives still exist but are more limited. For instance, the procurement process may allow for bidders to propose Alternative Technical Concepts, but these technical alternatives would have to stay within the confines of the ROD and be limited to small changes in alignment or footprint. Allowing substantial changes to the project definition would require a Supplemental Environmental Impact Statement and an amendment to the ROD, which could take several months and would expose a project to new environmental permitting and approval risks.

A small number of Departments of Transportation (DOTs) (including North Carolina and Georgia) have used a delivery mechanism called “Pre-Development Agreement” (PDA) to bring in private partners during the environmental process in order to include their input into the project definition with the hope of arriving at a preferred alternative that will bring technological innovation and be less costly to implement and operate.  The PDA typically involves the private partner participating in the preliminary design of the project during the environmental review process either at a reduced or deferred cost, in exchange for the right of first refusal to develop the project on a DBOM or DBFOM basis.

PDA arrangements are generally let as best value procurements, with proposers judged both on the technical qualifications as well as unit costs for implementing different types of construction.  The actual negotiation of the concession and construction agreements does not take place until after the preferred alternative is determined, although many of the fundamental risk transfer provisions are usually contracted in the PDA itself.  As a result, using a PDA requires a tradeoff between the benefits to be gained during the development stage and the necessity to maintain competitive tension on concession terms.  The actual construction price is usually arrived at through an open-book process and is submitted to the usual federal oversight and audit.

During the PDA process, the developer acts as a consultant to the public sponsor and the public sponsor retains control over the development process and the choice of the preferred alternative.  Once the PDA advances into an implementation form, the delivery method can take the form of any P3 model or of a traditional competitive procurement (in which case, the sponsor compensates the consultant for services rendered based on pre-agreed payment).

# Level I Screening

# Methodology

Approximately 115 projects were identified by the various Mn/DOT Districts and specialty offices during the Department’s Innovative Finance project screening process.  Of these 115 projects, Mn/DOT identified 43 possible candidates for P3 consideration.  After initial review, four of these candidates were either rendered redundant with other candidate projects (e.g. a regional project becoming a part of a statewide program) or packaged with another logical project (e.g. a project that extends into two Mn/DOT Districts).  The resulting 38 candidate projects were analyzed by the PB Team based upon the criteria outlined in this Section and are presented in Appendix 1.

The Level I screening involves assessing the complete list of 38 projects selected by Mn/DOT for this study against a list of essential attributes that make transportation projects viable for development on a P3 basis and meet the Department’s goals for considering P3 procurement strategies.  The first step in this process was to develop a list of appropriate criteria to reflect simultaneously the general attributes of a sound P3 project and the specific goals of the Department.  These goals are reflected in particular in the definition of the criticality criteria described hereafter.  The data gathered for each project to conduct the Level I screening is presented in Appendix 1.

The criteria retained for Level I screening are listed below:

- Project size and complexity

- Criticality

- Revenue potential

- Implementation timeframe

- Environmental clearance

The above criteria and how these criteria were applied to each project is further described in this Section and summarized in the flow chart in Figure 3. The Level I screening is primarily aimed at eliminating those projects that do not show the essential attributes for P3 delivery and meet the Department goals for considering P3s.  It was also considered important to limit the number of criteria to those that are essential to sound P3 delivery so as to limit the data collection phase associated with this initial screening.

Non-critical projects must have the potential to generate revenue and pay for a portion of their capital cost to be advanced to Level II screening.  All short-term (two to three year) to medium-term (four to eleven year) projects that are large and/or complex enough and meet the criticality criteria or generate revenues were advanced to Level II screening to assess their financing capacity and the extent to which their possible development as P3 projects could accelerate their implementation or result in cost savings and other efficiencies.

Figure 3: Level I Screening Process Flow Chart

# Screening Criteria

### Project Size and Complexity

Unlike traditional improvement projects, those implemented on a P3 basis include additional fixed transaction costs for both the public sector sponsor and the private developers with whom they are partnering.  These costs include the additional effort involved in completing the extensive procurement and award documents, running the competitive procurement process, together with the financial and legal advisory and due diligence services (and rating agency assessments when bonds are involved) that are necessary to bring a concession deal to financial close.  As a result, the candidate projects must be of a certain scale in order to be viable for development on a P3 basis.  Moreover, smaller, simpler projects offer fewer opportunities for innovation and cost efficiencies.

Based on the experience of the PB Team and our understanding of current market conditions, the approximate capital cost thresholds used to screen candidate projects were as follows:

- Highway, rail or transit improvements: $400 million

- Bridge improvements: $250 million

It should also be noted that smaller projects were considered as potential P3 candidates if they exhibited complex implementation or operations for which the Department had limited internal capabilities. .  Other transportation-related projects, such as the development of commercial truck rest stops or the implementation of fiber optic lines along highway or rail corridors, could be considered as viable P3 project candidates independently of size and complexity and were evaluated on a case by case basis.

Given that DOTs operate with constrained budgets, out of necessity, they often break larger projects into smaller and less costly components that can be implemented in phases within their budget capacities.  While this mode of operation is logical when implementing projects on a traditional basis, as part of its screening of potential P3 projects the project team has sought to bundle smaller improvements into larger packages. Smaller projects may become viable for development on a P3 basis if they can be bundled with other improvements into a larger procurement, or if they happen to complete or compliment preexisting systems.  Projects were only bundled together when synergies could be generated from a transportation or a commercial point of view (e.g. greater network connectivity, increased toll revenue) or when efficiencies could be generated due to the proximity of the projects (e.g. efficiencies in traffic management) or when projects exhibited technical similarities (e.g. gains from standardization).

### Criticality

Mn/DOT uses performance metrics to prioritize its capital investments and achieve performance targets for the Department’s highest priorities including safety, bridge and pavement preservation, mobility, and statewide system connectivity.

The criticality criterion developed for the screening reflects a prioritization of the projects to best align the potential P3 candidate projects with the Department’s priorities.  As shown in Figure 3, regardless of revenue potential, critical projects are advanced for consideration under the Level II P3 analysis. Such projects are either screened in the Level II if their implementation timeline is within eleven years or set aside for further consideration as potential P3 candidates if available information is not sufficient for further analysis at this stage.

Critical projects may be considered for either availability payments or the user fee finance model.  As presented in Section 1.3.5, choosing to deliver a project using a P3 with some form of availability payment mechanism is equivalent to prioritizing construction, operations and maintenance funds for that particular project.

Criticality is a multi-faceted concept which can be achieved in different ways.  The different metrics used by Mn/DOT to determine criticality are discussed further below.  It should be noted that many of these criteria reinforce one another so that a single critical project is likely to fulfill several of the criticality measures.

- Safety:  Mn/DOT’s primary responsibility is to develop new projects and maintain the condition of its entire network in a manner that ensures the safety of its users.  Safety measures are dictated through a wide variety of Mn/DOT’s standards and procedures.  Any serious safety deficiency, when detected, becomes Mn/DOT’s highest priority.  Any improvement involving the resolution of major safety issues is critical.

- Legislative Obligations:  Minnesota state law requires Mn/DOT to implement certain types of projects and improvements under prescribed situations.  One of these is Minnesota Laws 2008, Chapter 152 Section 165.14, which directs the Department to establish a Trunk Highway Bridge Improvement Program (“Chapter 152 Bridge Program”) to repair structurally deficient and fracture critical bridges within a ten year timeframe.  The law establishes a three-tiered priority for implementing these state-wide improvements which together have a construction value of approximately $2.5 billion.  In order for Mn/DOT to meet the requirements of Chapter 152, the State Legislature passed a surcharge on the state motor fuel tax in 2010 through 2013 to provide funding to the Chapter 152 Bridge Program.

- System Preservation:  Mn/DOT has developed a comprehensive performance monitoring program to document the conditions of the different infrastructure it operates that are reported in the Department’s Comprehensive Annual Financial Report and the Annual Transportation Performance Report.  These metrics are used to prioritize capital investments and ensure the highest level of performance of the transportation network.  Some of those metrics (such as pavement performance) are also used by credit rating agencies as part of the Department’s bond rating.  Lower performance not only results in lower level of service for users but could also have a negative impact on the Department’s Trunk Highway obligations.  Moreover, maintaining transportation assets in a state of good repair through preventive maintenance results in lower life-cycle costs, which is a Department goal.

- Mobility:  One of Mn/DOT’s top priorities is to manage congestion and improve travel time reliability in urban areas and improve speed and connectivity in inter-regional corridors.  Projects improving mobility are considered critical projects.

- Network Completion:  In certain situations, the implementation of an individual project can provide a missing link that completes a larger network, serving multiple travel sheds and making multiple combinations of movements possible.  When this is the case, an individual project can provide benefit to an entire region, thereby achieving the criticality criterion.  Projects were sometimes grouped together so as to achieve a network effect and have a greater impact on mobility; the resulting bundled projects were considered critical.

### Implementation Timeframe

Projects meeting Mn/DOTs implementation timeframe requirements must be ready to be advanced into procurement within the short-term (one to three years or medium –term (four to eight years).  In completing the implementation timeframe assessment, it must be recognized that Mn/DOT‘s current programming assumptions for its different projects are resource constrained and are a function of the Department’s priorities as well as when funding will be available to advance projects, rather than whether or not design work has been completed or the necessary environmental approvals are in place.  Projects not needed within this timeframe (e.g. long-term replacement projects) or not realistically accelerated within these timeframes were withheld from Level II assessment.

### Criticality and Implementation Timeframes

As described above, critical projects that are needed and can be implemented within the Department’s timeframe were advanced to the Level II screening.  As part of the criticality review, it is helpful to make an additional distinction between those projects that are immediately critical and those that are critical in the longer term.  Longer-term projects are generally needed in the ten to twenty year horizon (and beyond) and may involve the replacement of a large bridge or interchange towards the end of its useful life.

While the scope of this study is limited to identifying candidate P3 projects suitable for development in the short to medium term, it is also helpful to flag other projects with longer implementation timelines that may be suitable for development on a P3 basis.  Early recognition of a potential P3 candidate enables the Department to take steps early on that would facilitate the implementation of longer-term projects on a P3 basis at a later date.  Such steps could include considering the possibility of including a tolled operation alternative in the environmental studies of these facilities or considering early engagement of private sector partners using the PDA approach for larger and more complex projects.  Such projects were identified as “potential long-term P3 project” in Appendix 1.

### Environmental Approval

Obtaining the required environmental approvals is perhaps the most cost-, time, and labor-intensive requirement that DOTs must complete in order to advance new construction projects.  It is also a process that often involves the resolution of unforeseen issues that can result in delays and cost escalation.  Therefore, in order to ascertain whether or not projects can be advanced within Mn/DOT’s required short to medium term timeframe, a realistic assessment of their environmental status is essential.  The first step involved determining what type of environmental clearance would be required, ranging from a categorical exclusion to an environmental assessment or a full blown environmental impact statement.  Each of these options implies different timeframes and levels of effort to complete.  The PB Team reviewed the current environmental approval status of each candidate P3 project (see Appendix 1).  For projects that have not yet gained the necessary environmental approvals, the PB Team relied on conservative estimates for the timeframe of completing these requirements provided by Mn/DOT District staff.

### Revenue-Generating Projects

Revenue-generating projects that met the size and complexity screening criteria and had environmental clearance (or were in the environmental approval process) were advanced for Level II assessment.

# Level I Screening Results

The following Section summarizes the results of the Level I screening in four tables:

- Table 1 presents the short- to medium-term P3 project candidates advanced to Level II screening for each individual project

- Table 2 presents how some of those projects were grouped together to create more viable P3 project candidates (Figure 4 presents these projects on a map)

- Table 3 presents the long-term potential P3 project candidates, which were not reviewed in the Level II assessment but for which P3 delivery methods should be considered as the project concepts are further developed

- Table 4 presents the projects that were withheld from Level II analysis.

Appendix 1 provides more detailed information gathered for each of the 38 projects reviewed.

The P3 project candidates were categorized by District, with an identification number assigned to indicate this categorization.  No priority was assigned in the ID number, nor do these numbers correspond with Mn/DOT project numbers.  The only purpose for the nomenclature was to selectively assign the projects for assessment in this study.  The Project ID takes the form of Dx-y, where x is the District number and y is an ordinal number within each District to distinguish the candidate projects.  If the project was in the Metro district, the Project ID takes the form of M-y, where y is again an ordinal number to distinguish projects.  Statewide projects or programs start with the letter S and transit projects with the letter T when these projects span several Districts. Numbering may not be continuous as projects were removed from the screening (for instance, duplicates).

# Projects Proceeding to Level II Analysis

Based on the Level I screening methodology and criteria presented in Section 2, ten individual projects (out of 38) were selected for Level II screening analysis.  It should be noted that many of the projects advancing to Level II are not necessarily considered independently viable; rather, they were selected based upon their potential packaging with similar and connected projects.  The project description and a summary of the Level I analysis is presented in Table 1 and the specific project grouping advanced for Level II analysis are described in Table 2.  Figure 4 presents these projects on a map.  In summary, P3 project candidates advanced for Level II can be grouped in three major categories:

- Four revenue-generating  projects, predominantly in the metro area:

  - Two standalone projects: St. Croix River Crossing (M-11) and Lowry Hill Tunnel (M-14)

  - Two groups of MnPass projects (D3-4 / M-5 combined with M-10, and M-3 / M-6)

- Two very large statewide programs requiring dedicated revenue sources:

  - Pavement Preservation Program (S-1)

  - Chapter 152 Bridge Program (S-2)

- One statewide small-size program with revenue potential:

  - Truck Rest Stop (nicknamed “Truck Havens”) (S-3, although at this stage this program only includes one project)

Although the majority of the projects are in the metro area (nine out of twelve), from a value perspective, statewide programs represent approximately half of the total project costs advanced to Level II analysis.

Table 1: Short-Term and Medium-Term P3 Project Candidates Summary (Individual Projects)

| ID | Project/Cost (2010$) | Location | Type | Rationale |
| --- | --- | --- | --- | --- |
| D3-4 | I-94 MnPASS Shoulder Lane ($136M) | Rogers / Monticello | Managed Lanes | This managed lane facility is not critical on a standalone basis, as the levels of congestion are not severe in this segment of I-94. However, when packaged together with project M-5 and M-10, this corridor becomes an attractive P3 candidate due to continuity, system-level efficiencies, and revenue-producing weekend traffic. |
| M-3 | I-94 MnPass Shoulder Lane ($103M) | Minneapolis to St. Paul | Managed Lanes | I-94 managed lanes would provide for over 16,000 daily users. The capital cost is limited due to a concurrent Active Traffic Management installation. This project is combined with M6 for Level II analysis. |
| M-5 | I-94 / I-494 MnPass Shoulder Lane ($160M) | Rogers to Minnetonka | Managed Lanes | This combined managed lane facility does not currently experience severe congestion and volume peaks at 9,700 toll customers per day. Together, both facilities would cost only $160M, but when combined with project D3-4 and M-10, it may begin to serve as a backbone for the metropolitan system, with connections to I-394 MnPass. This system connectivity enhances its criticality. |
| M-6 | I-35W MnPass Shoulder Lane ($250M) | Downtown Minneapolis to US 10 | Managed Lanes | I-35W is a critical corridor for system connectivity, travel time reliability, and safety. As a result, it rates highly for criticality. Additionally, this facility is among the more costly to develop, with moderate levels of projected toll customer use (13,200 customers per day). Neither environmental clearance nor design has begun, indicating a possible application for PDA. This project could be combined with M-3. |
| M-10 | TH 610 Final Stage (new right of way) ($170M) | Northwest Metro | New Highway | TH-610 completes a missing gap in the northwest portion of the metropolitan area. With the gap, trips are diverted in order to access I-94. With completion, VMT may be reduced and mobility increased, yielding a critical project. This is a medium-term project and was considered without revenue generation potential. The project is advanced to Level II in combination with D3-4 and M-5. |
| M-11 | TH-36 St. Croix River Crossing ($600M) | Stillwater | Bridge Replacmt. | As a Chapter 152-designated fracture critical bridge, this project rates high for criticality. The project is revenue-generating and meets the cost threshold. |
| M-14 | I-94 Lowry Hill Tunnel ($1B+) | Minneapolis | Tunnel | The Lowry Hill Tunnel constitutes the largest bottleneck on the metropolitan system, with volumes from three interstate highways and the Minneapolis central business district all converging in this sharp-turn tunnel. The cost estimates are very high ($1 to $2B). However, this segment has very high volumes and could have strong revenue potential if tolled. This project may be a candidate for PDA. Although currently planned in the long-term, the project was advanced to Level II as its implementation could be accelerated through P3. |

| ID | Project/Cost (2010$) | Location | Type | Rationale |
| --- | --- | --- | --- | --- |
| S-1 | Pavement Preservation Program ($400M+) | Statewide | Program | Pavement preservation serves a critical role in safety and sustainability of the Minnesota transportation system and is identified as a top priority of Mn/DOT. |
| S-2 | Chapter 152 Bridge Improvement Program ($1B+) | Statewide | Program | The State’s bridge reconstruction and rehabilitation program serves a critical role in the safety and performance of the Minnesota system. Chapter 152 provides a dedicated revenue source for Tier 1 bridge projects, but many Tier 2 projects and most Tier 3 bridge projects are not fully funded by the program. |
| S-3 | Truck Haven Project ($TBD) | Statewide | Project/ Program | The truck rest stop program (nicknamed “Truck Havens”) meets safety criticality criteria, but revenues are limited where commercial truck volumes are low. Truck Havens may be considered individually on a case-by-case basis or as a series of facilities grouped into a single procurement. |

Table 2: Project Groups Advanced as P3 Project Candidates

| Project ID | Level II Project Name | Capital Cost (2010$) |
| --- | --- | --- |
| D3-4 / M-5 / M-10 | Northwest Metro Corridor (I-94 / I-494 MnPass Lanes and TH 610) | $499M |
| M-3 / M-6 | North Minneapolis-Central MnPass Lanes (I-35W / I-94) | $400M |

Table Note: See Figure 4 for project location

Figure 4: Map of Revenue-Generating Projects Advanced as P3 Candidates

# Projects with P3 Potential in the Long-Term

Five additional projects did not meet the strict description for Level II analysis.  However, these projects exhibit general characteristics that could make them attractive P3 project candidates in the long-term (beyond an eleven-year horizon).  Any future P3 consideration should include the possibility of including a tolled alternative in the environmental studies for these facilities as well as the possibility to use a PDA approach for larger and more complex projects.

Table 3: Long-Term Potential P3 Project Candidates

| ID | Project/Cost (2010$) | Location | Type | Rationale |
| --- | --- | --- | --- | --- |
| D1-1 | I-35 / I-535 "Can of Worms" Project ($490M) | Duluth | Bridge Replcmt. | The Can of Worms is a long-term critical project, with multiple bridges that must be replaced as required under the Chapter 152 bridge inventory. Environmental clearance has been completed. Although traffic volumes are fairly modest (around 59,000 AADT), its size, scale, and critical nature suggest the project should be considered as a P3 candidate in the long-term as well as for a PDA. |
| D1-3 | I-535 Blatnik Bridge ($200M) | Duluth | Bridge Replcmt. | The Blatnik Bridge is long-term critical for reconstruction, and would likely only require an environmental assessment. Its capital cost is relatively low, as is its traffic level. However, this facility by proximity could be packaged with the Can of Worms project and generate efficiencies during construction. |
| M-4 | TH 77 MnPass Shoulder Lane / Contraflow ($41M) | TH-13 to Old Shakopee Road | Managed Lanes | This managed lane project would yield a small number of daily customers (5,200 per day), but can be constructed at low cost $41M. As a standalone project, it is planned for the short-term. This project could achieve congestion relief objectives if combined with M-8, particularly if the interchange between TH77 and I-494 could be redesigned to address current congestion and add capacity to accommodate the new managed lanes on I-494. The project would not be a P3 candidate on a standalone basis. |
| M-8 | I-494 Bloomington MnPass Lane ($200M to $1B, depending on the alternative) | South Metro (US 212 to MSP Airport) | Managed Lanes | The project was considered by both the MHSIS and the MnPass System II Study. Although the corridor is highly congested (meeting criticality criteria), both studies concluded the facility was impractical for development in the short- to medium-term. Cost estimates range from $200M to $1B depending on the alternative, with average daily volumes on the MnPass lane exceeding 15,100 AADT (toll users). However, given the need for environmental clearance and greater project development, this project is best considered as a long-term candidate. |
| M-12 | TH-41 Bridge ($700M+) | Chaska | Bridge Replcmt. | The replacement of the TH-41 bridge constitutes a long-term critical project based upon the Chapter 152 bridge inventory. The high-cost project has an EIS currently underway. However, like project D3-8 above, moderate volumes on the existing bridge (16,500 AADT) depresses overall revenue generation possibilities. |

# Projects Withheld from Level II Analysis

Over half of the 38 projects following projects were withheld from Level II assessment, as they met neither the criticality measures nor the non-critical measures for implementation timeframe, environmental process, cost estimation, or revenue generation potential thresholds.  The projects withheld from Level II analysis are identified briefly in the table below and presented in more details in Appendix 1.  Although these projects were not advanced to Level II analysis, opportunities may still exist for private sector participation and/or other innovative finance techniques.  In particular, high speed rail projects generally provide ample opportunities for partnering with the private sector; however the information available at this stage was not sufficient to allow for the assessment of such opportunities for the two high-speed rail projects (T-1 and T-2).

Table 4: Projects Withheld from Level II Analysis

| ID | Project | Location | Type |
| --- | --- | --- | --- |
| D1-4 | TH 53 Realignment (new right of way) | n/a | New Highway |
| D2-1 | TH-72 Baudette (Rainy River) Bridge | Baudette | Bridge Replacement |
| D3-1 | TH 25 Expansion (expansion 2 to 4 lanes) | Monticello / Buffalo | Highway Expansion |
| D3-2 | TH 371 Expansion (expansion 2 to 4 lanes) | Nisswa / Jenkins | Highway Expansion |
| D3-3 | TH 371 Expansion (expansion 2 to 4 lanes) | Jenkins / Pine River | Highway Expansion |
| D3-5 | TH 55 Expansion (expansion 2 to 4 lanes) | Buffalo / Rockford | Highway Expansion |
| D3-6 | TH 55 Expansion (expansion 2 to 4 lanes) | Annandale / Buffalo | Highway Expansion |
| D3-8 | US 169 / US 10 Expansion (conversion to freeway design) | South Metro (US 212 to MSP Airport) | Highway Expansion / Managed Lanes |
| D3-7 | TH-24 New Mississippi River Crossing | Clearwater to Clear Lake | Bridge Replacement |
| D3-10 | Northstar Commuter Rail Extension (40 mile) | Big Lake to St. Cloud | Transit |
| D6-1 | TH 63 Multimodal Improvements (expansion 2 to 4 lanes) | Rochester | Highway Expansion |
| D6-2 | TH 19 Expansion (2 to 4 lanes) | Northfield | Highway Expansion |
| D7-1 | TH-14 Expansion (2 to 4 lanes) | Mankato to New Ulm | Highway Expansion |
| D7-2 | TH-60 Expansion (4-lane expansion) | St. James to Windom | Highway Expansion |
| D7-3 | TH-22 Expansion (2 to 4 lanes) | St. Peter to I-90 | Highway Expansion |
| D7-4 | US-14 / CSAH-12 New Alignment (new right of way) | Mankato | Interchange |
| M-1* | I-35E MnPASS Shoulder Lane | St. Paul / Northeast Metro | Managed Lanes |
| M-2 | US 169 MnPass Shoulder Lane (managed lane expansion) | Southwest Metro (Shakopee to I-494) | Managed Lanes |
| M-7* | TH 36 MnPASS Shoulder Lane | Managed Lanes | Managed Lanes |
| M-15 | I-694 MnPass Shoulder Lane (managed lane expansion) | North Metro (I-35W to I-35E) | Managed Lanes |
| T-1 | High Speed Rail - Twin Cities to Chicago (new high speed rail) | Minneapolis / St. Paul to Chicago | Transit |
| T-2 | High Speed Rail - Twin Cities to Rochester "Greenfield" Line (new high speed rail) | Minneapolis / St. Paul to Rochester | Transit |
| T-3 | Personal Rapid Transit (new PRT) | Potential locations: Edina, St. Paul, and Rochester | Transit |

*Table Notes: The scope for project M-1 initially included the reconstruction of the Cayuga Bridge for approximately $200M.  Over the course of this study, the final design for the bridge was awarded, rendering the project too small for P3 consideration.  Projects M-1 and M-7 were also considered together for a total cost of $165M (without the Cayuga Bridge).  Project M-7 may be considered as a potential alternative to M-3, which was advanced for Level II assessment in combination with M-6.

# Level II Assessment

The Level II assessment involves two types of analysis.  The first analysis is an evaluation of debt capacity of revenue-generating projects to determine what portion of their initial capital cost could approximately be expected to be recovered from revenue bonds.  The result of this analysis provides an indication as to the level of direct subsidy that a project may require and the type of revenue that could be leveraged by the private sector for a potential P3, i.e. user fees vs. availability payment.

The second analysis is a qualitative assessment of Level II projects for their potential to transfer risks and deliver efficiencies both in terms of cost reductions and schedule acceleration if they were implemented on a P3 basis.  This assessment is accomplished by comparing the projects to other similar projects or programs that have been implemented elsewhere on a P3 basis.  Based on its knowledge of the P3 project candidates in Minnesota and its familiarity with domestic and international P3 transactions, the PB Team has identified P3 projects that provide similarities to projects advanced to Level II.  The PB Team also conducted interviews with senior public official and private sector representatives involved with such projects to discuss the structures of these projects and the type of risk transfers and efficiencies that could be created.  Efficiency topics discussed include avoidance of cost overruns, cost savings due to schedule acceleration, savings due to grouping similar projects in large single procurements, and savings derived from life-cycle costing and asset management practices over the long term.

# Cost Recovery Analysis for Revenue-Generating Projects

# Assumptions

All projects or combinations of projects advanced to the Level II screening that have the potential to generate revenue have been assessed to determine what portion of their initial capital cost could be expected to be recovered from the net revenues they generate.  The cost recovery calculation was developed using planning level, order-of-magnitude revenue and cost estimates based on existing information or benchmarks when information was not available.  No new planning, engineering, or costing work was performed for this study.  To the extent possible, similar assumptions were applied across all projects.  Unless otherwise noted, all dollar amounts presented in this Section are in 2010$.

Given that the MnPass System Study Phase 2 assessment developed similar cost recovery calculations for the different MnPass projects, the PB Team, in consultation with Mn/DOT, based the analysis presented in this Section on the same inputs and assumptions as used in the MnPass System Study Phase 2 (including revenue and cost estimates).  In particular, the financing capacity is based on bonding capacity with a fixed rate of 6.25% independently of the analysis period.  The analysis is not a proxy for feasibility under P3 procurement as it does not include the cost of equity capital.  The toll increase assumptions were kept in line with the MnPass System Study Phase 2 although they are below the general forecast for Consumer Price Index.  However, certain adjustments had to be made to those assumptions, including modifications to the operating and maintenance (O&M) costs and adding rehabilitation and replacement (R&R) costs to the project cash flows.  Project costs were not adjusted for risks.

For non-MnPass projects for which no toll revenue estimates were available, PB multiplied current average daily traffic (ADT) volumes provided by Mn/DOT by toll rates of $1 and $2, respectively, and reduced this revenue to reflect some elasticity of demand associated with these toll rates.

As a result of these simplifying assumptions and the limited data available, the estimates of cost recovery capacity provided in this Section are preliminary planning level, order-of-magnitude estimates and should not be relied upon as a basis for advancing projects as P3 candidates without further studies.

### MnPass Projects

Projects under consideration in this Section include M3/M6 and D3-4/M5/M10.  Table 5 summarizes the assumptions used in the MnPass Phase 2 study, which are used as a basis for the cost recovery assessment of the MnPass projects selected for Level II screening, along with additional PB adjustments as follow:

- The annual O&M cost per lane mile was increased from $50,000 per lane mile to $86,750 to cover toll equipment maintenance, administration, marketing and public relations, enforcement, service patrols, technical services, utilities, and a contingency of 25%.

- An estimate for R&R cost was added in order to take into account the life-cycle cost of the assets.  The R&R cost was broken down into two categories:

  - Tolling Equipment R&R: assumed to be incurred every 10 years, each time equal to 25% of the initial capital cost of the tolling equipment.  This initial cost is assumed to equal $1.2 million per mile (2010$) for 6-lane road sections and $1.8 million (2010$) per mile for 8-lane road sections.  The toll equipment R&R cost was then distributed annually over 20 years.

  - Roadway R&R: roadway R&R cost is based on the PB Team’s industry experience and unit cost benchmarks and includes the primary R&R elements including asphalt crack sealing, patching, mill and overlay, and pavement markings.  Unit costs per foot or per square foot and average useful lives were applied to each project.  Similarly, the roadway R&R cost was then distributed annually over 20 years.

Table 5: Assumptions Used for the MnPass Projects

| Description | Value |
| --- | --- |
| Debt Service Coverage | 1.5x |
| Interest Rate | 6.25% p.a. |
| Maturity | 20 years |
| Tolls increase | 10.0% every 5 years |
| Inflation Rate | 3.0% p.a. |
| Annual MnPass projects O&M Costs per managed lane mile (2010$) | $86,750 |
| Annualized Tolling Equipment R&R per mile (2010$) | $30,000 for 6 lane sections $45,000 for 8 lane sections |
| Roadway R&R (2010$) | Asphalt crack sealing: $0.35/ft every 3 years Patching: $3.67/SF every 10 years Mill & Overlay: $2.42/SF every 10 years Pavement Marking: $0.70/ft every 2 years |

Table Note: Projects include M3/M6 and D3-4/M5/M10

### Non-MnPass Projects

The non-MnPass projects advanced to Level II include the new TH 36 St Croix River Crossing (M-11) and the Lowry Hill Tunnel (M-14), for which no specific financial capacity study had previously been undertaken.  A cash flow analysis was developed for each project using existing estimates of capital costs and order-of-magnitude estimates of O&M costs, R&R costs, and toll revenue.  These assumptions are presented below and were developed to be as consistent as possible with the MnPass assumptions.  All operating, maintenance, rehabilitation, and replacement costs are inflated at 3.0% per year over time.

TH 36 St Croix River Crossing (M11)

The assumptions used for evaluating the St Croix River Bridge are based on information included in the 2005 Supplemental Final Environmental Impact Statement (SFEIS) for the bridge as well as the “Draft St Croix River Crossing Project: Innovative Financing Study” developed by HNTB and dated October 21, 2010.  Detailed assumptions are presented in Table 6 and described below:

- Analysis Period

The coverage and interest rate were kept as assumed in the MnPass study.  However, the maturity was increased from 20 to 40 years, which is more in line with concession duration for this type of project.

- Traffic & Revenue

Traffic and revenue forecast was assumed to be consistent with Tables 5 and 6 of the “Draft St Croix River Crossing Project: Innovative Financing Study” developed by HNTB and dated October 21, 2010. Table 6 of the HNTB draft study, in particular, presents a forecast of annual gross toll revenues at the 20th percentile for two scenarios: one in which users are charged for a one-way toll (1WT), and another in which users are charged for a two-way toll (2W). The report describes the methodology used to forecast traffic in both of these cases, assuming a certain diversion rate, traffic growth, and toll rate growth over time.

- Operations, Maintenance, and Major Maintenance Expenses

O&M and major maintenance costs are also taken from the draft HNTB study (summarized in the table on pages 22 and 23). O&M cost is broken out between general operations, tolling operations, and routine and major maintenance costs. The tolling operations cost is the only one that varies depending on the tolling scenario, with an annual tolling operations cost about 12% higher in the two-way tolling scenario than in the one-way tolling scenario. More information on O&M costs assumptions are provided in the HNTB study.

Table 6: TH 36 St Croix River Crossing Cash Flow Analysis Assumptions

| Description | Value |
| --- | --- |
| Debt Service Coverage | 1.5x |
| Interest Rate | 6.25% p.a. |
| Maturity | 40 years |
| Annual Traffic Increase | See HNTB study |
| Toll Rates | 1WT: $3.00 2WT: $1.50 per direction Variable tolling by vehicle type |
| Tolls Increase | 2.5% every year 5 cents increase per year for video patrons |
| Inflation Rate | See HNTB study |
| General Operations Annual O&M Costs (2015$) | $1.69 M |
| Toll Operations Annual O&M Cost (2015$) | 1WT: $2.31 M 2WT: $2.60 M |
| Annualized Routine and Major Maintenance Costs* | $2.15 M |

* Average of escalated costs from 2015 through 2055

Lowry Hill Tunnel (M14)

Given the limited amount of information available on the potential Lowry Hill Tunnel after expansion from 6 lanes to 8 lanes, the PB Team relied on the assumptions used for the St Croix River Bridge when applicable, as well as on its experience on other tunnel projects.

Assumptions that are identical to the St Croix River Bridge include financing, tolling equipment O&M cost and R&R expenditures, and toll rate scenarios.  The assumptions that are specific to the Lowry Hill Tunnel are described below:

- Toll Revenue

Current traffic congestion in the tunnel does not allow for traffic growth with existing tunnel configuration.  The analysis conservatively assumes 1% growth per year starting in year 3 after the implementation of the toll through year 40 with the new tunnel configuration with 8 lanes (increased from 6 currently).  Traffic growth in years 1 and 2 was assumed to be 4.0% to account for ramp up, as for the St Croix River Bridge.

- O&M and R&R Cost

Based on the PB Team’s experience with similar facilities, this analysis assumes an annual O&M and R&R cost of $17.5M (2010$) for the tunnel’s equipment (excluding tolling), facilities, and roadway.  This estimate includes electrical service power cost, lighting maintenance, staffing, special systems (CCTV, Radio, FA, SCADA, etc.), tunnel infrastructure and facility/equipment for O&M cost.  For R&R costs, this includes jet fans, signage, lighting, signals, call boxes, CCTV, smoke/CO monitors, fire main and connections, paving, wall panels/tiles and miscellaneous support equipment.

Table 7: Lowry Hill Tunnel Cash Flow Analysis Assumptions

| Description | Value |
| --- | --- |
| Debt Service Coverage | 1.5x |
| Interest Rate | 6.25% p.a. |
| Maturity | 40 years |
| Annual Traffic Increase | 4.00% in year 1 4.00% in year 2 1.0% in years 3 through 40 |
| Toll Rates | $1 or $2 toll rate per transaction |
| Tolls increase every | 10.0% every 5 years |
| Traffic Sensitivity for tolls | - For $1 toll rate, traffic decreases by 10% compared to a no toll scenario. - For 2$ toll rate, traffic goes down by 25% compared to a no toll scenario. |
| Inflation Rate | 3.0% p.a. |
| Annual O&M and R&R Costs | $17.5 M |
| Annual Tolling Equipment O&M Cost (2010$) | Fixed Cost: $8,258,000 Variable Costs: - $0.10 per transaction - 4.0% of gross revenues |
| Annualized Tolling Equipment R&R (2010$) | $1,250,000 |

# Cost Recovery Analysis Results

The assumptions presented above were integrated in a cash flow model, which calculates the present value of future net toll revenues (toll revenues minus O&M and R&R costs) after coverage over the next 20 years for MnPass projects and 40 years for the St Croix River Bridge and the Lowry Hill Tunnel.  This present value is then compared to the estimated project capital cost to derive an estimate of the bonding capacity.

Table 8 presents a summary of the key variables that drive the results of this analysis and shows the outcome in terms of percentage of capital cost that can be covered by issuing revenue-backed bonds.  This outcome is also displayed in Figure 5, which shows the percentage estimate of the capital cost that could be covered by revenue-backed bonds as a function of the project’s capital cost.

Table 8: Level 2 Cost Recovery Analysis Summary (Order-of-Magnitude, 2010$)

| Project ID | Project Name |  | Length (Miles) | Capital Cost | Annual O&M and R&R in 2010 | Annual Revenues in 2010 | Proceeds from Project Revenue Bonds | Pct. of Capital Cost Covered | Implementation Timeframe |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Individual Projects |  |  |  |  |  |  |  |  |  |
| M-11 (1WT) | TH-36 St. Croix River Crossing |  | 0.75 | $600M [3] | $4.2M [5] | $12.9M [6] | $199M | 33% | Short-term |
| M-11 (2WT) | TH-36 St. Croix River Crossing |  | 0.75 | $600M [3] | $4.4M [5] | $14.4M [6] | $226M | 38% | Short-term |
| M-14 ($1 toll) | I-94 Lowry Hill Tunnel |  | 1.0 | $2,000M [4] | $17.5M | $51.3M | $268M | 13% | Medium- to Long-term |
| M-14 ($2 toll) | I-94 Lowry Hill Tunnel |  | 1.0 | $2,000M [4] | $17.5M | $85.5M | $807M | 40% | Medium- to Long-term |
| Combined Projects |  |  |  |  |  |  |  |  |  |
| D3-4 / M-5 / M-10 [1] |  | Northwest Metro Corridor (I-94 / I-494 MnPass Lanes and TH 610) | 37.5 | $499M [2] | $11.1M | $10.9M | Revenues do not cover O&M and R&R costs | 0% | Medium-term |
| M-3 / M-6 |  | North Minneapolis / Central MnPass Lanes (I-35W / I-94) | 24.2 | $400M [2] | $4.2M | $10.4M | $30M | 7% | Medium-term |

Table Notes:

[1] Assumes that M-10 (Greenfield project) is not tolled

[2] Source:  “MnPass System Study Phase 2: Draft Final Report,” Cambridge Systematics, July 28, 2010.

[3] Source:  “Draft St Croix River Crossing Project: Innovative Financing Study,” HNTB, October 21, 2010. “1WT” stands for one-way tolling and “2WT” for two-way tolling.

[4] Source:  “Downtown Minneapolis Freeway Study,” Minnesota Department of Transport, May 2007

[5] Source: “Draft St Croix River Crossing Project: Innovative Financing Study,” HNTB, October 21, 2010. 2015 gross toll revenues deflated to 2010$ using 2.5% per year

[6] Source: “Draft St Croix River Crossing Project: Innovative Financing Study,” HNTB, October 21, 2010. 2015 total O&M costs deflated to 2010$ using 3.00% per year.

Figure 5: Percentage Estimate of Capital Cost Covered by Toll Revenue Bonds (Order-of-Magnitude)

Notes: For project M-11, “1WT” stands for one-way tolling and “2WT” for tow-way tolling.

As a first order-of-magnitude, a shown in Figure 5, none of the Level II revenue-generating projects can cover more than 40% of their initial capital cost after O&M and R&R:

- The revenue from the St-Croix River Crossing could generate revenue sufficient to cover its O&M and R&R costs and approximately 30% to 40% of its capital costs (with one-way or two way tolling, respectively)

- The Lowry Hill Tunnel could generate revenue sufficient to cover its O&M and R&R costs and approximately 13% of its capital costs with a $1 toll rate, and 40% with a $2 toll rate, and

- The MnPass Projects barely generate sufficient revenue to cover their O&M and R&R (although network synergies may improve revenue).  The Northwest Metro Corridor (I-94/I-494 MnPass Lanes and TH610) does not quite generate sufficient revenue to cover its capital costs through revenue bonds after O&M and R&R, while the North Minneapolis-Central MnPass Lanes             (I-35W/I-94) covers only a small portion of capital costs.

Therefore, any P3 delivery model involving private financing would necessarily require an availability payment or a shadow toll payment mechanism potentially combined with a direct subsidy in the form of construction payments.  Mn/DOT is likely to retain most of (if not all) of the revenue risk.  The wide range of results also highlights the needs for more in-depth studies to estimate costs and revenues.

Section 3.2 provides a qualitative assessment of the type of efficiencies that could be generated through a P3 procurement for such projects.  The extent to which a P3 procurement would be beneficial to Mn/DOT in terms of cost savings and project delivery acceleration would need to be assessed through in depth Value-for-Money (VfM) analyses for each project, as further described in Chapter 4.

# Review of Potential P3 Delivery Options and Efficiencies

The second part of the Level II assessment involves a qualitative review and discussion of the form of procurement models that could be envisioned for the Level II projects along with discussions of the types of risk transfers and sources of efficiencies that could be realized.  The discussions presented in this Section are based on interviews with industry participants from the private and public sectors and research conducted by the PB Team on project examples that offer similarities with the Mn/DOT projects reviewed.  This Section primarily focuses on non-revenue generating projects, although the MnPass projects, the St. Croix River Crossing and the Lowry Hill Tunnel are also briefly addressed.

# Pavement Preservation Program

Mn/DOT has been developing performance management tools since the early 1990s to prioritize capital investments and achieve performance targets for the Department’s highest priorities including safety, bridge and pavement preservation, mobility, and statewide system connectivity, among others.  Performance reports are issued regularly to the Department’s executive management and the Districts to measure progress and provide a basis for policy direction and accountability.

Several indices are used to measure and report pavement performance in Mn/DOT’s 20-year Transportation Plan, including the Ride Quality Index (RQI), a measure of pavement smoothness, and the Remaining Service Life (RSL), an estimate of the time until the pavement will reach the end of its design life and require major rehabilitation.  In addition, the Pavement Quality Index (PQI) is a composite index reflecting both pavement smoothness and cracking.  This index is used to determine if the state highway system is meeting performance thresholds established for the Government Accounting Standards Board, Standard 34 (GASB 34) and is linked to bond rating requirements.

Pavement quality and preservation have been and continue to be a high priority as well as a challenge for the Department.  Mn/DOT’s May 2009 Annual Transportation Performance Report indicates that pavement performance statewide is either moderately or significantly below target and that trends point toward steady deterioration.  While in 2000, 0.7 percent of the State Principal Arterial Highways were classified as having poor ride quality, this number rose to over 5 percent in 2009 and was predicted to increase to 5.9 percent by 2012.  Conditions on Non-Principal Arterial Highways are worse.  In 2000, 2.9 percent of the Non-Principal Arterial Highways were classified as having poor ride quality. By 2009, this had increased to 8.5 percent and is estimated to reach 11.5 percent by 2012.

Funding has increased in recent years for pavement preservation due to the Chapter 152 bonding package, reaching an anticipated average of $270 million per year from 2009 to 2012, together with an additional $183 million from the American Recovery and Reinvestment Act.  However, Mn/DOT estimates that an additional $175 million to $400 million per year will be required from 2014 to 2019 to reach pavement performance targets by the 2019 horizon.

The Department is actively reviewing options for new revenue sources and financing techniques for pavement preservation.  For this reason, together with the scale and focus of a Pavement Preservation Program, P3 procurement may be a suitable option for moving a program forward.

### P3 Models Used for Pavement Preservation

Several P3 procurement options for pavement preservation have been used in Europe and in the U.S., with or without private financing.  The examples below illustrate some of the characteristics of such agreements and their incentive structures.  Some elements of these programs could be considered as part of a DBFOM procurement for the Department’s pavement preservation needs.

U.K. P3 Pavement Preservation Experience

Private Finance Initiative (PFI)

Under the Private Finance Initiative (PFI), the U.K. has deployed concession-like P3 agreements for pavement preservation and street management.  The first example of such agreement is the 30-year, GBP 600 million DBFOM contract for the City of Portsmouth.  The goals of the project were to rehabilitate the City’s road network to bring it to its performance target and maintain it to that level over the contract term; implement an affordable, sustainable, and flexible maintenance regime based on “best value;” optimize lane availability; and improve safety.

The contract comprises two phases.  The first five-year period is intended to rehabilitate approximately 300 miles of principal, secondary and tertiary roadways (26% of which were in critical condition and 22% in failed conditions) and replace 7,400 light poles; the second twenty-five year period passes “fence-to-fence” responsibility for the management of the network to the private sector, including:

- Rehabilitation of structural pavement, bridges and other structures, curbs, street lighting

- Minor, routine and cyclical maintenance

- Repair of damages to the roadway assets

- Network management (i.e. inventory, data collection, performance evaluation, recommendations for improvement)

- Claims by third parties

- Winter maintenance and emergency response

- Traffic management

- Sweeping and cleaning

- Management of public utilities

The payment mechanism is based on availability and performance (90%) and usage payment based on truck volume (10%).  Specified performance standards are expressed through a network condition index (measuring pavement performance including skid resistance, surface condition, and structural condition) as well as operation and maintenance criteria.  Payments start immediately and increase as sections of the network meet the required performance criteria.  Deductions are incurred for non-performance based on pavement condition, street lighting, lane closures, and service points.  As is common in such contracts, the concessionaire is responsible for the performance measure and the results are verified by an independent third party.

This PFI contract offers a single point of contract for the City and eliminates numerous interfaces, thereby increasing cost effectiveness.  The availability payment also allows for certainty in cost budgeting and prioritization of maintenance resources for pavement preservation in the long-term, while the output-based payment mechanism ensures constant level of performance.   Under the PFI structure, more risks are transferred to the private sector, but the contract also offers greater latitude for the private partner in the choice of means and methods.  A long-term contract allows the concessionaire to find the balance between upfront capital investment and long-term maintenance costs, thereby creating strong incentives for technological innovation and life-cycle cost optimization.  The increased scrutiny brought to bear by private financing also contributes to cost and schedule efficiencies.

Considered an innovative project at its inception, the procurement timeline was quite long with the business case developed in 1999, pre-qualifications in 2001, preferred bidder in 2004 based on best-value selection, followed by financial close, and contract start January 2005.  The concession was won by “Ensign Highway,” a Special Purpose Vehicle owned by Colas Ltd. and Colas SA.

Since then, other municipalities have been  implementing similar contracts including the City of Birmingham PFI (which closed in 2010 on a GBP 2.7 billion PFI), the City of Sheffield (in procurement), the London Borough of Hounslow (in procurement), and the Isle of Wight (in prequalification stage).

Managing Agent Contracts (MACs)

The first type of P3 contracts used for pavement preservation in the U.K. was the asset management contract called Managing Agent Contract (MAC).  The Highway Agency has been using MACs since 1997 to manage their pavement needs for the 4,500 route mile Strategic Network (18,000 lane miles) in the 14 areas across its network.  MACs are five to seven year contracts with no private sector financing ranging from $45 million to $75 million.  Contracts awarded based on “best value” criteria with a heavy weighting on the pavement management experience of the contractor.

Services included in such contracts include network management, technical and engineering advisory services, design, and construction, as well as some elements on routine maintenance and operations (e.g. utility management, winter maintenance).  Depending on the contract, the asset under management could include a combination of roadway, curbs and bicycle paths, drainage, technology systems, earthworks, landscaping, fencing and guardrails, traffic signals, lighting, as well as structures.  The contracts are based on output specifications using key performance indicators (KPIs) and the Highways Agency benchmarks all contractors through publication of the KPI results.

These contracts are based on active network management in close collaboration with the Highway Agency covering the entire suite of roadway asset management services from asset inventory and data collection, performance evaluation, recommendations for improvements and capital budgeting, to execution of the work.  Efficiencies are generated primarily through the integration of services by removing interfaces (e.g. among design, construction, and maintenance activities), elimination of redundant tasks, and reduction of disputes.  MACs also provide a single point of contact for the client, improving the utilization of resources internally.  Although the contract encourages considering the maintenance impact of capital decisions, the shorter duration of the contract arguably does not provide strong incentives for life-cycle cost optimization and the risk transfers are limited.  Conversely, the relatively short duration of the contract provides greater opportunities for competition.  The apparent conflict of interest of the contractor, or Managing Agent, in fulfilling the consultant and contractor roles is mitigated through the collaborative decision-making process with the Highway Agency as well as the payment mechanism.

Additional incentives for higher efficiencies are also created through the payment mechanism, which comprises a mix of lump sum payments, target costs, and cost plus fixed fee based on a set of rate schedule and escalation clauses.  Under the target cost mechanism, cost variances to target are shared between the public and private partner, allowing for risk and reward sharing and incentivizing the Managing Agent to develop more accurate estimates and improve delivery.  The combination of lump sum payments and target costs also provide the client with increased certainty on budget.  MACs are now considered a standard form of contracting in the UK and have attracted firms with a strong track record in pavement management including Atkins, Colas, Halcrow, Jarvis, among others.

A recent UK National Audit Office (NAO) report provided a mixed evaluation of the MACs:

- MACs largely follow best practices and contain the mechanisms necessary to allow the Agency to manage risks and deliver efficiencies over time, including pricing mechanisms, risk allocation, output specifications, and good visibility on cost

- MACs do not include direct incentives for contractors to minimize whole life costs

- The average cost overrun on projects was reduced from 27% to 12%; however, there are some significant cost variations among the various MACs

- More projects were delivered on schedule

- Roadway conditions have remained sensibly constant

- Travel time reliability has increased, but more users are reporting delays, and around 40 percent of these are attributing those delays to roadwork

- The cost of routine maintenance has increased by 11% above inflation between 2002-03 and 2008-09, while the highway Agency’s own estimate indicates an increase of 17% above general price inflation between 2004-05 and 2008-09 (which NAO could not validate)

- NAO reports shortcomings in the Agency’s management of MAC contracts, which focuses too much on contract compliance, rather than on the cost and quality of the work done.

U.S. P3 Pavement Preservation Experience

Led by Florida, Virginia, and the District of Columbia, a growing number of State DOTs and local transportation authorities across the United States are entering into performance-based contracts with private highway operating companies to provide routine roadway maintenance services for large geographic areas or specific groups of highway facilities for periods of five to seven years.  Common characteristics of these agreements include:

- Long term, fixed price agreements:  Fixed price agreements transfer risk from the public sector to their private partners with the longer contract terms enabling private partners to manage risk over time and seek long term solutions rather than one off fixes

- Performance-based contracts:  Established goals and performance monitoring procedures and penalties and reward structures effecting payments to the private partner if their performance fails to meet or exceeds established standards

- Negotiated contracts:  Teams are selected based on qualifications and cost, with terms negotiated competitively; awards are not based on (initial) low bid.

The services included in these contracts vary based on the specific needs and capabilities of the sponsoring agencies.  Typical services oftentimes encompass routine maintenance of all roadways and structures, including bridges, overpasses, interchanges, ramps, signs, gantries, lights and light poles, and ramps within the highway right-of-way.  They may also extend to roadside rest areas, landscaping, traffic services, and incident management.  In addition, the private partner may also be responsible for performing regular inspections of bridges and other structures and perhaps most importantly overall management of all maintenance activities within the right-of-way.

In the private sector, roadway asset management and pavement preservation contracts are commonly used as part of P3 arrangements for highway facilities where strict performance-based specifications are tied to payment.  These subcontracts typically have longer terms (e.g., 15 years for SH 130 in Central Texas), which creates incentives for the private partner to make lifecycle costing decisions.

The U.S. experience indicates that there can be a great deal of flexibility in the scope of the actual maintenance activities that may be included in asset management contracts.  However the savings associated with the transfer of the maintenance of a roadway to a private sector operator are mostly derived from performing multiple tasks in a single location in a consolidated timeframe.  Private U.S. highway operators claim that it is possible to realize a savings in the 20 to 40 percent range if roadway maintenance activities were executed under private, performance-based contracts.

The U.S. experience also provides two broad models for the private sector to collaborate with public agencies in the maintenance of highway assets.  One is as an extension of staff where the private partner does not have a monetary interest in the outcome of its policy decisions but helps the public agency formulate strategic recommendations on the maintenance of its highway network.  This approach is akin to the alliancing model used in Australia, the U.K. and elsewhere.  The other is an at-risk approach using performance-based agreements that penalize private operators if outcomes do not meet established specifications or reward them when expectations are exceeded.

### Lessons Learned for Mn/DOT and Next Steps

Based on the sample P3 agreement structures presented above, the following conclusions can be drawn for the Mn/DOT Pavement Preservation Program to be advanced as a P3:

Types of P3 Arrangements

- Given the pavement preservation needs of the State, a potential P3 procurement structure for a program could take the form of a DBFOM with an initial pavement rehabilitation effort for critical sections of pavement followed by a long-term (20 to 30 years) maintenance program for these sections and other sections that are likely to reach lower performance levels over the course of the contract (similar to the experience in the City of Portsmouth).

- Other P3 procurement models have been implemented demonstrating that there a wide range of scope for the pavement preservation and maintenance activities that may be included in a P3 agreement to meet the objectives of sponsor. Various incentive structures can also be implemented to transfer various degrees of risks and create greater incentives for cost and schedule efficiencies.  The presence of private financing is not a pre-requisite to generate such efficiencies, but it can help drive additional efficiencies under certain circumstances.

Contract Scope

- The scope of the rehabilitation work would require careful definition.  With the current performance of pavement in the State, critical portions of the pavement could be considered for initial rehabilitation or replacement as part of a larger DBFOM contract structure.  Critical sections of pavement in need of such repair are unlikely to be continuous.  However, allocating long-term maintenance and rehabilitation responsibilities for certain sections to the same private contractor could offer a more cohesive (and attractive) contractual scope.

- The scope of the P3 agreement can be tailored to meet Mn/DOT’s pavement preservation needs.  Based on industry interviews, a broader scope allows for better use of resources and hence greater cost efficiency.  At a minimum, the technical scope should encompass all aspects of pavement preservation so as to ensure a clear delineation of responsibilities.  In defining the contractual scope, the transfer of a single activity such as pavement replacement would not achieve the same level of efficiencies as the bundling of multiple maintenance activities including for instance guardrail, traffic lights, street light maintenance, etc.

- The precise allocation of operation and maintenance activities between the Department and the private sector for such a program (as for any other P3 project) would require careful analysis and clear contractual language so as to limit interface risks.  For instance, in a concession framework for pavement preservation, snow and ice removal operations are likely to remain a Mn/DOT responsibility (as this is a core competency of the Department and for economies of scale reasons).  The exact nature of snow and ice removal operations performed by the Department would need to be specified into a potential concession contract so the private partner could plan its pavement maintenance program accordingly.

General Contract Terms

- The size of a P3 contract for pavement preservation is important and a larger contract (or contracts) is preferable to multiple, smaller contracts.  Larger contracts first offer greater economies of scale, particularly given the likely discontinuities in the rehabilitation needs as noted above.  They are also more likely to attract larger, domestic and international contractors (whether or not such contactors already has a presence in the State) with the level of skills required for managing the long-term pavement preservation needs of the program and the sophistication required to bring technological innovation and lifecycle cost savings.

- Longer contract terms covering several replacement cycles (i.e.  20 to 30 year horizon) are required to create true incentives for life-cycle cost optimization. When considering pavement preservation investment program and contracting options, the engineering analysis and Value-for-Money analysis (see Section 4.4) should cover the entire lifecycle of the asset.  Moreover, longer contract terms (encompassing at least two replacement cycles) are also preferable to realize P3 efficiencies and benefits.

- For a P3 for pavement preservation to work effectively, it must be based on performance specifications.  From discussion with industry stakeholders, the difficulty for public agencies to shift focus from design and construction to output specifications is one of the greatest impediments to the development of such contracts.  Mn/DOT’s established experience with pavement KPIs would greatly facilitate implementation.  Nonetheless, Mn/DOT would likely have to devote considerable effort to identifying the precise specifications they would need a potential private sector partner to meet.  The way performance is measured in other contracts (such as the examples presented in this Section) could help Mn/DOT in further developing its own performance framework for a potential P3.

Public and Industry Relations

- In the definition of the scope, consultation with public-sector and private-sector stakeholders will be essential, starting with early outreach with Department employees and unions (see Section 4.3).

- While the U.S. experience does not match with the pavement preservation program goals of Mn/DOT, the domestic experience with contracted highway maintenance and pavement preservation is nonetheless valuable for the Department.  First, it offers Mn/DOT the opportunity to open a dialogue with other DOTs and build on their experience with long-term, performance-based contracts.  Second, it demonstrates that a number of private sector companies have interest and expertise with such contracts.  Private sector interest was also evident through interviews conducted by the PB Team with industry stakeholders.

- For a program of this nature some significant lobbying efforts may be expected from different market participants.  It would therefore be instrumental to develop a strategy early on to cope with such pressure, limit its influence on the project definition and goals of the Department, and communicate with all industry participants from local material producers and paving companies, firms with broader pavement management experience and concession contract management experience (e.g. Colas, Transfield), heavy civil companies that routinely engage in concession contracting (e.g. Bechtel, Fluor, Skanska), and concession companies/operators (e.g. Abertis, Bouyggues, Brisa, Egis, Transurban).

- Winter maintenance is at the center of Mn/DOT’s pavement preservation efforts.  Most experience in the U.S. with contracted highway maintenance and pavement preservation is in milder climates.  However, traditional highway concessions in cold climate (such as Canada) demonstrate that the private sector has the capability to deploy lifecycle pavement preservation techniques in cold climates.

Next Steps

Next steps for Mn/DPT’s Pavement Preservation Program should include:

- Investigating and securing the sources of revenue required that can be leveraged to pay for the Program

- Building on existing pavement KPIs and domestic and international experience (including broader highway concession contracts) to develop a more comprehensive set of pavement performance metrics that could serve as a basis for output-based contracting

- Identifying the scope of the program including the critical sections of pavements that would need initial replacement or rehabilitation in the short-term and the sections that are likely to require major maintenance, replacement or rehabilitation in the longer term

- Developing pavement preservation investment strategies over a long time horizon (30 to 40 years or more) by testing scenarios such as no investment or suboptimal investment for an extended period of time (to assess the life-cycle cost of deferring investment), mix of rehabilitation and preservation strategies necessary to maintain a given level of performance, optimal performance level, etc.

- Investigating avenues to increase the attractiveness of the program including opportunities such as utility rights or land and air development rights

- Developing a comprehensive Value-for-Money (VfM) analysis for the program; the above analyses of program scope and investment strategies would be part of a VfM analysis (see Section 4.4).

# Chapter 152 Bridge Program

Enacted in 2008, Minnesota’s chapter 152 bridge improvement program is a 10-year, legislatively mandated effort to rehabilitate or replace structurally deficient bridges across the state.  The program has dedicated funding comprised of $1.2 billion in bridge and other non-directed bonds, together with $1.3 billion from Mn/DOT’s State Road Construction Budget.  The Chapter 152 program includes 172 bridges that will require replacement, renovation or rehabilitation following a three-tier prioritization system based on such criteria as: functional obsolescence, structural deficiency, fracture criticality or average daily traffic.

The legislation requires that all work on Tiers 1 and 2 bridges – a group comprising 161 of the 172 Chapter 152 bridges – be completed by June 30, 2018.  Excluding the projects that are expected to be substantially complete by the end of 2010, the program capital cost for tiers 1 and 2 is estimated to range from $2.2 to $2.7 billion.  This includes several large bridge replacement projects such as: (1) the St Croix River bridge on Hwy 36 in the Metro area ($600 million) scheduled to be replaced between 2014 and 2018, (2) the Hwy 63 bridge over the Mississippi river and CP Rail in Red Wings (District 6) ($286 to $383 million) scheduled to be replaced in 2018, and (3) the Highway 43 bridge over the Mississippi river, railroad, streets in Winona (District 6) ($276 to $374 million) scheduled to be replaced in 2016.

The Chapter 152 Bridge program is being procured on an accelerated primarily design-bid-build (DBB) basis.  Two-thirds of the $2.5 billion program is supporting the restoration or reconstruction of major bridges and at least half of that work will be completed by the end of 2012.  Work on smaller bridges will also be underway in the next two years.  Given the advanced state of the delivery of the Chapter 152 Program, the use of P3s at this juncture would not be beneficial and could even delay the completion of the program because of the time that would be needed to issue P3 procurements.  There is approximately $150 million worth of work in the Chapter 152 Program for smaller bridges that will not begin in the next two years.  Most of these bridges are in the Metro District, as well as Districts 1, 6, and 8.  However, due to the limited cost of these improvements, even if they were bundled together in a single P3 procurement they would not meet the $250 million threshold for bridge P3 projects.

While P3s are not a viable procurement option for the Chapter 152 program in the near term, there may be potential benefit in using P3s for the rehabilitation or replacement of other bridges not currently included in the Chapter 152 program.  This would be particularly true for work on smaller bridges that could be implemented quickly without stand-alone environmental analyses.  The potential for efficiency gains could be further enhanced by bundling a large number of small bridges with similar designs into a P3 procurement, thereby incentivizing the private partner to utilize standardized designs and construction materials to compete the work.

This approach has been used on large bridge rehabilitation programs in Canada, Europe, Australia and New Zealand, as well as the Safe and Sound Bridge Program in Missouri.  Based on the Safe and Sound Bridge Program, North Carolina DOT plans to implement a similar program.  The following Section provides additional information on the Safe and Sound Bridge Program and is intended to illustrate how a similar approach could be structured in Minnesota.

### U.S. Experience with P3s for Bridge Programs: Missouri Safe and Sound Bridge Program

Prior to implementing the Safe and Sound procurement, the Missouri Department of Transportation (MoDOT) established a task force to research similar asset rehabilitation programs – including the MAC contracts in the U.K. – and make recommendations on how a P3 approach could be used in Missouri.  This process took nine months, during which time the task force became familiar with the DBFOM contracting model, the types of projects that would lend themselves best to the program, and strategies for including life-cycle costing considerations into the contract.  In the end, the task force identified a total of 802 bridges to include in the Safe and Sound Bridge Program.  After careful study, the task force removed larger bridges from the program, limiting the program to smaller bridges less than 1000 feet in length.  Most of these are located in rural areas and none of the work required any environmental approvals.  Four hundred of the bridges have similar structures with the same pile foundations.

In addition to identifying which bridges to include in the program, the task force also reviewed the design standards to be used for the program.  Normally, MoDOT uses established design standards for bridge work.  However, in order to maximize the cost savings potential of the Safe and Sound Bridge program, MoDOT held confidential sessions with potential private-sector partners to identify “additional applicable standards” for the bridge program.  This process led to such innovations as the use of adjacent girders – a first in Missouri – as well as design exceptions, some involving clearance heights.

After reviewing the condition of the bridges the task force recommended rehabilitating 248 of them.  MoDOT put these project bids in groups based on location, type or repair work, or project size using a modified design-bid-build approach to expedite completion.  The remaining 554 bridges in the program needed to be replaced entirely.  Initial plans called for the replacement bridges to be let on a DBFOM basis, with the private partner leveraging availability payments received from the state.  The procurement was implemented as a two-step process overseen by the MoDOT task force.  A request for Expressions of Interest was issued in September 2007, with submittals received in October and a shortlist issued in November and an expectation that an award would be made in the May-June 2008 timeframe.

When the bids were received, MoDOT’s Value-for-Money calculations indicated that it would be difficult to transfer risk in Missouri, because as more risk was transferred the cost of obtaining financing went up.   MoDOT and the private sector also likely had different perspectives on risk, resulting in the spread in prices.  Due to this dynamic, MoDOT found that there was no cost savings with a 25-year DBFOM transaction due to the higher cost of money, driven in part by the fact that there were no precedents for this type of transaction in the United States.

As a result of the high cost of the DBFOM structure utilizing availability payments, MoDOT restructured the replacement bridge as a Design-Build procurement with a one-year warranty period.  Such a short-term warranty offers limited value. The $487 million design-build contract was awarded to KTU, led by Kiewit, Traylor Bros and United Contractors, all of which are large firms with a national presence.  However, MoDOT officials report that the majority of the work has been subcontracted to local contractors.

MoDOT’s emphasis with the re-procurement was on accelerating of construction timeframes to minimize disruptions and exposure to inflation.  In the past, typical small bridge reconstruction projects took anywhere from 90 to 120 days.  However, the Safe and Sound replacement projects are now averaging 45 days.  This time savings has been facilitated by the fact that most of the bridges involved in the programs are on rural roads, allowing them to be closed all together during the construction period.

### Lessons Learned for Mn/DOT

The experience with the Safe and Sound Bridge program offers Mn/DOT with a number of lessons learned:

- The bundling of multiple bridge replacement projects in a large single contract can generate similar savings and efficiencies in terms of schedule acceleration and cost reduction as those described above for the pavement rehabilitation program.

- Given the longer expectancy of bridges and the ability to specify structural performance over time, the use of a P3 approach with a bridge program may provide better opportunities to capture life cycle costs savings when compared to pavement rehabilitation programs.

- It is not necessary to require a P3 project to include private financing in order to derive life-cycle, cost reduction or schedule acceleration efficiencies.

- There may be greater programmatic benefits from including shorter, more standard bridges in a large rehabilitation program when compared to longer, more complex bridges, which are usually better procured on a standalone basis.

# Managed Lanes Program

Priced managed lanes, known in Minnesota as MnPass Lanes, exist on I-394 and I-35W as High Occupancy Toll (HOT) lanes, where those who drive alone pay a toll to access the facilities and those who carpool receive access without paying a toll.  Although the current facilities have the established preferential treatment for HOV’s, two recent efforts by Mn/DOT and the Metropolitan Council both indicate that this preferential treatment may not be the chosen policy for future MnPass Lanes.  Indeed, the Mn/DOT study indicated that all vehicles except buses would be tolled.  From a P3 perspective, this policy choice increases the revenue potential, reduces enforcement costs (as mandatory transponder requirements could accompany automated license plate-based violation enforcement systems), and decreases the overall revenue risk to both the public and private sector partners.

The Level II screening analysis includes two groups of priced managed lane projects.  These groups combine Level I projects that serve as connected components of localized managed lane systems.  Taken together, these two groups (and the two existing facilities) comprise a regional network of priced managed lanes that may be attractive for P3 consideration due to synergistic relationships from one toll facility to another.  Furthermore, the groups of projects meet the screening criteria of large cost ($400M or more), revenue generation, and critical need.  The selected groups of priced managed lane projects are (see Figure 4):

- The Northwest Metro Corridor combining MnPass Lanes on I-94 and I-494 (extending to Monticello) with improvements on TH 610

- The North Minneapolis and Central Managed Lanes combining I-35W and I-94

Additionally, the proposed managed lanes on I-494 (Bloomington / Airport area) could also be considered as a long-term P3 candidate.  The selected two groups of projects have right-of-way, bridges, and natural and urban barriers that make widening to full design standards extremely difficult or cost prohibitive.  As a result, both studies envisioned a network built upon an aggressive deployment of Active Traffic Management (ATM) to complement the use of shoulder lanes for managed lane capacity expansion, notably connector and ramp metering, lane control signals, queue warning, and speed harmonization.  As applied on I-35W, for new priced managed lanes, the right side shoulder would be permanently converted to a general-purpose lane, with ramps realigned to meet the shoulder treatment.  The inside shoulder would be expanded to 14 feet, with use allowed for eligible traffic during peak periods, reverting to breakdown / refuge only in off-peak periods.  ATM would be used to manage flows, and provide warnings of downstream incidents.  Additionally, emergency refuge areas are constructed every ¼ mile whenever an interchange is not available downstream.

From a P3 perspective, this design preference has four important implications:

- The preference for shoulder lane adaptations reduces the pavement footprint for constructing new priced managed lanes.  Without the acquisition of new right of way to accommodate the facilities, the environmental approval process may be streamlined, reducing uncertainty in the pursuit of the project, as well as the capital cost of the project.  This may be a favorable outcome for P3 considerations.

- The reversion of shoulder lanes to breakdown lane use only in off-peak periods may diminish the revenue generation potential.  However, this reversion would occur only outside congested periods of the day.  Hence the “loss revenue” associated with the free usage of the facility during the off peak period may be limited.  Nonetheless, this has a negative impact to the overall revenue generation of the lanes.  Additionally, revenue risks are perceived to be greater for managed lane projects than other toll facilities as demand for the priced capacity is more difficult to estimate.

- There may be additional risks incurred by the P3 partner on the new priced managed lanes.  This risk primarily stems from the use of shoulder lanes.  Preferred FHWA design standards involve separation of managed lanes from general purpose lanes, and, full shoulders on the right side of the facility.  Under the preferred design for new MnPass lanes, shoulders may not be available and separation may be striped for continuous access (as currently done on I-35W).  Although ATM would be used to mitigate safety concerns, the liability implications for the private partner would require legal opinion.

- The implementation of ATM provides another opportunity for P3 partnership.  DBFOM opportunities in Minnesota may not only extend to the implementation and operation of the managed lanes itself (including toll collection), but also to the operations of the ATM system that accompanies the managed lanes.  An ATM system already operated under P3 agreements in the U.K. and elsewhere, provides an opportunity to manage all lanes of traffic in a corridor, not just the managed lanes.  As a result, this requires staff and financial resources that may extend beyond the current capacity of Mn/DOT.  A P3 partner could enhance the provision of these services.  Inclusion of the ATM system would also help alleviate the interface risk in operation between the priced capacity and the free capacity.

As for any other P3 project, a potential DBFOM for managed lane projects would need to provide for a careful definition of the allocation of risks and responsibilities between the public sponsor and the potential private partner.  In particular, traffic management responsibilities would be central to the contract.

The public sponsor however does not have to relinquish control on the toll policy.  A concession based on availability payment (such as the I-595 Corridor Improvement Project in Florida would allow the public sponsor to retain control on tolls if this is a policy objective.  Although it has never been applied in practice, shadow tolls (encouraging higher usage of the facility) combined with real tolls (to manage congestion) is also, at least in theory, possible.

Examples of managed lane P3 projects also include the IH 635 Managed Lanes in Dallas County, Texas and SR-91 Express Lanes in Orange County, California, among others.

# Interstate Truck Havens & Commercialized Rest Areas

Except where located on interstate toll roads or on roads pre-dating the Interstate Highway System (1956), rest areas with direct access from Interstate highways are prohibited from providing commercial services, other than vending, to the motoring public (23 USC 111).The rationale behind this policy is grounded in safety concerns on the Interstate Highway system and the desire to protect local businesses providing these types of services in local communities.

As a result of the prohibition, a large number of private truck stops are operated around the country off of the Interstate Highway right-of-way where traffic volumes are adequate to support such facilities.  They are generally located on inexpensive land, where zoning permits such facilities, where site conditions support water and wastewater services and that is convenient to Interstate interchanges.  They provide a variety of services and other amenities, many geared toward commercial truck drivers but also attractive to auto drivers.  Truck drivers indicate in studies that they are likely to choose a truck stop plaza to rest when they expect to stay for two or more hours to take advantage of the amenities offered.  Highly desired amenities include a well-lighted and secure parking facility, restrooms, private showers, restaurants, prepaid fuel card acceptance, truck repair facilities, entertainment facilities, travel information, and Internet connections.

Rest area procurements under concession models have been successfully implemented in the U.S. where federal regulations do not prohibit commercial activities within the Interstate right of way, mostly in States that benefit from legacy rest areas in the Northeast and parts of the Midwest (e.g. Delaware, Illinois, and Massachusetts).  Similar to other types of P3s, the scope and size of the contract is important and rest areas concessions have been granted on highly traveled corridors for large facilities (e.g. the 35-year concession recently awarded to HMSHost Corporation for the $35 million, 42,000-square foot welcome center on Interstate 95 in Delaware) or for a series of facilities ranging from a half dozen to a dozen or more facilities (e.g. Massachusetts, New Jersey, Maryland and Illinois) offering economies of scale.  Such projects have the potential to be self-financing, generate additional revenues for the State, and create jobs.  With the nature of these developments more akin to land development than traditional transportation project, the potential private partners for such concessions are more likely to be specialized developers and companies running commercial concessions that provide food, beverage and retail services.  Developers such as Petro, Pilot, or Love’s, among others, specialize in the facilities catering primarily to truck drivers.

Due to the prohibition of commercial activities, Minnesota currently has no commercial rest areas. Mn/DOT however, is investigating the viability of public-private and public-public partnerships to develop facilities serving truckers, nicknamed Truck Havens. The investigation will place an emphasis on sections of the Interstate system where truck volumes are too low to support the development of private truck stop operations.  The lack of adequate truck rest stop areas in these corridors poses a safety concern. A Mn/DOT study found that spacing rest areas at 30 miles or less on the Interstate system in Minnesota would reduce drowsy driving-related crashes.  In addition, rest areas provide truck drivers the opportunity to rest to meet their service limits. The lower volumes on these corridors, however, make the development of a commercial operation by the private sector unlikely, unless the State could participate in the development through public-private partnership.

The State could partner with the private sector in various ways by purchasing land on which the Truck Haven facility could be built and offering a lease agreement to a private partner to develop, finance, operate and maintain the facility as well as participating in the development cost of the facility and supporting infrastructure. The type of commercial arrangements between the State and the private partner would depend on the economics of the project; in a corridor with lower volumes, it is likely that the State would have to share in the development costs and/or make payments to the operating partner.  At the end of the lease term the State could, after confirming the continuing need for the facility, re-advertise the lease opportunity to interested parties.  Depending on the facility condition, some capital investment may be needed at the time a new lease is executed.

The Truck Havens that Mn/DOT is exploring could be built on land adjacent to the right-of-way at Interstate interchanges.  If the project were located within three miles of the interchange, the project could benefit from the branding recognition associated with Interstate Oasis Program providing unique signage on the Interstate for facilities that offer rest rooms, parking for automobiles and heavy trucks, and are staffed 24 hours a day.

Mn/DOT expects to explore various partnership models to address safety and commercial freight movements, including models such as DBFOM and DBOM concession agreements.  The nature of these developments also enables the use of innovative public finance mechanisms such as tax increment finance, assessment revenue bonds, and certificate of participation.

While Mn/DOT is only considering the development of a single Truck Haven facility at this time, bundling several faculties into a single procurement could help improve the economics of Truck Haven development in lower-volume corridors currently considered by Mn/DOT.

Other states such as Georgia are currently looking for efficiencies in the operations of their existing, non-commercial rest areas and welcome centers by investigating potential partnerships for the operations and maintenance of their facilities along with advertizing and sponsorship rights.  In the mid-2000s, Mn/DOT had explored the viability of a similar public-private partnership that would have added advertising within rest areas and rest area sponsorship.  The FHWA however, restricted the placement of rest area sponsorship signs to the rest area grounds and prohibited sponsorship sign placement along the Interstate.  This determination proved fatal to the business model proposed by Mn/DOT and bid upon by a private party.  Similar efforts are coming as States officials in New Mexico, Arizona, Louisiana and Virginia, are considering closing roadside rest stops to reduce operating costs.

# St. Croix River Crossing and Lowry Hill Tunnel

The St. Croix River Crossing (M-11) and Lowry Hill Tunnel (M-14) could be delivered under a traditional concession-like structure.  Based on the results presented in Section 3.1.2 (Figure 5), the Lowry Hill Tunnel could generate sufficient revenue to cover up to 40% of its capital costs after O&M and R&R and the St. Croix River Crossing between 30% and 40% of its capital costs.  At this early stage in the project development cycle, the Lowry Hill Tunnel could be a good candidate for a Pre-Development Agreement.  Tunnel projects of this type, complexity and magnitude are likely to attract strong domestic and international completion for a P3.

Given the limited financing capacity of the projects, they would likely work best as pure availability payment concessions (with or without construction payment).  The information reviewed at this stage is not sufficient to provide further guidance as to the exact allocation of risk and responsibility for these projects under P3 procurement, which would have to be determined though further planning and engineering work and a full VfM analysis.

Domestic and international examples of P3 procurements for bridges and tunnels are numerous, because such projects generally offer more stable and profitable cash flows stemming from a quasi-monopoly position.  Examples include the Cross City Tunnel Project in Sydney, Australia, the Limerick Tunnel in Ireland, the A25 Bridge in Quebec, and the Golden Ears Bridge in British Columbia, among many others.

# Strategic Guidance for Mn/DOT P3 Program

In order for its P3 program to be successful, MnDOT must incorporate a number of new elements into its overall project delivery process.  Although the screening and assessment of projects is essential, it is only the first step in a long list of tasks required to achieve eventually successful financial close of a P3 transaction.  Figure 6 illustrates the major steps in this process, highlighting the shift in paradigm for a DOT delivering P3 projects, shifting from the traditional design and construction functions to value and performance assessment, and contract management and oversight.

Figure 6: P3 Procurement Process Overview

In order for the identified P3 project candidates to move along to execution, the activities related to program framework need to be completed.  In particular, defining the legal, contractual and procurement framework for the P3 program needs to be completed before any project enters the procurement phase.  Similarly, no project should be advanced as a P3 without a comprehensive Value-for-Money analysis.

In addition, the ability of Mn/DOT to marshal the internal and external resources to manage both the process and the projects needs to be affirmed.  Private bidders are particularly wary of committing time and resources toward nascent P3 efforts unless they can get comfortable that their efforts will result in successful transactions.

Each of these major steps is more fully described below.  Additional project-specific next steps are presented in Chapter 3.

# Legislative Strategy

The passage of legislative authority for P3s has taken many different routes and forms in various States.  For example, in California and Georgia significant P3 legislative authority was finally adopted in 2009/2010, after many years of failed attempts.  In fact, California had been a leader among states in P3 legislation in the late 1980s and early 1990s with legislation AB 680 under which the SR125 and SR91 were developed, but had fallen behind the curve since then.  Failed legislative strategies have been traced back to, among others, (1) unfamiliarity with the concept (i.e. lack of education of the legislative bodies), (2) general skepticism about tolling, (3) opposition of public employee unions, and (4) uneven playing field for private competitors.

The necessary components of such legislation include:

- Clear authorization to lease or transfer assets and operating responsibilities to private entities

- Ability to enter into long-term binding agreements for financial support

- Authorization to award contracts on a best value basis (and competitive negotiations if so desired)

- Authorization to compensate the private partner using availability payments and clarity regarding the associated enabling appropriation mechanisms

- Clarity as to the authority of the private partner to impose user fees and determine the amount of those fees

- Clear definition of the process to be followed, including Request for Qualification, Request for Proposals, public hearings, and required legislative and administrative approvals and timelines

- Clarity on the tax treatment (tax treatment of the P3 transaction, sales tax on tolls, property interest taxes, etc.)

- Clarity regarding home rule (i.e. ability of local government to take action against the project).

To the extent that the Department already has certain of these authorities, the legislation can focus more on the process issues, but a comprehensive, publicly-debated and well-publicized package of P3 legislation builds a very strong foundation for a program of projects.

To begin this effort, it is advisable to identify one project to “showcase” and use to spearhead a more detailed program of projects to follow.  Legislators and constituents alike often find abstract discussion of public versus private pros and cons difficult to follow, at best.  Framing that discussion in light of one project’s costs, risks and timeline can far better illustrate the benefits of the P3 approach and can serve to educate all involved about the types of P3s and their appropriate uses.  In addition, having a real project to talk about will assure that the national and international players in the P3 market will pay attention to the legislative debate, and provide input as appropriate.

The work undertaken to date by the PB Team indicates that the group of projects including the St. Croix River Crossing, the Pavement Preservation Program, projects within the MnPass program, and the Lowry Hill Tunnel might be well suited for this initial foray into the markets.  These projects are all critical projects, aligned with the top priorities of the Department (and most are revenue-generating projects), which make them better candidates for communicating the Value-for-Money proposal.  However, a full Value-for-Money (VfM) analysis (see Section 4.4) must be undertaken before moving any of these projects forward.  We recommend that initial conversations with legislative leaders and committee staff begin as soon as the Department has decided to move forward one or two of these projects as possible P3 candidates.

# Organizational and Institutional Capabilities

In order to develop fully a P3 program, the institutional capacity of the State must be built through a combination of in-house expertise and specialized consultants and supported by political leadership (i.e. the program needs a political “champion”) to:

- Ensure that the State is effectively represented through the procurement and negotiations

- Provide the general public the confidence that the public interest is protected and that P3 agreements are not “giveaways” to the private sector or will result in “excessive” user fees

- Provide a long-term source of information and advocacy for the program

- Communicate to the private sector that the State is committed to the program, and

- Provide appropriate levels of oversight.

As pointed out earlier, delivering P3 projects represent a paradigm shift for a DOT from designing and constructing projects to setting value and performance standards and managing and overseeing contracts.  Such a change in the traditional delivery functions of a DOT requires building up new capabilities and reorganizing existing capabilities to focus on delivering services as opposed to building projects.

As good as the Department may be in planning and executing projects in the traditional design-build-build (DBB) arena, its experience in alternate project delivery methods is likely to be far more limited, scattered throughout many different divisions and offices, and often invisible to headquarters staff.  A first step in assessing the capabilities of the Department is to inventory what has been done, and by whom, either as DOT staff or in previous employments.

Although design-build is not a fully integrated P3 delivery method, it is nonetheless closer in approach than DBB and an essential building block of DBFOM contracts, so the existing experience of the Department in procuring, negotiating, managing and overseeing DB projects will serve as a solid basis to structure and transfer risks and develop oversight procedures.  As pointed out in Section 3.2.1, the Department’s experience with pavement performance KPIs will also be an excellent first step towards developing the required performance objectives of the highway projects in the P3 program.

Once that initial inventory is completed, a more strategic assessment of those resources arrayed against the skills needed to develop and manage the P3 program is in order.  Our experience has certainly shown us that few, if any, DOTs start their P3 programs with a fully staffed, experienced group, particularly given the recent history of budget shortfalls and senior staff retirements.  Attitude and willingness to innovate is as important in building P3 capabilities as experience; pairing internal staff with hands-on external consultants who will develop staff as well as the program is a proven winning combination.  The skills required can be broadly divided by project phases:  Project scope definition and development, procurement preparation, running the competitive procurement process, construction oversight, operations oversight, and contract management.

- Project Scope Definition and Development : The scope of an appropriate P3 project may well differ from that of a traditionally procured project, as it is often shaped by policy and legal factors, political considerations, market interests, risk transfer goals, and funding requirements.  At this early stage of P3 consideration, the P3 Program Management team needs to be broadly versed in all of these considerations, and not just in the technical elements of the project as would be typical.  It may well be that more senior management attention than would usually be directed to a project in the early stages of development is required to add these perspectives as well.  Organizationally, separating the P3 Program Management team from the decision-makers as might be typical for normal programmatic projects may not be the best approach to ensure that the P3 project fully reflects all of the issues of this type of project delivery.

- Procurement Preparation:  Undertaking the first few P3 projects will mean breaking new ground in internal procedures, in legal documentation, and in contractor/partner selection.  In order to achieve success, the procurement team will have to be willing to adopt new methods and approaches that are within the legal boundaries but that may well be beyond what has been done in the past administratively.  Creativity, willingness to explore new ways of doing things, and strong understanding of the legal envelope are only some of the skills required.  As will be discussed below, even the technical side of the bid preparation will change, from one that often was specification focused to one more directed to achieving mandated performance levels.

- Procurement Process and Selection:  Running a P3 process is a juggling act, as oftentimes several negotiations are taking place simultaneously in order to create a final bid package all can agree to.  Typically, legal counsel is far more involved than in a traditional state procurement, and the finance staff is at the table with a loud say as well.  Decisions need to be made quickly, and iterations of documents are required in hours not weeks.  The pace is fast, and the stakes high.  And all of it must be done legally and in accordance with public disclosure requirements.  Selection criteria look very different than in a DBB, as the finance and performance aspects take on far greater importance.  The P3 Program Management team needs to be cohesive, quick-thinking, and able to represent the State’s interest against large, multi-national and well-experienced proposers.

- Construction Oversight:  The traditional role of construction management falls to the P3 proposer under a P3, with the State’s role being to audit for compliance with contract terms, rather than the details and means and methods of the actual work.  This may be the area in which the largest paradigm shift occurs and where the Department can increase its risk exposure inadvertently if it becomes too involved in construction decisions and tries to override or second-guess the contractor’s decisions.  The classic example of the shift in perspective is that of testing concrete:  under a DBB, the State tests all the mixes and pours; under a DB, the State audits the testing done by the contractor and approves them.  Under a full P3, the State reads the audit reports done by the contractor or an Independent Engineer to ensure that all of the contractual tests have been done, and approves nothing but notes non-compliance.

- Operations Oversight:  Similar to construction oversight, the role shifts from hands-on, day-to-day running of operations to contract management for compliance.  In order for the oversight to be effective, the original contract must include output-based performance standards that can be readily measured, with penalties for failing to meet them.  How the contract standards are enforced needs to be part of the upfront documentation, and this role then again becomes one of reading and checking measurements rather than field supervision. This role also covers the oversight of the pricing policy for projects with user fees.

- Contract Management:  Like in most DB projects, the contractor will have committed to a not-to-exceed price for a given scope.  The game will always be to push for scope changes to increase pricing (and profit), so it is incumbent on the Department to ensure that the original scope is adequate for the work to be done, and that it is vigilant in monitoring any requested changes.  Particularly when the P3 involves operation and long-term maintenance, ensuring that all contracted work is performed and completed during construction and that all promised services are delivered takes on more of an audit/compliance tone than in a traditional contract as non-performance with contract terms often results in penalties being assessed against the private partner.

For each phase of the work, creating a delineation of the type of skills and experience required and then comparing it against available resources will help evaluate the gaps that need to be filled by either new hires or external sources.

A fundamental decision the Department will undoubtedly struggle with is that of centralization or distribution of these resources at the District level, once identified.  If the P3 program is going to be small and highly focused, then it makes sense to establish a small core group of expertise, place it in a highly visible part of the organization with close access to senior decision-makers both in the Department and the State as whole, and transfer front-end project responsibility to it.  As the program grows, or if it starts off with a broad slate of projects or statewide programs, it may be appropriate to keep the headquarters group as a clearinghouse, but transfer some responsibilities to the Districts.  Given the impact on employees in either case, this decision is best made with strategic input from external advisors who have seen both structures and understand the implications of each in the Mn/DOT context.

# Public Outreach Program

When asked about the primary reason for success or failure for a P3 project, government and private sector executives almost unanimously cite public outreach as the number one factor.  Whether the public was informed and understood the issues and the benefits, had the opportunity to participate in the debate, are all key success factors.

The outreach needs to be focused on key constituencies who have an interest in transportation improvements.  The policy makers (particularly at the beginning of the process), the general business community and its associations (e.g. chambers of commerce, regional employers), design and construction industry (e.g. contractors, construction trade unions, material suppliers, engineers, etc.), local transportation project sponsors, counties and municipalities, public employee unions, environmental groups and modal advocates are all among the potential stakeholders.  The outreach efforts must also encompass the general public, particularly when tolling is part of the discussion, and the distinction between tolling and private-sector participation must be made clear.

Communicating with the private sector in a P3 environment takes another dimension as it reaches industry participants not just within the State, but also nationally and internationally.  Such outreach towards potential bidders must clearly communicate the procurement process and provide reassurance that the State is committed to this process once the project is moved forward.

To generate support for initiating a P3 program, the key question that needs to be asked and answered is: Why consider P3s, instead of using conventional methods to deliver infrastructure?

Typically, the answers revolve around the benefits with respect to schedule, cost and risk.  These must be articulated, quantified, and documented, so that the natural skepticism that greets a change from business-as-usual can be overcome.  Another point that must constantly be made (within and outside the Department) is that P3 is just an additional tool in the public policy “toolbox”— it does not fit every project as the screening assessment demonstrates – and that the Department is driving the process.  But if enough stakeholders with diverse interests perceive P3 as a potential way to achieve their goals, then a critical mass of support can form.  As for the legislative strategy, articulating the answer to this question within the context of a particular project is much easier than doing so in general terms.

Finally, the role of leadership cannot be overlooked.  In most cases where P3 programs or projects have been instituted, there has been a leader or “champion” who made it a high priority.  In some cases, it has been a Governor, but sometimes even a mayor or State legislator who had a project in his/her jurisdiction that would otherwise languish, but has a chance for implementation — if P3 became an option.

# Value-for-Money Analysis

While the initial decision to invest in a public transportation infrastructure relies primarily on the evaluation of socio-economic public benefits and costs (e.g. congestion, air quality, employment, etc.), once this decision is made, public sector sponsors focus their effort on choosing a delivery and financing method that will ensure that users and taxpayers maximize the risk-adjusted return on their investment.  This is a financing decision that relies on the analysis of risk-adjusted cash flows to the public sponsor, and it excludes those non-cash economic benefits and costs that cannot be captured into quantifiable project-level inputs.

Although Value-for-Money (VfM) can be a useful tool to compare alternative approaches, it is not without its critics and difficulties, and is most effective at a point in time when the project is fully developed and all of its risks and costs identified.

The starting point of the VfM evaluation process is the development of a realistic public-sector base case for the project, referred to as the “Public Sector Comparator” (PSC).  The PSC aims to replicate the likely financial outcome of a traditional procurement process with public provision of operation and maintenance services.  It estimates the hypothetical, risk-adjusted, life-cycle cost if the project were to be funded, financed, built, operated, and maintained by the public sponsor.  The PSC establishes a benchmark for comparing the most efficient traditional form of public-sector procurement and public-sector provision of operation and maintenance services with the estimated likely private-sector bids under the risk-appropriate P3 delivery option such as DBFOM.  For the PSC to be realistic, it should represent the actual experience of the public sponsor in delivering projects, since the costs to be used should be reflective of final, as-built numbers and not engineering estimates.  This means that the PSC needs to reflect the risks of contract change orders, cost overruns, and schedule delays associated with the type of project and delivery method selected.

In order to compare two very different procurement approaches, the probable outcome of a private bid for the project under a given delivery method needs to be estimated.  The financial model designed to replicate this probable outcome is generally referred to as a “shadow bid.” The first step in developing a shadow bid is for the public sponsor to decide on a preliminary risk allocation (and mitigation) strategy to allocate risks and responsibilities between public-sector and private-sector partners to the parties that are best able to manage them.  The allocation of risks to the private sector that it cannot efficiently manage (e.g. environmental approval process) would be priced and result in lower value.  The shadow bid model must be derived from the analyst’s knowledge of the private sector entity likely to propose and deliver such project, current market conditions, and cost of risk transfers.  It should reflect schedule acceleration, life cycle cost decisions, and efficiencies generally allocable to private development and construction and, if appropriate, operation.

Design, procurement and construction costs, operation and routine maintenance costs, and rehabilitation costs must be estimated for the PSC and the shadow bid considering the specific risks and constraints of the project.  Risk analyses, using numerical simulations such as Monte Carlo, are often used and required.

The net present value of the risk-adjusted, life-cycle, public-sector procurement cost (i.e. the PSC) is then compared with the net present value of the likely private bid under the P3 option (i.e. the shadow bid).

While the VfM analysis provides a likely estimate of the value generated under a given procurement method, actually achieving this return on investment for the public sponsor under a P3 further requires sound procurement and management practices including, among others:

- The procurement process must guarantee a fair treatment of the competitors and transparent competition among bidders

- Value for money must be confirmed prior to award with actual bids received though competitive procurement and a revised PSC if warranted by new information

- Development of the P3 agreement and management of the contract must be focused on outputs and performance-based specifications, rather than traditional design specifications

- Strict enforcement of the P3 contract must be maintained throughout the performance period.

# Performance Standards

If the P3 structure being selected for a particular project includes operation and maintenance of the asset, then the procurement documents must fully define the mandatory performance requirements over the life of the contract.  These standards should be expressed in broad, performance-focused terms, such as “pavement shall have a roughness of X as measured by the international roughness index (IRI)” rather than defining specific thickness and asphalt mix requirements.  How and when to make lifecycle investment decisions should be determined by the bidders, who should be asked to demonstrate in their initial proposal how they will accomplish the goals of the State, so long as the performance standards are met.  Similarly, operating standards should be stated as service goals rather than as inputs, such as “response time to a motorist distress call shall be no longer than X minutes,” rather than specifying the resources that should be on stand-by to respond to such calls (i.e. means and methods).

One of the key tasks for the Department will be to establish a comprehensive set of performance metrics that it can rely upon to ensure that its strategic objectives are met through its P3 projects.  The type of metrics already in use by the Department is a very good first step in this direction.

Of course, monitoring performance over the life of the P3 agreement also requires that the Department embrace the paradigm shift described above to monitoring contract compliance rather than directing field-level changes.

# Conclusions

Through the two-step screening analysis and assessment presented in this report, the PB Team reviewed a list of 38 surface transportation projects with the objective to identify a list of the best short-term (two to three years) and medium-term (four to eleven years) projects that are most likely to generate greater value resulting from risk transfers and cost and schedule efficiencies through the use of public-private partnership (P3) delivery methods.

The final set of seven projects recommended for further analysis as potential P3 candidates, along with a starting point for the type of contract structures that may be possible, is presented below.  All P3 project candidates must undergo Value-for-Money analysis before moving into the procurement phase.

In the near term:

- The Saint Croix River Crossing is a P3 candidate as a toll bridge and Mn/DOT has started a more detailed analysis of revenue and costs and potential delivery under a DBFOM model as required by the legislature.  The order-of-magnitude analysis of bonding capacity revealed that project toll revenue could cover up to 40% of its capital costs after O&M and R&R needs.

- Two near-term groups of MnPass projects including the Northwest Metro Corridor (I-94/I-494 MnPass Lanes and TH610) and North Minneapolis-Central MnPass Lanes (I-35W/I-94) could be implemented under a DBFOM model.  As a first order estimate, the Northwest Metro Corridor does not appear to generate sufficient revenue to cover its capital costs through revenue bonds after O&M and R&R, while the North Minneapolis-Central MnPass Lanes barely breaks even (although network synergies may improve revenue).  Several payment mechanisms exist that could be used to implement such managed lane P3 projects and allow the State to retain control on toll rate if this is a policy objective.

- Parts of the statewide Pavement Preservation Program could be delivered under a DBFOM structure with an initial pavement rehabilitation program addressing the critical sections of pavement followed by a long-term (20 to 30 years) maintenance program for these sections and other sections that are likely to reach lower performance levels over the course of the contract.  The concession would require an availability payment.  To be delivered under a P3, the scope of the rehabilitation work (including geographic distribution and network continuity) and the allocation of O&M responsibilities between the Mn/DOT and a potential partner would require careful definition.  The program would also have to be based on a comprehensive set of metrics for pavement performance.  Mn/DOT’s experience with such metrics provides a solid basis to build from.  Such programs have been implemented under the Private Finance Initiative in the U.K.  Highway maintenance and pavement preservation P3 contracts have also been used in the U.S. providing Mn/DOT with public-sector counterparts to share existing experience and demonstrating private sector interest for such approaches.

- Truck Havens could also be delivered under a DBFOM structure.  The State currently has no commercial rest areas. To improve safety, Mn/DOT is investigating the feasibility of developing a partnership project serving truckers on sections of the State highway system where truck volumes are too low to support the private development of private truck stop operations.  To enable development, the State could partner with the private sector and participates in the development cost of the facility and/or supporting infrastructure.  With the nature of such developments more akin to land development than traditional highway projects, the potential private partners for such concessions are more likely to be specialized developers and private hospitality companies running commercial concessions that provide food, beverage and retail services.

Based on the conclusions of the order-of-magnitude cost recovery analysis, any P3 delivery model involving private financing would necessarily require an availability payment or a shadow toll payment mechanism potentially combined with a direct subsidy in the form of construction payments.  Mn/DOT is likely to retain most of (if not all of) the revenue risk.

In the medium- term:

- The Lowry Hill Tunnel meets the criticality criteria in the long-term for system preservation and in the medium-term for mobility.  Although at a preliminary planning stage, the project is likely to be very large (over $1 billion) and require innovative tunneling techniques.  At this stage, the project would be a good candidate for a Pre-Development Agreement, in which the private partner participates in the preliminary design of the project during the environmental review process either at a reduced or deferred cost, in exchange for the right of first refusal to develop the project on a DBFOM basis.  Tunnel projects of this type and magnitudes are likely to attract strong domestic and international completion for a P3.  The preliminary bond capacity analysis shows that, if the project were tolled, revenue could cover approximately 13% of its capital costs with a $1 toll rate or 40% of its capital costs with $2 toll rate after O&M and R&R.   Further detailed studies are required to assess alignment, scope, costs and revenues.

- Future Bridge Program (similar to the Chapter 152 Program) could be considered for P3 procurement.  An analysis of the Chapter 152 Program was initially developed but quickly arrived at the conclusion that the program was too far advanced to change the current procurement method.  For future bridge programs, the bundling of multiple bridge repair projects in a single, large private rehabilitation project can generate efficiencies in terms of schedule acceleration and cost reduction stemming from standardization in addition to other, more common risk transfers available under P3.  There may be greater programmatic benefits including smaller, more standard bridges in a P3 program when compared to larger more complex bridges, which are usually better procured on a standalone basis.  Given the long life expectancy of bridges and the ability to specify performance over time, the use of a P3 approach with a bridge program provides opportunities to capture life cycle costs efficiencies.  The same recommendations as to scope definition, responsibility allocation, and performance metrics apply to a potential Bridge Program as they do for the Pavement Preservation Program.

Longer-term projects (beyond eleven years) were not evaluated.  However, some of these projects should continue to be considered for P3 delivery as the projects are further developed, including the two high-speed rail projects in the State (Twin Cities to Chicago and Twin Cities to Rochester), the I-35 / I-535 "Can of Worms" Project, the I-535 Blatnik Bridge, the I-494 Bloomington MnPass Lane, and the TH-41 Bridge at Chaska.

In order for the identified P3 project candidates to move into implementation, a series of activities related to the framework of the Department’s P3 program need to be completed, which will require changes in legislation, changes in the way the Mn/DOT is organized, develops and delivers projects, and changes in the way Mn/DOT communicates with the public and the private sector.

From an organizational perspective, the Department will need to develop the right skill set to identify and develop P3 project candidates through a mix of in-house and consultant expertise, develop performance metrics covering construction, O&M, and R&R activities, prepare performance-based contractual documentation, run a competitive procurement process involving private financing, and manage and oversee P3 contracts after award.  Together with the Department’s experience with Design-Build contracting, the Department’s experience with performance metrics is solid first steps towards building in-house competencies for a P3 program.

As the program develops, the paradigm shift required for P3 delivery, from designing and constructing projects to setting value and performance standards and managing and overseeing contracts, will require mobilization at all levels of the Department to be accomplished successfully.

# Appendix 1 - Level I Project Screening Documentation

The present Appendix summarizes the information gathered for the Level I screening and the assessment of the Level I criteria for each project.

The P3 project candidates were categorized by District, with an identification number assigned to indicate this categorization.  No priority was assigned in the ID number, nor do these numbers correspond with Mn/DOT project numbers.  The only purpose for the nomenclature was to selectively assign the projects for assessment in this study.  The Project ID takes the form of Dx-y, where x is the District number and y is an ordinal number within each District to distinguish the candidate projects.  If the project was in the Metro district, the Project ID takes the form of M-y, where y is again an ordinal number to distinguish projects.  Statewide projects start with the letter S, and transit projects with the letter T when these projects span several Districts. Numbering may not be continuous as projects were removed from the screening (for instance, duplicates).

A variety of project types was submitted and analyzed under the Level I screening analysis.  These projects were further classified in project types, including:

- Bridge / Tunnel.  Bridge projects involve either reconstruction or rehabilitation of bridge structures, most of which are identified in the Chapter 152 bridge inventory categorization.

- New Highway.  New highway projects propose the construction of a controlled and/or limited access trunk highway facility in locations where one currently does not exist.  In certain cases, right-of-way may have been preserved for the corridor.  In other cases, the facility may extend one that terminates.  Like bridge and tunnel projects, for user fee analysis, these projects were analyzed as comprehensive toll facilities.

- Managed Lanes.  Managed lanes are lane expansions on trunk highway corridors, typically involving the construction of one additional concurrent flow lane in each direction.  These projects may involve a preference for higher-occupancy vehicles in concurrence with existing MnPass policies.  Furthermore, the established Mn/DOT policy is to price managed lanes for demand management purposes, not for revenue generation purposes.  Managed lanes are typically proposed for the metropolitan area.

- Highway Expansion.  These projects involve a lane expansion on trunk highway corridors, typically in rural or intercity corridors.  These projects may or may not include a toll component.

- Transit.  Transit projects involve the construction of new dedicated-rail transit services, either as an extension of existing commuter rail services, or as new construction of rail technologies that do not currently exist in Minnesota (including high speed rail).  User fees are estimated based upon the value of collected fares.

- Program.  Programmatic P3 projects involve a packaging of many discrete projects that comprise one Mn/DOT program.  In the context of this analysis, these programs were considered statewide in nature, whereby efforts to consolidate all conforming corridor or site projects into one managed, statewide program were pursued.

# D1-1: I-35 / I-535 "Can of Worms" Project

| District | One |
| --- | --- |
| Location | Duluth |
| Type | Bridge |
| Description | Improvement/replacement of the I-535/I-35/TH 53 Interchange in Duluth, a 3-level interchange with all system to system connections. Includes approximately 30 bridges, 7 of which are "fracture critical", which are currently designed and mandated under CH152, should be ready to let soon. Interchange built in 1970. Existing businesses constraining footprint: BNSF Rail yard, wastewater treatment plant, small business district. Complex construction/traffic staging. Project scope and definition unclear. |
| Cost Estimate | $490 M |
| Criticality | Long-term critical |
| Criticality Notes | Safety, Legislative Obligations, System Preservation |
| Implementation | Long-term |
| Environmental | Environmental Clearance complete; Design not begun |
| Funding | None |
| Revenue Potential | Current traffic levels are relatively modest; 59,000 I-35 AADT 2009 at peak |

Recommendation

Withhold from Level II screening

Other Notes: Greatest challenge is the project scope/definition and construction staging.  There is limited access and limited opportunity for alternative land use.

# D1-3: I-535 Blatnik Bridge

| District | One |
| --- | --- |
| Location | Duluth |
| Type | Bridge |
| Description | Border bridge with Wisconsin. Dimension is 7,975 feet long and rises up 120 feet above the water to accommodate the seaway shipping channel. Truss bridge built in 1960. The bridge was widened and the substructure was strengthened in 1993 to accommodate hard shoulders. The bridge was reduced to two lanes temporarily in 2008 to strengthen the gusset plates. Currently in good condition. |
| Cost Estimate | $200 M |
| Criticality | Long-term critical |
| Criticality Notes | Safety, Legislative Obligations, System Preservation |
| Implementation | Long-term |
| Environmental | Not begun. Bridge replacement would likely only require an Environmental Assessment. |
| Funding | None; would be shared 50% with Wisconsin |
| Revenue Potential | Current traffic levels are low (29,500 AADT 2009) |

Recommendation

Withhold from Level II screening

Other Notes: Dual state coordination may constrain options.  Wisconsin considering modification to access on Wisconsin side.  The bridge was tolled prior to 1960.  Opportunities for improved traffic management during construction and phasing in connection with "Can of Worms" project D1-1.

# D1-4: TH 53 Realignment

| District | One |
| --- | --- |
| Location | -- |
| Type | New Highway |
| Description | A portion of TH-53 is located on land presently owned by a mining company. According to the terms of the land lease, Mn/DOT is responsible for realignment of approximately two miles of highway and one interchange. |
| Cost Estimate | $30 - 200 M |
| Criticality | Not critical |
| Criticality Notes | N/A |
| Implementation | N/A |
| Environmental | N/A |
| Funding | None. |
| Revenue Potential | Unknown |

Recommendation

Withhold from Level II screening

Other Notes: Per Mn/DOT, terms of land lease obligate Mn/DOT to relocate the highway (to be verified by Mn/DOT legal counsel).  Depending on the term of the land lease and the extent to which the  mining company could benefit from improved highway connections, a partnership may be possible.  The King Coal Highway in West Virginia could provide an example of such a partnership with  a mining company.

# D2-1: TH-72 Baudette (Rainy River) Bridge

| District | Two |
| --- | --- |
| Location | Baudette |
| Type | Bridge |
| Description | Bridge preservation between US and Canada on TH-72 (functionally obsolete and fracture critical) |
| Cost Estimate | $50 - 70 M |
| Criticality | Not critical |
| Criticality Notes | N/A |
| Implementation | Medium-term |
| Environmental | Just beginning |
| Funding | Chapter 152 funding in 2019. Ontario indicates they should have funds available at that time as well. |
| Revenue Potential | The old bridge was a toll bridge when owned by the City of Baudette. The current bridge is now owned by MnDOT and Ontario. Current AADT is only 1,950. |

Recommendation

Withhold from Level II screening

Other Notes: Border with Ontario (enabling P3 legislation, strong P3 program).

# D3-1: TH 25 Expansion

| District | Three |
| --- | --- |
| Location | Monticello / Buffalo |
| Type | Highway Expansion |
| Description | 21 lane miles expansion from 2 to 4 lanes. Currently, this project is the highest volume 2-lane road in District 3 except for TH 55. |
| Cost Estimate | $75 M (2009) |
| Criticality | Not Critical |
| Criticality Notes | N/A |
| Implementation | Medium-term |
| Environmental | EA about 90% complete |
| Funding | Highway Investment Plan forecasts improvement project to begin 2015. |
| Revenue Potential | High volume for 2-lane road (20,400 AADT) |

Recommendation

Withhold from Level II screening

# D3-2: TH 371 Expansion

| District | Three |
| --- | --- |
| Location | Nisswa / Jenkins |
| Type | Highway Expansion |
| Description | Expansion from 2 to 4 lanes. Changed from a thru-town to a bypass alternative of Pequot Lakes which requires a supplemental EIS currently underway. Tolled lanes unlikely to be an option. Schedule is mainly driven by lack of funding. Mill and overlay project forecasted for 2011. Highway Investment Plan forecasts improvement project to begin 2018. Project connected to D3-3. |
| Cost Estimate | $65 M (2008) |
| Criticality | Not Critical |
| Criticality Notes | N/A |
| Implementation | Medium-term |
| Environmental | Final Supplemental EIS currently being prepared. Awaiting on legal review by FHWA. Next steps include municipal consent and ROW acquisition scheduled for 2 years prior to construction. |
| Funding | Funding constraint is main driver for schedule. |
| Revenue Potential | Moderate volume for 2-lane road (approximately 10,000 AADT). Toll lanes unlikely to be accepted by local communities even with tourism activity. High weekend volumes. |

Recommendation

Withhold from Level II screening

Other Notes: Supplemental EIS to bypass Pequot Lakes.  Business community is concerned that bypass would reduce local activity related to tourism.  Complex environmental issues (lakes, rivers...)

# D3-3: TH 371 Expansion

| District | Three |
| --- | --- |
| Location | Jenkins / Pine River |
| Type | Highway Expansion |
| Description | Expansion from 2 to 4 lanes. Project connected to D3-2. |
| Cost Estimate | $40 M (2008) |
| Criticality | Not Critical |
| Criticality Notes | N/A |
| Implementation | Long-term |
| Environmental | N/A |
| Funding | None. Funding constraint is main driver for schedule. |
| Revenue Potential | Moderate volume for 2-lane road (approximately 10,000 AADT). Toll lanes unlikely to be accepted by local communities even with tourism activity. High weekend volumes. |

Recommendation

Withhold from Level II screening

# D3-4: I-94 MnPass Shoulder Lane

| District | Three |
| --- | --- |
| Location | Rogers / Monticello |
| Type | Managed Lanes |
| Description | Implement a MnPass shoulder lane in lieu of expansion from 4 to 6 lanes on I-94 from Rogers to Monticello, connecting to Metro district I-94 expansion (project M-5). If the project were extended to Clearwater, it could be combined with project D3-7. |
| Cost Estimate | $136 M (2008) |
| Criticality | Not critical |
| Criticality Notes | N/A |
| Implementation | Medium-term |
| Environmental | Not begun |
| Funding | None. Bridges to be replaced along corridor in 2010. |
| Revenue Potential | Moderate volume corridor (approximately 60,000 AADT) for managed lanes. |

Recommendation

Proceed to Level II screening and combine with M5 and M10

Other Notes: Success of managed lane would require concurrent development of Metro project M-5.  Without of M-5, demand profile may not support managed lanes concept in this segment.

# D3-5: TH 55 Expansion

| District | Three |
| --- | --- |
| Location | Buffalo / Rockford |
| Type | Highway Expansion |
| Description | Expansion from 2 to 4 lanes. TH-55 volumes approach and at times exceed LOS D/E criteria for a 2-lane arterial. Project connected to D3-6. |
| Cost Estimate | $57 M (2008) |
| Criticality | Not critical |
| Criticality Notes | N/A |
| Implementation | Medium-term |
| Environmental | Environmental Assessment to begin 2010 |
| Funding | None identified |
| Revenue Potential | High volume for 2-lane road (19,000 AADT) |

Recommendation

Withhold from Level II screening

Other Notes: Conceptual design / EA will begin in 2010.  EA will include projects D3-5 and D3-6.

# D3-6: TH 55 Expansion

| District | Three |
| --- | --- |
| Location | Annandale / Buffalo |
| Type | Highway Expansion |
| Description | Expansion from 2 to 4 lanes. TH-55 volumes approach and at times exceed LOS D/E criteria for a 2-lane arterial. Project connected to D3-5. |
| Cost Estimate | $35 M (2008) |
| Criticality | Not critical |
| Criticality Notes | N/A |
| Implementation | Long-term |
| Environmental | Environmental Assessment to begin 2010 |
| Funding | None identified |
| Revenue Potential | Moderate volume for 2-lane road (11,000 AADT), with occasional high volumes with LOS E/F peaks. |

Recommendation

Withhold from Level II screening

Other Notes: Conceptual design / EA will begin in 2010.  EA will include projects D3-5 and D3-6.

# D3-7: TH-24 New Mississippi River Crossing

| District | Three |
| --- | --- |
| Location | Clearwater to Clear Lake |
| Type | Bridge |
| Description | TH-24 bridge replacement between Clearwater and Clear Lake scheduled in 2016 in Highway Investment Plan. Could be combined with D3-4. |
| Cost Estimate | $195 M |
| Criticality | Not critical |
| Criticality Notes | N/A |
| Implementation | Short-term |
| Environmental | Unknown |
| Funding | Highway Investment Plan forecasts improvement project to begin 2016 |
| Revenue Potential | Moderate volume for 2-lane bridge (13,000 AADT). Heavy recreation route. |

Recommendation

Withhold from Level II screening

Other Notes: Current TH-24 serves as Main Street for Clearwater.

# D3-8: US 169 / US 10 Expansion

| District | Three |
| --- | --- |
| Location | Elk River / Zimmerman |
| Type | New Highway |
| Description | Conversion from expressway to freeway design, including conversion of signalized intersections to interchanges between Elk River and Zimmerman (13 miles). |
| Cost Estimate | US 169 from Elk River to Zimmerman = $542 M (2008); US 10 portion = $230 M (2008) |
| Criticality | Not critical |
| Criticality Notes | N/A |
| Implementation | Long-term |
| Environmental | US 169 EA complete (2009); US 10 EA in progress |
| Funding | None identified |
| Revenue Potential | Moderate volumes for 4-lane arterials (35,000 AADT for US 169; 36,000 AADT for US 10) |

Recommendation

Recommend as possible long-term P3

Other Notes: US 169 will be difficult to stage for construction purposes.  An existing BNSF railroad relocation project could proceed sooner.

# D3-10: Northstar Commuter Rail Extension

| District | Three |
| --- | --- |
| Location | Big Lake to St. Cloud |
| Type | Transit |
| Description | First commuter rail line opened in late 2009 between Big Lake and Minneapolis (40 miles). Two stations are located in District 3 (Big Lake and Elk River). Northstar planned extension to St Cloud with several intermediate stops, for an additional 40 miles. The first 40 miles cost $265 M (YOE). Current Northstar run by Burlington Northern. |
| Cost Estimate | $40 M (2005), as estimated by 2002 FEIS |
| Criticality | Not critical |
| Criticality Notes | N/A |
| Implementation | Long-term |
| Environmental | Final EIS complete / ROD complete |
| Funding | Existing facility open with 50% federal participation. Rail district has requested bonding authority from State. |
| Revenue Potential | Daily ridership on existing line is 2,200 in December 2009. |

Recommendation

Withhold from Level II screening

Other Notes: BNSF Railroad has operational jurisdiction over Northstar service on its ROW.  Opportunity for P3 considerations may exist for O&M contracting or if the extension were to be combined with the existing facility into a single concession.

# D6-1: TH 63 Multimodal Improvements

| District | Six |
| --- | --- |
| Location | Rochester |
| Type | Highway Expansion |
| Description | Expansion of TH-63 from 2 to 4 lanes, done concurrently with a new Rochester Airport terminal in 7-10 yrs. |
| Cost Estimate | $ 66 M |
| Criticality | Not critical |
| Criticality Notes | N/A |
| Implementation | Medium-term |
| Environmental | EA just started (48th Street in Rochester to I-90) |
| Funding | Toll road possibility; transportation improvement district |
| Revenue Potential | High volumes for 2-lane road (29,000 AADT) |

Recommendation

Withhold from Level II screening

Other Notes: LRT service from airport to downtown.  May involve multiple agencies, including FAA.

# D6-2: TH 19 Expansion

| District | Six |
| --- | --- |
| Location | Northfield |
| Type | Highway Expansion |
| Description | Expansion of TH-19 from 2 to 4 lanes from Northfield to I-35 |
| Cost Estimate | Unknown |
| Criticality | Not critical |
| Criticality Notes | N/A |
| Implementation | Long-term |
| Environmental | Environmental Impact Statement underway |
| Funding | None identified |
| Revenue Potential | Low volumes (9,300 AADT) |

Recommendation

Withhold from Level II screening

Other Notes: Somewhat complex, including a river crossing and interaction with the City of Northfield and two college campuses

# D7-1: TH-14 Expansion

| District | Seven |
| --- | --- |
| Location | Mankato to New Ulm |
| Type | Highway Expansion |
| Description | Expansion of TH-14 from 2 to 4 lanes between North Mankato and New Ulm. This segment includes two greenfield bypasses of challenging sections and a bridge replacement over the Minnesota River. May be combined with project D7-4. |
| Cost Estimate | $ 200 - 250 M (including $51 M bridge replacement) |
| Criticality | Not critical |
| Criticality Notes | N/A |
| Implementation | Medium-term |
| Environmental | Final EIS complete end of 2010. |
| Funding | Minnesota River bridge replacement funded in 2018. |
| Revenue Potential | Parallel route may depress toll revenue; low volumes (6,800 AADT) |

Recommendation

Withhold from Level II screening

Other Notes: Medium level complexity, with existing alignment posing challenges yet new alignment being overly costly to construct and maintain.  Strong local public support with formal public-public partnership organization (Highway 14 Partnership).  Two interchanges in the corridor could also be part of the project, including 1) TH-14/CSAH-49 interchange (estimated at $36 M, intended to facilitate truck movement and development in the corridor associated with the Wal-Mart distribution center), and, 2) TH-14/TH-169 interchange ($60 - 100 M, with bridge widening over the Minnesota River).

# D7-2: TH-60 Expansion

| District | Seven |
| --- | --- |
| Location | St. James to Windom |
| Type | Highway Expansion |
| Description | Complete 4-lane expansion from 2-lane segments in three areas: Butterfield to St. James (6 miles), Mt. Lake to Butterfield (5 miles), and Windom to Mt. Lake (8 miles). All other sections in the corridor already have four lanes. |
| Cost Estimate | $90 - 105 M |
| Criticality | Not critical |
| Criticality Notes | N/A |
| Implementation | Short-term |
| Environmental | EIS complete in 1983; Environmental re-evaluation and design underway for Gap A |
| Funding | Gap A is funded by STIP ($29 M); remainder unfunded |
| Revenue Potential | Low volumes (5,500 AADT) |

Recommendation

Withhold from Level II screening

Other Notes: Environmental rules have changed since EIS completion.

# D7-3: TH-22 Expansion

| District | Seven |
| --- | --- |
| Location | St. Peter to I-90 |
| Type | Highway Expansion |
| Description | Expansion from 2-lanes to 4-lanes on TH-22 between St. Peter and I-90. Includes a major river crossing of Minnesota River. |
| Cost Estimate | Unknown |
| Criticality | Not critical |
| Criticality Notes | N/A |
| Implementation | Long-term |
| Environmental | No environmental work done to date |
| Funding | None identified |
| Revenue Potential | Low volumes (9,900 AADT) |

Recommendation

Withhold from Level II screening

# D7-4: US-14 / CSAH-12 New Alignment

| District | Seven |
| --- | --- |
| Location | Mankato |
| Type | New Highway |
| Description | Constructs two miles of arterial roadway, a new interchange, and grade separated crossing of the DM&E Railroad to the east of TH-22 and US-14. The project involves partnerships with Mn/DOT, City of Mankato, Blue Earth County, and Wal-Mart. Without the project, expansions on other roads would be necessary. May be combined with project D7-1. |
| Cost Estimate | $25 M (2008) |
| Criticality | Not critical |
| Criticality Notes | N/A |
| Implementation | Short-term |
| Environmental | Environmental Assessment completed in 2008. Construction starting 2010. |
| Funding | Blue Earth County has paid for $ 4.8M improvements upfront, with costs to be reimbursed by Mn/DOT over 5 years. Wal-Mart provided $500,000 / year for 10 years for local infrastructure to support distribution center. |
| Revenue Potential | Unknown |

Recommendation

Withhold from Level II screening

Other Notes: P3 agreement already in place between Wal-Mart and the City of Mankato.  Wal-Mart is paying the City of Mankato and Blue Earth County for the local infrastructure that was constructed to support a future distribution center.  The local infrastructure includes drainage improvements and roadway approaches that support the interchange project.  Wal-Mart also agreed to provide land for part of the interchange right-of-way at a nominal cost and their site development will incorporate drainage improvements that will compliment the area-wide infrastructure plans.  The Wal-Mart distribution center is  expected to generate  over 600 trucks per day, over 550 jobs, and create spinoff development of truck and trailer services that has already begun in this vicinity (and also in North Mankato near CSAH 41).

# M-1: I-35E MnPass Shoulder Lane

| District | Metro |
| --- | --- |
| Location | St. Paul / Northeast Metro |
| Type | Managed Lanes |
| Description | Cayuga bridge complex reconstruction to include a MnPass shoulder lane (priced dynamic shoulder lane) between downtown St. Paul and TH-36. This project would extend the lanes to CR-E. May be combined with project M-7. |
| Cost Estimate | $117.5M |
| Criticality | Critical |
| Criticality Notes | Legislative Obligations, System Preservation, Mobility, Network Completion |
| Implementation | Short-term |
| Environmental | No environmental clearance for managed lanes, bridge is already cleared. If necessary, bridge may be constructed to accommodate managed lanes, but striped as shoulder. |
| Funding | Managed Lane Tolling |
| Revenue Potential | Managed lane projected daily volumes (MnPass 2 preliminary estimate): 11,200 (2015) |

Recommendation

Withhold from Level II screening

Other Notes: RFP for preliminary design for Cayuga bridge and final design for highway lanes planned for Q3 2010.  Estimated to be let Jan 2012.  Bridge reconstruction, Plan is to widen by two lanes concurrent with reconstruction, possible implementation of managed lanes in conjunction with use of shoulder lanes between northern bridge terminus and TH-36 (MHSIS / MnPass system recommendation), southbound I-35E has left-side exit to downtown St. Paul.

# M-2: US 169 MnPass Shoulder Lane

| District | Metro |
| --- | --- |
| Location | Southwest Metro (Shakopee to I-494) |
| Type | Managed Lanes |
| Description | Add one priced managed lane in each direction between Shakopee and I-494 on US 169. |
| Cost Estimate | $92 - $125 M |
| Criticality | Not critical |
| Criticality Notes | N/A |
| Implementation | Medium- to long-term |
| Environmental | Not begun |
| Funding | Managed Lane Tolling |
| Revenue Potential | Managed lane projected daily volumes (MnPass 2 preliminary estimate): 13,100 (2015) |

Recommendation

Withhold from Level II screening

Other Notes: Project performs well for 2030 timeline in MHSIS, but is only identified as a "moderate" priority on the project.  May be impractical without bridge improvements over the Minnesota River

# M-3: I-94 MnPass Shoulder Lane

| District | Metro |
| --- | --- |
| Location | Central Metro (downtown Minneapolis to downtown St. Paul) |
| Type | Managed Lanes |
| Description | Add one priced managed lane in each direction on I-94 between downtown St. Paul and downtown Minneapolis, including direct connection to downtown Minneapolis. May be combined with project M-6. |
| Cost Estimate | $140 M; ATM project concurrent with I-94 pavement project currently programmed, reducing the overall cost for managed lanes |
| Criticality | Critical |
| Criticality Notes | Mobility, Network Completion |
| Implementation | Medium-term |
| Environmental | Active Traffic Management project concurrent with mill/overlay programmed; managed lane implementation would require environmental clearance |
| Funding | Managed Lane Tolling |
| Revenue Potential | Managed lane projected daily volumes (MnPass 2 preliminary estimate): 16,300 (2015) |

Recommendation

Proceed to Level II screening and combine with M6

Other Notes: The I-94 Managed Lanes study indicated this project has significant operational challenges and could not be built to full-shoulder treatment standards without full corridor reconstruction (cost $400 - $600M).  MnPass System 2 study recommends a design option that drastically reduces costs and avoids structural reconstruction.

# M-4: TH 77 MnPass Shoulder Lane / Contraflow Lane

| District | Metro |
| --- | --- |
| Location | South central Metro (TH-13 to Old Shakopee Road) |
| Type | Managed Lanes |
| Description | Add one priced managed lane in each direction or one priced contraflow lane on TH-77 across Long Meadow Lake, between TH-13 and Old Shakopee Road. May be combined with project M-8. |
| Cost Estimate | $41 M |
| Criticality | Long-term critical if combined with M-8 |
| Criticality Notes | Mobility |
| Implementation | Medium-term |
| Environmental | Not begun |
| Funding | Managed Lane Tolling |
| Revenue Potential | Managed lane projected daily volumes (MnPass 2 preliminary estimate): 5,200 (2015) |

Recommendation

Withhold from Level II screening (Long-term combined with project M-8)

Other Notes: Interchange at I-494 is a bottleneck, constraining demand on TH-77.  Current design features a zipper-lane option for crossing the Minnesota River.  Termination issue at I-494 provides context for combining with project M-8; however, connection is not provided within cost estimates.

# M-5: I-94 / I-494 MnPass Shoulder Lane

| District | Metro |
| --- | --- |
| Location | Northwest / West Metro (Rogers to Minnetonka) |
| Type | Managed Lanes |
| Description | Add one priced managed lane in each direction between Fish Lake and I-494 (I-94) and between I-94 and I-394 (I-494). May be combined with project D3-4. |
| Cost Estimate | $192.5M |
| Criticality | Critical |
| Criticality Notes | Mobility, Network Completion |
| Implementation | Long-term |
| Environmental | Not begun |
| Funding | Managed Lane Tolling |
| Revenue Potential | Managed lane projected daily volumes (MnPass 2 preliminary estimate): 3,700 (I-94, 2015) and 9,700 (I-494, 2015) |

Recommendation

Proceed to Level II screening and combine with D3-4 and M-10

Other Notes: I-494 / I-94 interchange could be complex; very complex interchange at I-394 / I-494 -- likely could not accommodate direct connection between MnPass lanes; I-494 segment is higher priority for traffic congestion reduction than I-94, which tends towards weekend traffic profile.

# M-6: I-35W MnPass Shoulder Lane

| District | Metro |
| --- | --- |
| Location | North Metro (Downtown Minneapolis to US 10) |
| Type | Managed Lanes |
| Description | Add one priced managed lane in each direction on I-35W between downtown Minneapolis and US 10, including direct connection to downtown Minneapolis. May be combined with project M-3. |
| Cost Estimate | $ 260 M (2009) |
| Criticality | Critical |
| Criticality Notes | Mobility, Network Completion |
| Implementation | Uncertain timeline (medium to long-term) |
| Environmental | Not begun |
| Funding | Managed Lane Tolling |
| Revenue Potential | Managed lane projected daily volumes (MnPass 2 preliminary estimate): 13,200 (2015) |

Recommendation

Proceed to Level II screening and combine with M-3 (or long term alone)

Other Notes: Large reconstruction activities at TH-36 required; MnPass System 2 study has sketched a direct connection to downtown Minneapolis that would be highly desirable for transit.

# M-7: TH 36 MnPass Shoulder Lane

| District | Metro |
| --- | --- |
| Location | Managed Lanes |
| Type | Managed Lanes |
| Description | Add one priced managed lane in the eastbound direction on TH-36 between I-35W and I-35E. May be combined with project M-1. |
| Cost Estimate | $ 47.5 M (2009) |
| Criticality | Critical |
| Criticality Notes | Mobility, Network Completion |
| Implementation | Long-term |
| Environmental | Not begun |
| Funding | Managed Lane Tolling |
| Revenue Potential | Managed lane projected daily volumes (MnPass 2 preliminary estimate): 10,100 (both directions, 2015) |

Recommendation

Withhold from Level II screening

Other Notes: Direct connections to I-35E and I-35W would be costly, and low cost/benefit of westbound lane without direct connection to I-35W.

# M-8: I-494 Bloomington MnPass Shoulder Lane

| District | Metro |
| --- | --- |
| Location | South Metro (US 212 to MSP Airport) |
| Type | Managed Lanes |
| Description | Add one priced managed lane in each direction between US 212 and Minneapolis / St. Paul International Airport. May be combined with project M-4. |
| Cost Estimate | $ 200 M (2009) |
| Criticality | Long-term critical |
| Criticality Notes | Mobility, Network Completion |
| Implementation | Long-term |
| Environmental | Not begun |
| Funding | Managed Lane Tolling |
| Revenue Potential | Managed lane projected daily volumes (MnPass 2 preliminary estimate): 15,100 (2015) in the managed lane only. |

Recommendation

Withhold from Level II screening

Other Notes: Very costly segment to construct to full design standards ($1B+ estimated).  The MnPass System 2 study has sketched an alternative that may be possible for less than $200M.  Very high volumes in this segment.

# M-10: TH 610 Final Stage

| District | Metro |
| --- | --- |
| Location | Northwest Metro |
| Type | New Highway |
| Description | Complete TH-610 between US 169 and I-94. This is a greenfield 4-lane divided freeway. |
| Cost Estimate | $ 170 M |
| Criticality | Critical |
| Criticality Notes | Mobility, Network Completion |
| Implementation | Medium-term |
| Environmental | Not begun |
| Funding | Funding TBD. No toll considered on this segment. |
| Revenue Potential | Unknown |

Recommendation

Proceed to Level II screening and combine with D3-4 and M-5

Other Notes: No freeway facility currently exists in this segment.

# M-11: TH-36 St. Croix River Crossing

| District | Metro |
| --- | --- |
| Location | Stillwater |
| Type | Bridge |
| Description | Reconstruct bridge over St. Croix River. Metro District intending to proceed with Design / Build for the bridge. |
| Cost Estimate | $600 M (2010$) |
| Criticality | Critical |
| Criticality Notes | Legislative Obligations, System Preservation |
| Implementation | Short-term |
| Environmental | Environmental clearance on hold; Design underway |
| Funding | Possibly full facility tolling |
| Revenue Potential | Moderate volumes for 2-lane bridge (18,000 AADT) |

Recommendation

Proceed to Level II screening

Other Notes: Very costly bridge replacement with  moderate overall traffic volumes.  Replacement is a Tier 1 project in the Chapter 152 requirements.  Wisconsin opposed to tolling the bridge.  Mn/DOT has begun detailed analysis for this project.

# M-12: TH-41 Bridge

| District | Metro |
| --- | --- |
| Location | Chaska |
| Type | Bridge |
| Description | Reconstruct bridge on TH 41 in Chaska. |
| Cost Estimate | $ 700 M + |
| Criticality | Long-term critical |
| Criticality Notes | System Preservation, Network Completion |
| Implementation | Long-term |
| Environmental | Environmental Impact Statement underway |
| Funding | Possibly full facility tolling |
| Revenue Potential | Moderate volumes for 2-lane bridge (16,500 AADT) |

Recommendation

Withhold from Level II screening

Other Notes: New alignment of TH-41 bridge was identified, with 20-year activities concentrated upon alignment of local highway systems and right-of-way preservation.

# M-14: I-94 Lowry Hill Tunnel

| District | Metro |
| --- | --- |
| Location | Minneapolis |
| Type | Tunnel |
| Description | Reconstruct Lowry Hill Tunnel and I-94 / I-35W commons. Toll all lanes of traffic for demand management (prior to reconstruction) and maintain tolling for repayment of capacity expansion. |
| Cost Estimate | $1B - $2B |
| Criticality | Critical |
| Criticality Notes | System Preservation, Mobility |
| Implementation | Long-term |
| Environmental | Not begun |
| Funding | Possibly full facility tolling |
| Revenue Potential | High volumes (190,000 AADT) |

Recommendation

Proceed to Level II screening

Other Notes: Extremely complex project, with large environmental constraints.  However, this facility is the key bottleneck for the Minneapolis freeway system.  Pricing the tunnel to reduce congestion and create funds to expand capacity would help alleviate regional congestion.

# M-15: I-694 MnPass Shoulder Lane

| District | Metro |
| --- | --- |
| Location | North Metro (I-35W to I-35E) |
| Type | Managed Lanes |
| Description | Add one priced managed lane in each direction on I-694 between I-35W and I-35E |
| Cost Estimate | $ 50 M (2009) |
| Criticality | Not critical |
| Criticality Notes | N/A |
| Implementation | Long-term |
| Environmental | Not begun |
| Funding | Managed Lane Tolling |
| Revenue Potential | Moderate to high volumes (100,000 AADT) |

Recommendation

Withhold from Level II screening

Other Notes: Previous reconstruction of I-35E / I-694 interchange provides capacity at this junction.  Upcoming bridge / interchange work on the I-694 corridor also provides opportunity to cooperatively develop lanes.  However, this facility likely does not stand on its own without managed lanes on I-35E.  Corridor was excluded from the MnPass System 2 study and only included in 2060 MHSIS.

# S-1: Pavement Preservation Program

| District | Statewide |
| --- | --- |
| Location | Statewide |
| Type | Program |
| Description | Mn/DOTs objective is to preserve the structural integrity of its pavements and minimize the share of state highways rated in “poor” condition by doing the right preventive maintenance, rehabilitation or replacement at the right time. Once pavement quality deteriorates to poor condition, premature and costly replacement may be necessary. To minimize life-cycle costs, pavement engineers identify the most cost-effective treatment for every segment of state roads to help achieve the twin objectives of higher level of service and maximum pavement life. Mn/DOT invested between $150 million to $250 million per year in pavements from 2004 to 2008. Anticipated 2009-12 spending will total about $295 million per year. This amount includes a total of $275 million in additional new funds being channeled into accelerated pavement projects from the Chapter 152 bonding package passed by the 2008 Legislature. In addition, $228 million will be used to accelerate pavement projects as a result of the 2009 American Recovery and Reinvestment Act. Nevertheless, this funding will be insufficient for the department to reach its performance targets. Mn/DOT estimates that an additional $175 million to $400 million per year over and above anticipated funding should be invested from 2013 to 2018 in order to reach performance targets by 2018. |
| Cost Estimate | $400M- 1.5+ B (total program) |
| Criticality | Critical |
| Criticality Notes | System Preservation |
| Implementation | Short- to medium-term |
| Environmental | Limited environmental studies required. |
| Funding | TBD |
| Revenue Potential | Mn/DOT investigating new dedicated revenue source. |

Recommendation

Proceed to Level II screening

Other Notes: Accelerating preservation measure would yield life-cycle cost savings as timely repair and replacement reduce long-term costs.  Pavement rehabilitation work will also require additional improvement to comply with ADA requirements.

# S-2: Bridge Improvement Program

| District | Statewide |
| --- | --- |
| Location | Statewide |
| Type | Program |
| Description | The chapter 152 bridge improvement program lists 172 bridges that will require replacement, renovation or rehabilitation. A three-tier system to prioritize bridges was included in the legislation. The prioritization is based on a series of criteria including functional obsolescence, structural deficiency, fracture criticality or average daily traffic. Under the legislation, Tiers 1 and 2 projects (which comprise 161 of the 172 bridges) will need to be replaced or require renovation or rehabilitation by June 30, 2018. Excluding the projects that are expected to be substantially complete by the end of 2010, the program capital cost for tiers 1&2 is estimated to range from $2.2B to $2.7B. This includes several large bridge replacement projects such as: 1) the St Croix River bridge on Hwy 36 in the Metro area ($600M) scheduled to be replaced between 2014 and 2018, 2) the Hwy 63 bridge over the Mississippi river and CP Rail in Red Wings (District 6) ($286M to $383M) scheduled to be replaced in 2018, and 3) the Hwy 43 bridge over the Mississippi river, railroad, streets in Winona (District 6) ($276M to $374M) scheduled to be replaced in 2016. In cases where the ownership of a bridge is shared between Minnesota and its neighboring States or Canada, only the Minnesota share of total capital cost was included. |
| Cost Estimate | $2.2 - 2.7 B (tiers 1 and 2 only) |
| Criticality | Critical |
| Criticality Notes | System Preservation, Legislative Obligations |
| Implementation | Short- to medium-term (tiers 1 and 2 required to be replaced or renovated by June 2018). |
| Environmental | Unknown |
| Funding | Chapter 152, bond funds appropriations. |
| Revenue Potential | Dedicated revenue source through Chapter 152 |

Recommendation

Proceed to Level II screening

Other Notes: Chapter 152 provides funding through the appropriations of funds from the issuance of bonds.  Opportunities may exist for program acceleration through standardization and by grouping bridges by categories according to design specifications and construction requirements.  Other States have implemented partnership programs that could serve as models for Minnesota such as the Missouri Safe and Sound Bridge Program.

# S-3: Truck Havens

| District | Statewide |
| --- | --- |
| Location | Statewide |
| Type | Single Project (Location To Be Determined); Program |
| Description | Truck rest stops contribute to the safety of the traveling public by providing fatigued truck drivers (and auto drivers) the ability to stop and rest. They also reduce the need for stoping along highway shoulders and provide an escape from driving under hazardous weather and road conditions. Though their primary value is accident prevention, they also address many needs of commercial truck operators and help promote the State economy and State tourism. There are currently no commercialized rest areas in the State. Mn/DOT is investigating potential location for a commercial truck rest stop along corridors with lower truck traffic volumes. On-going research will determine the location of the facility with the objective to minimize the impact of local business community while balancing the revenue generation objectives of the Department. The State’s truck rest stop program is nicknamed “Truck Havens.” |
| Cost Estimate | TBD |
| Criticality | Critical |
| Criticality Notes | Safety |
| Implementation | Short- to medium-term |
| Environmental | No environmental study |
| Funding | No funding |
| Revenue Potential | Commercial revenue |

Recommendation

Proceed to Level II screening

# T-1: High Speed Rail - Twin Cities to Chicago

| District | Transit |
| --- | --- |
| Location | Minneapolis / St. Paul to Chicago |
| Type | Transit |
| Description | Investigate and implement high speed rail between Minneapolis / St. Paul and Chicago. |
| Cost Estimate | Unknown |
| Criticality | Not critical |
| Criticality Notes | N/A |
| Implementation | Long-term |
| Environmental | Not begun |
| Funding | 98% of the $823M Federal HSR grant for the Twin Cities-Milwaukee-Chicago HSR went to the Madison to Milwaukee section. Federal HSR funding included $1M granted for a planning study to explore extension of HSR service from Madison to the Twin Cities. |
| Revenue Potential | Unknown |

Recommendation

Withhold from Level II screening

Other Notes: Opportunities exist for private sector participation in high speed rail.  Such opportunities would require a higher level of project definition to be evaluated.

# T-2: High Speed Rail - Twin Cities to Rochester "Greenfield" Line

| District | Transit |
| --- | --- |
| Location | Minneapolis / St. Paul to Rochester |
| Type | Transit |
| Description | Investigate and implement high speed rail between Minneapolis / St. Paul and Rochester. As this is entirely new alignment, the Greenfield route going through Rochester has two options: single track diesel (110 mph) and double track electric (220 mph) |
| Cost Estimate | St Paul to La Crosse - Single track diesel: $975M; Double track electric: $2,075M (2008) |
| Criticality | Not critical |
| Criticality Notes | N/A |
| Implementation | Long-term |
| Environmental | Not begun |
| Funding | None identified |
| Revenue Potential | 2030 net operating margin: Single track diesel: $112M; Double track electric: $302M (2008) |

Recommendation

Withhold from Level II screening

Other Notes: Not an FRA-designated HSR corridor.  Opportunities exist for private sector participation in high speed rail.  Such opportunities would require a higher level of project definition to be evaluated.

# T-3: Personal Rapid Transit

| District | Transit |
| --- | --- |
| Location | Potential locations include: Edina, St. Paul Ford Plant site, and Rochester |
| Type | Transit |
| Description | The Personal Rapid Transit (PRT) system envisioned (based upon an RFI response on May 18, 2010 by ULTra PRT) consists of a fleet of 18 low energy, battery powered, driverless vehicles capable of carrying four passengers and their luggage along a dedicated fixed guideway. The PRT is intended to serve as a circulator among densely populated areas and service centers, with connections to existing transit lines. The fixed guideway system serves and alternative to bus routes. |
| Cost Estimate | Capital cost: $13 M per one-way mile of fixed guideway; O&M cost: $3 M per year (per ULTra PRT response, May 2010) |
| Criticality | Not critical |
| Criticality Notes | N/A |
| Implementation | Medium- to long-term |
| Environmental | No environmental studies. |
| Funding | None identified |
| Revenue Potential | Transit system usually require subsidy, although partnership with local business is possible. |

Recommendation

Withhold from Level II screening

Other Notes: It is generally not recommended to limit a P3 project to a specific technology, unless this technology is widely used.  ULTra (Urban Light Transport) completed the construction phase for a 3.8 km (2.4 miles) system at London Heathrow Airport, the first such system implemented worldwide.  The closest analogue in the United States in the WVU PRT system in Morgantown, WV, operating since the 1970s.  The project could be further studied as a potential P3 candidate when the project scope is better defined with a technology choice broadening competitive opportunities.

# Acknowledgements and Contact Information

This report was written by the Parsons Brinckerhoff Team under the guidance of Brad Larsen, Director of Traditional & Innovative Finance for the Minnesota Department of Transportation and Project Manager for the Department.

Contact Information

Minnesota Department of Transportation

Office of Financial Management

395 John Ireland Blvd., MS 140

St.  Paul, MN 55155

Brad Larsen

Phone: (651) 366-4821

Email: brad.larsen@state.mn.us

David Gehr served as Principal-In-Charge and Michael Benouaich served as Project Manager for Parsons Brinckerhoff.  Contributors to the report also included David Franck, Patrick Hughes, Laurene Mahon, Benjamin Perez, and David Ungemah.

Contact Information

Parsons Brinckerhoff

510 First Avenue N, Suite 550

Minneapolis, MN 55403

Michael Benouaich
Phone: (202) 257-2505

Email: benouaich@pbworld.com

See project list and details in Appendix 1.

These values are order-of-magnitude estimates and not absolute thresholds.

The assumptions for this analysis were developed to be consistent with existing planning studies considering public delivery methods and do not include the cost of equity capital that would have to be incurred under a P3 delivery option.  Project costs were not adjusted for risks.

Terms defined in the report.

See Note 3.

Ibid.

Ibid.

See Table 3 for project listed as potential long-term P3 candidates.

Adapted from John B. Miller, “Principles of Public and Private Infrastructure Delivery,” Kluwer Academic Publishers, 2000

This project delivery approach is known by a number of different names, including "turnkey" procurement, Build-Operate-Transfer (BOT), or Build-Own-Operate-Transfer (BOOT). Such terminology implying a transfer of ownership is, in most cases, not accurate.

See Section 1.3.5.

Mn/DOT will consider APs as debt service under its Debt Policy.

Risks allocated that are allocated to but cannot be managed effectively by the private sector result in higher prices and overall lower Value-for-Money for the public sponsor (see Section 4.4).

This process was initiated with a half-day workshop session held at Mn/DOT headquarters in Saint Paul on Thursday, June 17, 2010.

These values are order of magnitude estimates and not absolute thresholds.

The I-394 MnPass Express Lanes were developed and operated under a P3 procurement.  Under this agreement, the private sector partners contributed 20% of the project's estimated $10 million construction cost.  Although the construction cost was small, the project was not only Minnesota's first electronic tolling project; it was also the State's only toll project at the time.  Consequently, the complexity of launching a new facility concurrent with a new tolling system was outside the established capabilities and experience of Mn/DOT.  A P3 procurement provided the mechanism for the Department to deliver the project more efficiently, with not only cost savings in construction and operations, but also the requisite expertise to maintain a high quality, customer-focused service.  Thus, while the total cost for this project was relatively small, the complexity justified the greater level of private sector participation.

Workshop session held at Mn/DOT headquarters in Saint Paul on Thursday, June 17, 2010, follow-on interviews with Brad Larsen, and “Annual Transportation Performance Report,” Minnesota Department of Transportation, May 2009.

The Chapter 152 Program was initially part of the Level I screening.  The PB Team in consultation with Mn/DOT concluded early on that the program was too far advanced to change the current procurement method.  However, given the potential merits of the program as a P3 candidate, the Level II assessment reviews the general characteristics of a future bridge program similar to Chapter 152 as a potential P3 candidate.

Cambridge Systematics, “MnPass System Study Phase 2: Draft Final Report,” Minnesota Department of Transportation, July 28, 2010.

Email communication from Brian Kary, Mn/DOT, dated August 16, 2010.

Source: Debt service coverage, interest rate, maturity, toll increases, and inflation assumptions per Cambridge Systematics, “MnPass System Study Phase 2: Draft Final Report,” Mn/DOT, July 28, 2010; all others, PB estimates. 
Even though project D3-4 (I-94 MnPass shoulder lane from Rogers to Monticello) is not included in the MnPass System Study Phase 2, it is still assumed to have the same characteristics as the other MnPass projects.

Preliminary results from the study titled “Draft St Croix River Crossing Project: Innovative Financing Study” developed by HNTB and dated October 21, 2010 were made available to PB for estimates of revenue and costs.

Sources: Toll rates, toll increases, traffic increases, costs, and inflation assumptions per HNTB study; debt service coverage and interest rate per MnPass System Study Phase 2: 
Cambridge Systematics, “MnPass System Study Phase 2: Draft Final Report,” Mn/DOT, July 28, 2010.
HNTB, “Draft St Croix River Crossing Project: Innovative Financing Study,” October 21, 2010.

Minnesota Department of Transport, “Downtown Minneapolis Freeway Study,” May 2007 did not define the preferred design for an expanded tunnel, and as such, PB was unable to use it for cost estimation purposes.

Ibid.

The assumptions for this analysis were developed to be consistent with existing planning studies and do not include the cost of equity capital that would have to be incurred under a P3 delivery option.

Fabrice Voisin, Business Development Director, Colas Inc., personal communication, September 8, 2010

Sources of information for this Section include personal communications with Fabrice Voisin, Business Development Director, Colas Inc. and a white paper from Andrew Ardrey and Peter McDermott “The “Managing Agent Contractor” (MAC) Contract – Getting it Right First Time,” Halcrow

Model, standard contract documents are available at http://www.highways.gov.uk/business/14156.aspx

National Audit Office, “Highways Agency, Contracting for Highways Maintenance,” Report by the Comptroller and Auditor General, HC 959 Session 2008–2009, 16 October 2009

NCHRP 20-24(18) “Outsourcing of State DOT Capital Program Delivery Functions,” National Academies, Washington, D.C., 2003

Richard Herlick, Executive Vice President, Transfield Services North America, personal communication

See description of Managing Agent Contracts in the U.K. in the previous Section.

Zane Webb, Western US Regional Manager, ICA, personal communication, September 10, 2010.

Cambridge Systematics, “MnPass System Study Phase 2: Draft Final Report,” Minnesota Department of Transportation, July 28, 2010.

Parsons Brinckerhoff, “Metropolitan Highway System Investment Study: Draft Final Report,” Metropolitan Council, August 16, 2010.

Proposed developments on land adjacent to the Interstate right-of-way with direct access to the rest area from the Interstate have historically been turned down by the Federal Highway Administration on the basis of 23 USC 111.

FHWA, “Commercial Driver Rest & Parking Requirements: Making Space for Safety”, Final Report FHWA-MC-96-0010, May 1996, p. vii

SRF Consulting Group, “Interstate Highway Safety Study - Analysis of Vehicle Crashes Related to Safety Rest Area Spacing,” Prepared for the Minnesota Department of Transportation Office of Technical Support, July 2007.

Established in Section 1310 of the Safe, Accountable, Flexible, Efficient Transportation Equity Act: A Legacy for Users (SAFETEA-LU)

State of Georgia Department of Transportation, “Request for Information for Advertizing and Sponsorship in Safety Rest Areas,” RFI Number 484-041310-P3.

The estimates of cost recovery capacity are preliminary planning level, order-of-magnitude estimates. Assumptions were developed to be consistent with existing planning studies and do not include the cost of equity capital that would have to be incurred under a P3 delivery option. Project costs were not adjusted for risks.

Ibid.

Ibid.