Design-bid-build Project

TPCE Template Guideline

Date: August 2013

For Project TPCE base cost and annual updates, please use the most current price information to calculate the base price.  Use MnDOT Cost Estimation and Cost Management Technical Reference Manual (TRM) for contingency calculation.  This guideline is the instruction on filling out design-bid-build TPCE template.

- Project with Defined Scope:

Average price is updated annually for each item number at the following site:

http://www.dot.state.mn.us/bidlet/avgPrice.html

Also internal historical price information is updated quarterly at the following website:

http://costestimating.dot.state.mn.us/reports/HistoricalPrices.xls

For questions regarding the cost base price from the above websites, please contact Mary Lacho at 651-366-4639 or Mary.Lacho@state.mn.us .

After the base cost is calculated, please use the current TPCE form with current inflation adjustments to get the construction cost estimate for the mid-point of construction year.

- Project without Defined Scope:

Approach 1:

If the project is in the development phase, there are many project details that might not be well defined.  If you can use historical information to get scope and item details, please use the above links to get the most updated price cost to estimate the project cost.  Use engineering judgment when referring to historical past projects.  For the new project consider differences in project length, new/or deleted work items between the two projects, etc.

Approach 2:

If you can only use a past similar project to calculate base cost to get a new estimate, please use the inflation conversion factor table to adjust base cost and estimate.  We encourage you to use the most current cost information with approach 1.  Only if there is no information available for approach 1, use this process.  For the new project consider differences in project length, new/ or deleted work items between the two projects, etc.

Use the most updated Cost Estimate Inflation Conversion Factor Table to adjust past historical data with engineering judgment and inflation conversion factor to estimate the future cost.  Each year the actual inflation rates and future inflation rates are reported and inflation conversion factor could change.

For questions regarding Cost Estimate Inflation Conversion Factor Table, please contact John Wilson at 651-366-3732 or john.wilson@state.mn.us  .

The following is a guideline for use to adjust historical cost information to estimate the future project cost:

- Adjust historical cost data with engineering judgment for project conditions to get the adjusted past project cost.

- Identify the year of historical data to be used as the “historical base cost fiscal year”.  Fill in the year on TPCE form (Cell F102).

- Identify the year of construction as the “Mid-Point of Construction year”, fill in the year on TPCE form (Cell F101).

- The Cumulative Inflation Factor Used will be calculated for you on TPCE form and will be used in the calculation for Total Cost (Column VI).

- If the historical year is beyond the years listed in the table, it will be prompt to contact John Wilson for the correct inflation conversion factor to use, and then you need to enter the correct factor in the form for “Cumulative Inflation Factor Used” (Cell F100) so it can be used in the total cost calculations.

Approach 3:

If you cannot use price cost to estimate the project cost, then a parametric estimating tool like “LWD” which uses historical letting results based on pavement areas to compute estimates based on similar type and size past projects can be used.  If your district does not have LWD estimating process or LWD historical database, please contact Eric Janssen 651-234-7692 in Metro district about the Metro district LWD estimating process and information. Use engineering judgment when referring to LWD process.

http://ihub/metro/design/projectmanagement.html#pre

- Contingency Estimation

For contingency estimate and three type of risk analysis, please follow the guideline on MnDOT Cost Estimation and Cost Management TRM.

TRM can be found at the following website:

http://dotapp7.dot.state.mn.us/edms/download?docId=670233

Risk Register can be found at the following website:

http://www.dot.state.mn.us/pm/documents/Risk%20Register.xlsx

Additional guidance on risk management can be found at the following website:

http://www.dot.state.mn.us/pm/guidance.html