Instructions for filling Out TPCE form

April 2012

IMPORTANT: Note that all color shaded cells are auto calculations. Do not overwrite the formula.

- Project Information:

- Filling out project information for the following fields:

  - SP: Get this information from PUMA.

  - Route: Get this information from PUMA.

  - Estimate Reporting Date: Enter the date this estimate completed

  - District: enter district number who is leading the project.

  - Prime Element ID: Get this information from PUMA. It is a unique ID linking project information for Mn/DOT databases.

  - Letting Date:  Enter current letting date

  - Project Length: enter project length in miles.

  - Project Description: Get this information from PUMA.

- Mid-point of Construction Year:  Roll down the sheet, to the end of the form, fill in “Mid-Point of Construction Year”.  Please note without filling in this information, the sheet will not be able to auto calculate column VII for anticipated inflation between the date the estimate is prepared until construction is half completed.

- Construction Letting

- Roll up the form to the second module frame titled “Construction Letting” division, Fill in column IV [Base Estimate] and column V [Contingency] under “Construction Letting Cost” group [Column I] in each “Category” [Column II] if applicable.  Please fill in the descriptions in column III [Details] when it is needed.

- The sheet will auto calculate column VI[Total] and column VII [Mid-point construction year dollar] based on information provided in column IV, column V, and mid-point construction year (at bottom of the form).

- The sheet will also auto calculate the blue shaded last row of the module [Construction Letting (A)] for all columns.  See point 9 for rounding information.

- Note that all color shaded cells are auto calculations. Do not overwrite the formula.

- Other Construction Total

The third module frame is “Other Construction Total” division.  There are three groups in column I: Preconstruction Cost, Post letting Cost, and Post construction costs.

  - Fill in column IV [Base Estimate] and column V [Contingency] under each group in each “Category” [Column II] if applicable.  Please fill in the descriptions in column III [Details] when it is needed.

  - The sheet will auto calculate column VI[Total] and column VII [Mid-point construction year dollar] based on information provided in column IV, column V, and mid-point construction year (at bottom of the form).

  - The sheet will also auto calculate the last row in each group: Preconstruction Cost (B), Post Letting Cost (C), Post Construction Cost(D) and the blue shaded last row of the module [Non-Letting (“Other”) Construction Elements (E)] for all columns.

  - For Post Letting Cost in SA/CO/Overruns, fill in an amount, however if no information is available, calculate an amount by multiplying 7% times the construction cost.  It is not in the auto calculation.

- The fourth module frame is “Construction Total” (F).  It should be the STIP estimate, may show up on multiple lines in the STIP and possibly over several years.

- Engineering

The fifth module frame is “Engineering” division.  There are two groups in column I: Pre-letting and construction.

  - Fill in column IV [Base Estimate] and column V [Contingency] under each group in each “Category” [Column II] if applicable.  Please consider both internal and external costs in column III [Details], such as consultants, locals etc..

  - The sheet will auto calculate column VI [Total] based on information provided in column IV and column V. Please note that column VII [Mid-point construction year dollar] will not be calculated under “Engineering cost”.  The engineering cost is not inflated because:

- The Engineering is over the entire project delivery time frame

- Over the last two years of data the State salaries have been fairly static, we may change it when the trend changes.

- There is little known relationship to the inflation that occurs with construction estimates.

- If the District is aware of some special reason then they can increase the contingency amount to try and anticipate that, if it does happen.

- Employees move in (new hires/promotions) and out (retirements/resignations) a classification may balance out the change in average wage rate from year to year.

So do not apply inflation to Engineering costs.

  - Note that when no cost information under each group is provided, the sheet will auto-calculate the pink shaded fields only using either 12% or 8% of construction cost rule respectively.  If there is ANY cost entered, it will only use the sum of the costs entered to auto calculate the pink shaded fields under each group respectively.  Do not over write the pink shaded cells.

  - Note that Construction Total line (F) under the Base Estimate (column IV) is used to calculate the amounts that would show in the pink shaded box in the Engineering division, 12% for Pre Construction amount and 8% for Construction amount.  If there is a number under the Contingency (column V) in the Construction total (line F) then that amount will also show in the pink shaded box in Engineering under the Contingency column.  Thus, the Engineering amount is calculated before the inflation factor for construction is applied.

  - The sheet will also auto calculate the last two rows “Engineering Cost” and “Engineering Total (G)” for all columns.  If there is no cost information provided, it will use the 20% construction total rule of thumb for engineering total cost.

- Right of Way

The sixth module frame is “Right of Way” division.  There are two groups in column I: Standard Real Estate Purchase and Relocation Costs.

  - Communicate with the District R/W Engineer/Manager when filling out this form.

  - Transferring R/W cost information from the Office of Land Management (OLM) cost estimation tool into Column IV [Base Estimate] and Column V [Contingency].

  - If the Right of Way cost is NOT using the OLM rounding rule in the R/W cost estimate tool, fill in the total cost in the green shaded cell provided in column VII to avoid double rounding.

  - Do not apply inflation due to the fact that the R/W estimate already applied market conditions in its calculation.

  - The sheet will auto-calculate the rounding number located in column VI [Total] and “ROW Total (H)”.

  - Note that these are only the acquisition costs.  R/W engineering cost is under “Engineering” division “Pre-Letting” group.

- The seventh module frame auto calculates the “Total Base Cost”, “Contingency” and “Total Project Cost Estimate (I)” columns.

- Rounding rules are auto applied for column VIII [Rounded Amount] in the following lines:

    - Construction letting (A)

    - Non-Letting (“Other”) Construction Elements (E)

    - Engineering Total (G)

    - ROW Total (H)

The yellow shaded cells are the estimates needed for the Project Summary Report - One pager.  The light blue shaded “Construction Total (F) should be the STIP estimate, but may show up on multiple lines in the STIP and possible over several years.  It is the sum of Construction Letting (A) and Non-Letting (“Other”) Construction Elements (E). The Total Project Cost Estimate (I) is used as the cost management baseline established as a point estimate at the end of scoping.  It is the sum of Construction Letting (A), Non-Letting (“Other”) Construction Elements (E), Engineering Total (G), and ROW Total (H). This information needs to be updated at least annually.

  - For costs in line A [Construction letting] and E[Non-Letting (“Other”) Construction Elements], the following rounding rules applied:

    - For projects under $1,000,000, round to the next $10,000.  (i.e. – a $156,123.86 project would round to $160,000).

    - For projects $1,000,000 to $100,000,000, round to the next $100,000.  (i.e. – a $1,509,000 project would round to $1,600,000 and a $12,772,000 project would round to $12,800,000).

    - For projects greater than $100 million, round to the next million.  (i.e. – a $300,500,000 project would round to $301,000,000).

  - For cost in line G[Engineering], the following rounding rules applied:

    - For projects under $300,000, round up to the next $10,000

    - For projects over $300,000, round up to the next $100,000.

  - For cost in line H [Right of Way], communicate with the District R/W engineer/manager for the cost estimates and whether or not they have rounded the R/W cost provided.  If Right of Way rounding is not transferred from the R/W cost sheet, the rounding will be applied in Column VIII automatically, consistent with the OLM rounding rules in the R/W cost estimate tool.