## RiskRegister
RISK REGISTER
| Prime S.P. |  |  |  |  | Probability | Cost | Schedule
| Route |  |  |  |  | 5 - H (>60%) | 5 - H (>$2000000) | 5 - H (>120d)
| Project Name: |  |  |  |  | 4 - M (>40%) | 4 - M (>$1000000) | 4 - M (>60d)
| Project Manager: |  |  |  |  | 3 - L (>20%) | 3 - L (>$500000) | 3 - L (>25d)
[6 empty] | 2 - VL (>10%) | 2 - VL (>$250000) | 2 - VL (>15d)
[6 empty] | 1 - EL (<=10%) | 1 - EL (<=$250000) | 1 - EL (<=5d)
Risk Identification |  |  |  | Risk Assessment |  |  |  |  | Risk Response |  |  |  | Risk Monitoring
Risk ID | Risk Name | Status | Description | Probability | Cost Impact | Schedule Impact | Overall Rating | Risk Exposure | Response Type | Response Action | Responsible Person | Contingency | Last Updated / Comments | Next Review Date
Note on B13: A short name or a code (e.g. RW-1) for easy reference
Note on C13: Active = is having affect on project or may still occur Retired = has happened and is past or probability went to zero
Note on D13: A precise description of what may happen and what it would affect
Note on E13: Approximate probability
Note on G13: A qualitative magnitude of impact
Note on H13: A calculated cell that indicates the importance of managing the risk
Note on J13: Avoid =change plans to eliminate possibility of risk Mitigate = take steps to lessen probability or impact Accept = make no change in plans and let it be Tranfer = put risk on others, e.g. contractor, insurance Enhance = take steps to increase probability or impact Exploit = take advantage of an opportunity Share = partner to increase probability
Note on K13: A description of what is planned to be done
Note on L13: The person responsible for executing the response
Note on M13: How the possibility of the risk will be accounted for in the scope, schedule, cost, or quality plan
Note on N13: Record of where the risk stands
Note on O13: The next time the risk will be reviewed

## dropdown (hidden)
Status | Probability | Impact |  | Affects | Response Type
Active | 5=Very High (60-99%) | 5 =Very High | Low | Scope | AVOID
Retired | 4=High (40-59%) | 4 =High | Med | Schedule | MITIGATE
| 3=Med (20-39%) | 3 =Med | High | Cost | ACCEPT
| 2=Low (10-19%) | 2 =Low |  | Quality | TRANSFER
| 1=Very Low (1-9%) | 1 =Very Low |  |  | ENHANCE
EXPLOIT
SHARE

## IssueList
ISSUE LIST
Prime S.P.
Route
Project Name:
Project Manager:
Issue Identification |  |  |  |  | Assessment & Response |  |  | Monitoring
Issue Name | Description | Date Added | Status | Date Retired | Impact | Planned Response | Owner | Last Updated/ Comments | Next Review Date
Note on A9: A brief description for easy reference
Note on B9: Precise description of what happened and what it affects
Note on C9: The date the issue was realized
Note on D9: Active=work is underway to resolve it Resolved=situation has been resolved & is no longer an issue
Note on E9: The date the issue was resolved
Note on F9: Qualitative magnitude of impact See table
Note on G9: A description of how the issue will be handled
Note on H9: The person responsible for resolving the issue
Note on I9: A record of where the risk stands
Note on J9: The next time the issue will be reviewed

## Pxl
Score | 1 | 2 | 3 | 4 | 5 | active
Probability | 0 | 10 | 20 | 40 | 60 | resolved
Schedule Impact | 5 | 15 | 25 | 60 | 120
Cost Impact | 100000 | 250000 | 500000 | 1000000 | 2000000
Public Response Impact | individual concerns | group concerned | Significant local opposition | Significant high-level opposition | Project likely to be terminated
| 5 - H (>60%) | 5 - H (>$2000000) | 5 - H (>120d)
| 4 - M (>40%) | 4 - M (>$1000000) | 4 - M (>60d)
| 3 - L (>20%) | 3 - L (>$500000) | 3 - L (>25d)
| 2 - VL (>10%) | 2 - VL (>$250000) | 2 - VL (>15d)
| 1 - EL (<=10%) | 1 - EL (<=$100000) | 1 - EL (<=5d)